## CDDRA_Data
Project | Trial | Work Package Code | Phase | Data Capture standards | EDC | Planned DB Go-Live Date | Actual DB Go-Live Date | FPFV Planned | DB Phase | Upcoming Milestone | Upcoming Milestone Date | FPFV Actual | Final Protocol Planned | Final Protocol Actual | Screen UAT Finalization Date | Impact Trial Status | LPLV Planned | LPLV Actual | Clinical DB Lock Planned | Clinical DB Lock Actual | DCN Objective | DM Study Priority | DRRA POC | DM Ops Cluster | GDO DM Sourcing | DO Ops Unit | Protocol Title | Trial Short Description | Franchise | DO DU | TDM | PDM | DM GHs | DM Sr GHs | Trial Lead | Horizon Work Package Manager | Lead DBD | Transition DBD | DBD Transition Status | Transition Date | Startup Comments | Protocol Finalization to DB Go Live (Wks.) Reason for not meeting KPI | Conformance Type | Old Rule File Developer | Rule File Developer | Rule File Status | Rule File Comments | RF Pending Forms | RF Pending DTS | LSH Setup Request Date (Prod) | Rule File Finalization to FPFV (Wks.) Reason for not meeting KPI | Study LSP | SMT Developer | DAP POC | Pre-DRM Status (Prod) | Pre-DRM Final Date (Prod) | DRM Status (Prod) | DRM Final Date | RF LSH Status Comments | SMT Finalization to FPFV (Wks.) Reason for not meeting KPI | JReview Publish Date | GPS Publish Date | Data Availability by FPFV Reason for not meeting KPI | DIAL Publish Date | ICRS Onboarding Date | FPFV to ICRS Onboarding Reason for not meeting KPI | DDPASS Comments | DDPASS Success Rate (%) | LSH Setup Type | DDPASS Conduct Status | List of blinded domains | LSH Lock Request Date | LSH Lock Date | LSH Lock to DBL Reason for not meeting KPI | %PPC Reason for not meeting KPI | Support Model | CDD Sourcing | CDD Delivery | Golive Date Tracker Legacy | 1st Time DCI Book Activation Date | ICON POC | Back up ICON POC | DM CRO | Onc/Pharma | CT4 instance | CRO | CRO Contact | NOVDD Comment | ALS Version | # of Visits | # of Forms | Updated # Unique CRF | # of Total CRFs Designed | # of Checks | Updated # Edit Checks | # of Custom Functions | # of Derivations | # of Field Edit Checks | Total No of Checks (Checks + Derivations + Field Edit Checks) | # of DTS | Updated # DTS | Updated Data Standards | Trial Indication | New Indication | Regional Scope | HORIZON WP Status | HORIZON Monthly Demand Trigger | LSH Setup Request Date (Test) | Pre-DRM Status (Test) | Pre-DRM Final Date (Test) | DRM Status (Test) | DRM Final Date (Test) | JReview Publish Date (Test) | LSH Test Status Comment | SDW Publish Date | List of Domains | List of Third Party Domains | SMT Fialization Date | Domains Applicable | Domains Passed (DDPASS) | Last DDPASS Conduct Date
CAAA405A1 | CAAA405A12301 | C4009835 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-02-15 05:30 | 2021-07-16 05:30 | 2021-09-30 05:30 | DB Conduct | DB Snapshot | 2022-03-15 05:30 | 2021-09-30 05:30 | 2021-01-18 05:30 | 2021-01-26 05:30 |  | Active | 2023-06-09 05:30 |  | 2023-07-21 05:30 |  | FALSE | Pioneer | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Phase III study for evaluation of the diagnostic performance of [18F]CTT1057 PET imaging in patients with prostate cancer with rising PSA levels [biochemical recurrence (BCR)] | CAAA405A12301 Ph III 18F-CTT1057 (PSMA) BCR | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Kalidindi, Neeharika | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Praseeda Thaikalloor | Praseeda Thaikalloor | Mokhamatam, Madhu Purnachandra Rao | Gehlawat, Priya | Not Started |  | 21May2021 : SSD will be provided by today. OSRM1 done. OSRM 2 on 28th. All approved SRFs, SDTM annotations and SRF shared with RF developer. 06May2021 : Golive moved to 27Jun2021 from 14jun2021as there are study specific forms pending. Followed up with SDTM programmer for SDTM annotations. OSRM1 is planned on 12th May 2021 for “CAA405A12301” study. Totally we have 13 study specific forms out of 13 we have received SDTM annotations for 7 forms however for the below mentioned 6 forms we are yet to receive. I request you to consider this request as high priority. 29Apr2021 : Received 7 approved SRFs. CRF build ongoing. Awaiting SDTM annotations. Possibility of movement of Golive Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 15Feb2021. Lead details updated from Madhu Mokhamatam to Priya Gehlawat based on the mail received from Madhu on 21st Sept 2021. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 15Feb2022: Since PPC02 has no impact on Rule File, SNOW-51 ticket has been raised with ticket number- RITM3494280 for LSH update. 25Jan2022: DBD shared PPC02 for Impact analysis. Reviewed and shared comments. 09Nov2021: Since PPC01 has no impact on Rule file, SNOW-51 ticket is raised with ticket number- RITM3169253 for LSH update. 05Oct2021: CAAA405A12301_Rule file_Version 3.0 is finalized in SUBWAY with LB DTS included in it and SNOW-51 Ticket is also raised with Ticket number- RITM3049846 for LSH Setup. 27Sep2021: CAAA405A12301_Rule file_Version 2.0 is finalized in SUBWAY with IRT DTS included in it and SNOW-51 Ticket is also raised with Ticket number- RITM3019703 for LSH Setup. 19July2021: that CAAA405A12301_Rule file_Version 1.0 is finalized in SUBWAY and SNOW-05 Ticket is also raised with Ticket number- RITM2784391 for LSH Setup. 15July2021: Rule file peer review is completed 1stJuly2021:Released the CAAA405A12301_Rule file_version 0.1 for Peer Review. 21June2021: Rule file development has been started. Go-Live shifted to 16th July 2021 07Jun2021: DBD informed that Screen UAT will be completed by this week and OSRM2 will be completed on 8th June. Go-Live is shifted to 8th July 2021. There have been some dynamic updates. Waiting for latest updated ALS to start the Rule file development 28May2021: Received rest of the 7 SS forms for review. Review is completed 10May2021: Received 9 study specific forms out of 16 along with annotation for review. Review ongoing. 03May2021 : yet to receive SS forms for review. Follow up with DBD 16Mar2021 : RF developer Assigned. | None | None | 2021-07-19 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2021-08-02 | Completed | 2021-08-06 05:30 |  |  | 2021-08-06 05:30 | 2021-08-06 05:30 |  | 2021-08-10 05:30 |  |  |  | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 2 | 9 | 61 | 0 | 78 | 828 | 0 | 213 | 44 | 167 | 1039 | 3 | 0 |  | Prostate cancer | No | Global | Open | Yes | [10 empty] | 2021-08-05 05:30 | [5 empty] | None of the above
CAAA405A1 | CAAA405A12302 | C4009836 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-14 05:30 | 2021-07-16 05:30 | 2021-09-30 05:30 | DB Conduct | DB Snapshot | 2022-03-15 05:30 | 2021-09-07 05:30 | 2021-01-18 05:30 | 2021-01-29 05:30 |  | Active | 2023-02-24 05:30 |  | 2023-04-07 05:30 |  | FALSE | Pioneer | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Phase II/III study for evaluation of the diagnostic performance of [18F]CTT1057 PET imaging for the detection of PSMA positive tumors using histopathology as a standard of truth | CAAA405A12302 Ph II/III 18F-CTT1057 (PSMA) PS | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Dsouza, Carlton | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Praseeda Thaikalloor | Praseeda Thaikalloor | Bonam, Rajesh Babu | Rao, S Shashikanth | Completed | 2021-09-30 05:30 | 06May2021 : Swapna P to co-lead the study. 30Apr2021 : SRF approval pending. Screen build completed for global forms along with few SS forms. Golive at risk as SSD is not final and yet to receive pending SRFs. Followup with TDM. Initial Golive 14May2021 moved to 14Jun2021 Study Transitioned to Rao, Shashikanth on 30Sep2021 |  | DRM | Saha, Saikat | Kuttoboina, Sujan Kumar | Completed | 25NOV2021: RF V2.0 final and SNOW 51 RITM3208162 request created for addition of YDL and LB1L DTS. And LB domain has been updated as part of PPC. 20Jul2021 : RF finalized by Saikat. Rule file Version 1.0 is final in Subway and SNOW 05 request RITM2791301 has been created for LSH setup. 16JUL2021: RF development is completed and peer review is ongoing and expected date of completion is 19JUL21. 2JUL2021: Study golive will be 26JUL2021 as per lead DBD confirmation. 16JUN2021: Study specific pages have been reviewed and provided comments. Waiting for the SDTM annotations for complete review of study specific pages. 11JUN2021: As per DBD confirmation golive is on 08JUL2021. We've requested for study status, Activity planner and update the iBOW. 26May2021: RF developer assigned. | None | None | 2021-07-20 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2021-08-03 | Completed | 2021-08-10 05:30 |  |  | 2021-08-11 05:30 | 2021-08-11 05:30 |  | 2021-08-23 05:30 | [5 empty] | No | [12 empty] | NA | [5 empty] | 2 | 5 | 59 | 0 | 66 | 768 | 0 | 201 | 41 | 197 | 1006 | 3 | 0 |  | Prostate cancer | No | Global | Open | Yes | [10 empty] | 2021-08-09 05:30 | [5 empty] | None of the above
CAAA503A1 | CAAA503A12201 | C4007902 | Phase II | Other | [7 empty] | 2018-07-03 05:30 |  | 2021-04-05 05:30 |  | Completed |  | 2019-07-05 05:30 |  |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced |  | Phase II study of preliminary diagnostic performance of [68Ga]-NeoBOMB1 in adult patients with malignancies known to overexpress Gastrin Releasing Peptide Receptor | CAAA503A12201 NeoFIND | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | [68 empty] | Breast cancer; Colorectal cancer; Non-small cell lung cancer; Prostate cancer; Small cell lung cancer | No | Global | Open | No | [16 empty] | None of the above
CAAA504A1 | CAAA504A12101 | C4010157 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-11-05 05:30 | 2021-03-05 05:30 | 2021-10-28 05:30 | DB Conduct | Final DBL | 2023-01-31 05:30 | 2021-10-14 05:30 | 2020-10-20 05:30 | 2020-10-08 05:30 |  | Active | 2022-12-27 05:30 |  | 2023-01-31 05:30 |  | FALSE | Race | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | Phase I, open-label, multicenter study to evaluate the imaging performance, safety, biodistribution and dosimetry of [68Ga]-FF58 in adult patients with selected solid tumors expected to overexpress Î±vÎ²3 and Î±vÎ²5 integrins | CAAA504A12101 Trial | N7 Oncology - NIBR | Langlo, Francois | BabuP, Anand | Kocharekar, Poonam Vilas | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Amanda Short; Gabrielle Dethioux | Gabrielle Dethioux | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR | Not Started |  | As per email from DBD golive moved from 02Feb21 to 05Mar20 Initial go live as 05Nov2020 when RF developer assigned on 19Aug2020. |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 04-Feb-2022: RF has been updated for PPC#1 and SNOW ticket(RITM3252144) raised for LSH refresh on 02-Dec-2021 26-Mar-2021: RF has been updated to include CMTRT extended varaibles 08-Mar-2021: Rule file has been finalized and SNOW05 ticket(RITM2338013) is raised for LSH set-up. 17-Feb-2021: Reviewed ALS and SDTM annotations and requested Lead DBP to update the forms as per review comments 21-Jan-2021: Reviewed the SRFs and provide comments to Lead DBP. Requested lead DBP to share the updated ALS for further review. | None | None | 2021-03-08 05:30 |  | Varate, Rohit | Varate, Rohit | Rohit Varate | Completed | 2021-03-16 | Completed | 2021-03-24 05:30 | SG : 24Mar2021: CM domain is pending as RF update is required. |  | 2021-03-24 05:30 | 2021-03-24 05:30 |  | 2021-03-31 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 4 | 65 | 0 | 78 | 623 | 0 | 200 | 51 | 211 | 885 | 1 | 0 |  | Brain metastases; Gastroesophageal cancer; Glioblastoma multiforme; Pancreatic carcinoma | Yes | Global | Open | Yes | [10 empty] | 2021-03-24 05:30 | [5 empty] | None of the above
CAAA601A1_MA | CAAA601A12401 | C4007881 | Phase IV | Other | CRO - EDC |  |  |  | DB Conduct |  |  |  |  | 2021-06-10 05:30 |  | Planned | [5 empty] | not known yet | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | An international, non-interventional, post-authorization retrospective registry of patients treated with LutatheraÂ® (lutetium (177Lu) oxodotreotide), to assess the efficacy and safety of LutatheraÂ® for the treatment of pancreatic neuroendocrine tumors (pNETs). | CAAA601A12401 NETTER-R | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Bhataiya, Vishal | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Paola Santoro | [18 empty] | Sai Krishna Mettugari | [48 empty] | Gastroenteropancreatic neuroendocrine tu | No | Global | Open | No
CAAA601A1 | CAAA601A12403 | C4009949 | Phase IV | NCDS_2 |  |  |  | 2022-04-30 05:30 |  | Final DBL | 2023-07-28 05:30 |  | 2021-04-12 05:30 | 2021-04-14 05:30 |  | Planned | 2023-06-30 05:30 |  | 2023-07-28 05:30 |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse |  | A Post Marketing Surveillance on LutatheraÂ® (Lutetium (177Lu) Oxodotreotide, 177Lu-DOTA0-Tyr3-Octreotate) in patients with somatostatin receptor positive gastroenteropancreatic neuroendocrine tumor (GEP-NET) in Korea | CAAA601A12403 Post Marketing Surveillance | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | Hyewon Lee | Hyewon Lee | [54 empty] | 40 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Carcinoid tumour; Gastroenteropancreatic neuroendocrine tu; Pancreatic neuroendocrine tumour | No | Global | Open | Yes | [16 empty] | None of the above
CAAA601A2 | CAAA601A22301 | C4007885 | Phase III | Other | [9 empty] | 2021-10-11 05:30 |  | Planned | 2027-07-30 05:30 |  |  |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced |  | A phase III multi-center, randomized, open-label study to evaluate the efficacy and safety of Lutathera in patients with Grade 2 and Grade 3 advanced GEP-NE | CAAA601A22301 NETTER-2 | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | Paola Santoro | Paola Santoro | [66 empty] | Gastroenteropancreatic neuroendocrine tu | No | Global | Open | Yes | [16 empty] | None of the above
CAAA601A3 | CAAA601A32201 | C4009746 | Phase II | NCDS_2 |  |  |  | 2022-05-18 05:30 |  | Final DBL | 2028-05-08 05:30 |  | 2022-05-03 05:30 | 2022-02-15 05:30 |  | Planned | 2028-03-26 05:30 |  | 2028-05-08 05:30 |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse |  | A multicenter open-label study to evaluate safety and dosimetry of Lutathera in adolescent patients with somatostatin receptor positive gastroenteropancreatic neuroendocrine (GEP-NET) tumors, pheochromocytoma and paragangliomas | CAAA601A32201 Phase IIB study NETTER-P | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | Paola Santoro | Paola Santoro | [54 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Gastroenteropancreatic neuroendocrine tu | No | Global | Open | Yes | [16 empty] | None of the above
CAAA601A4 | CAAA601A42101 | C4013389 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2022-01-28 05:30 | 2022-01-28 05:30 | 2022-03-17 05:30 | DB Set-Up | DB Snapshot | 2022-08-04 05:30 |  | 2021-08-30 05:30 | 2021-08-31 05:30 |  | Planned | 2025-06-20 05:30 |  | 2025-07-31 05:30 |  |  | None | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase Ib Dose Finding Study Assessing Safety and Activity of [177Lu]Lu-DOTA-TATE in Newly Diagnosed Extensive Stage Small Cell Lung Cancer (ES-SCLC) in Combination with Carboplatin, Etoposide and Tislelizumab in Induction and with Tislelizumab in Maintenance Treatment Phase | CAAA601A42101 SCLC SRI | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Wang, Yunhui | Das, Chiranjeeb | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Isabelle Naeije | Isabelle Na��ije | Gupta, Anshu | Gupta, Anshu |  |  |  | 1. There were many Screens updates as per CTT request till 24-Jan-2022 2. Many global CF has to be made as study specific. 3. In ECS new checks were added at the end. |  | Bairagi, Arpita | Bairagi, Arpita | Completed | 31Jan2022: SNOW 05 request RITM3436520 has been raised for the LSH PROD set up 25Jan2022: Rule File for the CAAA601A42101 study has been finalized in the Subway and the SNOW 05 request RITM3419832 has been raised for LSH TEST Set up. 20Jan2022: Received the communication that the DIVAL fields are removed from the DUS001 page and received the updated ALS and SOD. Shared the latest ALS and RF to the peer reviewer. 19Jan2022: Provided the Code-list and Test Code list, pertaining to be requested to be added in the Metadata to the DBD. Released the RF for the peer review. 18Jan2022: Received the updated ALS and SOD, consisting of the recent changes suggested. 17Jan2022: Received the updated SDTM annotation for ZJS001, ZJS002, B1S001_TR, ECG007 and ECG002_4 pages. Discussion is going on for DUS001 page regarding DIVAL fields. 12Jan2022: Started RF building. Received the comments regarding the updates requested along with updated ALS. 11Jan2022: Received the updated ALS along with the latest SDTM annotation for AEG002, MHO001_TR and latest SOD. Sent the additional comments to the DBD regarding the DB 11Jan2022: Saikat Saha supporting in RF development 10Jan2022: DBD shared updated ALS for review and RF development. Study specific codelist and TEST codes are shared with DBD to raise the request. 21Dec2021: ALS is reviewed and shared the comments with the DBD 20Dec2021: DBD shared the ALS for initial review 09Sep2021: DBD shared SRFs and SDTM Annotation for initial review | None | None | 2022-01-31 05:30 | LSH TEST Ticket raised on 25-Jan-2022, missed the KPI because of delay in Rule File finalization due to delay in receiving Rule File pre-requisite document from lead DBD. | KANUMURI, NAVYA SAI | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2022-02-14 | Completed | 2022-02-18 05:30 |  |  | 2022-02-18 05:30 | 2022-02-18 05:30 | [5 empty] | 0 | [14 empty] | NA | [5 empty] | 1 | 21 | 86 | 0 | 294 | 1159 | 0 | 321 | 48 | 273 | 1480 | 0 | 0 |  | Small cell lung cancer | Yes | Global | Open | Yes | 2022-01-25 05:30 | Completed | 2022-02-09 05:30 | Completed | 2022-02-17 05:30 | 2022-02-18 05:30
CAAA601A5 | CAAA601A52101 | C4013391 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-12-01 05:30 |  | 2022-03-10 05:30 | DB Set-Up | DB Go-live | 2022-02-24 05:30 |  | 2021-08-20 05:30 | 2021-08-23 05:30 |  | Planned | 2024-12-20 05:30 |  | 2025-02-07 05:30 |  |  | Pioneer | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase Ib Dose Finding Study Assessing Safety and Activity of [177Lu]Lu-DOTA-TATE in Newly Diagnosed Glioblastoma in Combination with Radiotherapy with or without Temozolomide and in Recurrent Glioblastoma as Single Agent | CAAA601A52101 GBM SRI | P0 Oncology (Solid Tumors all MA Onc projects) | Rudraswamymath, Jagadeesh | Rathod, Dimple | Das, Chiranjeeb | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Isabelle Naeije | Isabelle Na��ije | Supraja, Samala | Supraja, Samala | [5 empty] | R, Pratheeksha K | R, Pratheeksha K | Completed | 15Feb2022: SNOW05 ticket for LSH Test setup was raised on 11Feb2022 (SNOW05 Ticket number - RITM3487812). |  |  |  |  | KANUMURI, NAVYA SAI | Mettugari, Sai Krishna | Sai Krishna Mettugari | [13 empty] | 0 | [14 empty] | IQVIA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 6 | 0 |  | Glioblastoma | Yes | Global | Open | Yes | 2022-02-11 05:30 |  |  | Ongoing
CAAA602A1 | CAAA602A12101 | C4007903 | Phase I | Other | [7 empty] | 2018-05-17 05:30 |  | 2022-02-04 05:30 |  | Active |  |  |  |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced |  | A Phase 1/2 open-label, multi-center, dose-escalation study of safety, tolerability, pharmacokinetics, dosimetry, and response to repeat dosing of 177Lu-PSMA-R2 radio-ligand therapy in patients with prostate specific membrane antigen (PSMA) positive (68Ga-PSMA-R2) progressive metastatic castration-resistant prostate cancer, following previous systemic treatment. | CAAA602A12101 PROter | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | Noella Gilbert | Noella Gilbert | [66 empty] | Progression of prostate cancer; Prostate cancer | No | Global | Open | No | [16 empty] | None of the above
CAAA603A1 | CAAA603A12101 | C4007887 | Phase I | Other | [7 empty] | 2018-07-10 05:30 |  | 2022-02-04 05:30 |  | Active | 2024-12-31 05:30 |  |  |  | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced |  | A Phase I/IIa open-label, multi-center study to evaluate the safety, tolerability, whole-body distribution, radiation dosimetry and anti-tumoractivity of [177Lu]-NeoB administered in patients with advanced solid tumors known to overexpress gastrin-releasing peptide receptor (GRPR | CAAA603A12101 NeoRay | P0 Oncology (Solid Tumors all MA Onc projects) |  |  |  | Wisson, Ellen | Wisson, Ellen | Frederic Cortes | Amita Patel | [66 empty] | Solid tumor | Yes | Global | Open | No | [16 empty] | None of the above
CAAA617A1 | CAAA617A11201 | C4009166 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-01-19 05:30 | 2022-01-19 05:30 | 2022-01-31 05:30 | DB Conduct | DB Snapshot | 2022-05-17 05:30 | 2022-01-25 05:30 | 2020-09-30 05:30 | 2020-09-29 05:30 | 2022-01-17 05:30 | Active | 2026-04-01 05:30 |  | 2026-04-30 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Solid Tumor |  | CAAA617A11201 3L Post NAAD & Post Taxane (Japan) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Takano, Mamiko | Das, Chiranjeeb | Chouhan, Mithun Mahesh | Hiriyanna, Srinivas | AIRA KOBA | AIRA KOBA | Suzuki, Hiroko | Suzuki, Hiroko | Not Started |  |  | 1. Protocol has amended on last Sep, DB setup was able to be initiated after that, and it took some time for approving SRF. 2. Many SRF re-used from sister study. TDM required to be the same DB structure as sister study. However, sister study has setup before releasing new SRF process. Rule file developer found DB structure issues, then we had to make many correction. Then Screen UAT has performed again. 3. SRF review by DBD and Rule file DBD was not enough, we found some issues during DB and Rule file setup. A few SRF should have updated. | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 19Jan2022: DB Go-live is completed and the SNOW05# LSH PROD Setup request has been raised. 18Jan2022: Rule File Version 1.0 has been finalized and SNOW05# LSH Test Setup has been raised and shared with LSP and DBD. 14Jan2022: Peer Review has been completed. 05Jan2022: Rule file has been completed and shared for the Peer review. 20Dec2021: Rule file development has been started. DB Go-live has been pushed to 19-Jan-2022. 17Dec2021: ALS, SDTM Annotations and SRF review has been completed and comments has been shared with DBD. 15Dec2021: Rule file Pre-requisites has been received from the lead DBD. 09Aug2021 : reassigned to Satwik from Angella. 26May2021: RF developer assigned | None | None | 2022-01-19 05:30 | LSH TEST ticket raised on 18-Jan-2022, missed the KPI because delay in Rule file finalization due to the delay in receiving the Rule File pre-requisites and getting clarifications with few forms with Lead DBD and SDTM Programmer. LSH PROD ticket was raised on the day of DB go-live (19-Jan-2022) and met the KPI. | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sushant Sundar | Completed |  | Completed | 2022-01-31 05:30 |  |  | 2022-02-01 05:30 | 2022-02-01 05:30 | [5 empty] | 0 | [14 empty] | NA | [5 empty] | 1 | 40 | 90 | 0 | 507 | 1012 | 0 | 269 | 53 | 336 | 1401 | 4 | 0 |  | Prostate cancer | No | Global | Open | Yes |  | Completed | 2022-01-20 05:30 | Completed | 2022-01-25 05:30 | 2022-01-25 05:30 |  |  |  |  | 2022-01-31 05:30 | [5 empty] | None of the above
CAAA617A1 | CAAA617A12201 | C4014967 | Phase II | NCDS_2 |  |  |  | 2023-01-30 05:30 |  | Final DBL | 2026-06-24 05:30 |  | 2022-04-25 05:30 |  |  | Planned | 2026-06-30 05:30 |  | 2026-06-24 05:30 | [5 empty] | InHouse |  | An Open-label, Multi-center, Single-arm Study to Evaluate the Efficacy, Safety, PK and Dosimetry of 177Lu-PSMA-617 in Chinese Patients with Progressive PSMA-Positive Metastatic Castration-Resistant Prostate Cancer (mCRPC) | CAAA617A12201 China_Ph2 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Yuanxi Shi | Yuanxi Shi | Gupta, Anshu | Gupta, Anshu | [52 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Castration-resistant prostate cancer; Prostate cancer metastatic | No | Global | Open | Yes
CAAA617B1 | CAAA617B12201 | C4014972 | Phase II | NCDS_2 |  | 2022-02-03 05:30 |  | 2023-02-09 05:30 |  | Final DBL | 2028-03-21 05:30 |  | 2022-05-05 05:30 |  |  | Planned | 2028-02-09 05:30 |  | 2028-03-21 05:30 | [5 empty] | InHouse |  | An Open-label, Multi-Center, Randomized Efficacy and Safety Study Comparing 177Lu- PSMA-617 vs. a Change of androgen receptor-directed therapy in the Treatment of Taxane Naive Chinese Male Patients with Progressive Metastatic Castrate Resistant Prostate Cancer | CAAA617B12201 China_Ph2 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Larry Qiu | Xuhua Qiu | Supraja, Samala | Supraja, Samala | [52 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Prostate cancer | No | Global | Open | Yes
CAAA617B1 | CAAA617B12302 | C4009857 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-11-20 05:30 | 2021-04-22 05:30 | 2021-08-02 05:30 | DB Conduct | DB Snapshot | 2022-05-24 05:30 | 2021-02-02 05:30 | 2020-11-08 05:30 | 2020-11-16 05:30 | 2021-04-02 05:30 | Active | 2023-08-03 05:30 |  | 2025-03-05 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | PSMAfore: A phase III, Open-label, Multi-Center, Randomized Study Comparing 177Lu-PSMA-617 vs. a Change of androgen receptor-directed therapy in the Treatment of Taxane NaÃ¯ve Men with Progressive Metastatic Castrate Resistant Prostate Cancer | CAAA617B12302 Ph III pretaxane 2L mCRPC (PSMAfore) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Rathod, Dimple | Das, Chiranjeeb | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Renata Zieba | Renata Zieba | Bora, Deepthi Reddy | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 |  |  | DRM | Shafiudeen, Rehana Banu | Bairagi, Arpita | Completed | 13Sep2021 : RB : Rule file 3.0 finalized in the SUBWAY and the LSP is notified. 31Aug2021 : The Study is transitioned to Bairagi, Arpita. 31Aug2021 : RS2L,TR2L,TU2L included in Rule file. Working on DDPASS comments. Will finalize once completed. 05Aug2021 : Rule file 2.0 is finalized in SUBWAY. LSP is Notified. Missing forms DTS report updated. 06Jul2021 : QS1L, QS2L, QS3L, LBL reflecting in 06Jul2021 missing form DTS report. 28Jun2021 : The Rule File V2.0 is finalized in CREDI and the SNOW-51 ticket (RITM2716934) is raised. LSP is notified. 4May2021 : Rule file version 1.1 shared with the peer reviewer. 23Apr2021 : The form TUS006 is pending since the SDTM annotation is not yet final. 23Apr2021 : The Rule file 1.0 is finalized in SUBWAY and the LSP is notified. Peer review Angella 15Apr2021 : Received annotations for the rest of the bone scan forms 12Apr2021 : Round 1 peer review is completed. working on the comments. 8Apr2021 : The RF is sent for peer review 2Mar2021 : The study live is postponed to 30Mar2021 26Feb2021 : Received the SDTM annotations from the SDTM programmer. 17Feb2021 : Received the SRFs and the ALS from the DBD 04Feb2021 : Have requested the DBD for ALS, approved SRFs and SDTM annotation. | None | None | 2021-04-23 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2021-04-30 | Completed | 2021-05-03 05:30 |  |  | 2021-05-03 05:30 | 2021-05-03 05:30 |  | 2021-05-04 05:30 |  |  |  | 90 | RaveX - Inhouse | Yes |  | 2021-11-19 05:30 | 2021-11-22 05:30 | [9 empty] | NA | [5 empty] | 2 | 77 | 91 | 0 | 673 | 1007 | 0 | 271 | 48 | 221 | 1276 | 9 | 0 |  | Hormone-refractory prostate cancer | No | Global | Open | Yes | [10 empty] | 2021-05-03 05:30 |  |  |  | Interim-Analysis | Polavarapu, Vanaja | None of the above | Yes
CAAA617C1 | CAAA617C12301 | C4009865 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-01 05:30 | 2021-04-29 05:30 | 2021-06-11 05:30 | DB Conduct | DB Snapshot | 2022-07-07 05:30 | 2021-01-07 05:30 | 2020-12-11 05:30 | 2020-12-02 05:30 |  | Active | 2025-07-17 05:30 |  | 2026-01-28 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases |  | CAAA617C12301 Ph III mHSPC 2L Study (PSMAddition) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Chavan, Deepali Aniket | Das, Chiranjeeb | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Carolin Sachs | Carolin Sachs | Bonam, Rajesh Babu | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 01Jan2021 Conduct comments: Study transitioned from Pallabi to Deepthi |  | DRM | Shafiudeen, Rehana Banu | Bairagi, Arpita | Completed | 31Aug2021 : The Study is transitioned to Bairagi, Arpita. 31Aug2021 : The TU2L, RS2L, TR2L DTS include in the Rule file. It will be finalized once the DTS is final. 5Aug2021: Rule file V 2.0 finalized in SUBWAY and the LSP is notified. Included YRL, YDL, QS1L, QS2L, QS3L, LBL tables and TUS006, FAS001 forms in this version. 06Jul2021 : LBL, QS2L, QS3L, QS1Lreflecting in DTS report 06jul2021. 2Jun2021 : rule file 2.0 is sent for peer review. 05May2021 : FAS001, TUS006 forms are an exception for the V1.0 release, since the SDTM annotations are not yet final. Will be following up with the SDTM Programmer and get the forms included in the Rule file. 05May2021 : The Rule file V 1.000 is finalized in SUBWAY and the LSP is notified. 04May2021 : The Rule file peer review has been completed and working on the comments. 26Apr2021 : The Rule file was released for peer review. 14Apr2021 : Have completed the ALS review and have sent the comments to the DBD since it is a sister study of CAAA617B12302 the approved SRFs and SDTM annotations are used in this study. 1Apr2021 : Received the ALS and SRFs for review | None | None | 2021-05-05 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sai Krishna Mettugari | Completed | 2021-05-27 | Completed | 2021-05-28 05:30 |  |  | 2021-05-31 05:30 | 2021-05-31 05:30 |  | 2021-05-31 05:30 |  |  |  | 100 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 4 | 84 | 95 | 0 | 1045 | 1331 | 0 | 327 | 49 | 215 | 1595 | 9 | 0 |  | Prostate cancer | No | Global | Open | Yes | [10 empty] | 2021-05-28 05:30 | [5 empty] | None of the above
CAAA617D1 | CAAA617D12301 | C4014355 | Phase III |  | Rave EDC - Inhouse |  |  | 2022-09-30 05:30 | DB Set-Up | DB Go-live | 2022-08-11 05:30 |  | 2022-03-31 05:30 |  |  | Planned | 2028-02-18 05:30 |  | 2028-03-31 05:30 |  |  | Pioneer | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | An International Prospective Open-label, Multi-center, Randomized Phase III Study comparing [177Lu] Lu-PSMA-617 in combination with Standard of Care versus Standard of Care alone in adult male patients with Biochemically Recurrent (BCR) Prostate Cancer | CAAA617D12301 Lu-PSMA-617 Ph3 BCR Prostate Cancer | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Rastogi, Anisha | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Frederic Cortes | Fr��d��ric Cortes | RAMASWAMY, YAMINI | RAMASWAMY, YAMINI | [15 empty] | Sai Krishna Mettugari | [48 empty] | Prostate cancer | No | Global | Open | Yes
CAAA617F1 | CAAA617F12301 | C4014296 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-06-07 05:30 |  | 2022-09-30 05:30 | DB Set-Up | DB Go-live | 2022-08-11 05:30 |  | 2022-03-31 05:30 |  |  | Planned | 2028-03-09 05:30 |  | 2028-04-20 05:30 |  |  | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology |  | CAAA617F12301 Ph III_ nm CR Prostate Cancer | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Kundu, Sounak | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Katja Lehnhoff | Katja Lehnhoff | CHAUGHULE, JAGRUTI SUDHIR | CHAUGHULE, JAGRUTI SUDHIR | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 16 Feb 2022: Rule File programmer assigned. | [6 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 95 | [7 empty] | 1200 | 5 |  |  | Prostate cancer | No | Global | Open | Yes
CAAA802A1 | CAAA802A12101 | C4012360 | Phase I+II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-09 05:30 | DB Set-Up | DB Go-live | 2022-05-13 05:30 |  | 2022-02-11 05:30 | 2022-02-11 05:30 |  | Planned | 2024-01-18 05:30 |  | 2024-02-29 05:30 |  |  | other | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase I/II, open-label, multi-center study of [225Ac]Ac-PSMA-R2 in men with heavily pre-treated PSMA-positive metastatic castration-resistant prostate cancer (mCRPC) with or without prior 177Lu-labelled PSMA-targeted radioligand therapy. | CAAA802A12101 FIH study with Ac-PSMA-R2 | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Shaikh, Javeed | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Jean-Rene Basque | Jean-Rene Basque | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR | [6 empty] | Saha, Saikat | Not Started | [7 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 5 | 1 |  | Prostate cancer | No | Global | Open | Yes
CABL001A | CABL001A1401 | C4010424 | Phase IV | Other | Other |  |  | 2022-09-30 05:30 | Study Planned | DB Go-live | 2022-04-01 05:30 |  | 2022-04-30 05:30 |  |  | Planned | 2025-07-31 05:30 |  | 2025-11-27 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology |  | CABL001A1401 JPN PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | INOUE, YUSUKE | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | MASAYUKI SATO | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CABL001A | CABL001A2001B | C4008694 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2021-08-20 05:30 | 2021-10-12 05:30 | 2022-05-16 05:30 | DB Conduct | Final DBL | 2027-02-23 05:30 |  | 2021-04-16 05:30 | 2021-04-16 05:30 |  | Planned | 2027-01-12 05:30 |  | 2027-02-23 05:30 |  | FALSE | Roll over trial | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Open label, multi-center asciminib roll-over study to assess long term safety in patients who have completed a Novartis sponsored asciminib study and are judged by the investigator to benefit from continued treatment. | CABL001A2001B PIIIb-CML Rollover | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Joshi, Shrinivas | Kohli, Deepti | Chitre, Vrushali | Nair, Sreesha | Jacqueline Ewan | Jacqueline Ewan | Ganesan, Dhanalakshmi | Ganesan, Dhanalakshmi |  |  | 29Apr2021: Protocol has been finalized, received a draft activity planner. Timelines as per the draft planner- Go live- 4 Aug 2021 and FPFV 07 Sep 2021. Still the planner is under discussion and yet to receive the final planner (will be received by tomorrow). TDM has added the forms in the cart and is under review, team shall provide their comments by early next week. Initial Golive as 20Aug2021 when DBD assigned. |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 17Oct2021: RF development has been completed, SNOW 05 ticket has been raised and LSP has been notified and RF checklist uploaded in CREDI. 22Sept2021: SRF, ALS review has been done and comments have been shared. Waiting for the updated ALS to start RF development 11Aug2021: SRFs reviewed, comments shared with the DBD. Comments have been addressed. 14-Jul-2021: I have followed up with the DBD. The DBD has informed that the study go-live will be postponed. The TDM has been requested to update the iBoW. 26May2021 : RF Developer assigned. | None | None | 2021-10-16 05:30 |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | Completed | 2021-12-08 | Completed | 2021-12-14 05:30 |  |  | 2021-12-23 05:30 | 2021-12-23 05:30 |  | 2022-01-12 05:30 | [18 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2021-12-09 05:30 | [5 empty] | None of the above
CABL001A_MA | CABL001A2004 | C4008471 | Not Applicable | Other | CRO - EDC |  |  |  | DB Conduct |  |  |  | 2021-07-30 05:30 | 2021-08-02 05:30 |  | Active | [5 empty] | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | Retrospective chart review study of patients presented with CP-CML expressing T315I mutation and treated with Asciminib in managed access program | CABL001A2004 Retrospective chart review MAP pts | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Chandrakant, Khilari | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Ashley O'Loughlin | Ashley O'Loughlin | [17 empty] | Sai Krishna Mettugari | [28 empty] | Parexel | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes
CABL001A | CABL001A2102 | C1200469 | Phase I | NCDS | [7 empty] | 2016-05-19 05:30 |  | 2016-02-23 05:30 |  | Completed |  | 2016-07-06 05:30 |  | 2016-08-31 05:30 | FALSE |  |  |  | Outsourced |  | Human ADME ABL001 | CABL001A2102 Human ADME | PA Oncology (Hematology not for MA projects) | [5 empty] | Veronique Bedoucha | Veronique Paule Bedoucha | [15 empty] | Sundar, N Sushant | [16 empty] | OCRDC - Inhouse | [33 empty] | Chronic myeloid leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CABL001A | CABL001A2103 | C1001003 | Phase I | NCDS | CRO - EDC |  | 2016-04-20 05:30 |  | DB Locked |  |  | 2016-05-03 05:30 |  | 2016-01-13 05:30 |  | Completed |  | 2017-07-20 05:30 | 2018-01-16 05:30 | 2018-01-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase I, open-label, multi-center, single-dose, parallelgroup study to evaluate the pharmacokinetics of ABL001 in healthy subjects with normal hepatic function and subjects with impaired hepatic function | CABL001A2103 Hepatic Impairment PI-CML-CP/L0 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kulkarni, Abhijeet | K R, Chandran | Lateefuddin, Shariff Mohd | Gupta Bhaya, Soumya Kanti | Veronique Bedoucha | Veronique Paule Bedoucha | K S, Suneeth Kumar | [14 empty] | Kommu, Ranjith Kumar |  | Rohit Varate | [14 empty] | CRO | [6 empty] | ONC | Novartis | InHouse | 2016-04-20 05:30 |  |  |  | Parexel | [19 empty] | Hepatic impairment | No | Global | Open | Yes | [16 empty] | None of the above
CABL001A | CABL001A2104 | C1001001 | Phase I | NCDS | [7 empty] | 2017-03-02 05:30 |  | 2016-11-11 05:30 |  | Completed |  | 2017-06-07 05:30 |  | 2017-08-28 05:30 | FALSE |  |  |  | Outsourced |  | An open label, single dose, randomized cross-over study to characterize relative bioavailability of orally administered ABL001 CSF capsule and tablet formulations in healthy subjects | CABL001A2104 Rel. BA PI-HV | PA Oncology (Hematology not for MA projects) | [5 empty] | Veronique Bedoucha | Veronique Paule Bedoucha | Pedda Naganna, Krupakar Reddy | [14 empty] | Agavekar, Amit | [16 empty] | CRO | No | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-02-24 05:30 | [23 empty] | Chronic myeloid leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CABL001A | CABL001A2105 | C3001322 | Phase I | NCDS | CRO - EDC |  |  | 2018-11-13 05:30 | DB Locked |  |  | 2018-11-16 05:30 | 2018-04-26 05:30 | 2018-04-26 05:30 |  | Completed | 2019-05-17 05:30 | 2019-04-14 05:30 | 2019-06-27 05:30 | 2019-06-28 05:30 | FALSE |  | Bala, Indu | Cluster B (Haem,CRM,NS) | Outsourced | fGSK | Renal Impairment ABL001 | CABL001A2105 Renal Impairment study PI | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | P, Roja Rani | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Descamps | Laurence Descamps | Oguri, Praveen | [14 empty] | Sundar, N Sushant |  | Sandeep Kadam | [12 empty] | Old CRO Study. Will conduct DDPASS before any milestone |  | CRO | No | [5 empty] | ONC | Parexel | Outsourced |  |  |  |  | Parexel | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 1 | 0 |  | Renal impairment | No | Global | Completed | Yes | [16 empty] | None of the above
CABL001A | CABL001A2106 | C3001323 | Phase I | NCDS | CRO - EDC |  |  | 2018-09-17 05:30 | DB Locked | Final DBL Achieved |  | 2018-09-17 05:30 | 2018-04-17 05:30 | 2018-04-20 05:30 |  | Completed | 2019-02-28 05:30 | 2019-02-27 05:30 | 2019-05-23 05:30 | 2019-05-02 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase 1, open-label, fixed-sequence and staged drug-drug interaction study to investigate the effect of asciminib (ABL001) on the pharmacokinetics of midazolam (a sensitive CYP3A substrate), warfarin (a sensitive CYP2C9 substrate) and repaglinide (a sensitive CYP2C8 substrate) in healthy volunteers. | CABL001A2106 PI DDI ABL001 as perpetrator | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Atiketi, Spandana | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Descamps | Laurence Descamps | Oguri, Praveen | [14 empty] | Tidke, Shyam |  | Amit Agavekar | [12 empty] | DDPASS conducted before final DBL. All the domains passed in 1st DDPASS meeting, study locked now. | 100 | CRO | [6 empty] | ONC | Parexel | Outsourced |  |  |  |  | Parexel | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Chronic myeloid leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CABL001A | CABL001A2107 | C3001324 | Phase I | NCDS | CRO - EDC |  |  | 2019-04-08 05:30 | DB Locked |  |  | 2019-04-04 05:30 | 2018-11-30 05:30 | 2018-12-05 05:30 |  | Completed | 2020-04-10 05:30 | 2020-04-08 05:30 | 2020-06-04 05:30 | 2020-05-27 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A phase I, open label, drug-drug interaction study to assess the effect of steady-state itraconazole (strong CYP3A inhibitor), quinidine (P-gp inhibitor) and rifampicin (strong CYP3A inducer) on the pharmacokinetics of a single dose of asciminib in healthy subjects | CABL001A2107 PI DDI: ABL001 as victim | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | K R, Chandran | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Xiaolu Yu | Monali Sura | Tadiparthy, Ramakanth | Tadiparthy, Ramakanth | [15 empty] | Amit Agavekar | [21 empty] | ONC | Novartis | Outsourced |  |  | Kanchi, Pavan kumar | Gehlawat, Priya | Parexel | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Chronic myeloid leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CABL001I1 | CABL001A2108 | C4003299 | Phase I | Other | CRO - EDC |  |  | 2021-05-31 05:30 | DB Conduct |  |  | 2021-05-21 05:30 | 2020-10-01 05:30 | 2020-11-05 05:30 |  | Active | 2021-08-08 05:30 | 2021-08-08 05:30 | 2021-09-30 05:30 | 2021-10-06 05:30 | FALSE | Ph 1 CP HV trial | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Relative BA study to support formulation development of ABL001 dose strength &lt;20 mg single agent | CABL001A2108 rBA 40mg dose vs minitablet (pediat.) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | K R, Chandran | K R, Chandran | Chitre, Vrushali | Nair, Sreesha | Veronique Bedoucha | Veronique Paule Bedoucha | [17 empty] | Amit Agavekar | [28 empty] | Parexel | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CABL001A | CABL001A2109 | C4005626 | Phase I | Other | Other |  |  | 2021-05-21 05:30 | DB Conduct | Final DBL Achieved |  | 2021-05-21 05:30 | 2020-06-26 05:30 | 2020-06-19 05:30 |  | Active | 2021-12-01 05:30 | 2021-12-01 05:30 | 2022-01-31 05:30 | 2022-01-24 05:30 | FALSE | Ph 1 CP HV trial | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A randomized, single dose, open-label, two period, cross-over study to assess the bioequivalence of two tablet formulations of asciminib in healthy subjects | CABL001A2109 PI-CP-HV rBE clin vs. launch material | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | K R, Chandran | K R, Chandran | Chitre, Vrushali | Nair, Sreesha | Laurence Descamps | Laurence Descamps | [17 empty] | Amit Agavekar | [28 empty] | Parexel | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CABL001A | CABL001A2110 | C4015584 | Phase I |  |  |  |  | 2022-11-07 05:30 |  | Final DBL | 2023-07-25 05:30 |  | 2022-06-26 05:30 |  |  | Planned | 2023-05-23 05:30 |  | 2023-07-25 05:30 | [5 empty] | FULL Outsourced |  |  | CABL001A2110 PI DDI with strong CYP3A4/UGT inducer | PA Oncology (Hematology not for MA projects) | [6 empty] | Christine Reynolds | [66 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes
CABL001A | CABL001A2202 | C4007750 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-02-21 05:30 | 2021-12-03 05:30 | 2022-01-21 05:30 | DB Conduct | Final DBL | 2025-03-10 05:30 | 2021-12-06 05:30 | 2021-05-21 05:30 | 2021-05-06 05:30 |  | Active | 2025-02-04 05:30 |  | 2025-03-10 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A randomized, open-label, multi-center, phase II study of asciminib versus best available therapy in Chinese patients with Chronic Myelogenous Leukemia in chronic phase (CML-CP), previously treated with 2 or more tyrosine kinase inhibitors | CABL001A2202 China PII mono | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Joshi, Shrinivas | Kohli, Deepti | Chitre, Vrushali | Nair, Sreesha | Keira Ding | Liju Ding | Das, Devashish | KADAM, NAVINA VIJAY | Not Started |  | Feb 2022 : Devashish to transition study to Navina Kadam |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 16Feb2022: RF and Checklist Version 2.0 have been finalized with the EG and B1 DTS details in it. SNOW 51 request RITM3500478 has been raised and notified the LSP. 11Feb2022: RF updated with EG and B1 DTS tables and released for the peer review. 10Feb2022: EG1L and B11L DTS have been finalized in the CREDI. DBD confirmed. 2Feb2022: Observed the “Missing forms and DTS” report and got to know that EG1L, IRT and B1 DTS are finalized yet not informed by the DBD. Informed the DBD regarding this communication gap 6Dec2021: Study go-live achieved and LSH PROD ticket has been raised. Notified the LSP. 3Dec2021: Peer review completed, RF and Checklist finalized in the CREDI. LSH TEST ticket has been raised and notified the LSP. 2Dec2021: Received 1st round peer review comments. Sent the DB related comments to the DBD and updated the RF as per the comments. Shared the updated RF for 2nd round including all the latest changes. 1Dec2021: Shared the RF for peer review. DBD shared another new form to be added at the last moment. 29Nov2021: DBD replied to the peer review comments with the updated ALS, SOD and SDTM annotations. Shared some additional further comments. 16Nov2021: Sent the 1st round peer review comment to the DBD and asked for the latest SOD for RF building 11Nov2021: DBD shared the ALS, SDTM, SRFs for peer review. Go-live date updated to 3Dec2021 23Aug2021 : Received the activity planner for the study. 20Aug2021: RF developer assigned with Golive as 25Nov2021 | None | IRT DTS to be added. | 2021-12-06 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2021-12-14 | Completed | 2021-12-17 05:30 |  |  | 2021-12-17 05:30 | 2021-12-17 05:30 | FPFV happened before the actual date. | 2021-12-21 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | 2021-12-03 05:30 | [9 empty] | 2021-12-16 05:30 | [5 empty] | None of the above | Yes
CABL001A | CABL001A2301 | C1001002 | Phase III | NCDS | OC RDC - Inhouse | 2017-07-17 05:30 | 2017-07-17 05:30 |  | DB Conduct | Final DBL | 2025-02-26 05:30 | 2017-10-26 05:30 |  | 2017-02-23 05:30 |  | Active | 2024-12-18 05:30 |  | 2025-02-26 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase 3, multi center, open label randomized study of oral ABL001 versus bosutinib in patients with Chronic Myelogenous Leukemia in chronic phase (CML-CP), previously treated with 2 or more tyrosine kinase inhibitors. | CABL001A2301 PIII-CML-CP/L3-C (Bosutinib) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Gutta, Sudhakar Madhu | Kumar HC, Vijay | Chitre, Vrushali | Nair, Sreesha | Veronique Bedoucha | Veronique Paule Bedoucha | Govula, Shashikanth | Mareedu, Vasu |  | 2020-06-15 05:30 | [11 empty] | Agavekar, Amit |  | Amit Agavekar | [12 empty] | Planned DDPASS in Q2 | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-07-17 05:30 | 2017-07-17 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 122 | 0 |  |  | 0 |  |  |  | 676 | 8 | 0 |  | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CABL001A_MA | CABL001A2302 | C4008726 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-06-04 05:30 | 2021-09-03 05:30 | 2021-10-25 05:30 | DB Conduct | Final DBL | 2026-07-23 05:30 | 2021-10-13 05:30 | 2021-06-21 05:30 | 2021-07-05 05:30 |  | Active | 2026-06-11 05:30 |  | 2026-07-23 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | A phase 3b, multi-center, open-label, two cohort dose optimization study of oral asciminib in patients with Chronicy Myelogenous Leukemia in chronic phase (CML-CP) previously treated with 2 or more tyrosine kinase inhibitors | CABL001A2302 CML-CP 3L dose optimization | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Chandrakant, Khilari | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Marina White | Marina White | Gupta, Anshu | Mareedu, Vasu |  |  | 29Apr2021 : Madhu M supporting in Anshu's absence. TDM to Share activity planner. Activity may start next week. Initial DB golive 04Jun2021 when DBD assigned. |  | DRM | Kuttoboina, Sujan Kumar | Saha, Saikat | Completed | 21Oct2021 : Updated the RF with LBL, B11L, YDL and YRL DTS and sent for peer review. Received the peer review comments and finalized the RF and Checklist. SNOW 51 LSH ticket has been created 19Oct2021 : Received Yx DTS to review. Reviewed and provided the comments to the TDM. 10Oct2021 : Received the peer review comments, sent it back to the TDM. TDM confirmed that the changes will be included in the next versions and asked us to proceed with the finalization. 8Oct2021 : LB and B1 DTS have been finalized in the DMS. RF update and peer review in progress. 22Sep2021 : TDM reverted back the LB domain DTS. Reviewed again and sent with further comments to update. 21Sep2021 : Completed the review and provided the comments to the DBD and TDM. 20Sep2021 : Received 3 DTS for B1, LB and Yx domain to review. 06Sep2021 : Rule file and Rule File Review Checklist have been finalized on CREDI. Snow ticket has been raised as well. 03Sep2021 : Study went on live today. Will finalize the RF on 6th September 2021. 30Aug2021 : Study go-live has been pushed to 31Aug2021. 27Aug2021 : RF peer review completed and the updates are in progress. Asked DBD for the updated SDTM annotations and a few updates in the DB. 25Aug2021 : Rule File has been developed and sent for the Peer Review. 24Aug2021 : Provided additional ALS review comments. RF build complete. Waiting for further updates from DBD. Will release for peer review after that. 20Aug2021 : Got updated ALS from DBD. working on RF. 09Aug2021: Reassigned from Sujan to Saikat. 04Aug2021 : Received the updated ALS, SRFs and SDTM annotations. 26JUL2021: TDM has communicated there has been early FPFV. This is the reason there is more than one month gap between go-live date and FPFV date. 23JUL2021: Second round of OSRM updates are ongoing. Once updates are done, DBD will share required documents to RF developer for review. 16JUN2021: DB go-live has been planned on 30-AUG-2021 as per current Activity planner. Requested DM to update same in BOW. 11JUN2021: Requested lead DBD for to share current study status and activity planner. 21May2021: RF developer Sujan Assigned. | None | B12L DTS to be added | 2021-09-06 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2021-09-16 | Completed | 2021-09-23 05:30 |  |  | 2021-09-23 05:30 | 2021-09-23 05:30 |  | 2021-09-27 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 2 | 23 | 55 | 0 | 181 | 748 | 0 | 230 | 45 | 130 | 923 | 4 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2021-09-21 05:30 | [5 empty] | None of the above | Yes
CABL001E | CABL001E2101 | C3000628 | Phase I | NCDS | Other |  |  | 2017-12-19 05:30 | DB Locked |  |  | 2017-12-19 05:30 |  | 2017-09-25 05:30 |  | Completed | 2018-03-20 05:30 | 2018-03-31 05:30 | 2018-08-07 05:30 | 2018-06-26 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | DDI study assessing ABL+ IMA vs IMA vs ABL001 for DDI ; C-QT and food effect | CABL001E2101 PI DDI/Foodeffect (imatinib) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Vutukuri, Lakshmi | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha |  | Sabine Hertle | [15 empty] | Agavekar, Amit |  | Amit Agavekar | [14 empty] | CRO | No | -NA- | [11 empty] | Parexel | [19 empty] | Chronic myeloid leukaemia | No | Global | Completed | Yes | [15 empty] | R, Harini | None of the above | Yes
CABL001E | CABL001E2201 | C3000642 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2018-08-30 05:30 | 2018-08-30 05:30 | 2018-11-12 05:30 | DB Conduct | Final DBL | 2022-12-23 05:30 | 2018-11-22 05:30 | 2018-07-18 05:30 | 2018-05-28 05:30 |  | Active | 2022-11-11 05:30 |  | 2022-12-23 05:30 |  | TRUE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Ph2, multi-center, open-label, randomized study in CML-CP patients previously treated with imatinib and not achieved DMR (asciminib+imatinib vs continued imatinib vs switch to nilotinib) | CABL001E2201 PII-CML-CP/C (imatinib) 4-arm random | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Tupakula, Narasimha Penchala | Kohli, Deepti | Chitre, Vrushali | Nair, Sreesha | Monali Sura | Monali Sura | Bai, Chandrakala | Ahuja, Mohit | Completed | 2019-11-18 05:30 |  |  | DRM (DIAL) | Sama, Ashok | Shrivastava, Nikhil | Completed | 07-Feb-2022: Updated and finalized the RF V13.0 for correcting the typo error occurred in RF V12.0 in CM domain. Raised SNOW-51 (RITM3464493) ad notified the LSP. 02-Feb-2022: Updated and finalized the RF V12.0 as per the SDTM requirement for mapping Subject Status forms into SS domain. Raised SNOW-51 ad notified the LSP. 04-Jan-2021: B13L DTS included in the Rule File V11.0 and finalized. SNOW-51 is raised and LSP is notified. 20-Apr-2021: Rule File V10.0 WRT PPC#13 is updated and finalized. SNOW-51 is raised and LSP is notified. 15-Apr-2021: PPC#13 is currently ongoing. RF is impacted. 24Dec2020: SNOW-51 request raised for LSH setup WRT PPC#12. LSP notified for the same. No impact to Rule File. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 06Jul2020: Rule file V9.0 is Latest. Study transitioned from Ashok to Nikhil 22Apr2020: RF v9.0 is finalized. Newly added 3rd party table B12L in this RF v9.0. Feb2020 : Study transitioned from Chandrakala to Ashok 17Jan2020: RF v8.0 is finalized. Added EG domain - EGG001,EGG001_1,EGG001_2 in this RF v8.0. 25Oct2019: RF v7.0 is finalized. | None | None | 2018-09-12 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2018-10-15 | Completed | 2019-07-18 05:30 |  |  | 2018-10-15 05:30 | 2018-10-15 05:30 |  | 2019-08-23 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5 | 2022-02-19 05:30 | 2022-02-21 05:30 | [9 empty] | NA | [5 empty] | 13 | 40 | 90 | 0 | 347 | 958 | 0 | 204 | 35 | 279 | 1272 | 11 | 0 |  | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [10 empty] | 2019-07-18 05:30 | 29 | 29 | 2022-02-18 05:30 |  |  | None of the above
CABL001E | CABL001E2301 | C3000643 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2021-01-07 05:30 | DB On hold | Final DBL | 2024-09-11 05:30 |  | 2020-11-30 05:30 |  |  | Stopped (with patients) | 2024-07-03 05:30 |  | 2024-09-11 05:30 |  | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | 2 arm randomized ph3 study in CML-CP patients receiving 1L TKI treatment &gt;2 yrs and not reaching DMR (ABL001 + IMA vs stay on IMA) | CABL001E2301 PIII-CML-CP/C (imatinib) 2-arm random | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | K R, Chandran | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Anne-Sophie Longin | Anne-Sophie Longin | [15 empty] | Agavekar, Amit |  | Amit Agavekar | [28 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1100 | 10 | 0 |  | Chronic myeloid leukaemia | No | Global | Terminated | Yes | [16 empty] | None of the above
CABL001I1 | CABL001I12201 | C4008521 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-06-15 05:30 | 2021-08-19 05:30 | 2022-01-10 05:30 | DB Conduct | Final DBL | 2029-12-31 05:30 | 2021-12-27 05:30 | 2021-04-09 05:30 | 2021-04-01 05:30 | 2021-07-29 05:30 | Active | 2029-11-19 05:30 |  | 2029-12-31 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A multi-center, open-label study to determine the dose and safety of oral asciminib in pediatric patients with Philadelphia chromosome positive chronic myeloid leukemia in chronic phase (Ph+ CML-CP), previously treated with one or more tyrosine kinase inhibitors | CABL001I12201 PI/II-CML-2L-SA-pediatric | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kumar HC, Vijay | Kohli, Deepti | Chitre, Vrushali | Nair, Sreesha | Laurence Descamps | Laurence Descamps | Bora, Deepthi Reddy | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | 19Apr2021 : Leah supporting the study for the CRF review within DO Accelerate tool in Deepthi's absence. 10May2021 : As discussed with TDM Go-live will push to 1st week of July,2021. Initial golive 03Jun2021. 18June2021: Till 15th June,2021, Did not receive any of the below mentioned documents, when Planed Go-live is on 4th July,2021. • SSD • SRFs documents • ALS from DO Accelerate As documents has been received on 16th June,2021, So Go-live has been changed to 1st week of Aug. |  | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 02Feb2021: Rule file v3.0 is finalized in SUBWAY for the DTS (LB1L, YDL) addition. 09Sep2021: Rule file v2.0 is finalized in SUBWAY for the DTS (B11L, EG1L) addition. 19Aug2021: Rule File Version 1.0 finalized in subway. SNOW#05 (RITM2893247) Request raised for new study setup in LSH. 12Aug2021: RF Peer Review ongoing. Go-live pushed to 17-Aug-2021. 9Aug2021 : Reassigned from Angella to Satwik. Satwik developed RF and Review by Angella. 9-AUG-2021: RF Peer Review ongoing. DB comments have been shared with DBD for updates. ALS awaited. Go-live pushed to 12-AUG-2021. 30-Jul 2021: SRF related queries highlighted to TA POD and TDM. Awaiting confirmation. 26-Jul-2021: Documents received for RF creation (except UAT SOD). 26May2021: RF developer assigned | None | None | 2021-08-19 05:30 |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | Completed | 2021-09-27 | Completed | 2021-09-30 05:30 |  |  | 2021-10-05 05:30 | 2021-10-05 05:30 |  | 2021-09-23 05:30 | [5 empty] | No | [12 empty] | NA | [5 empty] | 1 | 17 | 69 | 0 | 285 | 802 | 0 | 218 | 44 | 162 | 1008 | 4 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2021-09-30 05:30 | [5 empty] | None of the above
CABL001J1 | CABL001J12301 | C4009521 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-09-01 05:30 | 2021-09-02 05:30 | 2021-10-29 05:30 | DB Conduct | DB Snapshot | 2022-06-20 05:30 | 2021-10-06 05:30 | 2021-05-19 05:30 | 2021-06-02 05:30 |  | Active | 2028-11-24 05:30 |  | 2029-01-19 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Ph III ABL vs Inv choice TKI (IMA/2GTKI) on CML-CP 1L all comers | CABL001J12301 PIII-CML-CP/L1-(IMA/2G TKI) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Atiketi, Spandana | Kohli, Deepti | Chitre, Vrushali | Nair, Sreesha | Sophie Ifrah | Sophie Ifrah | Moses, Leah | Kala, Arpit | Completed | 2021-12-13 05:30 | 13-Dec-2021 - Leah Moses transitioned Study to Arpit Kala 29Apr2021 : 9 weeks KPI was decided to be followed. Protocol Finalized. CRFs are being reviewed by the CTT. Awaiting specs to initiate DB Build. Initial golive planned as 01Sep2021 when DBD assigned. |  | DRM | Saha, Saikat | Kuttoboina, Sujan Kumar | Completed | 11JAN2022: RF V2.0 is final and Snow 51 RITM3367589 request has been created, request you to build B1, YR and YD domains and rebuild EG domain. Rule file Changes: B1 domain: B11L, B12L DTS have been added YR and YD domain: YRL and YDL DTS tables have been added EG domain: EG1L DTS has been added 27OCT2021: RF V1.0 is final and SNOW 05 request RITM3126254 has been created 03SEP2021: RF development has been completed. Peer review is ongoing and expected date of Rule file completion is 06SEP21. 12AUG2021: Lead DBD has shared latest ALS on 11AUG21 with two forms pending ePRO and Extra medullary involvement. Rest of the study specific pages have been reviewed and will work on Rule file development except two forms. 11AUG2021: DB Golive has been pushed to 31AUG21 as per lead DBD confirmation. Requested to update iBow. 26JUL2021: DB Go live date is planned on 16AUG2021 as of now. Study team are trying to meet this timeline. However, the DM and CTT have been informed that the timeline may need to be reconsidered owing to the initial delays in DOA, specs finalization and complexity of the study. As FPFV is on 30SEP2021, if required, we will push the DB go live date by 2 weeks. 09JUN2021: This is DO accelerate study. As per Current DB Go Live date is 21JUL2021, as per today not received any documents for review. Following up with Lead DBD on the status of the study 26May2021 : RF developer assigned. |  |  | 2021-10-27 05:30 | Delay in receiving pre requisites and multiple DB updates. Additional time take for RF development and peer review comments. | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2021-11-17 | Completed | 2021-11-17 05:30 |  |  | 2021-11-17 05:30 | 2021-11-17 05:30 |  | 2021-11-17 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 58 | 93 | 0 | 437 | 1117 | 0 | 220 | 48 | 339 | 1504 | 7 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2021-11-11 05:30 | [5 empty] | None of the above
CABL001J1_MA | CABL001J12302 | C4014545 | Phase III | NCDS_2 |  |  |  | 2022-09-30 05:30 |  | Final DBL | 2027-04-05 05:30 |  | 2022-04-29 05:30 |  |  | Planned | 2027-02-23 05:30 |  | 2027-04-05 05:30 | [5 empty] | InHouse |  |  | CABL001J12302 2022-ASC-2-INT 1L CML GMA study | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Catherine Bouard | Catherine Bouard | [54 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Chronic myeloid leukaemia | No | Global | Open | Yes
CABL001A | CABL001X2101 | C1001004 | Phase I | NCDS | OC RDC - Inhouse | 2014-03-31 05:30 | 2014-03-31 05:30 |  | DB Conduct | Final DBL | 2024-02-20 05:30 | 2014-04-24 05:30 |  | 2013-11-27 05:30 |  | Active | 2024-01-23 05:30 |  | 2024-02-20 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase I, multicenter, open-label study of oral ABL001 in patients with chronic myelogenous leukemia or Philadelphia Chromosome-positive acute lymphoblastic leukemia | CABL001X2101 FIH | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Atiketi, Spandana | Kumar HC, Vijay | Chitre, Vrushali | Nair, Sreesha | Nathalie Pognan | Nathalie Pognan | Shewane, Roshni | Katam, Veera Nagendra | Completed | 2021-01-06 05:30 | Study Transitioned to Nagendra Katam on 06Jan2021. | [10 empty] | Agavekar, Amit |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2014-03-28 05:30 |  | Shewane, Roshni | NA | [7 empty] | 315 | 0 |  |  | 0 |  |  |  | 557 | 3 | 0 |  | Leukaemia | No | Global | Open: Reapproval | Yes | [14 empty] | Interim-Analysis | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CABO809A0 | CABO809A02101 | C4008383 | Phase I | Other | CRO - EDC |  |  | 2022-03-29 05:30 | DB Set-Up | DB Go-live | 2022-03-01 05:30 |  | 2021-05-25 05:30 | 2021-07-26 05:30 |  | Planned | 2022-10-05 05:30 |  | 2022-12-07 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | An Open Label Cryptosporidium Controlled Human Infection Model (CHIM) to assess the efficacy and safety of ABO809 in healthy participants | CABO809A02101 Crypto CHIM Validation Study | R4 NITD - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Amanda Nguyen | Amanda Nguyen | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Cryptosporidiosis | Yes | Global | Open | Yes | [16 empty] | None of the above
CACZ885D | CACZ885D1401 | C1001005 | Phase IV | Other | Paper |  |  | 2012-03-05 05:30 | DB Locked |  |  | 2012-03-08 05:30 | 2011-09-28 05:30 | 2011-09-28 05:30 |  | Completed | 2020-12-17 05:30 | 2020-12-26 05:30 | 2021-11-15 05:30 | 2021-11-15 05:30 | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Drug use observational investigation of Ilaris | CACZ885D1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | NAKAGAWA, TOMOMI | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MAKOTO NAGASAKI | MAKOTO NAGASAKI | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Cryopyrin associated periodic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885D | CACZ885D2307E1 | C1001007 | Phase III | NOVDD | [7 empty] | 2012-01-16 05:30 |  | 2011-11-25 05:30 |  | Completed |  | 2015-10-13 05:30 |  | 2015-12-01 05:30 | FALSE |  |  |  | Outsourced |  | An open-label extension study to assess efficacy, safety and tolerability of canakinumab and the efficacy and safety of childhood vaccinations in patients with Cryopyrin Associated Periodic Syndromes (CAPS) | Infant/vaccination_CACZ885D2307E1 | P7 Immunology Hepatology and Dermatology | [6 empty] | Paula Ana Dos Reis Rebola Stevenson | [66 empty] | Autoimmune disorder | No | Global | Completed | [17 empty] | None of the above
CACZ885B2 | CACZ885D2310 | C4009034 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-04-24 05:30 | 2020-04-24 05:30 | 2020-04-30 05:30 | DB Locked | Final DBL Achieved |  | 2020-04-30 05:30 | 2020-04-10 05:30 | 2020-04-10 05:30 |  | Completed | 2020-12-28 05:30 | 2020-12-22 05:30 | 2021-02-23 05:30 | 2021-02-23 05:30 | TRUE | No Priority specified | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Phase 3 multicenter, randomized, double-blind, placebo controlled study to assess the efficacy and safety of canakinumab on cytokine release syndrome in patients with COVID-19-induced pneumonia (CAN-COVID) | CACZ885D2310 COVID_19 Ph3 study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Panyam, Pradeep Kumar | Doshi, Pranav | Vasi, Munir | Ninan, Esther | Vishal Mishra | Murtuza Shabbirbhai Bughediwala | Rana, Aamir | Rana, Aamir | Not Started |  |  |  | DRM | Shrivastava, Nikhil | Shrivastava, Nikhil | Completed | 26Nov2020: Backup: Rehana Whats planned: (Covid 19 study) Nothing planned as of now. 11-Sep-2020 (SHRIVNI5): B12L DTS included in RF V5.0 and finalized. SNOW-51 ticket raised for LSH rebuild. 23-Jun-2020 (SHRIVNI5): B11L DTS included in RF V4.0 and finalized. SNOW-51 ticket raised for LSH rebuild. 11-Jun-2020 (SHRIVNI5): RF V3.0 finalized for addition of 1 new CM page. Sent for LSH rebuild. 30-Apr-2020 (SHRIVNI5): RF V2.0 finalized and sent for LSH process for SS domain. 24Apr2020: RF finalized and sent for LSH setup | None | None | 2020-04-24 05:30 | RF finalized within Go-live + 5 days | Gandikota, Sree Lakshmi | Garje, Sagar | Sandeep Kadam | Completed | 2020-04-26 | Completed | 2020-04-26 05:30 |  |  | 2020-04-26 05:30 | 2020-04-26 05:30 |  | 2020-04-29 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#ZK | 2021-03-11 05:30 | 2021-03-12 05:30 | [9 empty] | NA | [5 empty] | 4 | 36 | 43 | 0 | 278 | 434 | 0 | 169 | 40 | 145 | 619 | 2 | 0 |  | Autoinflammatory disease; Corona virus infection | Yes | Global | Wind Down | Yes | [10 empty] | 2020-04-26 05:30 |  |  |  | Interim-Analysis | R, Harini | COVID19 | No
CACZ885G | CACZ885G1301 | C1001009 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-05-07 05:30 |  | 2014-11-18 05:30 |  | Completed | 2018-07-23 05:30 | 2018-08-01 05:30 | 2018-09-03 05:30 | 2018-09-11 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA Shared JP | DF ID | An open label, single-arm, active-treatment, efficacy and safety study of canakinumab (ACZ885) administered for at least 48 weeks in Japanese patients with Systemic Juvenile Idiopathic Arthritis (SJIA) | Japan registration_CACZ885G1301 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Tsukazaki, Mayuka | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther | YOTA TAKAHASHI | MAKI YAMAGUCHI | Bonam, Rajesh Babu | [14 empty] | Manoharan, Vivek |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2015-04-02 05:30 | 2015-04-02 05:30 |  |  | NA | [7 empty] | 126 | 0 |  |  | 0 |  |  |  | 451 | 12 | 0 |  | Juvenile arthritis | No | Local | Completed | Yes | [16 empty] | None of the above
CACZ885G | CACZ885G1302 | C4006696 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-08 05:30 | 2021-01-13 05:30 | 2021-03-31 05:30 | DB Conduct | Interim DBL | 2022-12-12 05:30 | 2021-03-30 05:30 | 2020-08-28 05:30 | 2020-09-11 05:30 |  | Active | 2024-01-26 05:30 |  | 2024-03-22 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | An open-label, single-arm, active-treatment study to evaluate efficacy and safety of canakinumab (ACZ885) administered for at least 48 weeks in Japanese patients with Adult Onset Stillâs Disease (AOSD) | CACZ885G1302 JPN AOSD Ph3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Tsukazaki, Mayuka | Doshi, Pranav | Vasi, Munir | Ninan, Esther | YOSHIUMI OKUBO | YOSHIUMI OKUBO | Suzuki, Hiroko | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | Initial go live as 08Jan2021 (DM BOW) and 29Jan2021 as per RaveX tracker when RF developer assigned on 17Apr2021. |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 26Apr2021: Rule file v3.0 is finalized in CREDI for the DTS (QS4L,QS5L,ZW1L,ZW2L and ZW3L DTSs) addition. Rule file v2.0 was finalized in CREDI for the DTS (LB1L,LB2L,QS1L,QS2L,QS3L DTSs) addition on 25Mar2021. 13Jan2021: Rule File version 1.0 finalized. No DTS has been finalized yet hence not included. 25Mar2021: RF v2.0 finalized with LB1L,LB2L,QS1L,QS2L,QS3L DTSs added. | None | None | 2021-01-13 05:30 |  | Polavarapu, Vanaja | Polavarapu, Vanaja | Sandeep Kadam | Completed | 2021-02-04 | Completed | 2021-02-05 05:30 | The initial ticket was assigned on 15-Jan-2021. Also the DRM build was completed for priority domains by 5-Feb-2021. As the FPFV got delayed there were few discussions happened between the team and we all agreed to provision the data before 15th-Feb-2021. The FPFV is due on 31-Mar-2021. |  | 2021-02-11 05:30 | 2021-02-11 05:30 | FPFV is planned to happen on 31-Mar-2021. | 2021-03-31 05:30 |  |  | The DDPASS meeting is ongoing. | 40 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 2 | 46 | 52 | 0 | 475 | 467 | 0 | 175 | 36 | 152 | 655 | 11 | 0 |  | Still's disease | No | Global | Open | Yes | [10 empty] | 2021-02-05 05:30 | [5 empty] | None of the above
CACZ885G | CACZ885G1401 | C3003526 | Phase IV | Other | CRO - EDC |  |  | 2018-12-28 05:30 | DB Conduct | Final DBL | 2025-10-31 05:30 | 2018-11-02 05:30 | 2018-07-05 05:30 | 2018-07-05 05:30 |  | Active | 2025-06-30 05:30 |  | 2025-10-31 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID |  | CACZ885G1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | MURAKAMI, TAKUMI | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MAKOTO NAGASAKI | MAKOTO NAGASAKI | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Juvenile arthritis | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885G | CACZ885G2306 | C1001011 | Phase IV | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-11-17 05:30 |  | 2014-05-13 05:30 |  | Completed | 2017-09-22 05:30 | 2017-09-25 05:30 | 2018-01-22 05:30 | 2018-01-22 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA Transaction | DF ID | Ã-SPECIFIC 4 Patients: Study of Pediatric EffiCacy and Safety wIth FIrst-line use of Canakinumab. An open-label canakinumab (ACZ885) dose reduction or dose interval prolongation efficacy and safety study in patients with Systemic Juvenile Idiopathic Arthritis (SJIA) | CACZ885G2306 Long-term Efficacy/Safety PAES | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Fasih, Arshad | Vasi, Munir | Vasi, Munir | Ninan, Esther | Darshna Modi | Gregory O'Neil | Bonam, Rajesh Babu | [14 empty] | Chakravarthy, Meghna |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | [6 empty] | Pharma | Novartis | InHouse |  |  |  |  | NA | [7 empty] | 312 | 0 |  |  | 0 |  |  |  | 408 | 14 | 0 |  | Juvenile arthritis | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885M | CACZ885M2201 | C3000163 | Phase II | NOVDD |  |  |  | 2018-06-08 05:30 |  |  |  | 2012-10-30 05:30 | 2018-01-19 05:30 | 2012-05-25 05:30 |  | Stopped (with patients) | 2019-12-20 05:30 | 2016-08-04 05:30 | 2018-04-11 05:30 | 2016-12-20 05:30 | FALSE |  |  |  | ED Outsourced |  |  | CACZ885M2201 PAD POC | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Neda Huseinovic | [66 empty] | Peripheral vascular disease | No | Global | Completed | Yes | [16 empty] | None of the above
CACZ885M | CACZ885M2301 | C1001014 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2011-04-11 05:30 |  | 2010-10-07 05:30 |  | Completed | 2019-02-21 05:30 | 2019-04-14 05:30 | 2019-04-30 05:30 | 2019-04-26 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | IDMA Transaction | DF CRM | A randomized, double-blind, placebo-controlled, event driven trial of quarterly subcutaneous canakinumab in the prevention of recurrent cardiovascular events among stable post-myocardial infarction patients with elevated hsCRP | CACZ885M2301_CANTOS | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Gupte, Smita | Gupte, Smita | Tummalapenta, Venkateswarlu | Nair, Sreesha | Parijat Nandy | Miriam Marshood | [15 empty] | Sahu, Ahallad |  | Amit Agavekar | [28 empty] | NA | [7 empty] | 156 | 0 |  |  | 0 |  |  |  | 1187 | 8 | 0 |  | Cardiovascular event prophylaxis | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885N | CACZ885N1401 | C1001016 | Phase IV | Other | Paper |  |  | 2017-02-15 05:30 | DB Conduct | Final DBL | 2027-05-19 05:30 | 2017-02-23 05:30 | 2016-08-24 05:30 | 2016-08-24 05:30 |  | Active | 2027-01-19 05:30 |  | 2027-05-19 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Drug use observationl study of Ilaris in Hereditary periodic fever sydrome | CACZ885N1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | NAKAGAWA, TOMOMI | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MAKOTO NAGASAKI | MAKOTO NAGASAKI | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Familial mediterranean fever; Mevalonate kinase deficiency; Tumor necrosis factor receptor-associate | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885N | CACZ885N2301 | C1001015 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-06-27 05:30 |  | 2014-01-24 05:30 |  | Completed |  | 2017-07-04 05:30 |  | 2017-09-05 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA | DF ID | A Phase III randomized placebo controlled parallel arm safety, efficacy and PK/PD umbrella study of canakinumab treatment in patients with active Hereditary Periodic Fevers (TRAPS, HIDS, and colchicine resistant FMF). | CLUSTER Phase III_CACZ885N2301 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sharma, Tanvi | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther | Michele Eckhardt | Michele Eckhardt | [15 empty] | Sahu, Ahallad |  | Sandeep Kadam | [28 empty] | Cognizant | [19 empty] | Periodic fever | No | Global | Completed | Yes | [16 empty] | None of the above
CACZ885N | CACZ885N2301E2 | C1001017 | Phase III | NCDS | [7 empty] | 2016-10-03 05:30 |  | 2016-06-07 05:30 |  | Completed |  | 2017-01-27 05:30 |  | 2017-02-22 05:30 | FALSE |  |  |  | InHouse |  | An extension study of CACZ885N2301, multi-center, open label study of Canakinumab in Japanese patients with Periodic Fever Syndromes (TRAPS, HIDS, or crFMF) | Extension in Japan_CACZ885N2301E2 | P7 Immunology Hepatology and Dermatology | [6 empty] | KAZUYUKI ISHIHARA | [68 empty] | Global | Completed | Yes | [16 empty] | None of the above
CACZ885T | CACZ885T2301 | C3003866 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-02-20 05:30 | 2018-06-13 05:30 | DB Conduct | Interim DBL | 2022-04-11 05:30 | 2018-03-16 05:30 | 2019-05-16 05:30 | 2017-11-16 05:30 |  | Active | 2027-01-15 05:30 |  | 2027-03-24 05:30 |  | TRUE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Two-arm Randomized Phase 3 study in high risk NSCLC comparing canakinumab vs placebo in Adjuvant Setting | CACZ885T2301 Adjuvant NSCLC-M | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Ware, Mahendra | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas | Sabine Turri | Sabine Turri | Bakka, Sandeep | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Shafiudeen, Rehana Banu | Bairagi, Arpita | Completed | 14-Feb-2022: CACZ885T2301_Rule File_version 12.0 is finalized in CREDI with B13L and B14L DTS table included in it. SNOW-51 ticket is also raised with ticket number- RITM3490385 for LSH update. 13-Sep-2021: Received B1 DTS for review. Review completed. 31-Aug-2021 : The study is transitioned to Bairagi, Arpita. 31-Aug-2021 : No Pending tasks. 14Jul2021 : The B12 DTS is included in the Rule file, finalized in CREDI and the LSP is notified. 06Jul2021 : B12L reflecting in 06jul2021 report 21May2021 : I have requested to share the DTS with me to get it included in the Rule file. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B11L DTS listed. Please check 6Jan2021: SG: No pending tasks. 18Sep2020 : Rehana worked on this update. All Forms included as per PPC (ZIS001_2, ZCS001_1, DSG001_1, OPS001, LBG002_TR) Snow ticket raised. 02Sep2020 : As per 02Sep2020 missing forms DTS report "ZIS001_2, ZCS001_1, DSG001_1, OPS001, LBG002_TR" forms . PPC implemneted on 31Aug2020. 10Feb2020 : LB included which was pending . Sent for LSH setup | None | None | 2018-05-12 05:30 | Legacy Process | Sundar, N Sushant | Kadam, Sandeep | Sushant Sundar | Completed | 2018-11-28 | Completed | 2020-05-07 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-05-18 05:30 | 2018-05-18 05:30 | Retrospective DRM studies | 2019-08-26 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB | [11 empty] | NA | [5 empty] | 17 | 37 | 90 | 0 | 274 | 1003 | 0 | 312 | 36 | 329 | 1368 | 7 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [10 empty] | 2020-05-06 05:30 | [5 empty] | GDD annual target
CACZ885U | CACZ885U2201 | C4008276 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-06-28 05:30 | DB On hold | Final DBL | 2024-02-23 05:30 |  | 2022-02-14 05:30 |  |  | Planned | 2024-01-12 05:30 |  | 2024-02-23 05:30 |  | FALSE | Other | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor |  | CACZ885U2201 Chinese study NSCLC_L1/2+C(PD1+taxan) | P0 Oncology (Solid Tumors, all MA Onc projects) | Boudraa, Yvane | Lokhande, Deepak Sharadkumar | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas |  | Shweta Malhotra | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Non-small cell lung cancer | No | Global | [18 empty] | None of the above
CACZ885U | CACZ885U2301 | C3004021 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-12-06 05:30 | 2019-01-15 05:30 | DB Conduct | Final DBL | 2022-11-03 05:30 | 2018-12-21 05:30 | 2019-06-17 05:30 | 2018-08-02 05:30 |  | Active | 2022-09-22 05:30 |  | 2022-11-03 05:30 |  | TRUE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase III randomized study of canakinumab + pembrolizumab alone as maintenace therapy following chemotherapy + pembrolizumab induction therapy in previously untreated adult patients with stage IIIb or IV non-small cell lung cancer. | CACZ885U2301 NSCLC 1L (ACZ+pembrolizumab) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kirubagaran, Agnes Vinitha | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas | Stephanie Deudon | St��phanie Deudon | Shrivastava, Nikhil | Rapaka, Sindhuja |  |  |  |  | DRM | Shrivastava, Nikhil | Choppadandi, Kranthikumar | Completed | 07-Jul-2021: B13L DTS is still On Hold 06Jul2021 : B13L is flagged in report . 19May2021: B13L is flagged in report but as per DBD its on hold. 19-Jan-2021: RF_Version 14.1 released for Peer review. PPC#13 updates and Study team requested to map Subject status pages to SS domain 19-Nov-2020: Rule File Version 13.0 is finalized to include B14L and B15L DTSs in LSH set-up 26-Oct-2020: B13L Not finalized yet 01Sep2020: B13L is not yet finalized 12Aug2020 : B13L Requested Lead DBP to share the current status of the DTS. Flagged in 04Aug report DTS is not yet finalized. 06-Jul-2020: No pending issues. RF 11.0 is finalized for PPC09. 13Jan2020 (SHRIVNI5): Rule file transition ongoing. The rule file is created and reviewed and finalized with Rave form domains. The service request was raised on 31st Dec and LSP is currently working on the request. The DTS related domains (LB, QS, ZO, TU, TR and B1) will be included in the rule file after DTS finalization. | None | None | 2019-01-03 05:30 | Transition study and Legacy Process | Manoharan, Vivek | Garje, Sagar | Sushant Sundar | Completed | 2019-01-07 | Completed | 2019-02-14 05:30 |  | Retrospective DRM studies | 2019-02-18 05:30 | 2019-02-18 05:30 | Retrospective DRM studies | 2019-08-30 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB | [11 empty] | NA | [5 empty] | 23 | 171 | 116 | 0 | 909 | 1302 | 0 | 318 | 40 | 344 | 1686 | 13 | 0 |  | Non-small cell lung cancer | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-02-15 05:30 | [5 empty] | GDD annual target
CACZ885T | CACZ885V2101 | C4000951 | Phase I | Other | CRO - EDC |  |  | 2019-12-30 05:30 | DB Locked |  |  | 2019-12-23 05:30 | 2019-10-16 05:30 | 2019-10-23 05:30 |  | Completed | 2021-04-01 05:30 | 2021-04-12 05:30 | 2021-04-28 05:30 | 2021-07-22 05:30 | FALSE | Other | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A randomized, open-label, single-dose, parallel-group study in healthy subjects to assess the PK comparability of canakinumab with either one injection (200 mg) of pre-filled syringe in needle safety device or auto-injector compared to two injections (150 and 50 mg) of pre-filled syringe in needle safety device | CACZ885V2101 200mg PFS BE Bridging Study | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas | Denis Weber | Denis Weber | [10 empty] | As this is FSOM trail ,only WLIMS LSH setup has been requested on 15-JAN-2021. |  |  | 2021-01-15 05:30 |  | Sultana, Salma |  | Sushant Sundar |  |  |  |  | 03-FEB-2021:TDM inputs: Since the sample status is now available in Pre-advance for all samples, think there is need to upload the data in Jreview. Hence, the PK analyst will not be raising SNOW ticket for this study 21-JAN-2021:PK,IG and BIM setup completed. 15-JAN-2021:WLIMS setup request | [9 empty] | FSOM - Outsourced | [13 empty] | Celerion | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Pharmacokinetic study | No | Global | Open | Yes | [16 empty] | None of the above
CACZ885T | CACZ885V2201C | C4000794 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-06-03 05:30 | 2019-09-06 05:30 | 2019-10-23 05:30 | DB Conduct | Final DBL | 2023-02-06 05:30 | 2019-11-05 05:30 | 2019-04-29 05:30 | 2019-04-23 05:30 |  | Active | 2022-08-11 05:30 |  | 2023-02-06 05:30 |  | FALSE | Other | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized, open-label, phase II study of canakinumab or pembrolizumab as monotherapy or in combination as neoadjuvant therapy in subjects with resectable non-small cell lung cancer (CANOPY-N) | CACZ885V2201C neo-adjuvant_NSCLC-C | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Wadikar, Ashish Dattatreya | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas | Funmi Abiola | Funmi Abiola | Choppadandi, Kranthikumar | Bakka, Sandeep |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 03Jun2019 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 29-Jul-2021: MI1L, MI6L DTS tables in included in RF_V9.0 21Jul2021 : DTSs MI6L, MI1L reflecting in 21Jul report. 21-Apr-2021: Rule File_V8.0 Finalized for PPC08, B15L and B16L DTSs, SNOW ticket raised for LSH update 21Jan2021: Kranthi: B14L has been included in RF V6.0 and raised SNOW ticket for LSH set-up 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B14L DTS listed. Please check 24-Nov-2020: Rule File Version 5.0 is finlaized to include B12L DTS 06-Jul-2020(Kranthi): No pending issues | None | None | 2019-10-24 05:30 | Legacy process | Sundar, N Sushant | Sundar, N Sushant | Sushant Sundar | Completed | 2019-11-12 | Completed | 2019-11-12 05:30 | Rave Production forms were not visibile for extraction to LSH. It was fixed by RaveX admin team on 7Nov2019. | System or Application issues (RAVE/LSH/JReview/GPS) | 2019-11-12 05:30 | 2019-11-12 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2019-11-26 05:30 |  |  |  | 74 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 13 | 12 | 85 | 0 | 180 | 799 | 0 | 233 | 37 | 198 | 1034 | 3 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [10 empty] | 2019-11-08 05:30 | [5 empty] | None of the above
CACZ885V | CACZ885V2301 | C3004022 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-09 05:30 | 2019-01-31 05:30 | DB Locked |  |  | 2019-01-23 05:30 | 2018-07-24 05:30 | 2018-07-20 05:30 |  | Active | 2021-12-20 05:30 | 2021-12-20 05:30 | 2022-01-31 05:30 | 2022-01-31 05:30 | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase III, multicenter, randomzied, double blind, placebo-controlled study evaluating the efficacy and safety of canakinumab (in combination with docetaxel versus docetaxel alone in patients with non-small cell lung cancer previously treated with PD(L)-1 inhibitors and platinum based chemotherapy | CACZ885V2301 NSCLC 2/3L (ACZ+Docetaxel) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Bawane, Ankush | Gupte, Smita | Mayekar, Meera | Hiriyanna, Srinivas | Judianne Wojna | Judianne Wojna | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR |  |  |  |  | DRM | Shrivastava, Nikhil | Saha, Saikat | Completed | 3Feb2022: RF and Checklist Version 14.0 have been finalized with the B17L DTS details in it. SNOW51 request RITM3453000 has been raised and notified the LSP 2Feb2022: RF is updated with the B17L DTS and sent for the peer review. 21Sep2021 : Reviewed the DTS and updated the RF. RF is sent for peer review. RF finalized and SNOW ticket has been raised. Informed the LSP as well. 20Sep2021 : Received B16L DTS to review and update in the RF. 13-Aug-2021 (Nikhil): Transition activities have been completed. Informed the study team. B14L and B15L DTS have been finalized in CREDI but B15L has some setup issue. TDM updating the next version and B15L DTS will be finalized soon. (Attached latest email for your reference) Rule File updates have been done but should be finalized post B15L DTS finalization. 11Aug2021 : Reassigned the study from Nikhil to Saikat. 13-Jul2021: DTS (B14L and B15L) review is currently ongoing and not yet shared with RF programmer. 06Jul2021 : B15L, B14L is reflecting in Missing form/DTS report. 29-Jan-2021: SNOW-51 ticket is raised for SMT update and SLH rebuild. No impact on the Rule File. LSP and SMT programmers are notified. 26Nov2020: Backup: Chandrakala Whats planned: Nothing planned as of now. 14-Sep-2020 (SHRIVNI5): RF V11.0 updated to include subject status forms in ODM domain as per DRA team's confirmation. Sent for LSH rebuild. 08-Sep-2020 (SHRIVNI5): RF V10.0 updated for subject status and Survival form and sent for LSH rebuild. 25-Aug-2020 (SHRIVNI5): B13L DTS has been included and RF V9.0 finalized. SNOW-51 ticket raised and LSP notified for LSH setup. 01-Jun-2020 (SHRIVNI5): B11L DTS has been included and RF V8.0 finalized. SNOW-51 ticket raised and LSP notified for LSH setup. 17-May-2020 (SHRIVNI5): B12L DTS has been included and RF V7.0 finalized. SNOW-51 ticket raised and LSP notified for LSH setup. 07-May-2020 (SHRIVNI5): DTS was finalized on 06-Mar-2020 but not yet included in the Rule file because it was missed to be informed by the DBP to the rule file developer. Need to include in the rule file. I will include by 15-May-2020. 01Apr2020 : Reassigned RF from Roshan to Nikhil 01Apr2020: No pending activity. 14 jan 20: Reached out to Praveen Jetty to know the status of LSH and SMT setup for the updates made | None | None | 2018-12-12 05:30 |  | Sundar, N Sushant | Kadam, Sandeep | Sushant Sundar | Completed | 2018-12-24 | Completed | 2019-09-20 05:30 |  | Retrospective DRM studies | 2018-12-18 05:30 | 2018-12-18 05:30 |  | 2019-09-10 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB | [11 empty] | NA | [5 empty] | 14 | 61 | 83 | 0 | 531 | 1136 | 0 | 253 | 38 | 337 | 1511 | 6 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [10 empty] | 2019-06-06 05:30 |  |  |  |  | Kadam, Sandeep | GDD annual target | Yes
CACZ885R1 | CACZ885X2205 | C1200453 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-12-19 05:30 |  | 2016-05-04 05:30 |  | Completed | 2019-03-04 05:30 | 2019-03-04 05:30 | 2019-06-25 05:30 | 2019-06-25 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | A multiple-dose, subject- and investigator-blinded, placebo-controlled, parallel design study to assess the efficacy, safety, and tolerability of ACZ885 (canakinumab)in patients with pulmonary sarcoidosis | CACZ885X2205 PIE POC in Pulmonary Sarcoidosis | N0 ATI - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Therese Swan | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Sarcoidosis | No | Global | Completed | Yes | [16 empty] | None of the above
CACZ885S1 | CACZ885X2206 | C1200353 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-04-05 05:30 |  | 2016-09-07 05:30 |  | Completed | 2020-04-27 05:30 | 2020-04-27 05:30 | 2020-05-21 05:30 | 2020-06-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A multiple-dose, subject- and investigator-blinded, placebo-controlled, parallel design study to assess the efficacy, safety and tolerability of ACZ885 (canakinumab) in pediatric and young adult patients with sickle cell anemia | CACZ885X2206 sickle cell PoC in pediatric patients | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Ewa Kubiak | Ewa Kubiak | [15 empty] | Challa, Nandini |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Sickle cell disease | No | Global | Completed | Yes | [14 empty] | DBL | Adi, Vishnupriya | None of the above | Yes
CADPT01A1 | CADPT01A12101C | C4001881 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-27 05:30 | 2019-02-28 05:30 | DB Conduct | Final DBL | 2022-04-29 05:30 | 2019-01-31 05:30 | 2018-07-05 05:30 | 2018-07-12 05:30 |  | Active | 2022-03-18 05:30 |  | 2022-04-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib, multicenter, open-label dose escalation and expansion platform study of select immunotherapy combinations in adult patients with triple negative breast cancer | CADPT01A12101C TNBC Combo | N7 Oncology - NIBR | Langlo, Francois | HernÃ¡ndez, Fernanda | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Emilie Bossuge | Emilie Bossuge | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022 |  | DRM (DIAL) | Tadiparthy, Ramakanth | Kuttoboina, Sujan Kumar | Completed | 09-DEC-20: Rule file updated as per PPC 7 and finalized. SNOW 51 Request RITM2070121 has been created Change: FAMHS001 form has been added 07-JUL-20: As of today, no pending forms and no pending DTS 02-MAR-20: PPC not implemented for to fix QS2G7 metadata issue., Following up with DBD on the same. No impact on RF. 22-JAN-20: QS2G7 Form There is inconsistency between Standard Reference metadata and Database for form QS2G7 and ECOG codes will be fixed via PPC.. 09-JAN-20: [SK] Rule file updated with new DTS LB02L and B1 and no pending action items as of today. LB02L, B11L added in Rule file 29-NOV-2019: Rule file update is ongoing. Will be finalized by 03-DEC-19. 09Jul19, PILLIBH2: proceed further in DRM after update the rulefile by adding QSCAT, QSTSTLG, NQVERNUM for QS1S462, other pending updates (FAAE for now) should be included in next version of rulefile FPFV not happened yet. Team working on Direct Data capture LAB DTS and PPC on priority. Study team fine with deprioriting Rule file and LSH Setup LSP Comments: ------------------------------------------------------------------------------------ Rule file and other Pre-Requisite not shared with LSP yet from the DBP. FPFV happend on 31-JAN-2019 as DM informed. LSP received SNOW05 along with Rulefile,DQP,SSD on 12-Feb-2019 post EOB. LSH setup started on 13-Feb-2019 LSH Setup completed for all the domain except EG1L TPD. ------------------------------------------------------------------------------------ PRE-DRM setup completed for the CRF domains, also TPD EG setup completed and LB01L is in-progress. | None | None | 2019-02-13 05:30 | Transition Study and Legacy process | Tidke, Shyam | Kumar D, Santosh | Rohit Varate | Completed | 2019-02-14 | Completed | 2019-07-04 05:30 |  |  | 2019-02-07 05:30 | 2019-02-14 05:30 | Study Transition | 2019-07-03 05:30 |  |  |  |  | RaveX - Inhouse | Yes | [12 empty] | IQVIA | [5 empty] | 10 | 102 | 110 | 0 | 947 | 1126 | 0 | 256 | 38 | 482 | 1646 | 4 | 0 |  | Triple negative breast cancer | No | Global | Open | Yes | [10 empty] | 2019-07-04 05:30 |  |  |  |  | Tidke, Shyam | None of the above | Yes
CADPT01C1 | CADPT01C12101 | C4006711 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-04-02 05:30 | 2020-06-25 05:30 | 2020-07-24 05:30 | DB Conduct | Final DBL | 2023-10-16 05:30 | 2020-07-22 05:30 | 2020-01-21 05:30 | 2020-01-21 05:30 |  | Active | 2023-08-17 05:30 |  | 2023-10-16 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib, multicenter, open-label dose escalation and expansion platform study of select drug combinations in adult patients with advanced or metastatic BRAF V600 colorectal cancer | CADPT01C12101 Phase Ib in V600 BRAF CRC | N7 Oncology - NIBR | Langlo, Francois | Greyling, Alida | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sarah DiDominick; Shizuka Origuchi | Shizuka Origuchi | Bonam, Rajesh Babu | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 02Apr2020 |  | DRM | Choppadandi, Kranthikumar | R, Pratheeksha K | Completed | 17Dec2021: RF has been updated for PPC 03 and SNOW51 ticket raised on 7Dec2021 (Ticket number - RITM3268059). RF Checklist also finalized in Subway. 06-Aug-2021: RF updated and raised SNOW ticket. to include ZJG002_13, ZJG002_14, ZJG006_13, ZJG006_14 21Jul2021 : Forms ZJG002_13, ZJG002_14, ZJG006_13, ZJG006_14 reflecting in 21Jul report. 18-Jun-2021: Rule File finalized for EG1L DTS, SNOW51 ticket raised, Ticket number - RITM2656620 26May2021 : Reassigned the study from Praveen Oguri to Kranthikumar Choppadandi. 26-May-2021: Received EG1L DTS on 26-May-2021, RF needs to be updated. 25-May-2021: Sent third follow up email to DBD to confirm on EG1L DTS finalization status. 26-Apr-2021: Sent follow up email to Rakesh Kurella to confirm on EG1L DTS finalization status. EG1L is flagged in missing form/DTS report. 19-Apr-2021: Sent email to Study DBD to confirm on DTS finalization status. 05Nov2020: Updating RF Version 4.0 FAMH page as per the updated SDTM annotations. 11Sep2020: No Activity. 21Jul2020: Rule file Version 1.0 is finalized and SNOW05 ticket is raised (RITM1619815). RF finalization got delayed as there were updates made to the forms after the initial RF was developed, SDTM annotations were updated for Diagnosis and extent of cancer page, Biomarker and Ophthalmic test CRF’s 05Jun2020 : RF ongoing 12May2020 : followed up with DBD on SDTM annotations. 19Mar2020 : Sent an followup email to DBD. 17Feb2020 : Followed up with DBD and yet to receive study specific forms for review. No RF activity started | None | None | 2020-07-21 05:30 | Transition Study | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-07-22 | Completed | 2020-07-24 05:30 |  | Pre-requisites not met | 2020-07-24 05:30 | 2020-07-27 05:30 | Pre-requisites not met | 2020-08-28 05:30 |  |  | Datasets are still under review,issues are yet to be shared by TDM and SDTM. Only 6 domains have been reviewed till date. | 57 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 5 | 65 | 138 | 0 | 1048 | 1267 | 0 | 312 | 47 | 473 | 1787 | 4 | 0 |  | Colorectal cancer metastatic | No | Global | Open | Yes | [10 empty] | 2020-07-24 05:30 | [5 empty] | None of the above
CADPT02A1 | CADPT02A12001 | C4004597 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-10-11 05:30 | 2019-12-16 05:30 | 2020-06-30 05:30 | DB Conduct | Final DBL | 2022-02-18 05:30 | 2020-06-04 05:30 | 2018-12-19 05:30 | 2019-07-09 05:30 |  | Active | 2022-05-22 05:30 |  | 2022-02-18 05:30 |  | FALSE | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - DAx | NASH EXploratory Single and COmbination Treatment (NEXSCOT): An open label, multicenter, platform study to evaluate the safety, tolerability, pharmacokinetics and efficacy of various single and combination treatments in patients with non-alcoholic fatty liver disease (NAFLD) who manifest a non-alcoholic steatohepatitis (NASH)-like biomarker phenotype | CADPT02A12001 NExSCoT - NASH Single and Combo Tx. | N5 DAx - NIBR | Langlo, Francois | Marripati, Sai Amrutha | Bhatkar, Priyanka | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Noah Stachulski | Theodore Stachulski | Oguri, Praveen | Thomas, Ankit |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 11Oct2019 |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 16Feb2022: PPC9 has no impact to Rule file hence, we have only SNOW#51- RITM3502131 Created for LSH/SMT updates. 28Oct2021: RF v5.0 finalized for PPC#08 updates. 24Oct2021: PPC7 has no impact to RF hence only RITM2904292 Created. 02Aug2021: Snow#51 raised for PPC#6 updates directly as no Impact to RF. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021: RF Version 4.0 finalized on 25-May-2021 and SNOW ticket raised(RITM2599993). 05Nov2020: No Activity. 11Sep2020: RF finalized and raised SNOW ticket on 17Aug2020 (ZJG006_1, LBG002_TR, MO1L DTS) 11-Aug-2020: Working on RF for PPC1 and PPC2 updates 27Jul2020 : ZJG006_1 has been flagged in 20thju report 07Feb2020 : Reassigned rule file developer (Chandrakala to Praveen) 24Dec2019: RF v1.0 finalized with no CRFs excluded. No DTs finalized yet. Raised SNOW05 | None | None | 2020-01-03 05:30 |  | Nagalla, Lakshmi Naga Lavanya | Varate, Rohit | Rohit Varate | Completed | 2020-01-06 | Completed | 2020-01-08 05:30 |  |  | 2020-01-08 05:30 | 2020-01-08 05:30 |  | 2020-08-21 05:30 |  |  |  | 52 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 12 | 60 | 0 | 138 | 838 | 0 | 223 | 33 | 199 | 1070 | 3 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [10 empty] | 2020-01-06 05:30 | [5 empty] | None of the above | Yes
CADPT03A1 | CADPT03A12101 | C4003691 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-07-24 05:30 | 2020-07-24 05:30 | 2020-08-28 05:30 | DB Conduct | Final DBL | 2024-01-26 05:30 | 2020-08-26 05:30 | 2019-10-30 05:30 | 2019-12-12 05:30 |  | Active | 2024-12-18 05:30 |  | 2024-01-26 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - DAx | A first-in-patient Phase I/II clinical study to investigate the safety, tolerability and efficacy of genome-edited hematopoietic stem and progenitor cells in sickle cell disease | CADPT03A12101 HIX763 + OTQ923 FIH in Sickle Cell | N7 Oncology - NIBR | Langlo, Francois | Palnitkar, Prachi | Bhatkar, Priyanka | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | Kurella, Rakesh Reddy | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 |  |  | DRM |  | Patnaik, Angella | Completed | 8-Sep-2021: RF Version 5.0 finalized in CREDI for PPC #1 updates. SNOW #51 raised for SMT/LSH updates, 23-AUG-2021: Added comment in Missing Forms tracker. Reminder sent to TDM/DBD for Reference Metadata availability. 12-AUG-2021: RF updates for PPC #1 on hold as the Test Codes for FAPR domain are not available in Reference Metadata. TDM notified to raise Reference Metadata request. 17-FEB-2021: LSH set-up pending. RF Version 4.0 and SNOW#51 raised on 9-NOV-2020. Have sent a reminder to study team for the DTS status. 02-DEC-2020: B11L DTS table added in RF and SNOW#51 raised on 9-NOV-2020. However, due to mismatch in Data format in Metadata Definition file, LSH set-up is not completed. TDM has been notified during the RF creation. 09-NOV-2020: RF finalized in CREDI. SNOW# 51 raised and SMT Programmer and LSP notified. 09-NOV-2020: B11L DTS table added and sent for Peer Review. 18-AUG-2020: RF updated for CM Domain. SMT/LSH programmer informed. 12-AUG-2020: RF updated for LB1L table addition for Lab DTS. SNOW ticket raised, TDM, DBD, LSP and SMT Programmer notified. 28-JUL-2020: RF finalized and SNOW#05 request raised for SMT development and New study set-up in LSH. 24-JUL-2020: RF Peer Review comments fixed and released for final review. 22-JUL-2020: SRF updated for CMS002. RF updated accordingly and sent to Peer Reviewer. 21-JUL-2020: Rule file released for Peer Review. 07_JUL-2020: RF creation initiated. 15JUN2020: First batch of 24JUN2020: SRF and ALS Review ongoing. 27APR2020: No documents received yet for review or RF development activities. Go-live pushed to 07-AUG-2020. 03Apr2020 : All documents received for RF Development 20th March except for 1form. 18MAR2020: DB Go-live pushed to 27MAY2020. 17MAR2020: UAT status requested from DBD. 27FEB202: Screen UAT completed. Received ALS, SRFs and SDTM annotations for review. 07Feb2020: No update from DBD | None | None | 2020-07-28 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-07-31 | Completed | 2020-08-18 05:30 | ​LSH request raised on 28th July, 2020 as DaVinci study. ​Miscommunication was corrected, study folder is in the process of creation in GPS. Post which SMT developer can work on the SMT files for the study. ​SMT files were provided on 17th August, 2020. DRM setup and data publishing was completed on 18th August, 2020 . | ​LSH request raised on 28th July, 2020 as DaVinci study. ​Miscommunication was corrected, study folder is in the process of creation in GPS. Post which SMT developer can work on the SMT files for the study. ​SMT files were provided on 17th August, 2020. DRM setup and data publishing was completed on 18th August, 2020 | 2020-08-18 05:30 | 2020-08-18 05:30 | ​LSH request raised on 28th July, 2020 as DaVinci study. ​Miscommunication was corrected, study folder is in the process of creation in GPS. Post which SMT developer can work on the SMT files for the study. ​SMT files were provided on 17th August, 2020. DRM setup and data publishing was completed on 18th August, 2020 | 2020-08-24 05:30 |  |  | 9 domains were reviewed by DM, no issues were reported. SDTM programmer function is in transition to a new programmer and they have not reviewed/provided comments yet. Awaiting new SDTM programmer for review. [RAMACHA1, 3rd Feb, 2021] 14 domains reviewed. 4 domains failed due to data entry issues and reference metadata issues. TDM is following up on the same. There are zero records in 9 domains which will be reviewed once data is available. [RAMACHA1, 19th Feb, 2021] 14 domains passed, 4 domains failed due to data/standard issue. 9 domains are pending review due to unavailability of data. [RAMACHA1, 16th March, 2021] 21 domains passed review. 6 failed and it is being followed up by the team | 78 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 3 | 44 | 79 | 0 | 417 | 770 | 0 | 176 | 41 | 230 | 1041 | 2 | 0 |  | Sickle cell disease | No | Global | Open | Yes | [10 empty] | 2020-08-18 05:30 |  |  |  |  | Pagolu, Sahithi Venkata | None of the above | Yes
CADPT05A0 | CADPT05A02101 | C4003912 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-07-18 05:30 | 2020-06-29 05:30 | 2020-12-14 05:30 | DB Locked | Final DBL Achieved |  | 2020-12-07 05:30 | 2019-04-04 05:30 | 2019-04-26 05:30 |  | Active | 2021-08-30 05:30 | 2021-08-29 05:30 | 2021-10-11 05:30 | 2021-09-15 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health |  | CADPT05A02101 CYP2D6 PG/PK HV | P6 Global Health | Vithala, Srinivas | Narayanappa, Divakar Kolar | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Kanan Jhala | Kanan Jhala | Mokhamatam, Madhu Purnachandra Rao | Rana, Aamir |  | 2020-08-07 05:30 | moved to 15Feb2020 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 18Jul2019 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 06-AUG-2021: RF Version 4.0 finalized in CREDI for reverting ZJ domain updates during PPC #3, as we should not unmap any forms in PPC via RF when PROD data is still present. SNOW#51 raised. 26-JUL-2021: RF Version 3.0 finalized in CREDI for SMT updates. SNOW#51 raised. 22-JUL-2021: Forms ZJG002_3_1, ZJG002_4_1 are excluded from the RF as they have been removed from all study matrices. They are still in active state in ALS as there is PROD data in it. This has clearly been mentioned in the Excluded forms tab in RF Version 2.0 21Jul2021 : Forms ZJG002_3_1, ZJG002_4_1 reflecting in 21Jul report. 15-JUL-2021: RF Version 2.0 for PPC #3 updates finalized in CREDI. SNOW #51 raised for SMT/LSH updates. 22-FEB-2021: PPC1 implemented. No updates to RF. SNOW#51 raised for SMT and LSH updates. 29JUN2020: RF Finalized in CREDI. SNOW#05 raised for New study set-up in LSH. 19JUN2020: DBD Notified DB Go-live is pushed to 23-JUN-2020. RF will be finalized post study Go-live. 26APR2020: Peer Review comments addressed. 22APR2020: Peer Review comments received. 14APR2020: RF Development completed. Released for Peer Review. 06APR2020: Screen UAT completed. Updated ALS received for RF development. 20APR2020: Updated ALS received from DBD. Go-live pushed to 15APR2020. 17MAR2020: DB set-up issues shared with DBD for DB updates. Awaiting updated ALS for Rule file creation. 07Feb2020 : Received SDTM annotations, ALS SRFs on 05Feb2020. RF will be started 7-JAN-2020: Screen UAT comments are being addressed now. | None | None | 2020-06-29 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2020-08-12 | Completed | 2020-10-21 05:30 |  |  | 2020-10-22 05:30 | 2020-10-22 05:30 |  | 2020-12-23 05:30 |  |  | FPFV IS ON 15-OCT -2020 | 100 | RaveX - Inhouse | Yes |  | 2021-09-15 05:30 | 2021-09-20 05:30 | [9 empty] | NA | [5 empty] | 5 | 7 | 43 | 0 | 57 | 462 | 0 | 169 | 32 | 90 | 584 | 1 | 0 |  | Pharmacokinetic study | No | Global | Open | Yes | [10 empty] | 2020-09-29 05:30 |  |  |  |  | Manoharan, Vivek | None of the above | Yes
CADPT06A1 | CADPT06A12201 | C4004704 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-03-01 05:30 | 2021-03-12 05:30 | 2021-11-05 05:30 | DB Conduct | Final DBL | 2024-03-25 05:30 | 2021-10-28 05:30 | 2020-10-28 05:30 | 2020-10-23 05:30 | 2021-02-17 05:30 | Active | 2024-01-22 05:30 |  | 2024-03-25 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS | EXploratory PLatform trial on Anti-Inflammatory agents IN Alzheimerâs Disease (EXPLAIN-AD): A randomized, placebo-controlled, multicenter platform study to evaluate the efficacy, safety, tolerability and pharmacokinetics of various anti-inflammatory agents in patients with mild cognitive impairment due to Alzheimerâs disease and mild Alzheimerâs disease | CADPT06A12201 PIE PoC Umbrella | N6 Neuroscience - NIBR | Langlo, Francois | Bhaumik, Romela | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | JoAnn Whittle | JoAnn Whittle | Rachakonda, Hima Sailaja | Shewane, Roshni | Not Started |  | Transition checklist not shared. Study Transition not started for Transitioned DBD Roshni Shewane. |  | DRM | Shafiudeen, Rehana Banu | Bairagi, Arpita | Completed | 31-Aug-2021 : The study is transitioned to Bairagi, Arpita. 31-Aug-2021 : No Pending tasks. 6Apr2021 : Rule file 2.0 finalized in SUBWAY, LSP is notified. 30Mar2021 : Update the same and sent for review. 28Mar2021 : LSP notified about 2 issues in the Rule file. 15Mar2021 : Rule file 1.0 is finalized in SUBWAY and the LSP is notified 1Mar2021 : Sent the Rule file for peer review 15Feb2021 : The golive is moved to 12Mar2021. Will start with the RF dev once UAT is completed. 27Jan2021 : Sent the review comments to the DSD. 12Jan2021 : Started with the ALS review 4Jan2021 : Requested for ALS 11Dec2020 : Received the SRs for review 29Nov2020 : The Study go-live is postponed to 28Jan2021 . 15Oct2020 : Requested DBP for the Study Status and awaiting for reply. | None | None | 2021-03-15 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2021-04-05 | Completed | 2021-04-05 05:30 |  |  | 2021-04-06 05:30 | 2021-04-06 05:30 |  | 2021-04-06 05:30 |  |  |  | 0 | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 4 | 11 | 52 | 0 | 117 | 648 | 0 | 194 | 38 | 123 | 809 | 13 | 0 |  | Cognitive disorder | No | Global | Open | Yes | [10 empty] | 2021-04-06 05:30 | [5 empty] | None of the above
CADPT07A1 | CADPT07A12101 | C4005729 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-10-21 05:30 | 2019-12-10 05:30 | 2020-07-15 05:30 | DB Conduct | Final DBL | 2024-05-15 05:30 | 2020-07-23 05:30 | 2019-07-02 05:30 | 2019-07-17 05:30 |  | Active | 2024-03-06 05:30 |  | 2024-05-15 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase I, open label, study of B-cell Maturation Antigen (BCMA)-directed CAR-T cells in adult patients with relapsed and/or refractory multiple myeloma | CADPT07A12101 BCMA CAR-T | N7 Oncology - NIBR | Langlo, Francois | Muthappa, Helen | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Lawrence Rispoli; Marc Credi | Lawrence Rispoli | Samuel, Giftson | Kala, Arpit |  |  | Oct-2021 : Giftson Transitioned to Arpit Kala Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 21Oct2019 |  | DRM | Choppadandi, Kranthikumar | R, Pratheeksha K | Completed | 15Feb2022: RF Finalized on 23Sept2021. Added DSG007, PRO001_2, PRO001_3 and PRH001_1 forms. Developed RF for XGO001, XGO001_1 forms. Due to the DDPASS comment, RF for FAMHS001 form is developed from the scratch. 11Aug2021 : Reassigned the study from Kranthi to Pratheeksha. 06-Aug-2021: Requested DBP to share the PPC status 21Jul2021 : DSG007, XGO001, XGO001_1 reflecting in missing forrm DTS report again (21jul2021 report). PPC ongoing 07-Jul-2021: PPC in progress to fix the issue of XGO001 forms. RF will be updated for all the pending forms once the PPC is implemented 06Jul2021: DSG007, XGO001, XGO001_1 reflecting in missing forrm DTS report again (06jul2021 report) 18-Jun-2021(Kranthi): requested DBP to share all the required document to initiate RF update (DSG007, XGO001, XGO001_1) in missing form DTS report 04-Jun-2021: Working on RF for PPC05 updates 26May2021 : Reassigned the study from Praveen Oguri to Kranthikumar Choppadandi. 26-May-2021: No activity, Latest RF Version 5.0. 26Apr2021: Added PRS003_1, TUS001_1 forms and addressed DDPASS comments for FACM, XG.. Rule File Version 5.0 ( PPC#5) and sent for peer review. Pratheeksha updated the version 5.0 on behalf of Praveen. 27-Jan-2021: RF Version 4.0, added B12L Navigate DTS and raised SNOW51 ticket.RITM2205908. 21-Jan-2021: Received updated B12L DTS, I will update RF today. 26-Nov-2020: B12L DTS is not yet finalized, I will include in RF once final version is shared with me. 05Nov2020: Included B14L DTS in RF and raised SNOW ticket on 29Oct2020. 23Oct2020 : follow up email sent to DBD for B14L DTS. 05Oct2020 : follow up email sent to DBD for B14L DTS. 24-Sep-2020: Sent email to Study DBD to update on DTS finalization status for B14L 11Sep2020: RF updated and raised SNOW ticket on 21Aug2020. 11Aug2020: B13L and B11L to be added in RF. Received B11L on 24Jul2020. Expected to complete by 14th. 22Jun2020 : B13L flagged in report 18Jun2020 : Peer review completed and working on peer review comments. 12May2020 : B2,FACE,PR,RS and B1 Domains upadted and rasied Snow ticket 08Apr2020 : Roshan updated the RF for penidng forms and DTS and Praveen performing Review 01Apr2020 : Reassigned RF from Roshan to Praveen 26MAR2020: Sent for Peer review by including all pending CRFs (PRO005, PRO006 & PRS001 (Domains : FACE, FAMH, PR, RS)) and added B1 DTS. 10MAR2020: Awaiting PPC to be implemented for pending forms PRO005, PRO006 & PRS001 (Domains : FACE, FAMH, PR, RS) and B11L DTS will be added along with PPC. 14Feb2020 : PPC #1 ongoing to fix PR and RS domain issues which would be completed by 21st Feb. FAMH and FACE domain, rule file will be updated along with the PPC #1 domain updates. 14 Jan 20: To work on PR domain post receiving comments from standards 09 Jan 20: Sent for SMT development. Excluded forms are still put on hold 07Jan2020: Rule file completed Excluded forms PRO005, PRO006 & PRS001: Giftson to respond on the same as attached mail PRTRT is required field to be collected however it is not present on CRFs for PRO005, PRO006 & PRS001 and hence excluded the same. 17Dec2019 : Released for peer review . Except TU/TR as PPC required for fix the screen design issue. 10 Dec 2019: Received updated ALS today from DBD. Working on the corrected CRFs. SDTM annotations still pending for study specific domains. | None | None | 2020-01-08 05:30 |  | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-01-08 | Completed | 2020-01-23 05:30 |  |  | 2020-01-23 05:30 | 2020-01-23 05:30 |  | 2020-08-21 05:30 |  |  | DDPASS was initiated, but terminated due to lack of data in the domains, and also awaiting PPC for the study. DDPASS to be resumed once PPC is completed. Mutual decision taken by all the stakeholders. | 83 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 10 | 46 | 141 | 0 | 586 | 1010 | 0 | 241 | 41 | 613 | 1664 | 5 | 0 |  | Multiple myeloma | No | Global | Open | Yes | [10 empty] | 2020-01-23 05:30 |  |  |  |  | Gouni, Harita | None of the above | Yes
CADPT08A1 | CADPT08A12201R | C4007468 | Phase II | Other |  |  |  | 2020-09-30 05:30 |  |  |  | 2020-11-04 05:30 | 2020-08-14 05:30 |  |  | Active | 2021-11-29 05:30 |  |  |  | FALSE |  |  |  | Outsourced |  |  | CADPT08A12201R Dose/Safety Conf. PanCAN sponsored | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Petra Hoever | Petra Daniela Hoever | [66 empty] | Pancreatic adenocarcinoma non-resectable | No | Global | Open | Yes | [16 empty] | None of the above
CADPT09A1 | CADPT09A12201 | C4011790 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-04-05 05:30 |  | 2022-06-03 05:30 | Study Planned | DB Go-live | 2022-04-29 05:30 |  | 2022-02-25 05:30 |  |  | Planned | 2024-07-18 05:30 |  | 2024-08-22 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A participant- and investigator-blinded, randomized, placebo-controlled, multicenter, platform study to investigate efficacy, safety, and tolerability of various single treatments in participants with idiopathic pulmonary fibrosis | CADPT09A12201 IPF PoC Platform study | N5 DAx - NIBR | Langlo, Francois | Chavan, Shweta S | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Kristina Wagner | Kristina Wagner | Kabra, Pratik Govind | Kabra, Pratik Govind |  |  | As per email received from TDM on 11-Feb-2022, Go live date is shifted to 22nd April 2022 and RIS date is 16th May 2022. |  |  |  | Saha, Saikat | Not Started | 6Jan2022: Study Assigned. | [6 empty] | Rohit Varate | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Idiopathic pulmonary fibrosis | No | Global | Open | Yes
CAFQ056C1 | CAFQ056X2201 | C1200714 | Phase II | NCDS | CRO - EDC |  |  | 2017-11-30 05:30 | DB Locked |  |  | 2017-12-04 05:30 |  | 2017-06-26 05:30 |  | Completed | 2019-12-20 05:30 | 2019-12-16 05:30 | 2020-05-05 05:30 | 2020-05-06 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A randomized, subject and investigator blinded, placebo-controlled, parallel group study to investigate whether AFQ056 reduces cocaine use in patients diagnosed with Cocaine Use Disorder (CUD) | CAFQ056X2201 PoC in cocaine use disorders | P6 Global Health | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Maria Berkheimer | Maria Berkheimer | [15 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Cocaine addiction | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A0 | CAIN457A02001B | C4009262 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-11-05 05:30 | 2020-12-16 05:30 | 2020-02-05 05:30 | DB Conduct | Final DBL | 2024-11-08 05:30 | 2020-12-22 05:30 |  | 2020-09-23 05:30 |  | Active | 2024-09-30 05:30 |  | 2024-11-08 05:30 |  | FALSE | Post Trial Access | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | An open-label, multi-center protocol for patients who have completed a previous Novartis sponsored Secukinumab study and are judged by the investigator to benefit from continued Secukinumab treatment | CAIN457A02001B PTA | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sannidhi, Pavan Kumar | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Roselyne Raffner | Roselyne Raffner | Gehlawat, Priya | Gehlawat, Priya | Completed | 2021-10-04 05:30 | Moved from 05 Nov to 09Nov2020. Protocol not final yet. Initial go live as 05Nov2020 when RF developer assigned on 19Aug2020. |  | DRM |  | Shrivastava, Nikhil | Completed | 01-Dec-2021: SNOW-51 raised for LSH/SMT updates WRT PPC#02 and notified the LSP. There is no impact to RF. 19-May-2021: Rule File V3.0 updated and finalized for YD domain as per latest global communication of IRT DTS. SNOW-51 raised and LSP is notified. 18-May-2021: Sent mail to TDM to update the table name of IRT DTS for YD domain. Post DTS updated, RF will be updated. 13-Jan-2021: Rule File V2.0 finalized in Subway for YD domain update as per latest guidance. LSP is notified. 16-Dec-2020 (SHRIVNI5): Rule File V1.0 finalized and SNOW-05 ticket is raised. LSP is notified. 26Nov2020: Backup: Rehana Whats planned: RF is created and review is completed. Need to update the RF if any further update comes and to finalize the RF once the study is pushed to Production. 11-Nov-2020: 1st round of RF review is done and no RF update is required. However database would be updated as per latest global communication. RF will be updated post DB updates will be shared for 2nd round of Review. 09-Nov-2020: Created the Rule File V0.1 and sent for peer review. Waiting for peer reviewer comments. 28-Oct-2020 (SHRIVNI5): DBD shared the study related documents. Started reviewing them. 17-Sep-2020 (SHRIVNI5): Sent mail to study DBD to provide study status and study related documents. Waiting the reply. | None | None | 2020-12-16 05:30 | RF finalized within Go-live + 5 days | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2021-01-13 | Completed | 2021-01-15 05:30 |  | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-01-15 05:30 | 2021-01-15 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-01-15 05:30 |  |  |  |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 10 | 29 | 0 | 54 | 428 | 0 | 157 | 34 | 76 | 538 | 1 | 0 |  | Ankylosing spondylitis; Psoriatic arthritis | No | Global | Open | Yes | [10 empty] | 2021-01-12 05:30 |  |  |  | Interim-Analysis |  | GDD annual target | Yes
CAIN457A | CAIN457A1401 | C1001022 | Phase IV | Other | Paper |  |  | 2015-12-18 05:30 | DB Conduct | Final DBL | 2022-06-06 05:30 | 2015-12-03 05:30 | 2015-06-17 05:30 | 2015-06-17 05:30 |  | Active | 2021-08-31 05:30 | 2021-08-27 05:30 | 2022-06-06 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Special drug use observational study of AIN457 in psoriasis | CAIN457A1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | NISHIKAWA, ERINA | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | MASAYUKI SATO | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Psoriasis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A1402 | C1001023 | Phase IV | Other | Paper |  |  | 2016-02-26 05:30 | DB Conduct | Final DBL | 2022-04-05 05:30 | 2016-02-25 05:30 | 2015-11-12 05:30 | 2015-11-12 05:30 |  | Active | 2021-11-28 05:30 | 2021-11-24 05:30 | 2022-04-05 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Special Investigation of AIN457A in pustular psoriasis | CAIN457A1402 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | NISHIKAWA, ERINA | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | MASAYUKI SATO | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Psoriasis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2105 | C1001025 | Phase I | NCDS | [7 empty] | 2016-07-12 05:30 |  | 2015-12-16 05:30 |  | Completed |  | 2017-01-14 05:30 |  | 2017-02-24 05:30 | FALSE |  |  |  | IDMA Shared |  | A randomized, double-blind, placebo-controlled,\nsingle dose study to evaluate the safety, tolerability and\npharmacokinetics of three doses (75, 150 and 300 mg) of\nsecukinumab after subcutaneous injection\nin healthy Chinese subjects | CAIN457A2105 China-Simple PK study in HV | P7 Immunology Hepatology and Dermatology | [6 empty] | Felicitas Irene Thom | [66 empty] | Psoriasis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2110 | C1001037 | Phase I | NOVDD | [7 empty] | 2015-12-17 05:30 |  | 2015-04-28 05:30 |  | Completed |  | 2016-12-20 05:30 |  | 2017-03-15 05:30 | FALSE |  |  |  | IDMA Shared |  | An open-label, single sequence crossover, study investigating the influence of secukinumab treatment on the pharmacokinetics of midazolam as a CYP3A4 substrate in patients with moderate to severe plaque psoriasis. | CAIN457A2110 DDI in PsO patients | P7 Immunology Hepatology and Dermatology | [6 empty] | Samantha Pappin | [54 empty] | 68 | 0 |  |  | 0 |  |  |  | 1059 | 4 | 0 |  |  |  | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A2 | CAIN457A21301 | C4014126 | Phase III |  |  |  |  | 2022-12-13 05:30 |  | Final DBL | 2025-09-01 05:30 |  | 2022-06-03 05:30 |  |  | Planned | 2025-07-21 05:30 |  | 2025-09-01 05:30 | [5 empty] | FULL Outsourced |  |  | CAIN457A21301 Japan Ph3 study up-titration | P7 Immunology Hepatology and Dermatology | [5 empty] | RYOHEI IWASAKI | RYOHEI IWASAKI | [66 empty] | Psoriasis | No | Global | Open: Reapproval | Yes
CAIN457A | CAIN457A2211E1 | C1001019 | Phase II | NOVDD | [7 empty] | 2010-05-11 05:30 |  | 2009-12-22 05:30 |  | Completed |  | 2016-10-18 05:30 |  | 2016-12-16 05:30 | FALSE |  |  |  | IDMA |  | A multicenter extension trial of subcutaneously administered AIN457 in patients with moderate to severe chronic plaque-type psoriasis. | CAIN457A2211E1_PhII Extension | P7 Immunology Hepatology and Dermatology | [5 empty] | Aude Lacombe; Isabelle Hampele; Pascaline Regnault | Pascaline Regnault | [66 empty] | Psoriatic plaque | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2302E1 | C1003038 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2012-06-19 05:30 |  | 2012-02-24 05:30 |  | Completed |  | 2017-06-26 05:30 |  | 2017-11-21 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA | DF ID | A multicenter, double-blind, randomized withdrawal extension study of subcutaneous secukinumab in prefilled syringes to demonstrate long-term efficacy, safety and tolerability up to 4 years in subjects with moderate to severe chronic plaque-type psoriasis completing preceding psoriasis phase III studies with secukinumab | CAIN457A2302E1_Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sharma, Tanvi | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther |  | Isabelle Hampele | [15 empty] | Chakravarthy, Praveen J |  | Sandeep Kadam | [28 empty] | Cognizant | [19 empty] | Psoriasis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2304E1 | C1001021 | Phase III | NCDS | [7 empty] | 2012-09-16 05:30 |  | 2012-06-21 05:30 |  | Completed |  | 2017-05-04 05:30 |  | 2017-09-15 05:30 | FALSE |  |  |  | IDMA |  | A multicenter, double-blind and open label, 4 year extension study of subcutaneous secukinumab in prefilled syringes, assessing long-term safety, tolerability and efficacy in subjects with moderate to severe chronic plaque-type psoriasis treated with either a fixed dose regimen or on a retreatment at start of relapse regimen | CAIN457A2304E1_Extension | P7 Immunology Hepatology and Dermatology | [6 empty] | Aude Eleonore Lacombe | [66 empty] | Psoriasis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2308 | C1001028 | Phase III | NCDS | [7 empty] | 2012-05-08 05:30 |  | 2012-01-06 05:30 |  | Completed |  | 2016-10-24 05:30 |  | 2016-12-30 05:30 | FALSE |  |  |  | IDMA |  | A randomized, double-blind, placebo controlled, multicenter study of subcutaneous secukinumab in prefilled syringes to demonstrate efficacy after twelve weeks of treatment, and to assess the safety, tolerability, usability and long-term efficacy in subjects with chronic plaque-type psoriasis FEATURE First study of SEcukinumAb in pre-filled syringes in subjecTs with chronic plaqUe-type psoriasis: REsponse at 12 weeks | CAIN457A2308 Feature PFS | P7 Immunology Hepatology and Dermatology | [5 empty] | Linda Wraith | Linda Wraith | [66 empty] | Psoriatic plaque | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457A | CAIN457A2309 | C1001029 | Phase III | NCDS | [7 empty] | 2012-10-17 05:30 |  | 2012-06-28 05:30 |  | Completed |  | 2016-10-27 05:30 |  | 2017-01-27 05:30 | FALSE |  |  |  | IDMA |  | A randomized, double-blind, placebo controlled, multicenter study of subcutaneous secukinumab in autoinjectors to demonstrate efficacy after twelve weeks of treatment, and to assess the safety, tolerability, usability and long-term efficacy in subjects with chronic plaque-type psoriasis | CAIN457A2309_Juncture AI Pen | P7 Immunology Hepatology and Dermatology | [5 empty] | Jimena Djimopoulos | Jimena Djimopoulos | [66 empty] | Psoriatic plaque | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457L | CAIN457A2310 | C1001024 | Phase III | NCDS | OC RDC - Inhouse | 2015-09-24 05:30 | 2015-09-24 05:30 |  | DB Conduct | Final DBL | 2023-05-12 05:30 | 2015-09-29 05:30 |  | 2021-07-06 05:30 |  | Active | 2023-03-31 05:30 |  | 2023-05-12 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo- and active controlled multicenter trial to demonstrate efficacy of subcutaneous secukinumab compared to placebo and etanercept (in a single-blinded arm) after twelve weeks of treatment, and to assess the safety, tolerability, and long-term efficacy in subjects from 6 to less than 18 years of age with severe chronic plaque psoriasis | CAIN457A2310 Pediatric_Severe PsO | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kaila, Saandeep Reddy | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Susan Cafoncelli | Susan Cafoncelli | Ambati, Purnachander | Shewane, Roshni | Completed | 2020-04-15 05:30 | Study Transition on 15 Apr2020 to Roshni Shewane. | [10 empty] | Kadam, Sandeep |  | Sandeep Kadam | [12 empty] | This is an old OC studym which was transitioned to me, I am initiating the DDPASS with the new template from 29-Sep-2020. | 100 | OCRDC - Inhouse | Yes | ZK;#ZK03;#Y5;#Y1 |  |  |  |  | Pharma | Novartis | ICON | 2015-09-02 05:30 | 2015-09-02 05:30 | Shewane, Roshni | Iliyas, Mohamed | NA | [7 empty] | 109 | 0 |  |  | 0 |  |  |  | 628 | 4 | 0 |  | Psoriatic plaque | No | Global | Open | Yes | [14 empty] | DBL | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CAIN457L | CAIN457A2311 | C1001030 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-05 05:30 | 2018-09-06 05:30 | DB Conduct | Final DBL | 2023-11-02 05:30 | 2018-08-29 05:30 | 2018-02-28 05:30 | 2018-02-09 05:30 |  | Active | 2023-09-14 05:30 |  | 2023-11-02 05:30 |  | FALSE | N/A | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Pediatric Study in children with moderate to severe Plaque Psoriasis | CAIN457A2311 Pediatric_moderate severe_PsO | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Patil, Shweta Ramesh | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Susan Cafoncelli | Susan Cafoncelli | Munukutla, Valli | Gehlawat, Priya | Completed | 2021-06-23 05:30 | 23Jun2021 : Transition from Valli Munukutla to Priya Gehalwat Transition from Nagendra Vedula to Valli Munukutla No PPC ongoing to this study |  | DRM (DIAL) | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 22-JUN-21RF 7.0 is final and SNOW 51 request created. As of today, no pending forms and no pending DTS 07-JUL-20: As of today, no pending forms and no pending DTS NVE:29 Nov 19: No Pending domains/updates expected. All domains(including 3rd party domains) are final. | None | None | 2018-09-25 05:30 | Transition Study and Legacy process | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Sandeep Kadam | Completed | 2018-10-03 | Completed | 2019-06-24 05:30 | DRM completed for following domains on 24-Jun-2019: AE, CM, DM, DS, DV, EC, EG, FAAE, IE, LB, MH, ODM, PR, QS, RP, SC, SV, VS, ZJ and ZW |  | 2018-10-05 05:30 | 2018-10-05 05:30 | Pre-requisites not met | 2019-08-21 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5 | [11 empty] | NA | [5 empty] | 12 | 33 | 48 | 0 | 284 | 639 | 0 | 193 | 33 | 145 | 817 | 4 | 0 |  | Psoriatic plaque | No | Global | Open | Yes | [10 empty] | 2019-06-24 05:30 |  |  |  | Interim-Analysis | Agrawal, Naina | None of the above | No
CAIN457A_MA | CAIN457A2312 | C1001551 | Phase III | NCDS | [7 empty] | 2013-06-19 05:30 |  | 2012-12-20 05:30 |  | Completed |  | 2016-11-02 05:30 |  | 2017-01-30 05:30 | FALSE |  |  |  | IDMA Shared |  | A randomized, double-blind, placebo-controlled, multicenter study to demonstrate the efficacy at 16 weeks of secukinumab 150 and 300 mg s.c. and to assess safety, tolerability and long-term efficacy up to 132 weeks in subjects with moderate to severe palmoplantar psoriasis | CAIN457A2312_Gesture_PP | P7 Immunology Hepatology and Dermatology | [5 empty] | Pascaline Regnault | Pascaline Regnault | [66 empty] | Psoriasis | Yes | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A_MA | CAIN457A2313 | C1001552 | Phase III | NCDS | [7 empty] | 2013-06-20 05:30 |  | 2012-12-20 05:30 |  | Completed |  | 2017-01-03 05:30 |  | 2017-03-22 05:30 | FALSE |  |  |  | IDMA Shared |  | A randomized, double-blind, placebo-controlled, multicenter, study to demonstrate the efficacy at 16 weeks of secukinumab 150 and 300 mg s.c. and to assess safety, tolerability and long-term efficacy up to 132 weeks in subjects with moderate to severe nail psoriasis | CAIN457A2313_Transfigure_Nail | P7 Immunology Hepatology and Dermatology | [5 empty] | Pascaline Regnault | Pascaline Regnault | [66 empty] | Psoriasis | Yes | Global | Completed | Yes | [16 empty] | None of the above
CAIN457A_MA | CAIN457A2317 | C1001553 | Phase III | NCDS | [7 empty] | 2014-02-25 05:30 |  | 2013-10-22 05:30 |  | Completed |  | 2016-06-28 05:30 |  | 2016-09-16 05:30 | FALSE |  |  |  | IDMA Shared |  |  | CAIN457A2317_Clear_H2H v Stelara | P7 Immunology Hepatology and Dermatology | [5 empty] | Aude Lacombe | Ami Shah | [67 empty] | No |  | Completed | [17 empty] | None of the above
CAIN457A | CAIN457A2318 | C1001031 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-02-28 05:30 |  | 2016-07-07 05:30 |  | Completed | 2018-12-26 05:30 | 2018-11-20 05:30 | 2019-01-30 05:30 | 2019-01-22 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A randomized, double-blind, placebo controlled, multicenter study of subcutaneous secukinumab, to demonstrate efficacy after twelve weeks of treatment and to assess safety, tolerability and long-term efficacy up to one year in subjects with moderate to severe chronic plaque-type psoriasis with or without psoriatic arthritis comorbidity | CAIN457A2318_China centric | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Annaji, Sudath | Pai, Ujwala | Vasi, Munir | Ninan, Esther | Pascaline Regnault | Pascaline Regnault | Meda, Sreelakshmi | [14 empty] | Ghate, Dhananjay |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | Y1;#Y5;#ZK;#ZK03 |  |  |  |  | Pharma | ICON | External Full | 2017-02-08 05:30 | 2017-02-08 05:30 |  |  | ICON | [7 empty] | 83 | 0 |  |  | 0 |  |  |  | 620 | 8 | 0 |  | Psoriatic plaque | No | Global | Open | Yes | [14 empty] | DBL | Bhosale, Pritam | None of the above | Yes
CAIN457N | CAIN457A2323 | C1001026 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-12-12 05:30 |  | 2016-02-24 05:30 |  | Completed | 2018-06-08 05:30 | 2018-06-08 05:30 | 2018-08-15 05:30 | 2018-08-29 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A multicenter, randomized, double-blind,\nplacebo-controlled, 52-weeks study to demonstrate\nthe efficacy, safety and tolerability of subcutaneous\nsecukinumAb injections with 2 mL pre-fiLLed syringes\n(300 mg) in adUlt subjects with moderate to seveRE\nplaque psoriasis - ALLURE | CAIN457A2323_Allure_2ml PFS | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi |  | Sharma, Tanvi | Vasi, Munir | Ninan, Esther | Isabelle Hampele; Pascal Charef | Isabelle Hampele | Meda, Sreelakshmi | [14 empty] | Shanmugam, Sharmila |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2016-09-14 05:30 | 2016-09-14 05:30 |  |  | ICON | [7 empty] | 82 | 0 |  |  | 0 |  |  |  | 662 | 7 | 0 |  | Psoriatic plaque | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457A2 | CAIN457A2324 | C1001032 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-06 05:30 | 2018-06-26 05:30 | DB Locked | Final DBL Achieved |  | 2018-06-25 05:30 | 2017-12-19 05:30 | 2017-12-20 05:30 |  | Completed | 2020-07-24 05:30 | 2020-07-15 05:30 | 2020-09-11 05:30 | 2020-09-10 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, multicenter study assessing short (16 weeks) and long-term efficacy (up to 1 year), safety, and tolerability of sub-cutaneous secukinumab in subjects of body weight 90 kg or higher with moderate to severe chronic plaque-type psoriasis | CAIN457A2324_High Dose | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vadla, Nagarajachari | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Jimena Djimopoulos | Jimena Djimopoulos | Kurella, Rakesh Reddy | Joshi, Alekhya |  |  |  |  | DRM (DIAL) | Kurella, Rakesh Reddy | Patnaik, Angella | Completed | 07-JUL-2020: No RF update required for PPC7 implemented today. LSPs informed about the SMT update and LSH re-build with the latest PROD ALS. | None | None | 2018-12-14 05:30 |  | Gandikota, Sree Lakshmi | Garje, Sagar | Sandeep Kadam | Completed | 2018-10-12 | Completed | 2019-07-16 05:30 |  |  | 2018-12-21 05:30 | 2018-12-21 05:30 | Retrospective DRM studies | 2019-08-29 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | ZK;#ZK03;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 8 | 18 | 46 | 0 | 119 | 670 | 0 | 212 | 36 | 170 | 876 | 6 | 0 |  | Psoriatic plaque | No | Global | Open | Yes | [10 empty] | 2019-07-16 05:30 | [5 empty] | HA Commitment
CAIN457N | CAIN457A2325 | C1001033 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-09 05:30 | 2018-12-21 05:30 | DB Locked | Final DBL Achieved |  | 2018-12-19 05:30 | 2018-04-11 05:30 | 2018-11-22 05:30 |  | Completed | 2020-07-29 05:30 | 2020-08-05 05:30 | 2020-10-12 05:30 | 2020-10-19 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457A2325_Mature_2 ml AI | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Deshpande Dubey, Aditi | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Isabelle Hampele | Isabelle Hampele | Ambati, Purnachander | Ahuja, Mohit |  |  |  |  | DRM (DIAL) | Suzuki, Hiroko | Kuttoboina, Sujan Kumar | Completed | 07-JUL-20: As of today, no pending forms and no pending DTS 29-NOV-2019: No action all forms/DTS included | None | None | 2019-01-17 05:30 | Transition Study and Legacy process | Gandikota, Sree Lakshmi | Garje, Sagar | Sandeep Kadam | Completed | 2019-01-21 | Completed | 2019-06-10 05:30 |  |  | 2019-01-22 05:30 | 2019-01-22 05:30 |  | 2019-08-21 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | ZK;#ZK03;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 9 | 16 | 66 | 0 | 127 | 764 | 0 | 186 | 37 | 294 | 1095 | 4 | 0 |  | Psoriasis | No | Global | Open | Yes | [10 empty] | 2019-06-10 05:30 | [5 empty] | None of the above
CAIN457A | CAIN457A2326 | C1001034 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-06-22 05:30 |  | 2015-11-16 05:30 |  | Completed | 2018-07-09 05:30 | 2018-07-09 05:30 | 2018-08-20 05:30 | 2018-08-23 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A 52-week, multicenter, randomized, double-blind study of secukinumab (300 mg) to demonstrate efficacy as assessed by Psoriasis Area and Severity Index and InvestigatorÂ¿s Global Assessment after 12 weeks of treatment, compared to ustekinumab, and to assess longterm safety, tolerability, and efficacy in subjects with moderate to severe plaque psoriasis (CLARITY) | CAIN457A2326 2nd H2H v Stelara CLARITY | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Annaji, Sudath | Sharma, Tanvi | Vasi, Munir | Ninan, Esther |  | Khaleel Ahmad | Meda, Sreelakshmi | [14 empty] | Shanmugam, Sharmila |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2016-03-31 05:30 | 2016-03-31 05:30 |  |  | ICON | [7 empty] | 61 | 0 |  |  | 0 |  |  |  | 477 | 1 | 0 |  | Psoriasis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457L | CAIN457A2406 | C4014963 | Phase IV | NCDS_2 |  |  |  | 2022-11-16 05:30 |  | Final DBL | 2025-10-17 05:30 |  | 2022-03-02 05:30 |  |  | Planned | 2025-07-25 05:30 |  | 2025-10-17 05:30 | [5 empty] | Outsourced |  | A real-world, prospective, multicenter study to assess the safety and effectiveness of secukinumab in pediatric patients aged 6 years to less than 18 years with moderate to severe chronic plaque psoriasis in China | CAIN457A2406 China Pediatric PsO PAC study | P7 Immunology Hepatology and Dermatology | [5 empty] | Zhixin Wang | Zhixin Wang | [54 empty] | 30 | [7 empty] | 600 | 2 |  |  | Plaque psoriasis | No | Global | Open | Yes
CAIN457B2 | CAIN457ADE16 | C4009192 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-15 05:30 |  | 2021-11-30 05:30 | DB Conduct | Final DBL | 2025-04-01 05:30 | 2021-11-29 05:30 | 2020-09-16 05:30 | 2021-07-07 05:30 |  | Active | 2025-02-05 05:30 |  | 2025-04-01 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, parallel-group, double-blind, placebo-controlled, multicenter, 16 week phase 3 study to investigate the efficacy and safety of secukinumab (AIN457) 300 mg s.c. in adult patients with active, moderate to severe Thyroid Eye Disease (ORBIT) | CAIN457ADE16 Thyroid Eye Disease Trial ORBIT | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | JADHAV, MEGHA AMOD | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Carmen Capusan | Tarquin Limmer | Moses, Leah | Moses, Leah | Not Started |  | 29Apr2021 : Owing to protocol amendment, the DB Go live and FPFV have been postponed to July and Aug respectively. The Database has been completed for the Protocol Version 1. Rule file version 1 has been drafted. We are awaiting the new specs based on the protocol amendment to initiate the updates in the database. Golive date 15Jan2021 planned when the RF developer was assigned on 28Oct2020. The DB Go live date was postponed from 15JAN2021 to 11MAY2021 owing to protocol amendment. Reason for protocol amendment: The received comments from the Ethics Committee and the Health Authority which will be addressed in a protocol update. Following the resubmission and formal approval of the protocol by both authorities, we will address comments from ISRC in an amendment. |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 24Nov2021:The Rule file v1.0 is finalized and Snow#05(PROD)- RITM3223500 Created for SMT and LSH set-up. 12Nov-2021: Snow#05 -RITM3182360 created for LSH-TEST(set-up). 26Oct2021: DBD confirmation-Considering the complexity of the protocol amendment, the database go live date has been extended to 12NOV2021. 09Aug2021: As per TDM confirmation discussion in last DQT meeting new FPFV 20Sep2021 and Go-Live 14Sep2021. As per DBD The FPFV maybe further pushed into october as we did not receive any confirmation on DB updates for Protocol amendment. 30Apr2021: Owing to protocol amendment, the DB Go live and FPFV have been postponed to July and Aug respectively. Rule file version 1.0 was developed and sent for peer review and now is on-hold for the PA to complete. 16Feb2021: RF v1.0 development is Ongoing.19-Feb2021: RF in review status. 28Jan2021: ALS, aCRF under RF developer review. Screen UAT tentative date is 05FEB2021 12Jan2021: SDTM annotations for SS crfs in discussion. 03Dec2020: Screen build is ongoing, SRFs are being reviewed by team. | None | None | 2021-11-24 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2021-12-15 | Completed | 2021-12-17 05:30 |  |  | 2022-02-17 05:30 | 2021-12-17 05:30 |  | 2022-02-17 05:30 |  |  |  | 0 | [14 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 4 | 0 |  | Thyroid associated orbitopathy | No | Local | Open | Yes | 2021-11-12 05:30 | Completed | 2022-01-04 05:30 | Completed | 2022-02-02 05:30 | 2022-02-04 05:30 |  |  |  |  | 2021-12-17 05:30 | [5 empty] | None of the above
CAIN457A_MA | CAIN457AJP02 | C1001036 | Phase IV | Other | Paper |  |  | 2015-12-25 05:30 | DB Locked |  |  | 2015-12-17 05:30 | 2015-11-16 05:30 | 2015-11-16 05:30 |  | Completed | 2019-12-31 05:30 | 2017-05-12 05:30 | 2019-07-31 05:30 | 2019-07-19 05:30 | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Observational study to investigate the safety and efficacy of secukinumab in psoriasis vulgaris and / or psoriatic arthritis patients dosed prior to mandatory PMS study. | CAIN457AJP02 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | NISHIKAWA, ERINA | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | YOSHIHISA SATOU | MASAYUKI SATO | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Psoriasis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457C2 | CAIN457C22301 | C4015863 | Phase III | NCDS_2 |  |  |  | 2023-03-13 05:30 |  | Final DBL | 2025-05-30 05:30 |  | 2022-08-19 05:30 |  |  | Planned | 2025-04-18 05:30 |  | 2025-05-30 05:30 | [5 empty] | InHouse |  |  | CAIN457C22301 PMR s.c. | P7 Immunology Hepatology and Dermatology | [6 empty] | Rebecca Gottschalk | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Polymyalgia rheumatica | Yes | Global | Open | Yes
CAIN457C2 | CAIN457C22302 | C4015864 | Phase III | NCDS_2 |  |  |  | 2023-03-13 05:30 |  | Final DBL | 2025-05-30 05:30 |  | 2022-08-19 05:30 |  |  | Planned | 2025-04-18 05:30 |  | 2025-05-30 05:30 | [5 empty] | InHouse |  |  | CAIN457C22302 PMR i.v. | P7 Immunology Hepatology and Dermatology | [6 empty] | Rebecca Gottschalk | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Polymyalgia rheumatica | No | Global | Open | Yes
CAIN457V1 | CAIN457F2304 | C1001042 | Phase III | NCDS | OC RDC - Inhouse | 2017-05-23 05:30 | 2017-05-23 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-05-23 05:30 |  | 2016-10-28 05:30 |  | Completed | 2020-11-09 05:30 | 2020-11-09 05:30 | 2020-12-10 05:30 | 2020-12-10 05:30 | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A three-part randomized, double-blind, placebo-controlled&#xD; study to investigate the efficacy and safety of secukinumab&#xD; treatment in Juvenile Idiopathic arthritis subtypes of&#xD; psoriatic and enthesitis-related arthritis | CAIN457F2304 Pediatric Study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sannidhi, Pavan Kumar | Kumar, Amresh | Vasi, Munir | Ninan, Esther | Roselyne Raffner | Roselyne Raffner | Ambati, Purnachander | Meda, Sreelakshmi | [13 empty] | Sundar, N Sushant |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | ZK03;#ZK;#Y1;#Y5 | 2020-12-08 05:30 | 2020-12-10 05:30 |  |  | Pharma | Novartis | ICON | 2017-03-24 05:30 | 2017-03-24 05:30 | Meda, Sreelakshmi | Shewane, Roshni | NA | [7 empty] | 172 | 0 |  |  | 0 |  |  |  | 506 | 5 | 0 |  | Enthesitis related arthritis; Juvenile arthritis; Juvenile psoriatic arthritis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457V1 | CAIN457F2304E1 | C3004550 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-03-11 05:30 | 2019-06-07 05:30 | DB Conduct | Interim DBL | 2022-03-16 05:30 | 2019-06-07 05:30 | 2018-09-25 05:30 | 2018-11-12 05:30 |  | Active | 2024-11-27 05:30 |  | 2025-01-08 05:30 |  | FALSE | There were talks of submitting data eventually to support dose up-titration possibly. | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | An extension study of subcutaneous secukinumab to evaluate the long term efficacy, safety and tolerability up to 4 years in patients with Juvenile Idiopathic Arthritis subtypes of Juvenile Psoriatic Arthritis and Enthesitis-related Arthritis | CAIN457F2304E1 Peds Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sannidhi, Pavan Kumar | Chaudhari, Vishal | Vasi, Munir | Ninan, Esther | Sophia Weise-Riccardi | Sophia Weise-Riccardi | Ahuja, Mohit | Ahuja, Mohit |  |  |  |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 17-Feb-2022: Updated and finalized the Rule File V8.0 for updating the test codes for ZW domain. Raised the SNOW-51 (RITM3505881) for LSH/SMT updates. Notified the LSP. 08-Feb-2022: Raised the SNOW-51 (RITM3468409) for LSH/SMT updates WRT PPC#05. No impact to Rule Fie. Notified the LSP. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 06Jul2020 : RF will be transitioned from Ashok to Nikhil Rule file V6.0 is the latest one. Mar2020 : RF transitioned from Chandrakala to Ashok. 10Dec2019: Transition completed (No dts, forms pending to be included in RF) with below actions pending from Mohit •RF v3.0 – 2 documents are uploaded in CREDI, need to get the duplicate removed. 29Nov2019: All the domains are present in the Rule File. Latest Rule File 6.0 is already shared with LSP which is related to LB domain update due to the DTS. There are some DDPASS meeting which are shared recently and I am looking into those. 22Nov2019: Transition initiated | None | None | 2019-04-16 05:30 |  | Majumdar, Shreya | Garje, Sagar | Sandeep Kadam | Completed | 2019-04-18 | Completed | 2019-05-17 05:30 |  |  | 2019-04-20 05:30 | 2019-04-20 05:30 |  | 2019-06-28 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 21 | 40 | 0 | 158 | 557 | 0 | 178 | 34 | 112 | 703 | 6 | 0 |  | Juvenile idiopathic arthritis | Yes | Global | Open | Yes | [10 empty] | 2019-04-18 05:30 | [5 empty] | None of the above
CAIN457H | CAIN457F2305E1 | C1001048 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2013-11-06 05:30 |  | 2013-04-23 05:30 |  | Completed | 2018-04-30 05:30 | 2018-03-16 05:30 | 2018-06-14 05:30 | 2018-06-14 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | An extension study to evaluate the sustainability of clinical benefits, safety and tolerability of secukinumab in patients with active Ankylosing Spondylitis | MEASURE 1_CAIN457F2305E1 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vemula, Jagadeesh | N, Ram Kumar | Vasi, Munir | Ninan, Esther | Sophia Weise-Riccardi | Sophia Weise-Riccardi | Meda, Sreelakshmi | [14 empty] | Rajhans, Khushbu Kumari |  | Sandeep Kadam | [21 empty] | Pharma | ICON | External Full |  |  |  |  | ICON | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 650 | 10 | 0 |  | Ankylosing spondylitis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2306E1 | C1001043 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2013-09-30 05:30 |  | 2013-05-08 05:30 |  | Completed | 2017-12-18 05:30 | 2018-01-11 05:30 | 2018-05-09 05:30 | 2018-03-23 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | :A three year extension study to evaluate the long term efficacy, safety and tolerability of secukinumab in patients with active psoriatic arthritis. | FUTURE 1_CAIN457F2306E1 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Krishnan, Vasudevan | N, Ram Kumar | Bhoir, Vinit Kisan | Ninan, Esther | Janice Woznicki; Sophia Weise-Riccardi | Sophia Weise-Riccardi | [15 empty] | Munusamy, Tamilarasan |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  |  |  |  | ICON | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 650 | 10 | 0 |  | Psoriatic arthritis; Psoriatic arthropathy | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457H | CAIN457F2308 | C1001050 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-10-18 05:30 |  | 2015-11-09 05:30 |  | Completed | 2019-03-21 05:30 | 2019-03-19 05:30 | 2019-05-02 05:30 | 2019-04-30 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A randomized, double-blind, placebo-controlled, phase III multicenter study of subcutaneous secukinumab in prefilled syringes, to compare efficacy at 16 weeks with placebo and to assess safety and tolerability up to 52 weeks in subjects with active Ankylosing Spondylitis | CAIN457F2308 MEASURE 5 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vemula, Jagadeesh | Vasi, Munir | Vasi, Munir | Ninan, Esther | Kamel Bouylout | Kamel Bouylout | Killamsetty, Nanari Ram | [14 empty] | Munusamy, Tamilarasan |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2016-09-14 05:30 | 2016-09-14 05:30 |  |  | ICON | [7 empty] | 76 | 0 |  |  | 0 |  |  |  | 687 | 12 | 0 |  | Ankylosing spondylitis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457H | CAIN457F2310 | C1001049 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2012-10-18 05:30 |  | 2012-06-04 05:30 |  | Completed | 2018-10-31 05:30 | 2018-09-18 05:30 | 2018-12-13 05:30 | 2018-10-23 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A randomized, double-blind, placebo-controlled phase III multicenter study of subcutaneous secukinumab in prefilled syringes to demonstrate the efficacy at 16 weeks and to assess the long-term efficacy, safety and tolerability up to 5 years in patients with active Ankylosing Spondylitis | CAIN457F2310 MEASURE 2 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Muraleedharan Thampy Santhanalekshmy, Karthika | N, Ram Kumar | Vasi, Munir | Ninan, Esther | Aimee Readie; Mukul Prakash | Mukul Prakash | [15 empty] | Ghate, Dhananjay |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | ICON | External Full |  | 2012-09-18 05:30 |  |  | ICON | [7 empty] | 96 | 0 |  |  | 0 |  |  |  | 634 | 14 | 0 |  | Ankylosing spondylitis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2312 | C1001038 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2013-04-14 05:30 |  | 2012-10-18 05:30 |  | Completed | 2019-03-29 05:30 | 2019-01-09 05:30 | 2019-03-20 05:30 | 2019-03-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A Phase III randomized, double-blind, placebo-controlled multicenter study of subcutaneous secukinumab in prefilled syringes to demonstrate the efficacy at 24 weeks and to assess the long term efficacy, safety and tolerability up to 5 years in patients with Active Psoriatic Arthritis. | CAIN457F2312 FUTURE 2 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chandrakant, Khilari | Sen, Sujoy | Vasi, Munir | Ninan, Esther | Mukul Prakash | Mukul Prakash | [15 empty] | Munusamy, Tamilarasan |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  | 2013-03-21 05:30 |  |  | ICON | [7 empty] | 115 | 0 |  |  | 0 |  |  |  | 671 | 15 | 0 |  | Psoriatic arthritis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457H | CAIN457F2314 | C1001047 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-01-14 05:30 |  | 2013-08-30 05:30 |  | Completed | 2017-12-12 05:30 | 2017-12-11 05:30 | 2018-02-08 05:30 | 2018-02-15 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A randomized, double-blind, placebo-controlled phase III multicenter study of secukinumab to demonstrate the efficacy at 16 weeks and to assess the long-term safety, tolerability and efficacy up to 3 years in subjects with active Ankylosing Spondylitis | CAIN457F2314 Measure 3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vemula, Jagadeesh | Sen, Sujoy | Bhoir, Vinit Kisan | Ninan, Esther | Susan Cafoncelli | Susan Cafoncelli | Meda, Sreelakshmi | [14 empty] | Munusamy, Tamilarasan |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  | 2013-11-12 05:30 |  |  | ICON | [7 empty] | 89 | 0 |  |  | 0 |  |  |  | 649 | 14 | 0 |  | Ankylosing spondylitis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2318 | C1001039 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-04-10 05:30 |  | 2013-10-15 05:30 |  | Completed | 2018-03-28 05:30 | 2018-03-28 05:30 | 2018-07-09 05:30 | 2018-07-09 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A phase III, randomized, double-blind, placebo-controlled multicenter study of subcutaneous secukinumab in autoinjectors, to demonstrate efficacy at 24 weeks and to assess the long term safety, tolerability and efficacy up to 3 years in subjects with active Psoriatic Arthritis | FUTURE 3_CAIN457F2318 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Dharamaraya Biradar, Geetha | Sen, Sujoy | Vasi, Munir | Ninan, Esther | Kamel Bouylout | Kamel Bouylout | Meda, Sreelakshmi | [14 empty] | Shanmugam, Sharmila |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  | 2014-02-20 05:30 |  |  | ICON | [7 empty] | 113 | 0 |  |  | 0 |  |  |  | 910 | 17 | 0 |  | Psoriatic arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457H | CAIN457F2320 | C1001045 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-05-18 05:30 |  | 2014-10-29 05:30 |  | Completed | 2018-01-02 05:30 | 2018-01-02 05:30 | 2018-04-19 05:30 | 2018-04-13 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A randomized, double-blind, placebo-controlled, phase III multicenter study of subcutaneous secukinumab (150 mg) with and without a subcutaneous loading regimen to assess efficacy, safety, and tolerability up to 2 years in patients with active ankylosing spondylitis | MEASURE 4_CAIN457F2320 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi |  | Sen, Sujoy | Bhoir, Vinit Kisan | Ninan, Esther | Cornelia Scheurer | Cornelia Scheurer | [15 empty] | Munusamy, Tamilarasan |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2015-04-30 05:30 | 2015-04-30 05:30 |  |  | ICON | [7 empty] | 87 | 0 |  |  | 0 |  |  |  | 699 | 14 | 0 |  | Ankylosing spondylitis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2336 | C1001041 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-05-29 05:30 |  | 2014-11-07 05:30 |  | Completed | 2017-12-19 05:30 |  | 2018-04-12 05:30 | 2018-02-06 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A phase III, randomized, double-blind, placebo-controlled multicenter study of subcutaneous secukinumab (150 mg) in pre-filled syringe, with or without loading regimen, to demonstrate efficacy, safety and tolerability up to 2 years in patients with active psoriatic arthritis (FUTURE 4) | FUTURE 4_CAIN457F2336 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chaudhari, Vishal | Vasi, Munir | Vasi, Munir | Ninan, Esther | Pranjali Gaunker | Pranjali Gaunker | [15 empty] | Rathinasabapathy, Mehala |  | Sandeep Kadam | [21 empty] | Pharma | ICON | External Full | 2015-05-22 05:30 | 2015-05-22 05:30 |  |  | ICON | [19 empty] | Psoriatic arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2342 | C1001040 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-08-31 05:30 | 2018-02-12 05:30 | 2015-03-24 05:30 |  | Completed | 2019-01-16 05:30 | 2019-01-24 05:30 | 2019-04-04 05:30 | 2019-03-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | A Phase III, randomized, double-blind, placebo controlled multi-center study of subcutaneous secukinumab (150 mg and 300 mg) in prefilled syringe to demonstrate efficacy (including inhibition of structural damage), safety, and tolerability up to 2 years in subjects with active psoriatic arthritis (FUTURE 5) | CAIN457F2342 PSA X-ray claim study FUTURE 5 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vemula, Jagadeesh | Sen, Sujoy | Vasi, Munir | Ninan, Esther | Denis Bourrelly | Denis Louis Bourrelly | Meda, Sreelakshmi | [14 empty] | Ghate, Dhananjay |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | LB;#Y1;#Y5;#ZK |  |  |  |  | Pharma | ICON | External Full | 2015-08-17 05:30 | 2015-08-17 05:30 |  |  | ICON | [7 empty] | 121 | 0 |  |  | 0 |  |  |  | 687 | 17 | 0 |  | Psoriatic arthritis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457J | CAIN457F2366 | C1001053 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-04-03 05:30 |  | 2016-10-27 05:30 |  | Completed | 2019-12-25 05:30 | 2019-12-30 05:30 | 2020-02-19 05:30 | 2020-03-09 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, active control, multicenter study to evaluate the efficacy at week 52 of subcutaneously administered secukinumab monotherapy compared with subcutaneously administered adalimumab monotherapy in patients with active psoriatic arthritis | CAIN457F2366 H2H with adalimumab wk52 Efficay PsA | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chaudhari, Vishal | Kumar, Amresh | Vasi, Munir | Ninan, Esther |  | Gregory O'Neil | Meda, Sreelakshmi | [14 empty] | Kumar, Ranjeet |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | ICON | 2017-03-09 05:30 | 2017-03-09 05:30 | Meda, Sreelakshmi | Mulla, Afreen | NA | [7 empty] | 107 | 0 |  |  | 0 |  |  |  | 751 | 15 | 0 |  | Psoriatic arthritis | No | Global | Terminated | Yes | [16 empty] | None of the above
CAIN457F | CAIN457F2367 | C4009631 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-02-10 05:30 | 2021-06-14 05:30 | 2021-07-23 05:30 | DB Conduct | Interim DBL | 2022-07-01 05:30 | 2021-06-24 05:30 | 2020-11-04 05:30 | 2020-11-20 05:30 |  | Active | 2023-04-28 05:30 |  | 2023-06-09 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A phase III randomized, double-blind, placebo controlled, multicenter, bridging study of subcutaneous secukinumab, to demonstrate efficacy after sixteen weeks of treatment and to assess safety, tolerability and long-term efficacy follow-up to one year in Chinese subjects with active psoriatic arthritis. | CAIN457F2367 China Stand-alone PsA phase 3 study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Jiao, Guang | Qian, Celia | Vasi, Munir | Ninan, Esther | Amit Ranjan | Amit Ranjan | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini | Not Started |  | 13May2021 : Screen UAT is completed (Jesica). Edit checks (Jesica, Nagendra, Priya). Edits checks pending (37) Pending CFs - 79 (Ashok, Sukanya and Priyanka), pending programmable PDs - 6, Manual PDs done including UAT. eSAE - released for UAT. 28Apr2021 : Study status below. 1) Edit check build is going and releasing checks in batch wise for UAT. 2) CF programming for CFs and PDs are pending. 3) tSDV will be initiated shortly. 4) DTS review ongoing. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 10Feb2021 |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 12Aug2021: QS1L, QS2L, QS3L, QS4L,QS6L, QS7L, LB1L, ZW1L DTSs have been added in RF, raised SNOW ticket(RITM2855313) and LSP notified. QS5L and ZW2L have not been finalized yet. Once finalized I will be adding them in the RF. 26-Jul-2021: The DTS has been reviewed and comments have been shared. Once the DTS is finalized will be adding it in the RF 21Jul2021 : DTSs QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, LB1L, ZW1L, ZW2L reflecting in 21Jul report. 01-Jul-2021: DTS's are under review. 15Jun2021: Rule File is Finalized in CREDI, SNOW05 Ticket raised(RITM2672473) for LSH Set-up and RF checklist has also been uploaded in CREDI. 17May2021: Screen UAT completed on 13-May-2021 06May2021 : Study specific forms reviewed. Follow up with DBD on current status. 10Feb2021 : RF developer assigned. | None | None | 2021-06-15 05:30 | RF finalized within Go-live + 5 days | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2021-06-30 | Completed | 2021-06-30 05:30 |  | KPI met - incorrect source date entry (example FPFV) | 2021-07-02 05:30 | 2021-07-02 05:30 | Initial FPFV targeted on 02 July 2021 but changed at last moment | 2021-07-02 05:30 |  |  |  | 80 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 2 | 20 | 56 | 0 | 222 | 742 | 0 | 231 | 39 | 192 | 973 | 11 | 0 |  | Psoriatic arthritis | No | Global | Open | Yes | [10 empty] | 2021-07-01 05:30 | [5 empty] | None of the above | Yes
CAIN457H | CAIN457H1301 | C1001046 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-03-22 05:30 |  | 2015-11-30 05:30 |  | Completed | 2018-08-29 05:30 | 2018-05-16 05:30 | 2018-08-01 05:30 | 2018-07-25 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA Shared JP | DF ID | An open-label, phase III, study of subcutaneous secukinumab to assess efficacy, safety and tolerability at up to 52 weeks in Japanese patients with active Ankylosing Spondylitis | Japan Study_CAIN457H1301 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Ichinowatari, Mihoko | Sen, Sujoy | Bhoir, Vinit Kisan | Ninan, Esther | KAZUYUKI ISHIHARA | RYOHEI IWASAKI | Ambati, Purnachander | [14 empty] | Bothe, Dnyanesh |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2016-03-11 05:30 | 2016-03-11 05:30 |  |  | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 526 | 13 | 0 |  | Ankylosing spondylitis | Yes | Local | Completed | Yes | [16 empty] | None of the above
CAIN457H | CAIN457H1401 | C3001610 | Phase IV | Other | CRO - EDC |  |  | 2019-03-29 05:30 | DB Conduct | Final DBL | 2022-06-15 05:30 | 2019-02-28 05:30 | 2019-01-31 05:30 | 2019-01-29 05:30 |  | Active | 2021-12-15 05:30 |  | 2022-06-15 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Observational study to investigate the safety and efficacy over 52 weeks in Ankylosing Spondylitis (AS) patients treated with Cosentyx (secukinumab) | CAIN457H1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | MATSUNAKA, REIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | MASAYUKI SATO | [17 empty] | Sandeep Kadam | [28 empty] | IQVIA | [19 empty] | Ankylosing spondylitis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457I | CAIN457H2315 | C1001052 | Phase III | NCDS | OC RDC - Inhouse | 2016-03-14 05:30 | 2016-03-14 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-04-29 05:30 | 2017-10-31 05:30 | 2015-10-01 05:30 |  | Completed | 2021-03-15 05:30 | 2021-03-11 05:30 | 2021-04-27 05:30 | 2021-04-19 05:30 | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo-controlled phase III multicenter study of subcutaneous secukinumab in prefilled syringes, to demonstrate the clinical efficacy, safety and tolerability of secukinumab compared to placebo in patients with non-radiographic axial spondyloarthritis at week 16 as well as week 52 and long term efficacy and safety up to week 104 | PREVENT_CAIN457H2315 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chaudhari, Vishal | Kumar, Amresh | Vasi, Munir | Ninan, Esther | Moreshwar Patwardhan | Moreshwar Ramchandra Patwardhan | TEMBHARE, HITESH | Meda, Sreelakshmi | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | -NA- | 2021-04-20 05:30 | 2021-04-21 05:30 |  |  | Pharma | ICON | ICON | 2016-03-14 05:30 | 2016-03-14 05:30 | Meda, Sreelakshmi |  | NA | [7 empty] | 103 | 0 |  |  | 0 |  |  |  | 690 | 17 | 0 |  | Non-radiographic axial spondyloarthritis; Spondyloarthropathy | Yes | Global | Open | Yes | [14 empty] | Interim-Analysis | Sahu, Ahallad | None of the above | No
CAIN457I | CAIN457I2301 | C4009634 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-07-10 05:30 | 2021-06-28 05:30 | 2021-07-22 05:30 | DB Conduct | Final DBL | 2024-11-12 05:30 | 2021-07-21 05:30 | 2020-11-17 05:30 | 2020-11-18 05:30 |  | Active | 2024-10-01 05:30 |  | 2024-11-12 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo controlled, multicenter study of subcutaneous Secukinumab, to compare efficacy at 16 weeks with placebo and to assess safety and tolerability up to 52 weeks in Chinese participants with active non-radiographic axial spondyloarthritis (nr-axSpA). | CAIN457I2301 China Ph3 bridging nr-axSpA | P7 Immunology Hepatology and Dermatology | Molander, Lei Ann | Shi, Ruolian | Qian, Celia | Vasi, Munir | Ninan, Esther | Coco Liang | Hongzi Liang | Kashyap, Sandeep | Kashyap, Sandeep | Completed | 2021-09-27 05:30 | 29Apr2021 : Go-Live Date: As per TDM this study is selected as a Bullet Study in China and FPFV Date will be updated by GTD (Mostly by July 2nd week), As been discussed in the DQT meeting. Study Status: Screen UAT Completed, Edit Checks First Batch 1, 200 checks are released to UAT, Need to Release Remaining 288 Edit checks and CF’s by 14MAY2021. PD & tSDV: Spec Not Finalized yet. Support Required: Will be helpful if CF Programmer is assigned. Most of the checks are Related to CF. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 10Jul2021 |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 15Jul2021: CAIN457I2301_Rule File_Version 2.0 is now finalized in CREDI with QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, ZW1L and IRT DTS included in the Rule file. SNOW-51 Ticket is also raised with Ticket number-RITM2776637. 09Jul2021 : QS, ZW DTS included in RF and sent for peer review. IRT DTS was shared for review. Reviewed and shared the comments with DBD. 29June2021: CAIN457I2301_Rule file_version 1.0 is finalized in CREDI and SNOW-05 ticket is also raised with ticket number-RITM2718484. 27May2021: Rule file Peer Review is completed 24May2021: Rule file V0.1 is released for Peer Review 12May2021: Rule file development has been started. 11May2021: DBD confirmed with TAPOD, and requested DM for the re-approval of the Central lab Cover pages SRF and change the domain from ‘LB’ to ‘ZE’. DBD will share the updated ALS, once the SRF is approved. 06May2021: Completed the review of all the study specific forms. Requested the DBD to confirm on the domain of all the three Central Lab Assessment Cover Pages. 03May2021 : SS forms and SRF shared by DBD on 07Apr2021. SRF and SS review ongoing. 03Apr2021 : RF developer assigned. | None | None | 2021-06-29 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2021-07-23 | Completed | 2021-07-28 05:30 |  | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-07-28 05:30 | 2021-07-28 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-07-28 05:30 | 2021-07-28 05:30 |  |  |  |  | Yes | [12 empty] | NA | [5 empty] | 2 | 20 | 62 | 0 | 229 | 994 | 0 | 255 | 44 | 156 | 1194 | 10 | 0 |  | Non-radiographic axial spondyloarthritis | Yes | Global | Open | Yes | [10 empty] | 2021-07-27 05:30 | [5 empty] | None of the above | Yes
CAIN457I | CAIN457I2401 | C4012833 | Phase IV | NCDS_2 |  |  |  | 2023-03-27 05:30 |  | Final DBL | 2028-04-17 05:30 |  | 2022-06-29 05:30 |  |  | Planned | 2028-02-21 05:30 |  | 2028-04-17 05:30 | [5 empty] | InHouse |  |  | CAIN457I2401 Withdrawal PMC study | P7 Immunology Hepatology and Dermatology | [6 empty] | Roselyne Raffner | Das, Devashish | Das, Devashish | [52 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Non-radiographic axial spondyloarthritis | No | Global | Open | Yes
CAIN457K | CAIN457K2340 | C1001056 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2017-10-16 05:30 | 2017-11-30 05:30 | DB Conduct | Final DBL | 2022-05-04 05:30 | 2017-11-30 05:30 |  | 2017-07-06 05:30 |  | Active | 2021-12-23 05:30 | 2021-11-29 05:30 | 2022-05-04 05:30 |  | FALSE | Not a part of GDD Objective as per HORIZON | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, partially-blinded, active-controlled multicenter study of secukinumab to demonstrate reduction of radiographic progression versus GP2017 (adalimumab biosimilar) at 104 weeks and to assess the long term safety, tolerability and efficacy up to 2 years in patients with active ankylosing spondylitis | SURPASS_AIN457K2340 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Panyam, Pradeep Kumar | Chaudhari, Vishal | Vasi, Munir | Ninan, Esther | Hiroshi Sawata | Prateek Kulshrestha | Munukutla, Valli | Gehlawat, Priya | Completed | 2021-06-23 05:30 | 23Jun2021 : Transition from Valli Munukutla to Priya Gehalwat PPC-10 eSAE PPC initiaated. The changes are included in the PPCR portal by the TDM. eSAE team has to provide the IA Transition from Nagendra Vedula to Valli Munukutla |  | DRM (DIAL) | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 07-JUL-20: As of today, no pending forms and no pending DTS. NVE:29 Nov 19: No Pending domains/updates expected. All domains(including 3rd party domains) are final. | None | None | 2018-05-23 05:30 | Transition Study and Legacy process | Polavarapu, Vanaja | Agavekar, Amit | Sandeep Kadam | Completed | 2019-01-03 | Completed |  | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-05-28 05:30 | 2018-09-28 05:30 | Pre-requisites not met | 2020-06-06 05:30 |  |  | DDPASS is going on as we have final DBL in Jan-2022 | 100 | RaveX - Inhouse | Yes | DV;#EC;#SV;#ZJ | [11 empty] | NA | [5 empty] | 12 | 16 | 58 | 0 | 128 | 691 | 0 | 208 | 36 | 248 | 975 | 11 | 0 |  | Ankylosing spondylitis | Yes | Global | Open | Yes | [10 empty] | 2020-06-09 05:30 | [5 empty] | None of the above
CAIN457L | CAIN457L1401 | C4011654 | Phase IV | Other | Other |  |  | 2022-02-28 05:30 | DB Set-Up | Final DBL | 2025-01-31 05:30 | 2022-02-14 05:30 | 2021-10-30 05:30 | 2022-01-06 05:30 |  | Active | 2024-09-30 05:30 |  | 2025-01-31 05:30 |  | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID |  | CAIN457L1401 JPN PMS | P7 Immunology Hepatology and Dermatology | YAMADA, KAYO | MORI, YUMIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | CHIE NARITA | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Psoriasis; Psoriatic arthritis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457M | CAIN457M2301 | C3004544 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-12-10 05:30 | 2019-02-01 05:30 | DB Conduct | Interim DBL | 2022-05-12 05:30 | 2019-01-31 05:30 | 2018-08-16 05:30 | 2018-08-10 05:30 |  | Active | 2022-08-01 05:30 |  | 2022-09-12 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, multicenter study assessing short (16 weeks) and long-term efficacy (up to 1 year), safety, and tolerability of 2 subcutaneous secukinumab dose regimens in adult patients with moderate to severe hidradenitis suppurativa (SUNSHINE) | CAIN457M2301 hidradenitis suppurativa | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Patil, Shweta Ramesh | Doshi, Pranav | Vasi, Munir | Ninan, Esther | Pascaline Regnault; Raghavender Goud Palusa | Raghavender Goud Palusa | Oguri, Praveen | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | Jan - 2022 : Rakesh Transitioned study to Prashant |  | DRM (DIAL) | Oguri, Praveen | Shrivastava, Nikhil | Completed | 26May2021 : Reassigned the study from Praveen Oguri to Nikhil. 26May-2021: No Activity, latest RF Version 9.0 05Nov2020: PPC10 implemented, received ALS on 04Nov2020, working on RF updates. 11Sep2020: RF Version 8.0 finalized and raised SNOW ticket. 17Feb2020: All forms and Finalized DTSs included in RF nothing is pending. 07Feb2020 : Reassigned the Rule file developer (Chandrakala to Praveen). 10Dec2019: RF needs an update to FA domain, ongoing discussion with SDTM and standards for the same. This will be updated by Praveen and then transitioned. Few versions and related checklist for the RF are missing in CREDI, awaiting confirmation from Praveen. FPFV in Feb2019 22Nov2019: Transition initiated | None | None | 2019-01-23 05:30 | Transition Study and Legacy process | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2019-01-28 | Completed | 2019-06-28 05:30 |  |  | 2019-01-28 05:30 | 2019-01-28 05:30 |  | 2019-08-21 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB;#Y1;#Y5;#ZK;#ZK03 | [11 empty] | NA | [5 empty] | 16 | 24 | 58 | 0 | 201 | 729 | 0 | 229 | 36 | 214 | 979 | 11 | 0 |  | Hidradenitis suppurativa | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-06-28 05:30 |  |  |  |  | Praveen kumar, Chakka Giri | None of the above
CAIN457M | CAIN457M2301E1 | C3004608 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-01-03 05:30 | 2020-01-27 05:30 | 2020-03-13 05:30 | DB Conduct | Interim DBL | 2023-04-27 05:30 | 2020-03-18 05:30 | 2019-08-29 05:30 | 2019-09-17 05:30 |  | Active | 2026-07-28 05:30 |  | 2026-09-08 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457M2301E1 Extension Study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Peswani, Amita | Doshi, Pranav | Vasi, Munir | Ninan, Esther | Ajit Kore | Ajit Kore | Lingampalli, Rohit | Katam, Veera Nagendra | In Progress | 2021-07-17 05:30 | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 03Jan2020 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 04-Mar-2021: FAAE1L DTS included in RF_V7.0 29-Jan-2021: RF_V6.0 finalized to include OPS001 form in LSH set-up 25-Sep-2020: QS5L and QS6L DTSs are included in RF_V5.0 and raised SNOW ticket for LSH update 02Sep2020 : As per 02Sep2020 missing forms DTS report QS5L, QS6L DTS pending 25-Aug-2020: Finalized RF V4.0 as per the PPC01 11-Aug-2020: Requested Lead DBP to provide the DTS status for QS5L, QS6L, CM1L. 03-Jul-2020: Followed up with Lead DBP to provide the updated DTS to include it in RF as QS5L, QS6L, CM1L flagged in missing report. 09-Jun-2020: Finalized RF V3.0 with LBL, QS1L, QS2L, QS3L, QS4L, QS7L and QS8L DTS tables. SNOW51 raised QS5L, QS6L abd CM1L needs to be updated 27May2020 : sent a followup email to DBD for pending DTS. 12May2020 : received LBL,QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, QS8L, CM1L DTS to be included in RF. Most were finlaized mid of march and not sent to RF developer. Provided comments on all DTS on 13May2020 and awaiting Updated DTS. 06-Feb-2020: RF finalized in CREDI and raised SNOW05 ticket for DRM files and LSH setup | None | None | 2020-02-06 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-02-18 | Completed | 2020-03-13 05:30 | FPFV postponed to 13 Mar 2020 |  | 2020-03-18 05:30 | 2020-03-18 05:30 |  | 2020-06-08 05:30 |  |  |  | 25 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 26 | 50 | 0 | 197 | 565 | 0 | 190 | 32 | 150 | 747 | 10 | 0 |  | Hidradenitis suppurativa | No | Global | Open: Reapproval | Yes | [10 empty] | 2020-03-06 05:30 | [5 empty] | None of the above | Yes
CAIN457M | CAIN457M2302 | C3004545 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-12-19 05:30 | 2019-02-25 05:30 | DB Conduct | Interim DBL | 2022-05-12 05:30 | 2019-02-25 05:30 | 2018-09-14 05:30 | 2018-08-10 05:30 |  | Active | 2022-08-01 05:30 |  | 2022-09-12 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, multicenter study assessing short (16 weeks) and long-term efficacy (up to 1 year), safety, and tolerability of 2 subcutaneous secukinumab dose regimens in adult patients with moderate to severe hidradenitis suppurativa (SUNRISE) | CAIN457M2302 hidradenitis suppurativa | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sinkar, Abhijeet | Doshi, Pranav | Vasi, Munir | Ninan, Esther | Pascaline Regnault; Raghavender Goud Palusa | Raghavender Goud Palusa | Oguri, Praveen | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 |  |  | DRM (DIAL) | Oguri, Praveen | Shrivastava, Nikhil | Completed | 26May2021 : Reassigned the study from Praveen Oguri to Nikhil. 26-May-2021: No activity, latest RF Version 9.0 05Nov2020: PPC10 implemented, received ALS on 04Nov2020, working on RF updates. 11Sep2020: RF Version 8.0 finalized and raised SNOW ticket. 07Feb2020 : Reassigned the Rule file developer (Chandrakala to Praveen). 10Dec2019: RF needs an update to FA domain, ongoing discussion with SDTM and standards for the same. This will be updated by Praveen and then transitioned. Few versions and related checklist for the RF are missing in CREDI, awaiting confirmation from Praveen. FPFV in Feb2019 22Nov2019: Transition initiated | None | None | 2019-02-05 05:30 | Transition Study and Legacy process | Praveen kumar, Chakka Giri | Garje, Sagar | Sandeep Kadam | Completed | 2019-02-08 | Completed | 2019-07-04 05:30 |  |  | 2019-02-08 05:30 | 2019-02-08 05:30 |  | 2019-08-23 05:30 |  |  | Inprogress - Reporting activity is in the month of Oct. Planned to complete in Q2 | 100 | RaveX - Inhouse | Yes | LB;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 16 | 24 | 58 | 0 | 201 | 729 | 0 | 225 | 36 | 214 | 979 | 11 | 0 |  | Hidradenitis suppurativa | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-07-04 05:30 |  |  |  | Interim-Analysis | R, Harini | None of the above | Yes
CAIN457M | CAIN457M2303 | C4002355 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  |  | DB On hold | [6 empty] | Stopped (with patients) |  |  | 2024-03-04 05:30 | 2024-03-04 05:30 |  | NA - study was canceled before set-up | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457M2303 H2H versus SOC (adalimumab) | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vasi, Munir | Vasi, Munir | Vasi, Munir | Ninan, Esther |  | Rebecca Gottschalk | [17 empty] | Sandeep Kadam | [36 empty] | 50 | [7 empty] | 800 | 8 |  |  | Hidradenitis suppurativa | No | Global | Terminated | Yes
CAIN457O1 | CAIN457O12301 | C4011310 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-11-15 05:30 |  | 2023-01-10 05:30 | DB Set-Up | DB Go-live | 2022-10-10 05:30 |  | 2022-04-08 05:30 |  |  | Planned | 2024-11-07 05:30 |  | 2024-12-19 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Randomized, double blind, placebo controlled study to assess efficacy, safety and tolerability of secukinumab 300 mg in adult patients with active overuse rotator cuff tendinopathy (RCT) refractory to conventional Standard of Care (SoC) | CAIN457O12301 Phase 3 in Rotator Cuff Tendonopathy | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Patil, Shweta Ramesh | Chaudhari, Vishal | Vasi, Munir | Ninan, Esther | Kamel Bouylout | Kamel Bouylout | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini |  |  | 28Apr2021: Initial golive planned as 15Nov2021. Currently CTT meeting going on. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Not Started | 07Sep2021: The DBD informed that the study has been cancelled. 07Sep2021: Requested the DBD to share the status of the study. 06Jul2021 : RF developer assigned with DB golive as 15Nov2021. | [6 empty] | Sandeep Kadam | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Tendon disorder; Tendonitis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457O1 | CAIN457O12302 | C4011323 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-12-15 05:30 |  | 2021-12-28 05:30 | Study Cancelled | Final DBL | 2024-11-14 05:30 |  | 2022-05-27 05:30 |  |  | Planned | 2023-10-18 05:30 |  | 2024-11-14 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Randomized, double blind, placebo controlled study to assess efficacy, safety and tolerability of secukinumab 300 mg in adult patients with active overuse rotator cuff tendinopathy (RCT) refractory to conventional Standard of Care (SoC) | CAIN457O12302 Phase 3 Rotator Cuff Tendonopathy | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chaudhari, Vishal | Chaudhari, Vishal | Vasi, Munir | Ninan, Esther | Roselyne Raffner | Kamel Bouylout | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini |  |  | 29Apr2021 : Not yet started Initial golive when study assigned 15Dec2021. | [12 empty] | Sandeep Kadam | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Tendon disorder; Tendonitis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457Z1 | CAIN457P12301 | C4003347 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-11-07 05:30 | 2019-11-26 05:30 | 2019-12-13 05:30 | DB Conduct | Interim DBL | 2022-03-31 05:30 | 2019-12-11 05:30 | 2019-09-11 05:30 | 2019-08-22 05:30 |  | Active | 2022-12-22 05:30 |  | 2023-02-16 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457P12301 AS IV Regimen | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vemula, Varun | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Kamel Bouylout | Kamel Bouylout | Ahuja, Mohit | Ahuja, Mohit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 07Nov2019 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 11-May-2021: ZW2L Included in RF 07-May-2021: Working on the ZW2L DTS and RF updates 25-Mar-2021: ZW2L DTS tables included and released for peer review. 27-Aug-2020: RF_V6.0 finalized 13-Aug-2020: All the DTS tables(ZWL, LBL, QS1L, QS2L, QS3L, QS4L,QS5L,QS6L,QS7L,QS8L,QS9L,QS10L,QS11L) are added to RF version 5.0 27Jul2020 : As per 20Jul report ZWL, LBL, QS1L, QS2L, QS3L, QS4L,QS5L,QS6L,QS7L,QS8L,QS9L,QS10L,QS11L DTS are missing.&nbsp; DBD shared the DTSs on 24th Jun and 3rd Jul. These were finalized earlier but had issue with Subway renderer. 16Jul2020 : LBL included in RF and sent for Review. 03-Jul-2020: Didn't receive DTS from Lead DBP. Requested DBP for the current status of DTS. Flagged in missing report 22-May-2020: AES002, MHS002 and MHS003 are&nbsp; added in RF_V3.0 09Mar2020: Awaiting response from DBD 02-Mar-2020: Updated Rule file to include ZWS004 and awaiting SDTM annotations for MHS002. 05Feb2020: AES002, MHS003 to be removed from the study as per upcoming PPC. Awaiting SDTM annotations for MHS002, ZWS004 Page to be updated via PPC 17Dec2019: Rulefile finalized. Excluded 4 forms. AES002, MHS002, MHS003: Pages excluded due to unavailability of SDTM annotations and will be added in next version ZWS004: ZWTEST doesn't have the Dictionary attached. CRF will be included after updating the field in upcoming PPC 06Dec19 : Rule file sent for peer review (Chandra) except 4 forms which needs SDTM programmer inputs. 29-Nov-2019: Shared documents required by the Rule File programmer to start with Rule File on 28th Nov. 27-Nov-2019: Sent a reminder for the study status and required documents 23-Oct-2019: Requested Study DBP for the status of the study and the required documents. | None | None | 2019-12-30 05:30 | SDTM annotations delayed | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2020-01-02 | Completed | 2020-01-17 05:30 | 2-Jan-2020:: DQP is not attached to ticket and the attached Timepoints file format is not correct. Discussed with Kranthi |  | 2020-01-17 05:30 | 2020-01-17 05:30 | Pre-requisites not met | 2020-01-17 05:30 |  |  |  |  | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 8 | 18 | 59 | 0 | 162 | 798 | 0 | 206 | 35 | 136 | 969 | 17 | 0 |  | Ankylosing spondylitis | No | Global | Open | Yes | [10 empty] | 2020-01-07 05:30 | [5 empty] | None of the above
CAIN457P1 | CAIN457P12302 | C4003348 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-10-25 05:30 | 2019-11-13 05:30 | 2020-01-31 05:30 | DB Conduct | Final DBL | 2022-06-28 05:30 | 2020-01-12 05:30 | 2019-05-30 05:30 | 2019-09-25 05:30 |  | Active | 2022-05-17 05:30 |  | 2022-06-28 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457P12302 PsA IV Regimen | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Akula, Kiran | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Mukul Prakash | Mukul Prakash | Ahuja, Mohit | Ahuja, Mohit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 25Oct2019 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 18-Jun-2021: RF_V10.0 finalized for PPC06 updates 11-May-2021: ZW2L DTS added in RF 07-May-2021: ZW2L DTS is now updated and requested peer reviewer to review and confirm if the RF update is fine. 25-Mar-2021: RF updated to include ZW2L DTS table and released for peer review. 22-Mar-2021: RF(8.0) has been finalized for ZWS002 form updated SDTM annotations. 01-Mar-2021: RF_V6.1 released for peer review 27Aug2020: RF_V6.0 finalized 13-Aug-2020: All the final DTS tables(ZWL, LBL, QS1L, QS2L, QS3L, QS4L,QS5L,QS6L,QS7L,QS8L,QS9L,QS10L,QS11L) are added in RF V3.0, 4.0 and 5.0 27Jul2020 : As per 20Jul report ZWL, LBL, QS1L, QS2L, QS3L, QS4L,QS5L,QS6L,QS7L,QS8L,QS9L DTS are missing.&nbsp; DBD shared the DTSs on 24th Jun and 3rd Jul. These were finalized earlier but had issue with Subway renderer. 07-Jul-2020(Kranthi): Included CMS001 form in latest RF. 22Jun2020 : CMS001 form flagged in missing forms/DTS report. RF developer to check. 24-Feb-2020: Updated RF to include ZWS004 form and requested SMT/LSH programmer to initiate the LSH update 17Feb2020 : Pending ZWS004 form included in RF and awaiting UAT SOD from Mohit. Followed up with him for the same. 05Feb2020: Rule file pending for ZWS004. 10Dec2019: Rulefile is final now and requested LSP to initiate the SMT. 27-Nov-2019: Rulefile V0.1 created. pending with peer review (Bhargav) | None | None | 2020-01-06 05:30 | SDTM annotations delayed | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-01-06 | Completed | 2020-01-27 05:30 |  | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-01-27 05:30 | 2020-01-27 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-04-27 05:30 |  |  | QS TPD PRod data not received yet. LB review pending | 70 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 18 | 62 | 0 | 214 | 746 | 0 | 197 | 35 | 153 | 934 | 15 | 0 |  | Psoriatic arthritis | No | Global | Open | Yes | [10 empty] | 2020-01-07 05:30 | [5 empty] | None of the above
CAIN457Q1 | CAIN457Q12301 | C4004126 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-02-15 05:30 | 2020-03-18 05:30 | 2020-08-03 05:30 | DB Conduct | Final DBL | 2026-03-19 05:30 | 2020-07-07 05:30 | 2019-11-01 05:30 | 2019-10-16 05:30 |  | Active | 2026-01-08 05:30 |  | 2026-03-19 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A two-year, phase III randomized, double-blind, parallel-group, placebo-controlled trial to evaluate the safety, efficacy, and tolerability of 300 mg s.c. secukinumab versus placebo, in combination with SoC therapy, in patients with active lupus nephritis | CAIN457Q12301 Lupus Nephritis | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Padigela, Hari | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Denis Bourrelly | Denis Louis Bourrelly | Bonam, Rajesh Babu | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Feb2020 |  | DRM | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 03MAR2021: LB1L DTS received and RF is finalized. SNOW 51 RITM2323754 has been created on 03MAR21. 11FEB2021: Rule file has been finalized and SNOW 51 RITM2257429 request has been created. Changes: Forms LBG001, LBG001_1,QS7L DTS and ZW1L DTS have been added 04Feb2021 : PPC 02 is completed by study DBD, Requested DBD to share the difference report and SOD. Awaiting response. 6Jan2021: SG: PPC2 is being initiated. PPC review to be done and consequently Rule file update. 9Dec2020: No planned PPC. Requested Rakesh to initiate a PPC to fix only this issue.. 05-Nov-2020 (SHRIVNI5): CRF LBG001_TR_5, LBG001_TR_6 and XIG002 included in the Rule File V4.0 and finalized in Subway. SNOW-51 raised and LSP notified regarding the same. Note: CRF forms LBG001 and LBG001_1 have DB design issue and DBD will correct in the next PPC. Post that RF will be updated to include these two forms. 5Nov2020: Rule file review is complete however we are facing some issue with Subway. Incident will be raised today(5Nov). LBG001_TR_5, LBG001_TR_6, XIG002 included in Rulefile. LBG001 and LBG001_1: Rakesh to update the pages in the next PPC. 28-Oct-2020 (SHRIVNI5): LBG001_TR_5, LBG001_TR_6 and XIG002 forms included in the Rule File and sent for peer review. Form LBG001 and LBG001_1 have DB design issue and DBD will correct in the next PPC. 20Oct2020 : new forms (LBG001 and LBG001_1) have database design issue and I have informed DBD to correct in the PPC at the earliest. Until then, these two forms could not be included in the Rule File. new forms (LBG001_TR_5, LBG001_TR_6 and XIG002) can be added in the Rule file but I have not yet received the SOD from DBD. I have been following up multiple time but has not yet received. 05Oct2020 : Nikhil will work on the pending Forms and DTS. 24Sep2020 : Added CMS002, APMHS001, DDG001, MHS001: Removed INDTYPE, LTDAT as these are inactivated in the trial. Added GNDRV, GNDRV1 and Final 8Sep2020: Rule file with DTS's (QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS8L) is fianlized and shared with LSP. PPC changes to be implemented in the next version. 04Sep2020 : As per 02Sep2020 missing forms DTS report we have "LBG001, LBG001_TR_5, LBG001_1, XIG002, LBG001_TR_6" & DTSs QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, QS8L misisng. PPC implemented and shared the SDTM annotations on 03Sep2020. Plan to incldue all in one version after consulting DBD. DTS are included and ready to final. 11AUG2020: Awaiting SDTM response on DSS001 page. Once confirmed will include all DTS's and pending pages. Planned for implementation by 21AUG2020. 27Jul2020 : As per 20thJul report apart from the forms listed (under 22nd June record) ZWL, QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, QS8L DTSs are also pending. 06Jul2020: Followup email sent to Lead DBD 22Jun2020 : As per missing forms/DTS report LBG001, LBG001_TR_5, LBG001_1, XIG002, LBG001_TR_6 forms are missing. Also DSS001, LBS001, LBS001_1 forms were in not includede in RF. Check with DBD and update RF accordingly. Requested Ashok to look into in Shashi's Absence. Sent an email to DBD as well. 18May2020: Rule file to be updated. Targeted date of completion 26May2020. 08Apr2020 : Awaiting response from DBD on pending forms. Following up on the same. 31Mar2020 : DBD has to have confirmation from CTT on the action for pending forms DSS001, LBS001, LBS001_1. Notified DBD and awaiting response since Golive 19-Mar-2020: Rule file finalized. SNOW05 raised 19-Mar-2020. 9-Mar-2020: Sent for Peer rev | None | None | 2020-03-19 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-06-04 | Completed | 2020-06-25 05:30 | FPFV is 07 Jul 2020 FPFV has been postponed to 3rd week of June 2020​ |  | 2020-06-30 05:30 | 2020-06-30 05:30 |  | 2020-07-22 05:30 |  |  | 1st DDPASS planned on 29th Sep 2020 | 0 | [14 empty] | NA | [5 empty] | 5 | 32 | 65 | 0 | 288 | 745 | 0 | 200 | 36 | 129 | 910 | 12 | 0 |  | Lupus nephritis | Yes | Global | Open | Yes | [10 empty] | 2020-06-16 05:30 | [5 empty] | None of the above
CAIN457Q1 | CAIN457Q12301E1 | C4012591 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-06-30 05:30 |  | 2022-08-04 05:30 | DB Set-Up | DB Go-live | 2022-06-30 05:30 |  | 2022-01-04 05:30 | 2021-12-16 05:30 |  | Planned | 2029-01-08 05:30 |  | 2029-02-16 05:30 |  |  | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A three-year, open-label extension study of subcutaneous secukinumab to evaluate the long-term efficacy, safety and tolerability in patients with active lupus nephritis | CAIN457Q12301E1 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sharma, Shweta Abhay | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Denis Bourrelly | Denis Louis Bourrelly | Gupta, Anshu | Gupta, Anshu | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 14 Dec 2021: RF programmer assigned. |  |  |  |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | [28 empty] | NA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 550 | 3 | 0 |  | Lupus nephritis | No | Global | Open | Yes
CAIN457R1 | CAIN457R12301 | C4004577 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-10-15 05:30 | 2021-07-30 05:30 | 2021-09-06 05:30 | DB Conduct | Final DBL | 2025-08-18 05:30 | 2021-10-06 05:30 | 2021-03-22 05:30 | 2021-03-29 05:30 | 2021-07-07 05:30 | Active | 2025-06-09 05:30 |  | 2025-08-18 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A Randomized, parallel group, double blind, placebo controlled multicenter phase III trial to investigate the efficacy and safety of secukinumab 300 mg administered subcutaneously verses placebo in combination with a glucocorticoid taper regimen, in patients with Giant Cell Arteritis (GCA) | CAIN457R12301 GCA s.c. | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Basani, Sravan | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Moreshwar Patwardhan | Moreshwar Ramchandra Patwardhan | Kabra, Pratik Govind | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | 14Jun2021: Multiple discussions for study specific pages in the CTT. Updates received from the study team on SRFs on 1st June. 11 new SRFs were added and 2 SRFs were updated. All these SRFs are approved and are under development. Go-live has been pushed to 28-July 2021. 28Apr2021 : CRF build in progress. After 2 weeks will plan for Dynamics 30-Mar-2021: As per latest updated timelines received from TDM, FPFV has been postponed to 10th August 2021 and Go-live is planned as 14th July 2021. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 08Mar2021 Initial golive was 15Oct2020 when RF developer was assigned on 01Jun2020. |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 12Aug2021: QS1L, QS2L, QS3L, QS4L, LB1L,LB2L, IRT and MO1L DTS added in RF, SNOW ticket raised (RITM2864800), LSP notified and checklist finalized in subway. 03Aug2021: The Rule File is finalized in subway with (SNOW05 Ticket number RITM2838067), LSP is notified, RF Checklist finalized in subway. 14-Jul-2021: Rule File is under development 18Jun2021: Received first set of SRF's for review on 15Jun2021. 19May2021: The SRFs are being developed 06May2021 : Followup with DBD 27Apr2021 : Study reassigned from Praveen to Pratheeksha. 26-Apr-2021: Study go-Live planned on 29-Jul-2021. RF development activity has not started. Sent email to Pratik to share study build status. 02-Dec-2020: I will send study status request email after 15-Dec-2020 01Jun2020 : RF developer (Praveen O) assigned with Initial golive planned as 15Oct2020. | None | None | 2021-08-03 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2021-08-16 | Completed | 2021-08-18 05:30 |  |  | 2021-08-18 05:30 | 2021-08-18 05:30 |  | 2021-08-23 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 2 | 35 | 61 | 0 | 431 | 895 | 0 | 257 | 45 | 320 | 1260 | 9 | 0 |  | Temporal arteritis | Yes | Global | Open: Reapproval | Yes | [10 empty] | 2021-08-16 05:30 | [5 empty] | None of the above | Yes
CAIN457R1 | CAIN457R12301E1 | C4009897 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-11 05:30 | Study Planned | DB Go-live | 2022-10-04 05:30 |  | 2022-05-03 05:30 |  |  | Planned | 2023-03-27 05:30 |  | 2023-05-08 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457R12301E1 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Edgoankar, Charuta | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther |  | Moreshwar Ramchandra Patwardhan | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 300 | 2 | 0 |  | Giant cell arteritis | No | Global | Open | Yes | [16 empty] | None of the above
CAIN457R1 | CAIN457R12302 | C4004578 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-03-31 05:30 |  | 2022-05-13 05:30 | Study Planned | DB Go-live | 2022-03-01 05:30 |  | 2022-01-18 05:30 |  |  | Planned | 2024-04-18 05:30 |  | 2024-06-27 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CAIN457R12302 GCA i.v. | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Akula, Kiran | Edgoankar, Charuta | Dhuri, Sejal | Ninan, Esther | Moreshwar Patwardhan | Moreshwar Ramchandra Patwardhan | Gupta, Anshu | Gupta, Anshu | [6 empty] | Saha, Saikat | Not Started | 24Jan2022: Asked for the Activity planner, DBD shared the activity planner and confirmed that study protocol is not yet finalized. No work has been started yet for the study. 14Dec2021: Study Assigned. |  |  |  |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Temporal arteritis | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457S1 | CAIN457S12201 | C4006166 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-03-13 05:30 | 2020-06-23 05:30 | 2020-09-07 05:30 | DB Conduct | Final DBL | 2022-06-16 05:30 | 2020-07-27 05:30 | 2019-11-21 05:30 | 2019-11-25 05:30 |  | Active | 2022-05-03 05:30 |  | 2022-06-16 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A proof of concept study to evaluate the efficacy, safety and tolerability of secukinumab 300 mg over 32 weeks in adult patients with biopsy-proven forms of lichen planus not adequately controlled with topical therapies - PRELUDE | CAIN457S12201 Lichen Planus PoC | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Mahesuni, Sakshi Rajesh | Srinivasan, Subramani | Dhuri, Sejal | Ninan, Esther | Isabelle Hampele | Isabelle Hampele | Sinha, Deepakshi | Prasanna Kumar, VTSSR | Not Started |  | Initial go live as 13Mar2020 when RF developer assigned on 12Jan2020. |  | DRM | Patnaik, Angella | Bairagi, Arpita | Completed | 11Aug2021 : Reassigned the study from Angella to Arpita. 27-MAY-2021: QS have 11 DTS (QS1L to QS11L) – of which QC load was successful for all except QS2L (it has duplicate record issue) OP1L >> QC data has duplicate record issue FAOT1L >> QC loading failed due to metadata issue. (FARESCD length in DTS is 200 while in .MD file its mentioned as 40) 5-MAY-2021: RF Version 4.0 finalized for QS10L DTS table name update. LSH set-up pending due to test transfers issues. 28-APR-2021: LSP confirmed LSH has been rebuild for PPC#2 impacted domains. iBOW and Missing forms tracker have been updated accordingly. 18-APR-2021: LC : DVG002 form in missing forms and DTS Report. 25-MAR-2021: RF V3.0 finalized for PPC2 updates. SNOW#51 raised for SMT and LSH updates. 25-MAR-2021: RF V3.0 for PPC2 updates released for Peer Review. 12FEB2021: RF V2.0 finalized for 13 DTS tables and OPS001 form. SNOW#51 raised for SMT and LSH updates. 4-FEB-2021: RF V2.0 is kept on hold for 13 DTS tables (QS1L,QS2L,QS3L,QS4L,QS5L,QS6L,QS7L,QS8L,QS9L,QS10L, QS11L, FAOT1L, OP1L) and CRF domain update for OPS001 until vendor sign-off. 3-DEC-2020: RF updated for 12 DTS table addition and released for Peer Review. 23-OCT-2020: SNOW#51 raised for LSH and SMT updates for DV, DS and ZJ domain due to PPC1. No RF updates required. 07-JUL-2020: No DB updates or DTS received post RF V1.0 finalization. 24JUN2020: RF Finalized, SNOW#05 raised for SMT And LSH set-up. 18JUN2020: Still did not receive ALS post UAT confirmation for sending the study for Peer Review. Study Go-live planned on 22-JUN-2020, as confirmed by TDM. 27APR2020: DB updates provided to DBD. Awaiting final ALS for verifying the RF and sending for the Peer Review. 26APR2020: All forms included in RF. Awaiting team's confirmation on OPS001 to be added to OP or DS domain as it has Treatment Assignment information. Also DBD to confirm the derivation of TPTTXT from the study specific variable in ZJ forms. 14APR0202: Received the ALS for RF development today post Screen UAT completion.. 06APR2020: Screen UAT not completed. Go-live pushed to 20APR2020. 03Apr2020 : Received all docs for RF development today. 17MAR2020: RF development initiated. 02MAR2020: SRFs, ASL and SDTM annotations received from DBD. 07Feb2020: No update from DBD | None | None | 2020-06-24 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-08-05 | Completed | 2020-08-06 05:30 | ​FPFV is 27 Jul 2020 | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-08-06 05:30 | 2020-08-06 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-09-01 05:30 |  |  |  | 25 | [14 empty] | NA | [5 empty] | 6 | 18 | 61 | 0 | 138 | 716 | 0 | 226 | 34 | 199 | 949 | 15 | 0 |  | Skin disorder | Yes | Global | Open | Yes | [10 empty] | 2020-08-05 05:30 | [5 empty] | None of the above
CAIN457S1 | CAIN457S12301 | C4005572 | Phase III | NCDS_2 |  |  |  | 2023-06-27 05:30 |  | Final DBL | 2027-04-09 05:30 |  | 2023-02-10 05:30 |  |  | Planned | 2027-01-29 05:30 |  | 2027-04-09 05:30 | [5 empty] | InHouse |  |  | CAIN457S12301 Lichen Planus | P7 Immunology Hepatology and Dermatology | [6 empty] | Isabelle Hampele | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Skin disorder; Skin disorder | Yes | Global | Open | Yes
CAIN457S1 | CAIN457S12301E1 | C4006171 | Phase III | NCDS_2 |  |  |  | 2023-12-08 05:30 |  | Final DBL | 2026-03-12 05:30 |  | 2023-08-01 05:30 |  |  | Planned | 2026-01-29 05:30 |  | 2026-03-12 05:30 | [5 empty] | InHouse |  |  | CAIN457S12301E1 Lichen Planus Extension Trial | P7 Immunology Hepatology and Dermatology | [6 empty] | Isabelle Hampele | [54 empty] | 40 | [7 empty] | 450 | 8 |  |  | Skin disorder | Yes | Global | Open | Yes
CAIN457S1 | CAIN457S12302 | C4005557 | Phase III | NCDS_2 |  |  |  | 2023-06-23 05:30 |  | Final DBL | 2025-11-20 05:30 |  | 2023-02-10 05:30 |  |  | Planned | 2025-09-11 05:30 |  | 2025-11-20 05:30 | [5 empty] | InHouse |  |  | CAIN457S12302 Lichen Planus | P7 Immunology Hepatology and Dermatology | [6 empty] | Isabelle Hampele | [54 empty] | 60 | [7 empty] | 900 | 8 |  |  | Skin disorder | Yes | Global | Open | Yes
CAIN457S1 | CAIN457S12302E1 | C4006171 | Phase III | NCDS_2 |  |  |  | 2023-12-08 05:30 |  | Final DBL | 2026-03-12 05:30 |  | 2023-08-01 05:30 |  |  | Planned | 2026-01-29 05:30 |  | 2026-03-12 05:30 | [5 empty] | InHouse |  |  | CAIN457S12302E1 Lichen Planus Extension Trial | P7 Immunology, Hepatology and Dermatology | [6 empty] | Isabelle Hampele | [54 empty] | 40 | [7 empty] | 450 | 8 |  |  | Skin disorder | Yes | Global
CAIN457X1 | CAIN457X12301 | C4011154 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-09-21 05:30 | 2021-11-19 05:30 | 2022-02-15 05:30 | DB Conduct | Final DBL | 2028-07-24 05:30 |  | 2021-08-27 05:30 | 2021-08-31 05:30 |  | Planned | 2028-06-12 05:30 |  | 2028-07-24 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized,parallel-group,double-blind,placebo-controlled,multicenter phase III study to investigate the efficacy and safety of secukinumab(Cosentyx) 300 mg administered subcutaneously in patient with active peripheral spondyloarthritis (pSpA). | CAIN457X12301 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sannidhi, Pavan Kumar | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Mukul Prakash | Mukul Prakash | Musku, Srikanth Reddy | SIRIPURAM, RAJSHEKHAR TIRUPATI | Completed | 2022-01-28 05:30 | 29Apr2021: Protocol is in Final Review, FPP Planned for MAY End. No work started. Initial DB golive 21sep21 when DBD is assigned. |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 1Feb2022- The DTSs QS1L,QS2L,QS3L,QS4L,QS5L,QS6L,QS7L,QS8L,QS9L,QS10L, ZW1L,ZW2L and ZW3L have been added in the RF and SNOW51 ticket (RITM3442388) raised and checklist finalized. 23Nov2021: The RF was finalized in Subway and SNOW05 ticket raised for Test (RITM3213370) and Prod (RITM3213411) set-up on 22-Nov2021 and notified the LSP. RF checklist finalized on 23Nov2021. 10Aug2021: As confirmed by the DBD, the study protocol is not finalized yet due to the CAT Review Comments. 06Jul2021 : RF developer assigned with DO golive as 12Nov2021. | None | None | 2021-11-22 05:30 |  | Kokane, Swapnil | Kokane, Swapnil | Sandeep Kadam | [28 empty] | NA | [5 empty] | 1 | 84 | 57 | 0 | 460 | 780 | 0 | 245 | 37 | 149 | 966 | 15 | 0 |  | Spondyloarthropathy | Yes | Global | Open | Yes | [16 empty] | None of the above
CAIN457O1 | CAIN457X2201 | C1200304 | Phase II | NCDS | CRO - EDC |  |  | 2017-12-18 05:30 | DB Locked |  |  | 2017-12-15 05:30 |  | 2017-09-15 05:30 |  | Completed | 2019-11-01 05:30 | 2019-10-17 05:30 | 2020-04-15 05:30 | 2020-04-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A randomized, double-blind, placebo-controlled, parallel group, Phase II, 24 week study investigating the efficacy, safety and tolerability of AIN457 in patients with active overuse tendinopathy refractory to oral NSAIDs/acetaminophen, physiotherapy or corticosteroid injections | CAIN457X2201 anti-IL-17 as disease-modifying thera | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Rafael Levitch Meran | Andrea Kovacs | [15 empty] | Girvasiya, Shaili |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Tendonitis | No | Global | Open | Yes | [16 empty] | None of the above
CAMG334A | CAMG334A2301 | C1001057 | Phase III | NCDS | OC RDC - Inhouse | 2016-11-09 05:30 | 2016-11-09 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-03-20 05:30 |  | 2016-06-20 05:30 |  | Completed | 2021-01-28 05:30 | 2021-01-28 05:30 | 2021-03-11 05:30 | 2021-03-16 05:30 | FALSE | DCN Priority | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 12-week double-blind, randomized, multicenter study comparing the efficacy and safety of once monthly subcutaneous 140 mg AMG334 against placebo in adult episodic migraine patients who have failed 2-4 prophylactic Treatments (LIBERTY) | CAMG334A2301 LIBERTY PhIIIb Tx Failure | P4 Neuroscience | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Ilse Devrieze | Ilse Devrieze | Meda, Sreelakshmi | Katam, Veera Nagendra | [13 empty] | Girvasiya, Shaili |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | -NA- | 2021-03-17 05:30 | 2021-03-18 05:30 |  |  | Pharma | Novartis | ICON | 2016-11-09 05:30 | 2017-07-26 05:30 |  | Mareedu, Vasu | NA | [7 empty] | 70 | 0 |  |  | 0 |  |  |  | 605 | 14 | 0 |  | Migraine | Yes | Global | Open | Yes | [16 empty] | None of the above
CAMG334A | CAMG334A2302 | C1001060 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-01-05 05:30 | 2018-02-12 05:30 | DB Locked | Final DBL Achieved |  | 2018-02-08 05:30 |  | 2017-06-08 05:30 |  | Completed | 2020-02-07 05:30 | 2020-01-13 05:30 | 2020-04-07 05:30 | 2020-03-13 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 12 week double-blind, randomized, multi-center study comparing the efficacy and safety of once monthly subcutaneous AMG334 against placebo in adult episodic migraine patients | CAMG334A2302 EMPOwER | P4 Neuroscience | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Matt Quinn | Matthew Quinn | Shrivastava, Nikhil | Sama, Ashok |  |  |  |  | Pre-DRM | Shrivastava, Nikhil | Maricherla, Vijayroshan | Completed | 01Apr2020: No pending activity 13Jan2020 (SHRIVNI5): Rule file transition completed. 15Apr2020 : Study Locked | Study Locked | Study Locked | 2018-03-29 05:30 | Legacy Process | Kommu, Ranjith Kumar |  | Amit Agavekar | Completed | 2018-04-04 | Not Applicable |  | ​Locked |  | 2018-04-04 05:30 | 2018-04-04 05:30 | Rule file error or delay |  |  |  | CE, CM , FACE and FACM , QS domains yet to receive production transfers | 100 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK;#ZK03 | [11 empty] | NA | [5 empty] | 9 | 8 | 41 | 0 | 60 | 415 | 0 | 137 | 33 | 128 | 576 | 9 | 0 |  | Migraine | Yes | Global | Open | Yes | [14 empty] | DBL | Mettugari, Sai Krishna | GDD annual target | Yes
CAMG334A | CAMG334A2304 | C4000575 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-07-16 05:30 | 2019-09-02 05:30 | DB Conduct | Final DBL | 2024-08-09 05:30 | 2019-08-26 05:30 | 2018-11-01 05:30 | 2018-12-05 05:30 |  | Active | 2024-06-28 05:30 |  | 2024-08-09 05:30 |  | FALSE | Mission Possible | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 12-week phase 3, randomized, double-blind, placebo-controlled study to evaluate the efficacy and safety of once monthly subcutaneous erenumab 70 mg in adult chronic migraine patients. | CAMG334A2304 China CM Study | P4 Neuroscience | Chaghasbanian, Harut | Bapat, Neha | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Ilse Devrieze | Ilse Devrieze | Ambati, Purnachander | Ahuja, Mohit |  |  |  |  | DRM | Ambati, Purnachander | Shrivastava, Nikhil | Completed | 16-Mar-2021: SNOW-51 raised to rebuild QS domain as per PPC#10. LSP is notified. No impact to Rule File. 19-Feb-2021: SNOW-51 ticket is raised for LSH and SMT setup WRT PPC#09. There is no impact to Rule File. LSP and SMT programmers have been notified. 12-Jan-2021: SNOW-51 was raised on 14th Oct2020 to rebuild DS and DV domains as per PPC#08. LSP and SMT developers were notified. No impact to Rule File. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 19-May-2020 (SHRIVNI5: Domain of the form 'FMHBN01' has been updated from FAMH to FA domain in RF V6.0 and finalized. Snow-51 ticket raised for LSH setup. 16-Apr-2020 (SHRIVNI5): RF V5.0 updated for CM and DS domain and sent for LSH rebuild. LSH rebuild is also completed. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 22Jan2020 (SHRIVNI5): RF version 3.0 updated wrt PPC 3. All the missing forms and DTS are included in this version. SNOW-51 raised for the same.22Jan2020 (SHRIVNI5): None as all the missing forms are included RF version 3.0 (QS1S595, QS1S595_1, SSG001_4, DSG002_1, SSG001_4 and ECG002_1). 22Jan2020 (SHRIVNI5): None as all the missing DTS are included RF version 3.0 (9 DTS (BDI, CE, FACE, CM, HIT6, LB, MIDAS, MPFID, eCSSRS)) 13Jan2020 (SHRIVNI5): Rule file updates are ongoing to include the missing forms and DTS. | None | None | 2019-08-06 05:30 | Transition Study and Legacy process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Amit Agavekar | Completed | 2019-09-17 | Completed | 2019-09-20 05:30 |  | Study Transitioned. | 2019-09-20 05:30 | 2019-09-20 05:30 | Study Transitioned. | 2019-11-27 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 14 | 69 | 49 | 0 | 253 | 660 | 0 | 163 | 33 | 130 | 823 | 11 | 0 |  | Chronic migraine | No | Global | Open | Yes | [10 empty] | 2019-09-18 05:30 | [5 empty] | GDD annual target
CAMG334A_MA | CAMG334A2401 | C1202203 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2019-04-12 05:30 | 2019-04-18 05:30 | 2019-05-22 05:30 | DB Conduct | Final DBL | 2022-12-15 05:30 | 2019-05-15 05:30 | 2018-11-09 05:30 | 2018-11-15 05:30 |  | Active | 2022-11-04 05:30 |  | 2022-12-15 05:30 |  | FALSE | GMA Phase 4 | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 12 months prospective, randomized, interventional, multicenter, active-controlled study comparing sustained benefit of two treatment paradigms (erenumab qm vs oral prophylactics) in adult episodic migraine patients. | CAMG334A2401 - APPRAISE | P4 Neuroscience | Vithala, Srinivas | Narisepalli, Satishkumar | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Haripriya Tumuluri | Haripriya Tumuluri | Munukutla, Valli | Iliyas, Mohamed | Completed | 2021-06-22 05:30 | 22Jun2021 : Transition from Valli Munukutla to Iliyas, Mohamed (Ext) Transition from Lakshmi Peri to Valli Munukutla Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 12Apr2019 PPC-06 is ongoing. Provided the IA and they are planning to add few changes to the tSDV RBM model. |  | DRM | Peri, Lakshmi | Shrivastava, Nikhil | Completed | 08-Nov-2021: SNOW-51 raised for LSH/SMT updates WRT PPC#07. No impact to Rule File. LSP has been notified. 16-Feb-2021: PPC#04 implemented but there is no impact on the Rule File. SNOW-51 ticket is raised for LSH and SMT updates. LSP and SMT programmer have been notified. 26Nov2020: Backup: Chandrakala Whats planned: PPC#04 is in draft state. PPC form is reviewed but no impact on RF. Need to raised SNOW-51 once PPC is implemented. 25-Nov-2020: RF V10.0 updated and finalized for mapping subject status forms from SV to SS domain. SNOW-51 raised and LSP is notified. 23-Oct-2020 (SHRIVNI5): RF V9.0 updated and finalized WRT PPC#03. SNOW-51 raised and LSP is notified. 28-Jul-2020 (SHRIVNI5): RF V8.0 was finalized to correct the table name. SNOW-51 raised and LSP notified. 21-Jul-2020 (SHRIVNI5): RF V7.0 with respect to PPC02 has been finalized and sent for LSH rebuild. 01Apr2020 : Reassigned RF from Roshan to Nikhil 01Apr2020: No pending activity 03MAR2020:LSH setup completed for finalized DTSs 14 Jan 20: Received DTS update today. Will start working along with the previous request made on 09 Jan 20. 09 Jan 20: Rule file to be updated to change domains for subject status page as per study team request. Need to seek confirmation from standards to do so | None | None | 2019-04-26 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Amit Agavekar | Completed | 2019-05-03 | Completed | 2019-05-23 05:30 |  | Pre-requisites not met | 2019-05-23 05:30 | 2019-05-23 05:30 | KPI met - incorrect source date entry (example FPFV) | 2019-08-15 05:30 |  |  |  | 50 | RaveX - Inhouse | Yes | -NA- | 2021-11-18 05:30 | 2021-11-22 05:30 | LSH refresh executes for 2.5 days due to huge data. | [8 empty] | NA | [5 empty] | 8 | 32 | 44 | 0 | 157 | 725 | 0 | 216 | 33 | 117 | 875 | 13 | 0 |  | Migraine | No | Global | Open | Yes | [10 empty] | 2019-05-21 05:30 |  |  |  | Interim-Analysis | Adi, Vishnupriya | None of the above | Yes
CAMG334A | CAMG334ACN01 | C4004363 | Phase I | Other | Other |  |  | 2020-05-12 05:30 | DB Locked |  |  | 2020-05-11 05:30 | 2019-05-03 05:30 | 2019-04-17 05:30 |  | Completed | 2020-08-31 05:30 | 2020-08-31 05:30 | 2021-03-12 05:30 | 2021-03-08 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | An open label, randomized, parallel group study to characterize pharmacokinetics, safety and tolerability of a single subcutaneous dose of erenumab in healthy Chinese subjects | CAMG334ACN01 China Ph1 HV PK | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Lin Liu | Lin Liu | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Chronic migraine | No | Global | Open | Yes | [16 empty] | None of the above
CAMG334C1 | CAMG334C12301 | C4005497 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2020-09-11 05:30 | DB On hold | Final DBL | 2024-12-03 05:30 |  | 2020-01-24 05:30 |  |  | Stopped (with patients) | 2024-10-21 05:30 |  | 2024-12-03 05:30 |  | FALSE | DCN Priority | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | CAMG334C12301 Persistent Post Traumatic_HA_Ph III | P4 Neuroscience | Ball, Michael | Dhuri, Sejal | Dhuri, Sejal | Purra, Shashikanth | Nair, Sreesha |  | Daniela Heintz | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Post-traumatic headache | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CAMN107A | CAMN107A1201 | C1001061 | Phase II | Other | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2023-11-02 05:30 | 2013-06-25 05:30 |  | 2013-04-09 05:30 |  | Active | 2023-10-04 05:30 |  | 2023-11-02 05:30 |  | FALSE | Roll-over study for patients completed previous AMN studies | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open label, multi-center nilotinib roll-over protocol for patients who have completed a previous Novartis-sponsored nilotinib study and are judged by the investigator to benefit from continued nilotinib treatment | AMN107A1201 “Short description of study” | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kikawa, Mirai | Kshetrapal, Abhishek | Okuzono, Seigou | Nair, Sreesha | ERI TANABE | ERI TANABE |  | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | Suneela.gogineni@ppdi.com | Earlier DBD: Jugnu Kumari | [14 empty] | Gastrointestinal stromal tumour | No | Global | Open | Yes | [16 empty] | None of the above
CAMN107A | CAMN107A1401 | C1001062 | Phase IV | Other | Paper |  |  | 2019-06-24 05:30 | DB Locked |  |  | 2009-03-19 05:30 | 2018-12-03 05:30 | 2009-01-21 05:30 |  | Completed | 2019-01-18 05:30 | 2014-09-30 05:30 | 2019-01-18 05:30 | 2019-01-18 05:30 | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Protocol of a special drug use observational study of Tasigna for chronic phase and accelerated phase chronic myelogenous leukemia in patients resistant to imatinib | CAMN107A1401 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | MATSUNAKA, REIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | ASAMI HORA | HARUKA NISHIOKA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CAMN107A | CAMN107A1402 | C3002855 | Phase IV | Other | CRO - EDC |  |  | 2018-08-31 05:30 | DB Locked |  |  | 2018-01-09 05:30 | 2019-04-29 05:30 | 2017-09-21 05:30 |  | Active | 2021-01-29 05:30 | 2019-12-08 05:30 | 2021-11-30 05:30 | 2021-11-30 05:30 | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Special drug use surveillance of Tasigna for pediatric CML | CAMN107A1402 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | MATSUNAKA, REIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | HARUKA NISHIOKA | HARUKA NISHIOKA | [17 empty] | Amit Agavekar | [28 empty] | IQVIA | [19 empty] | Chronic myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CAMN107A | CAMN107A2203 | C1001063 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-08-20 05:30 |  | 2013-03-04 05:30 |  | Completed | 2020-08-21 05:30 | 2020-08-28 05:30 | 2020-09-30 05:30 | 2020-09-22 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A multi-center, open label, non-controlled phase II study to evaluate efficacy and safety of oral nilotinib in pediatric patients with newly diagnosed Ph+ chronic myelogenous leukemia (CML) in chronic phase (CP) or with Ph+ CML in CP or accelerated phase (AP) resistant or intolerant to either imatinib or dasatinib | CAMN107A2203 PII-CML/Phpos/L2-M | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Khodake, Pruthviraj | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Elizabeth Demmisse; Vanessa McGuire | Vanessa McGuire |  | Gandla, Prashanth | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | Marco.Cramarossa@ppdi.com | Earlier DBD: Asha Rajanna | [14 empty] | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CAMN107E | CAMN107A2303 | C1001066 | Phase III | NOVDD | Paper |  |  |  | DB Locked |  |  | 2007-07-31 05:30 |  | 2007-02-07 05:30 |  | Completed | 2019-08-09 05:30 | 2019-08-21 05:30 | 2019-10-01 05:30 | 2019-10-01 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | FULL Outsourced | Hematology | A phase III multi-center, open-label, randomized study of imatinib versus nilotinib in adult patients with newly diagnosed Philadelphia chromosome positive (Ph+) chronic myelogenous leukemia in chronic phase (CML-CP) | CAMN107E2303 PIII-CML/Phpos/add-on L1-C (imatinib) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Deshpande Dubey, Aditi | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Descamps | Laurence Descamps |  | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | CMED | Oncology | BP21 |  | Florina Popescu (fpopescu@cmedresearch.com) | Earlier DBD: Shelly Antle /Asha | [14 empty] | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CAMN107E | CAMN107A2303E1 | C1001065 | Phase III | NOVDD | Paper |  |  |  | DB Locked |  |  | 2008-04-16 05:30 |  | 2007-02-07 05:30 |  | Completed | 2019-08-09 05:30 | 2018-11-21 05:30 | 2019-10-01 05:30 | 2019-10-01 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | FULL Outsourced | Hematology | A phase III multi-center, open-label, randomized study of imatinib versus nilotinib in adult patients with newly diagnosed Philadelphia chromosome positive (Ph+) chronic myelogenous leukemia in chronic phase (CML-CP) | CAMN107E2303E1PIII-CML/Phpos/add-on L1-C(imatinib) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Deshpande Dubey, Aditi | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Descamps | Laurence Descamps | [17 empty] | Amit Agavekar | [28 empty] | CMED | [19 empty] | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CAMN107A | CAMN107A2408 | C1001566 | Phase II | NCDS | OC RDC - Inhouse | 2012-12-12 05:30 | 2012-12-12 05:30 |  | DB Conduct | Final DBL | 2025-03-20 05:30 | 2012-12-20 05:30 |  | 2012-09-26 05:30 |  | Active | 2025-02-06 05:30 |  | 2025-03-20 05:30 |  | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase II, single arm, open label study of nilotinib discontinuation after achieving and maintaining MR4.5 | CAMN107A2408 (ENESTop) - CML/Phpos/L2-M | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Atiketi, Spandana | K R, Chandran | Chitre, Vrushali | Nair, Sreesha | Hassan El Gazri | Hassan El Gazri | Meda, Sreelakshmi | Gehlawat, Priya | [13 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2012-12-13 05:30 | Meda, Sreelakshmi | Mareedu, Vasu | NA | [7 empty] | 67 | 0 |  |  | 0 |  |  |  | 269 | 3 | 0 |  | Chronic myeloid leukaemia | No | Global | Open | Yes | [14 empty] | Interim-Analysis | Challa, Nandini | None of the above | Yes
CAMN107A | CAMN107A2409 | C1001567 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2023-06-07 05:30 | 2013-03-29 05:30 |  | 2018-09-05 05:30 |  | Active | 2023-04-28 05:30 |  | 2023-06-07 05:30 |  | FALSE | roll-over, phase IV study (extension program) | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open label, multi-center nilotinib roll-over protocol for patients who have completed a previous Novartissponsored nilotinib study and are judged by the investigator to benefit from continued nilotinib treatment | CAMN107A2409 (STEP) Rollover PIV-CML/Phpos/M | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | K R, Chandran | K R, Chandran | Chitre, Vrushali | Nair, Sreesha | Vanessa McGuire | Vanessa McGuire |  | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | Racquel Silva (Racquel.Silva@ppdi.com) | Earlier DBD: Chandrima /Asha | [14 empty] | Chronic myeloid leukaemia; Gastrointestinal stromal tumour | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CAMN107I | CAMN107I2201 | C1001067 | Phase II | NCDS | OC RDC - Inhouse | 2013-01-28 05:30 | 2013-01-28 05:30 |  | DB Conduct | Final DBL | 2025-04-02 05:30 | 2013-03-04 05:30 |  | 2012-11-02 05:30 |  | Active | 2025-02-20 05:30 |  | 2025-04-02 05:30 |  | FALSE | TBD | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A single-arm, multicenter, nilotinib treatment-free remission study in patients with BCR-ABL1 positive Chronic Myelogenous Leukemia in chronic phase who have achieved durable minimal residual disease (MRD) status on first line nilotinib treatment | CAMN107I2201 (ENESTfreedom) TFR PII-CML/CP/L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Arfeen, Mohammad | K R, Chandran | Chitre, Vrushali | Nair, Sreesha | Vanessa McGuire | Vanessa McGuire | Bakka, Sandeep | Gehlawat, Priya | [13 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [12 empty] | Planned for Q3 | 100 | OCRDC - Inhouse | Yes | -NA- | 2021-03-11 05:30 | 2021-03-12 05:30 |  |  | ONC | Novartis | ICON |  | 2013-01-22 05:30 |  |  | NA | [7 empty] | 72 | 0 |  |  | 0 |  |  |  | 226 | 5 | 0 |  | Chronic myeloid leukaemia | Yes | Global | Open | Yes | [14 empty] | Interim-Analysis | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CAPI015A | CAPI015A2201J | C1001069 | Phase III | NCDS | OC RDC - Inhouse | 2015-11-25 05:30 | 2015-11-25 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-11-30 05:30 |  | 2015-07-31 05:30 |  | Completed | 2020-04-16 05:30 | 2020-04-30 05:30 | 2020-06-26 05:30 | 2020-06-26 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, placebo-controlled, two-cohort parallel group study to evaluate the efficacy of CAD106 and CNP520 in participants at risk for the onset of clinical symptoms of Alzheimers disease | CAPI015A2201J | P4 Neuroscience | Chaghasbanian, Harut | Joshi, Shrinivas | Dhuri, Sejal | Purra, Shashikanth | Nair, Sreesha | Julie Forseth | Julie Forseth | Meda, Sreelakshmi | Meda, Sreelakshmi | [13 empty] | Manoharan, Vivek |  | Amit Agavekar | [13 empty] | 25 | OCRDC - Inhouse | Yes | ZK;#ZK02;#ZK03;#Y1;#Y5 |  |  |  |  | Pharma | ICON | ICON | 2015-11-25 05:30 | 2015-11-25 05:30 | Meda, Sreelakshmi | Rajhans, Khushbu Kumari | NA | [7 empty] | 292 | 0 |  |  | 0 |  |  |  | 554 | 31 | 0 |  | Alzheimer's disease | Yes | Global | Wind Down | Yes | [16 empty] | None of the above
CASB183A0 | CASB183X1101 | C1001573 | Phase I | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2014-08-13 05:30 | 2024-03-20 05:30 | 2014-03-24 05:30 |  | Completed | 2020-01-30 05:30 | 2014-08-13 05:30 | 2020-02-28 05:30 | 2019-09-19 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CASB183X1101 Japan PhI MM | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | Ohtaka, Masahiro | Prajapati, Vaishali | Sonmale, Pravin | Ninan, Esther | RIE NAGAHARI | MARI UMEZU | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Plasma cell myeloma | No | Global | Completed | Yes | [16 empty] | None of the above
CASB183A0 | CASB183X2104 | C1001574 | Phase I | GSK | [7 empty] | 2014-10-13 05:30 |  |  |  | Completed |  |  |  | 2017-05-16 05:30 | FALSE |  |  |  | Outsourced |  |  | CASB183X2104 Gastric Cancer Er2 L2c, | PA Oncology (Hematology not for MA projects) | [6 empty] | Maanasa Gowda | [67 empty] | Yes |  | Completed | [17 empty] | None of the above
CASB183A_MA | CASB183X2X01B | C1001805 | Phase IV | GSK | CRO - EDC |  |  | 2012-02-08 05:30 | DB Locked | Final DBL Achieved |  | 2012-02-08 05:30 |  | 2011-04-29 05:30 |  | Completed | 2018-06-18 05:30 | 2018-04-05 05:30 | 2018-06-07 05:30 | 2018-08-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | MM RR L2C, CASB183X2X01B | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vankayala, Vijay | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Caroline Bensasson | Caroline Bensasson | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 525 | 5 | 0 |  | Solid tumor | No | Global | Completed | Yes | [16 empty] | None of the above
CAUZ848A | CAUZ848A1101 | C4000085 | Phase I | NCDS_2 |  |  |  | 2020-01-06 05:30 |  |  |  |  | 2019-10-04 05:30 |  |  | Stopped (with patients) | 2020-03-09 05:30 |  | 2020-04-20 05:30 | 2020-04-20 05:30 |  |  |  |  | InHouse |  | AUZ848A_1101 PhI PK study (Caucasian and Japanese) | CAUZ848A1101 PhI PK study (Caucasian and Japanese) | P6 Global Health | [6 empty] | HIKOE SUZUKI | [66 empty] | Infection parasitic | No | Local | Terminated | Yes
CBAF312A0 | CBAF312A02101 | C4011786 | Phase I | Other |  |  |  | 2022-04-07 05:30 |  | Final DBL | 2022-09-19 05:30 |  | 2022-02-03 05:30 |  |  | Planned | 2022-07-05 05:30 |  | 2022-09-19 05:30 | [5 empty] | FULL Outsourced |  |  | CBAF312A02101 | P4 Neuroscience | [6 empty] | Nicola Collar | [66 empty] | Drug interaction | No | Global | Open | Yes
CBAF312A | CBAF312A1401 | C3001328 | Phase IV | Other | CRO - EDC |  |  | 2020-10-30 05:30 | DB Conduct | Final DBL | 2025-06-30 05:30 | 2020-10-28 05:30 | 2020-07-31 05:30 | 2020-08-05 05:30 |  | Active | 2025-02-28 05:30 |  | 2025-06-30 05:30 |  | FALSE | Japan PMS | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Observational study to confirm safety and efficacy for up to 12 months in SPMS patients treated with Mayzent (siponimod) | CBAF312A1401 JPN PMS | P4 Neuroscience | YAMADA, KAYO | KASAHARA, TETSUYA | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MINE KIMURA | MINE KIMURA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBAF312A | CBAF312A2005 | C4008398 | Not Applicable | Other | [8 empty] | 2021-08-16 05:30 | 2021-10-04 05:30 |  | Active | [8 empty] | Outsourced |  |  | CBAF312A2005 Database Study | P4 Neuroscience | [5 empty] | Shad Razac | Shad Razac | [66 empty] | Multiple sclerosis | No | Global | Open | Yes
CBAF312A0 | CBAF312A2124 | C1001073 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-10-28 05:30 |  | 2016-07-13 05:30 |  | Completed |  | 2017-03-13 05:30 |  | 2017-04-26 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA Shared | NIBR - NS | An open-label, three-period, single-sequence study to evaluate the effect of the CYP3A4 inhibitor itraconazole on siponimod (BAF312) single-dose pharmacokinetics, safety, and tolerability in healthy subjects with CYP2C912 and 13 genotypes | BAF312A DDI with CYP3A4 inhibitor CBAF312A2124 | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Andrea Feller | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [28 empty] | NA | [19 empty] | Drug interaction | No | Global | Completed | Yes | [16 empty] | None of the above
CBAF312A0 | CBAF312A2125 | C1001072 | Phase I | NCDS |  |  |  | 2018-04-10 05:30 | DB Locked |  |  | 2016-09-19 05:30 | 2017-10-31 05:30 | 2016-07-25 05:30 |  | Completed | 2019-07-30 05:30 | 2016-12-01 05:30 |  | 2017-01-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - NS | An open-label, multiple dose, two-period, single-sequence study in healthy subjects with the CYP2C911 (wild type) genotype to evaluate the effect of the CYP2C9/3A4 inducer rifampin on siponimod pharmacokinetics | BAF312 DDI with CYP2C9 inducer CBAF312A2125 | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Hetu Gadhia | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [28 empty] | NA | [19 empty] | Drug interaction | No | Global | Completed | Yes | [16 empty] | None of the above
CBAF312A | CBAF312A2201E1 | C1001071 | Phase II | NOVDD | [7 empty] | 2010-08-30 05:30 |  | 2009-09-04 05:30 |  | Completed |  | 2016-10-10 05:30 |  | 2017-02-28 05:30 | FALSE |  |  |  | Outsourced |  | An extension study to the CBAF312A2201 study to evaluate long-term safety, tolerability and efficacy of BAF312 given orally once daily in patients with relapsing-remitting multiple sclerosis. | PhII Ext Study_CBAF312A2201E1 | P4 Neuroscience | [6 empty] | Daniel Detka | [66 empty] | Multiple Sclerosis; Relapsing-remitting multiple sclerosis | No | Global | Completed | Yes | [16 empty] | None of the above
CBAF312A | CBAF312A2304 | C1001070 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Conduct | Final DBL | 2024-05-09 05:30 | 2012-12-20 05:30 |  | 2012-07-18 05:30 |  | Active | 2024-03-01 05:30 |  | 2024-05-09 05:30 |  | FALSE | Not applicable | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A multicenter, randomized, double-blind, parallel-group, placebo-controlled variable treatment duration study evaluating the efficacy and safety of Siponimod (BAF312) in patients with secondary progressive multiple sclerosis | CBAF312A2304 - EXPAND - PhIII SPMS | P4 Neuroscience | Chaghasbanian, Harut | Bindiganavale, Swetha | Almeida, Snehal | Purra, Shashikanth | Nair, Sreesha | Kamin Personett | Kamin Personett | [15 empty] | Tidke, Shyam |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [11 empty] | 0 |  |  |  | 720 | 7 | 0 |  | Multiple sclerosis | Yes | Global | Open | Yes | [16 empty] | None of the above
CBAF312A | CBAF312A2403 | C4007705 | Phase IV | Other |  |  |  | 2021-12-16 05:30 |  | Final DBL | 2033-05-26 05:30 | 2021-12-15 05:30 | 2021-06-30 05:30 | 2021-10-08 05:30 |  | Active | 2032-05-31 05:30 |  | 2033-05-26 05:30 |  | FALSE |  |  |  | Outsourced |  | Post-Authorization Safety Study for Assessment of Pregnancy Outcomes in Patients Treated with Mayzent (siponimod): An OTIS Observational Pregnancy Surveillance Study | BAF312A2403 Pregnancy Registry | P4 Neuroscience | [5 empty] | Shad Razac | Shad Razac | [66 empty] | Multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBAF312A | CBAF312A2404 | C4006973 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-05-26 05:30 | DB On hold | Final DBL | 2024-07-03 05:30 |  | 2022-05-03 05:30 | 2020-06-23 05:30 |  | Planned | 2027-01-25 05:30 |  | 2024-07-03 05:30 |  | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | CBAF312A2404 Pulmonary function study | P4 Neuroscience | Chaghasbanian, Harut | Kanani, Pooja | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha |  | Lucien Gazi | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 500 | 3 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBAF312D | CBAF312D2101 | C4009925 | Phase I | NCDS_2 |  |  |  | 2023-01-24 05:30 |  | Final DBL | 2023-09-07 05:30 |  | 2022-09-13 05:30 |  |  | Planned | 2023-08-10 05:30 |  | 2023-09-07 05:30 |  | FALSE |  |  |  | InHouse |  |  | CBAF312D2101 PK/BE study | P4 Neuroscience | [6 empty] | Denise Serra | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBAF312D | CBAF312D2301 | C4003102 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-08-20 05:30 | 2021-08-20 05:30 | 2021-10-25 05:30 | DB Conduct | DB Snapshot | 2022-04-11 05:30 | 2021-10-05 05:30 | 2021-01-28 05:30 | 2021-01-28 05:30 |  | Active | 2029-06-01 05:30 |  | 2029-07-23 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | CBAF312D2301 PhIII Pediatric for BAF&OMB programs | P4 Neuroscience | Chaghasbanian, Harut | Almeida, Snehal | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Pernilla Adolfsson | Ingrid Pernilla Adolfsson | Suzuki, Hiroko | Kala, Arpit | Completed | 2022-01-05 05:30 | 09JUN2021: Screens have been reviewed and provided comments as per latest ALS recieved. 03May2021 : Devashish supporting in Hiroko's Absence. Screen Peer review comments shared by DBD on 29th Apr2021. Updates from TDM received on Screens. Initial golive planned as 27Apr2021 when DBB assignment was requested by TDM. |  | DRM | Kuttoboina, Sujan Kumar | Saha, Saikat | Completed | 7Feb2022: Updated the EG domain for the EG1L and EG2L DTS for the blinding information. Finalized both the RF and Checklist 8.0 in SubWay. SNOW51 request RITM3457973 has been updated with the current document links. 4Feb2022: Updated the RF with the blinding information and the TDM confirmed to update the DQP with proper information in the later versions. Both the RF and Checklist version 7.0 are finalized in SubWay. SNOW51 request RITM3457973 has been raised and notified the LSP. 3Feb2022: LSP confirmed that the EG DTS needs to be separated as per the blinding information provided in the DQP. The information available in the DQP is insufficient, asked TDM to update it. 28Jan2022: Reviewed the DTS and provided the comment to the TDM. Updated the RF and waiting for DTS to be finalized. 20Jan2022: Received the LB1L DTS for review. 18Jan2022: Both the RF and Checklist finalized with the DTS details. SNOW51 request raised and notified the LSP. 17Jan2022: Both the EG DTS have been finalized as confirmed by the TDM. 17Dec2021: Received 2 EG DTS for review, provided the the review comments to the TDM. 16Dec2021: RF and Checklist have been finalized in the SubWay. SNOW 51 request has been raised and notified the LSP. 15Dec2021: Released the RF For peer review with the MO DTS in it. 30Nov2021: Received the MO DTS to review. Reviewed and provided the comments to the TDM. 29Nov2021 : RF and Checklist have been finalized in the SubWay, LSH ticket updated and notified the LSP. 24Nov2021 : RF is updated with the pending details for ZX domain. RF released for peer review. 16Nov2021 : RF and Checklist finalized in the DMS. SNOW 51 ticket raised and notified LSP. 11Nov2021 : Updated the RF with the DTS information and sent for peer review. All the DTS are finalized into the SubWay. 10Oct2021 : Reviewed the DTS and sent along with the comments. 8Oct2021 : Received 17 DTS to review. 13Sep2021 : RF has been updated with the blinded information and finalized in the SubWay. SNOW 51 RITM2970418 has been raised and notified the LSP. 23AUG2021: RF has been finalized and SNOW 05 RITM2902664 request has been created. 23AUG2021: Rule file will be finalized today 23AUG21. Saikat working on RF peer review comments. 18AUG2021: Go-live date is pushed to 20AUG21 10AUG2021: Go-Live date is extended to August 16th. 09Aug2021 : Reassigned from Sujan to Saikat. 26JUL21: RF completed by Saikat with ZX domain pending due to SDTM annotation is not available. Requested lead DBD to send the SDTM annotation. Peer review is ongoing for rest of the pages. 23JUL21: RF development is ongoing by Saikat. 09JUN21: Study specific pages have been reviewed as pet latest ALS and sent comments to Lead DBD 17-MAY-21: Study specific pages have been reviewed and provided comments to Lead DBD. Waiting for the updated ALS. 16-APR-21: Study specific pages review is ongoing, received all required documents from Lead DBD on 14APR21. 01-APR-21: Planned Go Live date is 11MAY2021 and SRF's under discussion. 01-Feb-2021 : RF developer Assigned | None | LB1L DTS to be added | 2021-08-23 05:30 |  | Ravichandran, Rajanandhini | Ravichandran, Rajanandhini | Amit Agavekar | Completed | 2021-09-07 | Completed | 2021-09-14 05:30 |  |  | 2021-09-16 05:30 | 2021-09-16 05:30 |  | 2021-09-16 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 23 | 104 | 0 | 324 | 1598 | 0 | 328 | 36 | 374 | 2008 | 16 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2021-09-13 05:30 | [5 empty] | None of the above
CBAF312C | CBAF312X2207 | C1200385 | Phase II | Other | CRO - EDC |  |  | 2017-12-22 05:30 | DB Locked |  |  | 2017-12-24 05:30 |  | 2017-07-20 05:30 |  | Completed | 2020-06-15 05:30 | 2020-05-13 05:30 | 2021-04-01 05:30 | 2021-04-01 05:30 | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - NS | A phase II, patient- and investigator-blinded, randomized, placebo-controlled study to evaluate efficacy, safety and tolerability of BAF312 (siponimod) in patients with stroke due to intracerebral hemorrhage (ICH) | CBAF312X2207 PIE POC in ICH | N6 Neuroscience - NIBR | Langlo, Francois | Palav, Mahesh | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Patricia Wagner | Diego Albrecht | [15 empty] | Tidke, Shyam |  | Rohit Varate | [13 empty] | 0 | FSOM - Outsourced |  | -NA- | 2021-04-29 05:30 | 2021-05-03 05:30 | [9 empty] | IQVIA | [19 empty] | Haemorrhagic stroke | Yes | Global | Terminated | Yes | [16 empty] | None of the above | Yes
CBASICHR | CBASICHR0009 | C1200298 | Not Applicable | NCDS | CRO - EDC |  |  | 2018-03-16 05:30 | DB Locked |  |  | 2018-03-22 05:30 |  | 2017-07-20 05:30 |  | Completed | 2019-12-02 05:30 | 2019-02-27 05:30 | 2019-05-10 05:30 | 2019-05-10 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CBASICHR0009 Multicenter longitudinal study of hum | R1 CBT - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Alok Pachori | [17 empty] | Rohit Varate | [28 empty] | CMED | [20 empty] | No | Global | Open | Yes | [16 empty] | None of the above
CBASICHR | CBASICHR0011 | C1200318 | Not Applicable | NCDS | CRO - EDC |  |  | 2017-12-18 05:30 | DB Locked |  |  | 2018-01-22 05:30 |  | 2017-05-03 05:30 |  | Active | 2019-06-28 05:30 | 2019-06-28 05:30 |  | 2020-02-25 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | Study to acquire bone marrow hematopoietic stem cells from adults with sickle cell disease and to assess their potential for gene editing, cell expansion and multi-lineage repopulation | CBASICHR0011 Bone marrow aspirate collection from | R1 CBT - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Sickle cell disease | No | Global | Open | Yes | [16 empty] | None of the above
CBASICHR | CBASICHR0027 | C4000187 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-01-31 05:30 | 2020-02-06 05:30 | 2020-05-28 05:30 | DB Conduct | Final DBL | 2023-07-21 05:30 | 2020-05-19 05:30 | 2019-09-20 05:30 | 2019-09-24 05:30 |  | Active | 2023-06-11 05:30 |  | 2023-07-21 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ID |  | CBASICHR0027 China NASH Registry | R1 CBT - NIBR | Langlo, Francois | Bhaumik, Romela | Bhatkar, Priyanka | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Jamie Zhou | Shiyang Zhou | Yadav, Santosh | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | 1. Initial golive as of 04Oct2019 was 31Jan2020 2. Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. |  | DRM | Shafiudeen, Rehana Banu | R, Pratheeksha K | Completed | 09Nov2021: PPC 03 was completed on 2Nov2021. The PPC did not have any impact on the Rule File. SNOW51 ticket (RITM3168755) has been raised for LSH rebuild on 9Nov2021 and the LSP is notified. 31-Aug-2021 : The study is transitioned to R, Pratheeksha 31-Aug-2021 : No Pending tasks. 14-Jul-2021 : Rule file 5.0 is finalized in CREDI. B11L DTS is included in RF 5.0 18-May-2021 : SNOW 51 request has been raised for PPC #2 implementation. No RF updates were required for this PPC request. 22Jan2021: Rule file updated to include DSG005, XIG002 and SNOW ticket raised on 22Jan2021. 20Jan2021 : LC : As per missing forms/DTS report dated 15Jan2021 DSG005, XIG002 are listed. 6JAN2021: SG: No pending tasks. 8Sep2020: Rule file finalized and shared with LSP. Included MOL DTS 02Sep2020 : As per 02Sep2020 missing forms DTS report "MOL" DTS pedning Shahsi to update status 21-Apr-2020 (SHRIVNI5): Lab DTS (LBL) included in RF (LB domain) and sent for LSH setup along with SMT files. 03Mar2020 : Released for SMT and LSH setup. 17Feb2020 : released for peer review (Nikhil) on 14thFeb. 12Feb2020 : All forms included and will be released for peer review by 13Feb2020 10Feb2020: 4 forms SDTM Annotations pending. Rest of the forms included in RF and will be sent for peer review today 30-Dec-2019: Awaiting ALS, SRF's and SDTM annotations. | None | None | 2020-03-03 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-03-06 | Completed | 2020-03-19 05:30 |  |  | 2020-03-20 05:30 | 2020-03-20 05:30 |  | 2020-08-24 05:30 |  |  |  | 11 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 4 | 6 | 37 | 0 | 75 | 279 | 0 | 79 | 5 | 157 | 441 | 4 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [10 empty] | 2020-03-19 05:30 | [5 empty] | None of the above
CBASICHR | CBASICHR0031 | C4000878 | Not Applicable | Other | CRO - EDC |  |  | 2020-08-14 05:30 | DB Conduct | Final DBL | 2025-12-29 05:30 | 2020-08-10 05:30 | 2019-08-26 05:30 | 2019-08-26 05:30 |  | Active | 2026-05-10 05:30 |  | 2025-12-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - OPHTHA | Basic human research study of novel glaucoma endpoints and identification of optimal patient populations for neuroprotection trials | CBASICHR0031 Non-Int glaucoma neuroprotection | R1 CBT - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Vanessa Vallejo | Vanessa Vallejo | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Glaucoma | No | Global | Open | Yes | [16 empty] | None of the above
CMHV370A1 | CBASICHR0036 | C4003622 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-11-15 05:30 | 2021-04-23 05:30 | 2021-05-28 05:30 | DB Conduct | Final DBL | 2022-07-06 05:30 | 2021-06-07 05:30 | 2020-01-01 05:30 | 2021-07-01 05:30 |  | Active | 2022-05-25 05:30 |  | 2022-07-06 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI |  | CBASICHR0036 SLE/SjS prescreening | N0 ATI - NIBR | Langlo, Francois | Kumari, Sangita | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Matthias Jecklin | Matthias Jecklin | Rachakonda, Hima Sailaja | Palande, Sujit |  |  | Initial golive when study assigned to Shashikant G was 15Nov2020. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Nov2020 |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 08-Dec-2021: RF v2.0 is finalized in CREDI for PPC#1 updates. 23Apr2021 : Rule file and checklist v1.0 archived in credi, SNOW 05 request has been created and notified to LSP. Sujan Supported the RF finalization with peer review by Rehana. 09Feb2021: Study was on hold now go live has moved to 22-Mar-2021 confirmed by DBD 07Dec2020: Study Go-Live confirmed by DBD as 15Feb2021. 03Dec2020: Study is postponed for now, DBD is following up with TDM for timelines. DBD had few discussions for Study specific Crfs with RF developer. | None | None | 2021-04-23 05:30 |  | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2021-04-30 | Completed | 2021-05-04 05:30 |  |  | 2021-05-04 05:30 | 2021-05-04 05:30 |  | 2021-05-06 05:30 |  |  | DDAPSS initiated on 05Oct2021, delayed because SDTM programmer had access issues. Domains are yet to be reviewed by SDTM programmer. | 0 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 2 | 1 | 23 | 0 | 24 | 284 | 0 | 87 | 7 | 54 | 345 | 1 | 0 |  | Mixed connective tissue disease; Sjogren's syndrome; Systemic lupus erythematosus | No | Global | Open | Yes | [10 empty] | 2021-05-03 05:30 | [5 empty] | None of the above
CBLZ945C1 | CBASICHR0053 | C4010948 | Not Applicable | Other |  |  |  | 2021-10-05 05:30 |  | Final DBL | 2023-02-06 05:30 | 2021-10-05 05:30 | 2020-12-16 05:30 | 2020-12-18 05:30 |  | Active | 2022-12-26 05:30 |  | 2023-02-06 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CBASICHR0053 digital devices for ALS assessment | P4 Neuroscience | [6 empty] | Vanessa Vallejo | [66 empty] | Amyotrophic lateral sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBASICHR | CBASICHR0054 | C4011012 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2021-01-11 05:30 | 2021-08-31 05:30 | 2021-08-16 05:30 | DB On hold | Final DBL | 2024-10-10 05:30 |  | 2020-12-16 05:30 | 2021-05-27 05:30 |  | Planned | 2024-08-30 05:30 |  | 2024-10-10 05:30 |  | FALSE | medium | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CBASICHR0054 Blood Sample Collection study | R1 CBT - NIBR | Navarro, Christelle | Niu, Mengmeng | Li, Shuai | Datta, Debtanu | Krishnan, Kripesh | Catherine Lavecchia | Catherine Lavecchia | Kumari, Jyoti | Shewane, Roshni | Not Started |  | Nov-2021 : Transition Checklist not shared to Roshni Shewane. Transition activity not started. 21Apr2021 : Update from Niu, Mengmeng on study status below. Here are some status update regarding the DB go-live timeline of the study as previously mentioned in Teams. Protocol final date: Team now is trying to draft and finalize protocol in interventional template. Hope it can be final by the end of April as previous planned; DB go live date: I estimated we need more than 8 weeks for DB go live after final protocol, maybe go live in July but the exact day depends on the protocol final date; CRF changes: Currently at least 6-8 CRFs should be changed or new added compared to previous NoPHIS protocol, and need to submit SRFs; I’m designing the CRFs and discussing with teams; eSAE: If eSAE used for this study or not is under discussion with SAE SME which is different from last version of protocol; FPFV and site initiate date: Not have accurate information now as the study is event driven based on parent studies and commercial participants; DB go-live planner: Will send it out for you and team review after protocol stable (nearly final), to avoid multiple change which relies on protocol final date; Study DBD assigned in Oct2020. Study initial plan was to golive by 11Jan2021. Then moved to 09 Feb021. Now it has moved to 09Apr021. |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 31Aug2021: The Rule File has been finalized in the CREDI, SNOW05 Ticket has been raised (RITM2930607), LSP notified, Rule File Checklist Version 1.0 finalized in CREDI. 10Aug2021: The RF is developed and is under review. 14-Jul-2021: There was delay from the SDTM end in providing the annotation. SRFs and ALS have now been reviewed by Kranthi. Waiting for updated ALS. 18JUN2021: Received SRFs for review. 11May2021: The DBD has confirmed that the protocol is in finalization stage. 26Apr2021: reassigned the study from Praveen to Pratheeksha. 21-Apr-2021: Sent follow up email to study DBD Jyoti to confirm on study setup status and to share CRF's for Review. 02-Dec-2020: Sent email to Jyoti to provide study setup status and to share study specific forms for review. 28Oct2020: RF developer assigned (Praveen Oguri) | None | None | 2021-08-31 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2021-09-13 | Completed | 2021-09-16 05:30 |  |  | 2021-09-17 05:30 | 2021-09-17 05:30 |  | 2021-09-17 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 3 | 39 | 0 | 45 | 409 | 0 | 138 | 36 | 130 | 575 | 0 | 0 |  | Eye disorder | No | Global | Wind Down | Yes | [10 empty] | 2021-09-16 05:30 | [5 empty] | None of the above
CBASICHR | CBASICHR0059 | C4014483 | Not Applicable |  |  |  |  | 2022-04-15 05:30 |  | Final DBL | 2023-03-27 05:30 |  | 2021-11-15 05:30 | 2021-11-16 05:30 |  | Planned | 2023-02-14 05:30 |  | 2023-03-27 05:30 | [5 empty] | InHouse |  |  | CBASICHR0059 Mobile Spirometry study | R1 CBT - NIBR | [5 empty] | Nils Burger | Nils Burger | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes
CBASICHR | CBASICHR0063 | C4016269 | Not Applicable | [6 empty] | Final DBL | 2023-03-21 05:30 |  | 2022-04-05 05:30 |  |  | Planned |  |  | 2023-03-21 05:30 | [5 empty] | InHouse |  |  | CBASICHR0063 endpoint eval in IRD and GA Patients | R1 CBT - NIBR | [6 empty] | Nils Burger | [66 empty] | Hereditary retinal dystrophy | No | Global | Open | Yes
CBCL201A1 | CBCL201X2102C | C3000352 | Phase I | NCDS | OC RDC - Inhouse |  |  | 2018-03-20 05:30 | DB Locked | Final DBL Achieved |  | 2015-11-16 05:30 | 2018-01-19 05:30 | 2015-06-16 05:30 |  | Completed | 2018-07-10 05:30 | 2018-07-10 05:30 | 2018-09-18 05:30 | 2018-08-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase Ib dose escalation study of BCL201 in combination with idelalisib in patients with Follicular Lymphoma (FL) and Mantle Cell Lymphoma (MCL) | CBCL201X2102C | N7 Oncology - NIBR | Langlo, Francois | Folami, Idowu | Fisher, Martin | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Maria Cintrao Dos Santos Rosa | Maria Joao Cintrao Dos Santos Rosa | Goyal, Rishu | [14 empty] | Kommu, Ranjith Kumar |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2015-11-04 05:30 | 2015-11-03 05:30 |  |  | ICON | [7 empty] | 227 | 0 |  |  | 0 |  |  |  | 745 | 3 | 0 |  | Follicular B-cell non-Hodgkin's lymphoma; Mantle cell lymphoma | No | Global | Terminated | Yes | [16 empty] | None of the above
CBGJ398E1 | CBGJ398X1101 | C1200250 | Phase I | NCDS | OC RDC - Inhouse |  | 2012-10-17 05:30 |  | DB Locked | Final DBL Achieved |  | 2012-10-19 05:30 |  | 2012-08-09 05:30 |  | Completed | 2019-02-07 05:30 | 2019-02-07 05:30 | 2019-05-10 05:30 | 2019-03-18 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I study of oral BGJ398 in Asian patients with advanced solid tumor having alterations of the FGF-R pathway | CBGJ398X1101 TCO Ph1 Advanced Solid Tumors Study | N7 Oncology - NIBR | Langlo, Francois | Kikawa, Mirai | Kansagara, Sachinkumar | Okuzono, Seigou | Gupta Bhaya, Soumya Kanti | TAKAYUKI HOSOYAMA | TAKAYUKI HOSOYAMA | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse |  | 2012-10-09 05:30 |  |  | NA | [7 empty] | 163 | 0 |  |  | 0 |  |  |  | 348 | 3 | 0 |  | Metastatic neoplasm | No | Global | Completed | Yes | [14 empty] | DBL | Polagoni, Bharghavi | None of the above | Yes
CBGJ398A | CBGJ398X2101 | C3000354 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2009-12-11 05:30 |  | 2009-08-19 05:30 |  | Completed | 2018-09-04 05:30 | 2018-10-08 05:30 | 2018-11-26 05:30 | 2018-11-14 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I, open-label, multi-center, dose escalation study of oral BGJ398, a pan FGF-R kinase inhibitor, in adult patients with advanced solid malignancies | CBGJ398X2101 | N7 Oncology - NIBR | Langlo, Francois | N, Ram Kumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Carolyn McGarry | Carolyn McGarry |  | Lingampalli, Rohit | [15 empty] | Rohit Varate | [28 empty] | Other | Oncology | BP21 | INC | Alexander Oswald (alexander.oswald@incresearch.com) | Earlier DBD: Brinda Shree | [14 empty] | Malignant tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CBGJ398D1 | CBGJ398X2102 | C3000355 | Phase I | NCDS | OC RDC - Inhouse |  |  | 2018-06-22 05:30 | DB Locked | Final DBL Achieved |  | 2013-10-02 05:30 | 2017-12-12 05:30 | 2013-05-03 05:30 |  | Completed | 2020-01-03 05:30 | 2016-07-27 05:30 | 2020-03-13 05:30 | 2017-02-17 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase Ib, open-label study of oral BGJ398 in combination with oral BYL719 in adult patients with select advanced solid tumors | CBGJ398X2102 | N7 Oncology - NIBR | Langlo, Francois | N, Ram Kumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Carolyn McGarry | Carolyn McGarry | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [12 empty] | NA | [19 empty] | Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CBGJ398C1 | CBGJ398X2201 | C1200235 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2013-12-09 05:30 |  | 2013-07-10 05:30 |  | Completed | 2019-01-21 05:30 | 2018-10-03 05:30 | 2019-04-03 05:30 | 2018-12-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase 2, multicenter, open-label study of BGJ398 in patients with recurrent resectable or unresectable Glioblastoma | CBGJ398X2201 TCO - PhII BGJ398 in Glioblastoma | N7 Oncology - NIBR | Langlo, Francois |  | Ward, Anthea | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Tatiana Levitan | Pilli, Bhaskar | [14 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse |  | 2013-11-15 05:30 |  |  | NA | [7 empty] | 147 | 0 |  |  | 0 |  |  |  | 531 | 3 | 0 |  | Glioblastoma multiforme | No | Global | Completed | Yes | [14 empty] | DBL | Kommu, Ranjith Kumar | None of the above
CBGJ398B1 | CBGJ398X2204 | C1200691 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-07-14 05:30 |  | 2014-02-26 05:30 |  | Completed | 2019-10-18 05:30 | 2019-04-05 05:30 |  | 2018-08-28 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase II multicenter, single arm study of oral BGJ398 in adult patients with advanced or metastatic cholangiocarcinoma with FGFR2 gene fusions or other FGFR genetic alterations who failed or are intolerant to platinum-based chemotherapy | CBGJ398X2204 | N7 Oncology - NIBR | Langlo, Francois | Parveen, Yasmin | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Mary Ising | [15 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Sold | Moved to Array Pharma |  | 2014-05-16 05:30 |  |  | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 7 | 0 |  | Cholangiocarcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CBKM120E | CBKM120E2101 | C1001074 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2011-12-30 05:30 |  | 2011-08-12 05:30 |  | Completed |  | 2017-05-17 05:30 |  | 2017-06-30 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | 'A Phase I, two-stage, multi-center, open-label dose escalation study of BKM120 in combination with adjuvant temozolomide and with concomitant radiation therapy and temozolomide in patients with newly diagnosed glioblastoma' | CBKM120E2101_PIb GBM/New/L1-C (radio/temozolomide) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Silvestre, Stephanie | Vavasseur, Celine | Vavasseur, Celine | Hiriyanna, Srinivas | Stephanie Savary | Stephanie Savary | [17 empty] | Sushant Sundar | [28 empty] | PPD | [19 empty] | Glioblastoma multiforme | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CBKM120E | CBKM120E2102 | C1001075 | Phase I | NCDS |  |  |  | 2018-06-08 05:30 |  |  |  | 2014-02-28 05:30 | 2018-01-19 05:30 | 2013-08-14 05:30 |  | Completed | 2019-12-20 05:30 | 2016-07-07 05:30 | 2020-02-28 05:30 | 2016-09-19 05:30 | FALSE |  |  |  | InHouse |  |  | PIb/II/Recur/L2-3C(Carboplatin or CCNU)BKM120E2102 | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Valerie Donnet | [15 empty] | Agavekar, Amit | [16 empty] | OCRDC - Inhouse | No | -NA- | [31 empty] | Glioblastoma multiforme | Yes | Global | Completed | [17 empty] | None of the above
CBKM120F | CBKM120F2302 | C1001076 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2012-08-07 05:30 |  | 2012-05-03 05:30 |  | Completed | 2019-04-24 05:30 | 2019-04-19 05:30 | 2019-05-08 05:30 | 2019-05-02 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | Solid Tumor | A phase III randomized, double blind placebo controlled study of BKM120 with fulvestrant, in postmenopausal women with hormone receptor-positive HER2-negative locally advanced or metastatic breast cancer which progressed on or after aromatase inhibitor treatment | CBKM120F2302 PIII_HER2_HR_PIK3CA L2_C(fulvestrant) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Laurence Bourdeau | Laurence Bourdeau | Ahuja, Mohit | [14 empty] | Sundar, N Sushant |  | Sushant Sundar | [12 empty] | Old OC Study. Will conduct DDPASS before any milestone |  | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse |  | 2012-07-18 05:30 |  |  | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 624 | 4 | 0 |  | Breast cancer | No | Global | Completed | Yes | [15 empty] | Chakravarthy, Meghna | None of the above | Yes
CBKM120F | CBKM120F2303 | C1001077 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2012-10-03 05:30 |  | 2012-06-09 05:30 |  | Completed |  | 2017-09-21 05:30 |  | 2017-10-30 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase III randomised, double blind, placebo-controlled study of BKM120 with fulvestrantin postmenopausal women with hormone receptor positive HER2-negative AI treated, locally advanced or metastatic breast cancer who progressed on or after mTOR inhibitor based treatment. | BKM120F2303_PIII_HER2_HR PIK3CA_L3_C (fulvestrant) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Stephanie Savary | Stephanie Savary | [15 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Breast cancer metastatic | No | Global | Terminated | Yes | [16 empty] | None of the above
CBKM120H | CBKM120H2201 | C1001078 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2013-10-01 05:30 |  | 2013-05-03 05:30 |  | Stopped (with patients) |  | 2017-03-30 05:30 |  | 2017-04-05 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Phase II multicenter randomized, double blind, placebo controlled study assessing the efficacy of buparlisib (BKM120) plus paclitaxel vs. placebo plus paclitaxel in patients with platinum pre-treated recurrent or metastatic head and neck squamous cell carcinoma. | Ph II-HNSCC R/M/L2-C (paclitaxel) BKM120H2201 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vavasseur, Celine | Vavasseur, Celine | Vavasseur, Celine | Hiriyanna, Srinivas | Laurence Bourdeau | Laurence Bourdeau | [15 empty] | Kommu, Ranjith Kumar |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Squamous cell carcinoma of head and neck | No | Global | Terminated | Yes | [16 empty] | None of the above
CBKM120F_MA | CBKM120Z2402 | C1001807 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-01-02 05:30 |  | 2012-07-11 05:30 |  | Completed |  | 2017-07-21 05:30 |  | 2017-09-18 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase II study of BKM120 in patients with relapse and refractory mantle cell lymphoma, follicular lymphoma and diffuse large B cell lymphoma. | CBKM120Z2402 GMA PII global-Lymphoma L123M | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Marchand, Matthieu | Vavasseur, Celine | Gracey Sugunan, Unni Krishnan | Hiriyanna, Srinivas |  | Carolyn Nienstedt | [17 empty] | Sushant Sundar | [28 empty] | PPD | [19 empty] | Non-Hodgkin's lymphoma |  | Global | Terminated | Yes | [16 empty] | None of the above
CBLZ945C1 | CBLZ945C12101 | C4005226 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-12-19 05:30 | Study Planned | DB Go-live | 2022-05-20 05:30 |  | 2022-08-05 05:30 |  |  | Planned | 2023-07-04 05:30 |  | 2023-08-01 05:30 |  | FALSE | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD |  | CBLZ945C12101 DDI study in HV with Riluzole | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Emilie Francoise Armelle Voltz | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Amyotrophic lateral sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CBLZ945C1 | CBLZ945C12102 | C4011789 | Phase I | Other |  |  |  | 2022-12-15 05:30 |  | Final DBL | 2023-10-10 05:30 |  | 2022-11-12 05:30 |  |  | Planned | 2023-08-29 05:30 |  | 2023-10-10 05:30 | [5 empty] | FULL Outsourced |  |  | CBLZ945C12102 relative BA study | P4 Neuroscience | [6 empty] | Wendy Weis | [66 empty] | Amyotrophic lateral sclerosis | No | Global | Open | Yes
CBLZ945C1 | CBLZ945C12201 | C4002509 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-10-14 05:30 | 2019-10-24 05:30 | 2019-12-20 05:30 | DB Conduct | Final DBL | 2022-11-23 05:30 | 2019-12-30 05:30 | 2019-05-08 05:30 | 2019-05-08 05:30 |  | Active | 2022-10-11 05:30 |  | 2022-11-23 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | An open-label, adaptive design study in patients with amyotrophic lateral sclerosis (ALS) to characterize safety, tolerability and brain microglia response, as measured by TSPO binding, following multiple doses of BLZ945 using positron emission tomography (PET) with the radioligand [11C]-PBR28 | CBLZ945C12201 Clinical PET study (PoM) | P4 Neuroscience | Langlo, Francois | Singh, Abhishek Kumar | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Ozana Fischer; Raphael Sommer | Ozana Fischer | Samuel, Giftson | Kala, Arpit |  |  | Nov-2021 : Giftson transitioned to Arpit Kala. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 14Oct2019 |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 08-Oct-2021: Raised SNOW-51 for LSH and SMT updates WRT PPC#09 and notified LSP. RF is not impacted for this PPC. 17-Sep-2021: Updated and finalized the Rule File V5.0 WRT to PPC#08. SNOW-51 raised and LSP is notified. 09-Apr-2021: As per PPC#06, SNOW-51 is raised for LSH and SMT updates. There is no impact to Rule File. LSP and SMT programmers have been notified. 26Nov2020: Backup: Angella Whats planned: Nothing planned as of now. 06Jul2020: Rule File V4.0 is the latest one. RF will be transitioned from Ashok to Nikhil 17Mar2020: RF v4.0 latest in SUBWAY, SNOW51 ticket : RITM1219414 for SMT. Mar2020: RF transitioned to Ashok from Chandrakala 17Feb2020: The LBL dts is included in RF v3.0 already confirmed by RF developer(Chandrakala). 13Feb2020 : As per missing report LBL DTS not included. Need confirmation from Lead and RF developer. Have sent followup email. 23Dec2019: RFv2.0 updated with pending domains and sent for review. 21Nov2019: RF v1.0 final Pending forms/DTS: LB, QS domains excluded . No DTS finalized yet. Sent for SMT creation. | None | None | 2019-11-28 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2019-12-01 | Completed | 2019-12-05 05:30 | LSH Setup completed. |  | 2019-12-05 05:30 | 2019-12-05 05:30 |  | 2020-05-05 05:30 |  |  | PR, FAPR - These domains received via 3rd party yet to be reviewed. LB and EG pending issues need to be resolved. [RAMACHA1, 3rd Feb, 2021] 4 domains failed DDPASS. Follow up from TDM and SDTM ongoing. 15 domains out of 19 passed review. DDPASS Success Rate : 79% | 79 | RaveX - Inhouse | Yes | -NA- |  |  | IA Lock : LQ'er - Nivetha Lakshmi Thirugnanasambandham LSH Lock Request Date : Nov 1, 2021 LSH Lock Date : Nov 2, 2021 | [8 empty] | NA | [5 empty] | 10 | 17 | 68 | 0 | 297 | 569 | 0 | 191 | 36 | 171 | 776 | 4 | 0 |  | Amyotrophic lateral sclerosis | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-12-03 05:30 |  |  |  |  | Adi, Vishnupriya | None of the above | Yes
CBLZ945C1 | CBLZ945C12202 | C4013828 | Phase II |  |  |  |  | 2024-05-01 05:30 |  | Final DBL | 2028-11-14 05:30 |  | 2023-10-23 05:30 |  |  | Planned | 2028-10-03 05:30 |  | 2028-11-14 05:30 | [5 empty] | InHouse |  |  | CBLZ945C12202 Ph2/3 in ALS | P4 Neuroscience | [6 empty] | Daniela Heintz | [66 empty] | Amyotrophic lateral sclerosis | No | Global | Open | Yes
CBLZ945A1 | CBLZ945X2101 | C3000356 | Phase II | NCDS | OC RDC - Inhouse |  | 2016-09-02 05:30 | 2018-06-08 05:30 | DB Conduct | Final DBL | 2022-10-03 05:30 | 2016-10-21 05:30 | 2018-01-19 05:30 | 2016-06-08 05:30 |  | Active | 2017-05-11 05:30 |  | 2022-10-03 05:30 |  | FALSE | None | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I/II, open-label, multi-center study of the safety and efficacy of BLZ945 as single agent and in combination with PDR001 in adults patients with advanced solid tumors | CBLZ945X2101 FIH in all solid tumors | N7 Oncology - NIBR | Langlo, Francois | Talisetty, Kedarinath | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Christian Miess | Christian Miess | Ahuja, Mohit | Iliyas, Mohamed | [13 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | ICON | 2016-09-02 05:30 | 2016-09-02 05:30 | Shewane, Roshni | Gehlawat, Priya | NA | [7 empty] | 195 | 0 |  |  | 0 |  |  |  | 782 | 7 | 0 |  | Breast cancer; Glioblastoma multiforme; Pancreatic cancer; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CBPD952A | CBPD952AJP03 | C1001576 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2005-04-01 05:30 | 2019-04-29 05:30 | 2003-10-09 05:30 |  | Completed | 2023-04-10 05:30 | 2008-09-25 05:30 | 2023-04-10 05:30 | 2013-10-10 05:30 | FALSE |  |  |  | Outsourced |  |  | CBPD952AJP03 Japan PMS | P5 Ophthalmology | [5 empty] | RYUHEI WADA | YOSHIHISA SATOU | [66 empty] | Macular degeneration | No | Global | Terminated | Yes | [16 empty] | None of the above
CBYL719A0 | CBYL719A2105 | C1001080 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-12-21 05:30 |  | 2015-08-25 05:30 |  | Completed |  | 2017-10-01 05:30 | 2017-11-09 05:30 | 2017-11-08 05:30 | FALSE | Priority not assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase 1, open-label, single-dose, multicenter, parallel group study to assess the pharmacokinetics and safety of alpelisib (BYL719) in subjects with hepatic impairment compared to matched healthy control subjects | CBYL719A2105 Ph I PK/Hepatic Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Silvestre, Stephanie | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas | Franck Letellier | Stephanie Savary | [17 empty] | Sushant Sundar | [28 empty] | PPD | [19 empty] | Hepatic impairment | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719A0 | CBYL719A2109 | C3003606 | Phase I | NCDS | CRO - EDC |  | 2018-04-03 05:30 | 2018-05-28 05:30 | DB Locked |  |  | 2018-05-30 05:30 | 2017-10-26 05:30 | 2017-11-21 05:30 |  | Completed | 2019-03-11 05:30 | 2019-03-13 05:30 | 2019-04-10 05:30 | 2019-04-10 05:30 | FALSE | Priority not assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A single-center, open-label, randomized, four period, four sequence crossover study to investigate the bioequivalence of alpelisib optimized final market image formulation and the final market image (FMI) tablet formulation in healthy volunteers in the fasted and fed state | CBYL719A2109 OCD PhI CP HV BE | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Maradani, Satish | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Valerie Donnet | Goyal, Rishu | [14 empty] | Sahu, Ahallad |  | Sushant Sundar | [14 empty] | FSOM - Outsourced | [6 empty] | ONC | Other | Outsourced |  |  | Kanchi, Pavan kumar | Mareedu, Vasu | PRA Health | [19 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719A | CBYL719A2110 | C4007033 | Phase I | Other | CRO - EDC |  |  | 2020-10-15 05:30 | DB Locked |  |  | 2020-10-19 05:30 | 2020-05-13 05:30 | 2020-05-19 05:30 |  | Completed | 2020-11-30 05:30 | 2020-12-30 05:30 | 2021-03-31 05:30 | 2021-04-15 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | FULL Outsourced | Solid Tumor | A phase I, open-label, single sequence, two period study to investigate the effect of multiple doses of rifampicin, a potent CYP3A4 inducer, on the single and repeated dose pharmacokinetics of alpelisib in healthy subjects | CBYL719A2110 Ph 1 HV DDI CYP3A4 inducer | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Marchand, Matthieu | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas | Pierre-Alexis Ruffie | Pierre-Alexis Fabien Ruffi�� | [17 empty] | Sushant Sundar | [28 empty] | Celerion | [7 empty] | 70 | 0 |  |  | 0 |  |  |  | 550 | 1 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CBYL719A | CBYL719A2111 | C4007034 | Phase I | Other | CRO - EDC |  |  | 2020-12-28 05:30 | DB Conduct |  |  | 2020-12-21 05:30 | 2020-05-13 05:30 | 2020-05-15 05:30 |  | Active | 2021-05-27 05:30 | 2021-03-28 05:30 | 2021-08-31 05:30 | 2021-08-31 05:30 | FALSE | DDI trials | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | FULL Outsourced | Solid Tumor | A phase 1, open-label, fixed-sequence drug-drug interaction study to investigate the effect of alpelisib on the pharmacokinetics of midazolam (a sensitive CYP3A substrate), bupropion (a sensitive CYP2B6 substrate), repaglinide (a sensitive CYP2C8 substrate), warfarin (a sensitive CYP2C9 substrate) and omeprazole (a sensitive CYP2C19 substrate) in healthy subjects. | CBYL719A2111 Ph 1 HV DDI CYP Cocktail | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Marchand, Matthieu | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas | Sandrine Bach-Berkowicz | Sandrine Bach-Berkowicz | [17 empty] | Sushant Sundar | [28 empty] | Celerion | [7 empty] | 70 | 0 |  |  | 0 |  |  |  | 550 | 2 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CBYL719A | CBYL719A2201 | C1001079 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-03-11 05:30 |  | 2013-07-26 05:30 |  | Completed |  | 2017-07-08 05:30 |  | 2017-07-17 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II randomized, double-blind placebo controlled, study of letrozole with or without BYL719 or buparlisib, for the neoadjuvant treatment of postmenopausal women with hormone receptor-positive HER2-negative breast cancer | CBYL719A2201 Ph II neoadj HR+ BC/C (letrozole) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Franck Letellier | Franck Letellier | [15 empty] | Tidke, Shyam |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | [12 empty] | NA | [19 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719C | CBYL719C1201 | C4005954 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-08-26 05:30 | 2020-09-15 05:30 | 2020-11-30 05:30 | DB Conduct | DB Snapshot | 2022-08-31 05:30 | 2020-11-20 05:30 | 2020-06-08 05:30 | 2020-07-02 05:30 |  | Active | 2027-02-02 05:30 |  | 2027-04-12 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II open-label, 2-Part, multi-center study of BYL719 (alpelisib) in combination with fulvestrant for men and postmenopausal women with PIK3CA mutation hormone receptor (HR) positive, HER2-negative, advanced breast cancer which progressed on or after aromatase inhibitor treatment in Japan | CBYL719C1201 EPIK-B6 Japan, HR+, HER2- ABC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Ohmori, Hiroko | Vithanala, Kiran Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | MASAE KAI | MASAE KAI | Dadapogu, Jesica Priyadarshini | Rapaka, Sindhuja | Not Started |  | Initial go live as 26Aug2020 when RF developer assigned on 01Jun2020. |  | DRM | Shrivastava, Nikhil | Saha, Saikat | Completed | 3Nov2021 : Got peer review comments and RF is ready to be finalized. RF and Checklist is finalized in the CREDI. LSH ticket has been raised and notified LSP. 29Oct2021 : Received the updated ALS, SOD and Difference report to create the RF. RF created and released for Peer Review 23Sep2021 : Reviewed the PPC form and sent back the comments regarding the RF impact. 22Sep2021 : Received the PPC form to review. 13-Aug-2021 (Nikhil): Transition activities completed. Informed the Study Team. 11Aug2021 : Reassigned the study from Nikhil to Saikat. 21-Jul-2021: RF V3.0 updated and finalized WRT the issue mentioned by LSP on the typo error of FATST value (PMISCAN) in FAMH domain. SNOW-51 raised and LSP notified. 26May2021 : Reassigned the study from Praveen Oguri to Nikhil. 26-May-2021: No Activity, latest RF version 2.0 15Feb2021: LBL, QS1L, RS1L, TR1L, TU1L DTS's were added in RF Version 2.0. (RITM2266413) 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 LBL, QS1L, RS1L, TR1L, TU1L DTSs listed. Please check 05Nov2020: No Activity. 15Sep2020 : RF final and Snow05 raised for LSH setup 11Sep2020: RF Development is completed and peer review in progress. 11Aug2020 : SS forms reviewed and provided feedback. Screen UAT not completed yet. | None | None | 2020-09-15 05:30 |  | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2020-10-13 | Completed | 2020-10-13 05:30 |  |  | 2020-10-13 05:30 | 2020-10-13 05:30 |  | 2020-12-24 05:30 |  |  |  |  | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 4 | 41 | 86 | 0 | 305 | 1085 | 0 | 294 | 44 | 248 | 1377 | 6 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [10 empty] | 2020-09-30 05:30 | [5 empty] | None of the above
CBYL719C | CBYL719C2201 | C4005639 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-11-15 05:30 | 2020-12-14 05:30 | 2021-02-05 05:30 | DB Conduct | Interim DBL | 2022-05-15 05:30 | 2021-01-20 05:30 | 2019-12-17 05:30 | 2019-12-19 05:30 |  | Active | 2025-10-29 05:30 |  | 2026-01-08 05:30 |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Phase II randomized, controlled study: fulvestrant Â± alpelisib as 2L treatment in HR+/HER2-negative advanced breast cancer recurrent/progressed on/after prior AI (CDK4/6i inclusive) treatment in Chinese patients | CBYL719C2201 EPIK-B7 China 2L in HR+/HER2- aBC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sahu, Kalyani | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Yuanxi Shi | Yuanxi Shi | Suzuki, Hiroko | TEMBHARE, HITESH |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Nov2020 |  | DRM | Shafiudeen, Rehana Banu | R, Pratheeksha K | Completed | 31-Aug-2021 : The study is transitioned to R, Pratheeksha. 31-Aug-2021 : No Pending tasks. 27Jul2021 : RF V 5.0 is finalized in CREDI, SNOW 51 ticket is raised and the LSP is notified. B11L DTS was included in this version. 14-Jun-2021 : RF V 4.0 is finalized in CREDI, SNOW 51 ticket is raised and the LSP is notified. 9-Jun-2021 : The Rule file setup for the YRL and YDL DTS is updated as per the latest Communication and set for peer review. 13-Jan-2021 : The Rule file setup for the Yx DTS is updated as per the latest Communication and the RF V 3.0 is finalized in CREDI 14-Dec-2020 : RF is finalized in CREDI 8-Dec-2020 : RF is ready for finalization. Once the study is live RF can be finalized. 3-Dec-2020 : Have completed the review. 11Nov2020 : working on the peer review comments. 27Oct2020 : Study went on hold, awaiting for further information on resuming the study, yet, have sent the study for RF peer review, to keep it complete from our side. 13Oct2020 : SDTM programmer is not yet assigned for this study. Informed TDM about that. 9Oct2020 : Completed the SRF and ALS review and shared the comment to DBP. 29Sep2020 : Started with the ALS review 24Sep2020 : Received the ALS, SRFs for the SS forms. Started with the approved SRFs review. 14sep2020 : followed-up with DBD on study status and SS forms | None | None | 2020-12-14 05:30 |  | Sundar, N Sushant |  | Sushant Sundar | Completed | 2021-02-18 | Completed | 2021-02-18 05:30 |  | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-02-18 05:30 | 2021-02-18 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-02-23 05:30 |  |  | DDPASS is ongoing | 30 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 3 | 86 | 96 | 0 | 1043 | 1246 | 0 | 365 | 49 | 285 | 1580 | 2 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [10 empty] | 2021-02-10 05:30 | [5 empty] | None of the above
CBYL719M1 | CBYL719C2202 | C4009935 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-08-15 05:30 | 2021-11-02 05:30 | 2022-02-28 05:30 | DB Conduct | Final DBL | 2024-08-08 05:30 |  | 2021-05-17 05:30 | 2021-04-22 05:30 | 2021-09-23 05:30 | Planned | 2024-06-21 05:30 |  | 2024-08-08 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase II, multicenter, randomized, open-label, active-controlled study to assess the safety and efficacy of dapagliflozin + metformin XR versus metformin during treatment with alpelisib (BYL719) in combination with fulvestrant in participants with HR+, HER2-, advanced Breast Cancer with a PIK3CA mutation following progression on/after endocrine-based therapy | CBYL719C2202 EPIK-B4 (HR+/HER2-aBC Hyperglycaemia) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kambothu, Sai Sumanth | Jayavaram, Pavan | Regula, Ramakrishna | Hiriyanna, Srinivas | Pierre-Alexis Ruffie | Pierre-Alexis Fabien Ruffi�� | Kabra, Pratik Govind | SIRIPURAM, RAJSHEKHAR TIRUPATI | Completed | 2022-01-27 05:30 | As per email received from PDM on 20-Oct-2021, Go-Live has been moved to 01-Nov-2021. As per email received from TDM on 11-Aug-2021, latest proposed date for FPFV 29Nov201 based on yesterday’s CTT Meeting. Considering latest FPFV date (29Nov2021) Go-live would be 3rd week of Oct 2021. As per email received from TDM on 09-July-2021, Protocol amendment has been planned for this study. The amendment will be implemented before FPFV which means that the stat-up timelines will shift and will be shared with the team upon final confirmation. 28Apr2021 : In the activity planner shared by TDM, the FPFV date is 24-Aug-2021 and Go-live date is 27-Jul-2021. However, as per iBOW, the FPFV planned date was 13-Sep-2021 and Go-live date was 31-Aug-2021. Sent email to TDM for clarification. Initial DB golive planned as 15Aug2021 when DBD was assigned. |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 16Nov2021: The LSH PROD set-up request was raised on 16Nov2021 with RITM3192710 as SNOW05 Ticket number. 9Nov2021: The RF is finalized on 02Nov2021. SNOW05 ticket raised for LSH Test Set-up(RITM3146240), LSP notified and Checklist finalized on 9Nov2021 23Sept2021: The screen UAT is not completed yet. There was a delay from the TDM end in completing the screen UAT. Documents will be shared after the UAT is completed. 11Aug2021: The TDM confirmed that 29Nov2021 will be the FPFV and Go-live would be in 3rd week of October. 10Aug2021: According to the activity planner the go-live date is 17-Nov-2021 and FPFV date is 22-Dec-20211. The DBD has already asked the TDM to update the Go-Live date. 2-Jul-2021: The Go-Live might be postponed as informed by the DBD. The date is not confirmed. 26May2021: RF Developer assigned. | None | None | 2021-11-02 05:30 | RF finalized and LSH TST set-up requested on 2-Nov-2021. Post LSH TST set-up confirmation, LSH PROD request was raised on 16-Nov-2021. | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2021-11-22 | Completed | 2021-11-25 05:30 |  |  | 2021-11-30 05:30 | 2021-11-30 05:30 |  | 2021-11-30 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 28 | 75 | 0 | 246 | 1033 | 0 | 268 | 49 | 200 | 1282 | 5 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [10 empty] | 2021-11-23 05:30 | [5 empty] | None of the above
CBYL719C | CBYL719C2301 | C1001085 | Phase III | NCDS | OC RDC - Inhouse | 2015-07-10 05:30 | 2015-07-10 05:30 |  | DB Conduct | Final DBL | 2022-08-15 05:30 | 2015-07-23 05:30 |  | 2015-04-13 05:30 |  | Active | 2022-07-01 05:30 |  | 2022-08-15 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | SOLAR-1: A phase III randomized double-blind, placebo controlled study of alpelisib in combination with fulvestrant for men and postmenopausal women with hormone receptor positive, HER2-negative advanced breast cancer which progressed on or after aromatase inhibitor treatment | CBYL719C2301 SOLAR-1 mBC/HR+/PIK3CA+/-/L2-C(fulv) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kambothu, Sai Sumanth | Jayavaram, Pavan | Regula, Ramakrishna | Hiriyanna, Srinivas | Sarah Rawlings | Sarah Rawlings | Choppadandi, Kranthikumar | Shewane, Roshni | Completed | 2020-05-05 05:30 | Study Transition completed to transition DBD Roshni Shewane on 05-May-2020 | [10 empty] | Agavekar, Amit |  | Sushant Sundar | [12 empty] | DDPASS will be conducted before next Milestone. |  | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2015-07-10 05:30 | 2015-07-10 05:30 | Shewane, Roshni | Mareedu, Vasu | NA | [7 empty] | 134 | 0 |  |  | 0 |  |  |  | 872 | 12 | 0 |  | Breast cancer metastatic | No | Global | Open | Yes | [14 empty] | Interim-Analysis | Tidke, Shyam | None of the above | Yes
CBYL719N1 | CBYL719C2303 | C4009936 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-08-01 05:30 | 2021-10-21 05:30 | 2021-11-29 05:30 | DB Set-Up | Final DBL | 2027-01-08 05:30 | 2021-11-29 05:30 | 2021-07-27 05:30 | 2021-07-05 05:30 |  | Active | 2026-11-27 05:30 |  | 2027-01-08 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Phase III randomized, double-blind, placebo controlled study of alpelisib in combination with fulvestrant for men and postmenopausal women with HR-positive, HER2-negative advanced breast cancer with a PIK3CA mutation, who progressed on or after aromatase inhibitor and a CDK4/6 inhibitor | CBYL719C2303 EPIK-B5 (HR+/HER2- aBC Post CDK4/6) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sumaiya, Sara | Jayavaram, Pavan | Regula, Ramakrishna | Hiriyanna, Srinivas | David Steele | David Steele | Gupta, Anshu | Mareedu, Vasu |  |  | 16Apr2021 : TDM (Sumaiya, Sara) reached out in Anshu's absence to see any requirements or deliverables from DBD, As of now there is none. TDM will reach out for support as needed. Initial golive 01Aug2021: |  | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 19Jan2021: Rule file Version 3.0 has been finalized in CREDI. LB, YR, YD DTS tables are added. 02Nov2021: Rule file Version 2.0 has been finalized in CREDI as per the LSP comments. 22Oct2021: Rule file Version 1.0 has been finalized in CREDI and the LSP is notified. 21Oct2021: Rule file peer review has been completed. 13Oct2021: Rule file has been shared for the peer review. Go-live is pushed to 21 Oct 2021. 11Oct2021: Rule file development is started. 08Oct2021: Screen UAT is completed and received the Updated UAT ALS. 13Sep2021: Received SRFs, SDTM Annotations, ALS for review. Screen UAT is not yet completed 12Aug2021: Screen UAT status and RF pre-requisite documents not yet received. Reminder sent to DBD. 09Aug2021 : Reassigned to Satwik from Angella. 26May2021: RF Developer assigned | None | None | 2021-10-22 05:30 |  |  |  | Sushant Sundar | [28 empty] | NA | [5 empty] | 1 | 156 | 79 | 0 | 179 | 1116 | 0 | 325 | 49 | 223 | 1388 | 9 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [10 empty] | 2021-11-10 05:30 | [5 empty] | None of the above
CBYL719C_MA | CBYL719C2401 | C4006099 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2019-12-02 05:30 | 2020-03-20 05:30 | 2020-06-30 05:30 | DB Locked | Final DBL Achieved |  | 2020-02-01 05:30 | 2019-10-30 05:30 | 2019-10-30 05:30 |  | Active | 2021-09-01 05:30 | 2021-09-10 05:30 | 2021-10-29 05:30 | 2021-10-13 05:30 | FALSE | NI study | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | PIK3CA Registry: A descriptive study of PIK3CA mutations in patients with HR+/Her2- advanced breast cancer | CBYL719C2401 Alpelisib mutation analysis registry | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sadhu, Soumen Kumar | Sadhu, Soumen Kumar | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | LaTonya Smith | LaTonya Smith | Kancharla, Susmita | Rapaka, Sindhuja | Completed |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 02Dec2019 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 30-JUL-2021: PPC #5 is related to tSDV updates and has no impact on RF, SMT, LSH. 12-MAY-2021: RF Version 4.0 is now final for PPC#4 updates. SNOW#51 (RITM2560913) has been raised for SMT and LSH updates. 20-APR-2021: RF Version 4.0 is now final for FAMH SDTM annotations update. SNOW#51 (RITM2484517) has been raised for SMT and LSH updates. 16-MAR-2021: RF Version 3.0 is now final for RP domain update. SNOW#51 (RITM2373785) has been raised for SMT and LSH updates. 25JAN2021: SNOW#51 raised for SMT and LSH updates for PPC2. No RF updates required. 07-JUL-2020: RF up to date for all final DTS and Post Production updated till PPC1 implemented in the study. 19JUN2020: RF updates finalized for PPC1. SNOW#51 raised for SMT and LSH updates. 06APR2020: RF finalized in CREDI. SNOW#05 raised for LSH set-up. 3APR2020: Peer review comments received and responded back. 26MAR2020: Sent for Peer Review. 19MAR2020 : DBD shared the final ALS for RF today. 17MAR2020: DB set-up issues shared with DBD for DB updates. Awaiting updated ALS for Rule file creation. 03MAR2020: OSRM2 planned for today. DBD will provide pre-requisites after screen UAT completion. 07Feb2020: There are 2 Study specific forms and SRFs to be approved. RF not started. 7-JAN-2020: SRFs not yet approved. DB Go-live date will be confirmed from CTT by 8-JAN-2020. 2-JAN-2020: Study specific SRFs not yet provided to DBD for study build. DBD requested for tentative Go-live date. | None | None | 2020-04-06 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sai Krishna Mettugari | Completed | 2020-04-15 | Completed | 2020-06-26 05:30 |  | KPI met - incorrect source date entry (example FPFV) 1. FPFV date was in Jun2020. 2. Study transitioned and issues in Pre-requisite documents 3. SMT support delayed since SMEs occupied with other priority work. | 2020-06-26 05:30 | 2020-06-26 05:30 | KPI met - incorrect source date entry (example FPFV) 1. FPFV date was in Jun2020. 2. Study transitioned and issues in Pre-requisite documents 3. SMT support delayed since SMEs occupied with other priority work. | 2020-07-02 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 1 | 21 | 0 | 22 | 154 | 0 | 44 | 7 | 77 | 238 | 1 | 0 |  | Breast cancer | No | Global | Open | Yes | [10 empty] | 2020-06-14 05:30 | [5 empty] | None of the above
CBYL719C | CBYL719C2404 | C4010447 | Phase IV | Other | CRO - EDC |  |  |  | Study Planned |  |  |  | 2021-03-15 05:30 | 2021-03-25 05:30 |  | Planned |  |  |  |  | FALSE | NIS Trial | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A non-interventional study of alpelisib in combination with fulvestrant in postmenopausal women, and men, with hormone receptor (HR) positive, human epidermal growth factor receptor 2 (HER2) negative, locally advanced or metastatic breast cancer with a PIK3CA mutation after disease progression following endocrine therapy as monotherapy in the real world setting | CBYL719C2404 NIS-PDC HR+ HER2- aBC in EU | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sumaiya, Sara | Vithanala, Kiran Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Corinne Rebischung | Sarah Rawlings | [17 empty] | Sushant Sundar | [28 empty] | IQVIA | [19 empty] | Advanced breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CBYL719F1 | CBYL719F12002 | C4005964 | Phase IV | Other | CRO - EDC |  |  | 2020-06-03 05:30 | DB Locked |  |  | 2020-06-09 05:30 |  | 2020-01-30 05:30 |  | Completed | 2021-04-16 05:30 | 2020-10-13 05:30 | 2021-05-28 05:30 | 2021-05-28 05:30 | FALSE | DCN Priority | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | Retrospective chart review study of patients with PIK3CA-Related Overgrowth Spectrum (PROS) who have received alpelisib as part of a compassionate use program (EPIK-P1)) | CBYL719F12002 PROs Chart Review Study | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Trivedi, Ekta | Trivedi, Ekta | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Fabian Romen | Fabian Romen | [17 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | PIK3CA related overgrowth spectrum | Yes | Global | Open | Yes | [16 empty] | None of the above
CBYL719O1 | CBYL719F12101 | C4008761 | Phase I | Other | CRO - EDC | 2021-05-20 05:30 |  | 2022-02-03 05:30 | DB Set-Up | Final DBL | 2022-02-25 05:30 |  | 2021-03-11 05:30 | 2021-03-08 05:30 |  | Planned | 2022-05-31 05:30 |  | 2022-02-25 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases |  | CBYL719F12101 PhI BE Granules vs Tablets HV | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Trivedi, Ekta | Trivedi, Ekta | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Sumerah Bakhsh | Sumerah Bakhsh | [17 empty] | Sai Krishna Mettugari | [28 empty] | Celerion | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | PIK3CA related overgrowth spectrum | No | Global | Open | Yes | [16 empty] | None of the above
CBYL719F1 | CBYL719F12201 | C4005153 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-01-14 05:30 | 2021-02-24 05:30 | 2021-03-31 05:30 | DB Conduct | DB Snapshot | 2022-06-03 05:30 | 2021-04-19 05:30 | 2020-10-01 05:30 | 2020-10-01 05:30 | 2020-12-22 05:30 | Active | 2029-12-26 05:30 |  | 2030-01-25 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A phase II open label 3 cohort trial in 3 different age groups trial in PIK3CA-Related Overgrowth Spectrum (PROS) with BYL719 | CBYL719F12201 PhII Confirmatory (EPIK-P2) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Joy, Ananya | Trivedi, Ekta | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Ghislaine Vincent | Ghislaine Vincent | Bora, Deepthi Reddy | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | Go- Live Delayed Due To: 1. Updated the Dynamics after UAT 2. UAT for RSG testing has not been sent on time for Safetly team. 3. FPFV Planned is pushed so Go-live date is Extending. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 14Jan2020. |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 18AUG2021: RF 7.0 is final and SNOW 51 request RITM2887262 has been created as attached. Requested for to rebuild MH and FAMH domain as per latest SDTM annotations. 04AUG2021: FAMH domain has to be update as per latest SDTM annotations. "Clinical manifestation of PROS" has to map MH and FAMH domains. 03AUG2021: RF 6.0 is final and SNOW 51 request RITM2827273 has been created Requested to rebuild DV, DS, LB and create SS domains as per PPC1 changes. 06Jul2021 : QS14Lreflecting in missing form DTS report 25JUN21: RF V5.0 is final and SNOW 51 RITM2709803 request created. QS14L DTS added. 09JUN21: RF V4.0 is final QS1L to QS13L DTS added in Rule file. 03JUN21: RF V3.0 is final and SNOW 51 request RITM2636309 created as per IRT V2.0 DTS. Table names YR has been updated to YRL and YD has been updated to YDL. 17MAY21: RF version 2.0 final and SNOW 51 request RITM2573352 created with following changes: LB: LB1L, ZR: ZR1L, ZI: ZI1L, YR and YD DTS’s have been added FAMH, FT and DV domains have been updated. 16APR21: RF Development is ongoing for LB1L, ZI1L, ZR1L and expected date of finalization is 19APR21 25FEB21: RF has been finalized and SNOW 05 RITM2305903 request has been created 01FEB21: The RIS have been postponed to March 23rd and expected DB golive is 23FEB21. 25JAN21: Rule file has been release for peer review and peer review is ongoing. 19JAN21: Few screen level updates have been done and the expected DB golive is on 27JAN21 12JAN21: Medidata SOD data extraction issue has been resolved, Rule file will be release on 19JAN21 for peer review. 05JAN21: Received all the required supporting documents for RF development except SOD data due to Medidata issue. RF development is ongoing. 10NOV20: SDTM annotations have been received. Requested DBD for to share study specific pages for review. 20OCT20: Lead DBD is following up for SDTM annotations with SDTM programmer. 12OCT20: Lead DBD study specific pages have been designed and requested for SDTM annotations. 09OCT20: Study specific pages discussion are ongoing. 24SEP20: Study specific page modeling review is ongoing 08SEP20: Study specific pages have been sent for SDTM annotations. Once we've SDTM annotations, will start on RF development. 01SEP20:The expected date of protocol finalization is 14SEP20. 24JUL20: Study specific pages have been reviewed for couple of pages and expecting so more pages for review. 07JUL20: At the moment, no RF actitivities is ongoing. 25JUN20: DBD golive has been pushed to 15SEP20 and tentative timelines of study specific forms review is on 16JUL20 28MAY2020: Planned Go-live is in August, but protocol is not yet finalized. So once protocol gets finalized Lead DBD will let us know the RF developer. 26May2020 : No update from DBD Sent a follow-up email. 24-MAR-20: No Rule file activities have been started. Golive is scheduled on 04MAY2020. 03-FEB-2020: Golive is scheduled on 20-APR-2020 as per current plan and SRF discussions ongoing and expected date of screens finalization is on 14-FEB-2020. 29-NOV-2019: Screens are not finalized yet | None | None | 2021-02-25 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2021-03-09 | Completed | 2021-03-16 05:30 | The initial SNOW ticket assigned does not contain final Rule File, DQP and other prerequisites for LSH setup. Hence a new ticket for LSH Setup (SNOW-05) was raised on 12th and it is closed on 19th March. |  | 2021-03-18 05:30 | 2021-03-18 05:30 |  | 2021-03-31 05:30 |  |  | The DDPASS review is on-going, not all domains has data yet hence only 60% of domains passed. | 60 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 4 | 26 | 80 | 0 | 546 | 983 | 0 | 246 | 36 | 222 | 1241 | 19 | 0 |  | Activated PI3 kinase delta syndrome | Yes | Global | Open | Yes | [10 empty] | 2021-03-15 05:30 | [5 empty] | None of the above
CBYL719F1 | CBYL719F12401 | C4009670 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2021-08-31 05:30 | 2021-12-03 05:30 | 2022-01-03 05:30 | DB Conduct | Interim DBL | 2022-07-20 05:30 | 2022-01-27 05:30 | 2021-06-15 05:30 | 2021-06-15 05:30 |  | Active | 2027-05-27 05:30 |  | 2027-07-07 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Phase II study to evaluate the long-term safety and efficacy of alpelisib in patients with PIK3CA-Related Overgrowth Spectrum (PROS) who previously participated in Study CBYL719F12002 (EPIK-P1) | CBYL719F12401 PROS PhIV Interventional Study | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Kalidindi, Neeharika Chamundeswari | Trivedi, Ekta | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Amy Zhou | Yan Zhou | Moses, Leah | Pamula, Vinay |  |  | 29Apr2021 : Not yet started Initial golive when DBD assigned 31Aug2021. |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 10Feb2022: Reviewed the IA and provided the comments to the TDM and asked LSP to confirm. 10Feb2022: TDM shared the PPC#1 IA for review. 3Dec2021: Study has been pushed to production. LSH PROD ticket has been raised and notified the LSP. 24Nov2021 : Received the updated ALS for updated LAB chemistry pages. No update required in RF. Sent the necessary comments. 22Nov2021 : The Go-live date has been pushed to 30Nov2021. 15Nov2021 : Checklist has been finalized in the CREDI. 13Nov2021 : RF has been finalized in the CREDI and LSH TEST ticket has been raised. Will raise the LSH PROD ticket once the study goes live. Notified the LSP. 10Nov2021 : Received all the necessary SDTM related annotations and rationale as suggested by the peer reviewer. Waiting for the DBD to share the final copy of the ALS. 8Nov2021 : RF released after second round updates and received the 2nd round peer review comments. 1Nov2021 : Received 1st round peer review comments and shared them to the DBD to make necessary updates. 27Oct2021 : RF released for peer review. 22Oct2021 : Sent DBD further comments for the updates to be made in the DB and pending SDTM annotations to be shared. DB go-live pushed to 15-Nov-2021 13Oct2021 : Received information for new updates incorporated in the DB and a new page added. Asked for the SDTM annotations. 11Oct2021 : Received the updated annotation for RSS001 from SDTM programmer and sent for further updates. 6Oct2021 : Had a discussion with the team, RSS001 has to be updated along with the SDTM annotation. Pending activity. Go-Live date has been pushed to 10th November 2021. 5Oct2021 : Design correction needed for RSS001 due to wrong design in DB. Shared the comments to TDM. 1Oct2021: RF is pending with 3 SDTM annotations. 1 new form TUS001 has been added and EG form has been removed. 28Sep2021 : Received comments and updates from the DBD. DBD shared the updated ALS and SOD. 23Sep2021 : Reviewed the ALS and shared the review comments to update the ALS. 21Sep2021 : Received Yx DTS to review. Reviewed and provided the comments to the DBD. 20Sep2021 : Received latest ALS, SDTM and SRFs for the study. 14Sep2021 : Discussions are ongoing, not yet received the ALS, SDTM and SRFs. 07Jul2021 : Received the activity planner from the DBD 06Jul2021 : RF developer assigned with DB go-live as 09Sep2021. | None | YDL DTS to be added | 2021-12-03 05:30 |  | Praveen kumar, Chakka Giri | Praveen kumar, Chakka Giri | Sai Krishna Mettugari | Completed | 2021-12-24 | Completed | 2021-12-24 05:30 | LSHTST application is undergoing planned downtime from 18th Nov to 29th Nov 2021 and currently all study set up requests in LSH Test are on hold. Study set up will be initiated as soon as LSHTST application is up and available for business use. |  | 2021-12-24 05:30 | 2021-12-24 05:30 |  | 2021-12-24 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 600 | 1 | 0 |  | PIK3CA related overgrowth spectrum | Yes | Global | Open | Yes | 2021-11-13 05:30 | [9 empty] | 2021-12-24 05:30 | [5 empty] | None of the above
CBYL719G1 | CBYL719G12301 | C4005441 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-01-20 05:30 | 2020-03-11 05:30 | 2020-02-05 05:30 | DB Conduct | Final DBL | 2031-04-03 05:30 | 2020-07-16 05:30 | 2019-09-17 05:30 | 2020-06-17 05:30 |  | Active | 2031-02-18 05:30 |  | 2031-04-03 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | EPIK-B2: A two part, Phase III, multicenter, randomized (1:1), double-blind, placebo-controlled study to assess the efficacy and safety of alpelisib (BYL719) in combination with trastuzumab and pertuzumab as maintenance therapy in patients with HER2-positive advanced breast cancer with a PIK3CA mutation | CBYL719G12301 EPIK-B2 (HER2+ ABC PIK3CA Mutant) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sumaiya, Sara | Vangara, Soundarya | Regula, Ramakrishna | Hiriyanna, Srinivas | Franck Letellier | Franck Letellier | Maricherla, Vijayroshan | Rao, S Shashikanth | Not Started |  | Transition from Santosh to Arpit. Arpit to Vijay Roshan Earlier golive planned as 20Jan2020 as of 27Nov2019. |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 26Aug2021: B11L DTS update is still pending and requested DBP to share the updated DTS 21Jul2021 : DTS B11L reflecting in 21Jul report as well 07-Jul-2021: Provided DTS review comments to DBP on 30-Jun-2021 and waiting for the updated DTS to add the table name in RF 06Jul2021 : B11L reflecting in missing form DTS report 18-Jun-2021: requested Lead DBP to share the B11L DTS to add it in RF. 25-Sep-2020: Updated the RF as per PPC02 and released for peer review. 29Jul2020: FAMH included and RF final. 07-Jul-2020: Working on RF update to include FAMH form. Will be completed by 15-Jul-2020. 22Jun2020 : FAMHO001 flagged in report. RF developer to check, Pending for long time 18-May-2020: Requested SDTM annotations for FAMH. 08Apr2020 : For FAMH its pending with SDTM programmer and DATS team. Study team following up on the same. RF developer has shared the Annotations. 23Mar2020: RF final and sent for LSH pre-drm setup and SMT development. Notified DBD to add the missing components to reference metadata. Excluded FAMH as SDTM annotations are under discussion. Form will be included in next version. 12Mar2020: Released Rule File for review on 12Mar2020. 09Mar2020 : RF development plan to complete by 11Mar2020. 17Feb2020 : followed up with DBD for docs. 05Feb2020: Requested for documents for SS review and RF | None | B11L | 2020-03-23 05:30 |  | Sultana, Salma | Sundar, N Sushant | Sushant Sundar | Completed | 2020-04-13 | Completed | 2020-04-28 05:30 | FPFV seems to be not correct. Jreview and GPS publish dates are different, reason not known. |  | 2020-04-28 05:30 | 2020-06-17 05:30 |  | 2020-04-30 05:30 |  |  |  | 100 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 6 | 87 | 90 | 0 | 798 | 1226 | 0 | 332 | 47 | 251 | 1524 | 12 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [10 empty] | 2020-04-25 05:30 | [5 empty] | None of the above
CBYL719H1 | CBYL719H12301 | C4005447 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-12-13 05:30 | 2020-03-11 05:30 | 2020-06-15 05:30 | DB Conduct | Final DBL | 2025-12-24 05:30 | 2020-06-08 05:30 | 2019-11-13 05:30 | 2019-12-09 05:30 |  | Active | 2025-11-12 05:30 |  | 2025-12-24 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | EPIK-B3: A Phase III, multicenter, randomized, double-blind, placebo-controlled study to assess the efficacy and safety of alpelisib (BYL719) in combination with nab-paclitaxel in patients with advanced triple negative breast cancer with either phosphoinositide-3-kinase catalytic subunit alpha (PIK3CA) mutation or phosphatase and tensin homolog protein (PTEN) loss without PIK3CA mutation | CBYL719H12301 EPIK-B3 (TNBC) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vangara, Soundarya | Vangara, Soundarya | Regula, Ramakrishna | Hiriyanna, Srinivas | Valerie Donnet | Valerie Donnet | R, Ankit | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. R, Ankit transitioned the study to Chandana Sarasani on 28-Jun-2020. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 13Dec2019 |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 19JUN21: Finalized Rule file V9.0 and SNOW 51 request RITM2786176 has been created for the addition of new DTS B12L. 09JUN21: As per latest SDTM annotations, FAMH domain has been updated and RF V8.0 is finalized and SNOW 51 RITM2646947 request has been created 21MAY21: As per SDTM team request RF version 7.0 and SNOW 51 RITM2590367 request has been created Note: SS and FAMH domains have been updated. 16APR21: PPC#3 has been initiated, change request form has been reviewed and provided comments 24FEB21: As of today no missing forms and missing DTS. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B11L DTS listed. But B11L DTS has been finalized on 28DEC20 and RF has been finalized on 28DEC20. SNOW 51 request RITM2124102 has been created. 19JAN2021: LSP is working on the LSH setup for the below changes. 15JAN2021: RF 5.0 was finalized on 16DEC20 with PPC2 changes (Forms OPG003,OPG003_1,OPG003_2,OPG003_3,OPG003_4 have been added as part of PPC2) but LSH setup is not completed. Informed to LSP and Following up with LSP on the same. 28DEC20: B11L DTS has been finalized on 28DEC20 and RF has been finalized on 28DEC21. SNOW 51 request RITM2124102 has been created. 21DEC20: RF updated and sent for peer review 07DEC20: B11L DTS has been found as missing in Missing report but as per DM confirmation DTS is not finalized. 25AUG20: No pending forms and DTS. SMT files and LSH was updated on 06AUG20. 07JUL20: As of today, no pending forms and no pending DTS. Note: SMT developer kept on hold below changes due to other urgent deliverables. 08JUN20: RF V3.0 has been finalized and SNOW 51 Request has ben created. No pending forms and pendig DTS as on 08JUN20. 27MAY20: New DTS LBL, QS1L, QS2L and QS3L have been added and sent for peer review (Kranthi) 21MAY20: DAP team requesting to add one variable MLENDAT. I've requested to provide rationale for the same since standard form also doesn't contain MLENDDAT variable. 30Apr2020 : Included pending form FAMHO001 and raised snow ticket. nothing is pending as of now 28APR2020: Rule file updated with FAMHO001 form and sent for peer review 14Apr2020 : All forms included except FAMH form and raised the Snow ticket. FAMH will be included by 16Apr2020. 08Apr2020 : RF peer review comments addressed and sent for 2nd round. There is one form for which SDTM annoationas seems to be insonsistent with the annotations library from other study. Following up with SDTM programmer and DBD. 24MAR2020: Requested for peer review. 15MAR2020: RF sent for peer review 09Mar2020: RF ongoing and plan to complete the development by 11th. 02-MAR-2020: Rule file development is ongoing and the expected date of Rule file development is 04MAR20 13-FEB-2020: Received all the required documents RF started. SS forms reviewed and provided feedback. 04-DEC-2019: Protocol is not finalized yet and Activity planner not yet released. 29-Nov-2019: SRF not finalized yet, still under discussion. As of today there is no date on Screens finalization SNOW05 raised on 14APR2020. Assigned to LSP on 17APR2020. Prerequisites were attached to ticket on 22APR2020Challa Nandini. | None | None | 2020-04-14 05:30 |  | Challa, Nandini | Sahu, Ahallad | Sushant Sundar | Completed | 2020-04-23 | Completed | 2020-05-19 05:30 | 03-FEB-20: SDTM discussion ongoing for one study specific form and also mapping visit discussions ongoing. 28-JAN-20: Screen UAT round 1 completed. Expecting some more changes in the unique CRF. SRF discussions is ongoing between DM and TA pod.20-MAY-20: SNOW 51 raised RITM1309529, ZJ and DV DRM setup is pending, ML needs Rule file update. |  | 2020-05-19 05:30 | 2020-05-19 05:30 |  | 2020-09-01 05:30 |  |  |  |  | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 7 | 132 | 101 | 0 | 853 | 1321 | 0 | 342 | 42 | 283 | 1646 | 7 | 0 |  | Triple negative breast cancer | No | Global | Open | Yes | [10 empty] | 2020-05-19 05:30 | [5 empty] | None of the above
CBYL719I1 | CBYL719I12301 | C4006113 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-05-15 05:30 |  | 2021-12-22 05:30 | DB On hold |  |  |  | 2021-08-24 05:30 |  |  | Stopped (with patients) | 2026-12-25 05:30 |  | 2027-02-05 05:30 | 2027-02-05 05:30 | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor |  | CBYL719I12301 - 1L RM HNSCC (Pembro) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vavasseur, Celine | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Marcus Elder | Maricherla, Vijayroshan | Lingampalli, Rohit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15May2020 | [12 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Squamous cell carcinoma of head and neck | No | Global | [18 empty] | None of the above
CBYL719J1 | CBYL719J12301 | C4006112 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-06-30 05:30 |  |  | DB On hold |  |  |  | 2021-03-03 05:30 | 2021-03-04 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A two part, phase III, multicenter, randomized (1:1), double blind, placebo-controlled study to assess the efficacy and safety of alpelisib (BYL719) in combination with nab-paclitaxel in patients with platinum and anti-PD(L)1 pre-treated Recurrent or Metastatic (R/M) Head and Neck Squamous Cell Carcinoma (HNSCC). | CBYL719J12301 EPIK-H (2L/3L RM HNSCC) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sahu, Kalyani | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Laurence Bourdeau | Laurence Bourdeau | Gandla, Prashanth | Gandla, Prashanth | Not Started |  | Moved from 10Aug2020 to 04Jan2021 |  | DRM |  | Kuttoboina, Sujan Kumar | Ongoing | 05APR2021: As just announced during the CTT meeting, this is to inform you of a current change in strategy for the development of alpelisib in 2nd/3rd line R/M HNSCC. Upon assessment of the overall global development strategy of alpelisib, a decision was made last Friday to not proceed with Study CBYL719J12301 as a Novartis sponsored registration intent trial. Therefore, this study will not be opened at sites as planned. 30NOV20: Study Go-live date is on 30-JUN-2021 and as of no RF development has been started 10NOV20: For this trial FPFV is expected in July month 2021. I will update exact date once I will receive complete information from study team. 29OCT20: As per CTT draft protocol will be ready by 18-Nov20. After that I believe we will get final timeline. 20OCT20: No updates from study team about timelines of the study. Lead DBD is following up with TDM. 12OCT20: Study timelines might change due to the study design changes. Will come to know the latest updates on 15OCT20. 07JUL20: NO RF activites ongoing at this moment. 28MAY2020: As per Lead DBD commuication: DB Go live - 04-Jan-2021 FPFV is expected- 29-Jan-2021 26May2020 : No update from DBD Sent a follow-up email. | [6 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Squamous cell carcinoma of head and neck | No | Global | Terminated | Yes | [16 empty] | None of the above
CBYL719K1 | CBYL719K12301 | C4006115 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-05-15 05:30 | 2021-04-29 05:30 | 2021-07-01 05:30 | DB Conduct | Final DBL | 2025-03-20 05:30 | 2021-07-02 05:30 | 2020-08-28 05:30 | 2021-05-17 05:30 |  | Active | 2025-01-31 05:30 |  | 2025-03-20 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase III randomized study to assess the efficacy and safety of alpelisib (BYL719) in combination with olaparib in patients with no germline BRCA mutation detected, platinum-resistant or refractory, high grade serous ovarian cancer | CBYL719K12301 EPIK-O (Ovarian Cancer) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vithanala, Kiran Kumar | Vithanala, Kiran Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Alexandre Weimann | Alexandre Weimann | Maricherla, Vijayroshan | Bora, Deepthi Reddy |  |  | 29-APR-2021: Study Pushed to PROD. Moved to 03Jun2020. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15May2020 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 23-DEC-2021: RF Version 6.0 final in SubWay for B11L DTS table addition. SNOW#51 request has been raised for SMT/LSH updates. 07-OCT-2021: RF Version 5.0 final in SubWay for LB domain update. SNOW#51 request has been raised for SMT/LSH updates. 22-SEP-2021: RF Version 4.0 final in SubWay for PPC #2 updates. SNOW#51 request has been raised for SMT/LSH updates. 20-JUL-2021: RF Version 3.0 final in SubWay for DTS table addition (LB1L, QS1L, QS2L, QS3L, YDL, YRL). SNOW#51 request has been raised for SMT/LSH updates. (Note: DTS table name will be corrected in Version 2.0) 9-JUL-20201: RF Version 2.0 final in SubWay for PPC1 updates. SNOW#05 request raised for new study set-up in LSH. Lab DTS comments have been provided to TDM. RF update will be initiated post DTS finalization. 06Jul2021 : OPS001, LBG001_3_TR, CES001, MIO001 forms and LBL1L reflecting in missing form/DTS report (Rule file updates are in progress). 30-APR-2021: RF Version 1.0 final in SubWay. SNOW#05 request raised for new study set-up in LSH. 15-Apr-2021: SDTM annotations to be provided by EOB 19-Apr-2021. 05-APR-2021: Received SRF, ALS for initiating RF activities. SDTM annotations not yet received. 3-DEC-2020: The study dynamics under progress. Study will get postponed as informed by DBD. BOW and Master tracker to be updated once dates are confirmed by DBD (Roshan). 07-JUL-2020: Database Go-Live pushed to 15-Dec-2020 25JUN2020: Email sent to DBD for an update on the study status. 29APR2020: Study Go-live has been pushed to Sep 2020. | None | None | 2021-04-30 05:30 |  | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2021-05-19 | Completed | 2021-05-26 05:30 |  |  | 2021-05-26 05:30 | 2021-05-27 05:30 |  | 2021-06-04 05:30 |  |  |  | 80 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 4 | 158 | 93 | 0 | 845 | 1238 | 0 | 370 | 41 | 298 | 1577 | 11 | 0 |  | Ovarian cancer | Yes | Global | Open | Yes | [10 empty] | 2021-05-26 05:30 | [5 empty] | None of the above
CBYL719A | CBYL719X2101 | C1200276 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-10-05 05:30 |  | 2010-04-27 05:30 |  | Completed | 2020-06-30 05:30 | 2020-04-16 05:30 | 2020-06-11 05:30 | 2020-06-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase IA, multicenter, open-label dose escalation study of oral BYL719, in adult patients with advanced solid malignancies, whose tumors have an alteration of the PIK3CA gene | CBYL719X2101 Phase IA Advanced Solid Tumor Study | P0 Oncology (Solid Tumors all MA Onc projects) | Langlo, Francois | Greyling, Alida | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Dragana Jankovic | Dragana Jankovic |  | Gupta, Anshu | [15 empty] | Rohit Varate | [28 empty] | Syneos Health | Oncology | BP21 | INC | Rachel.Pyke@INCResearch.com | Earlier DBD: Asha Rajanna |  |  | 325 | 0 | [10 empty] | Metastatic neoplasm | No | Global | Open | Yes | [16 empty] | None of the above
CBYL719D1 | CBYL719X2104 | C1202205 | Phase I | NOVDD | [7 empty] | 2012-11-12 05:30 |  | 2012-06-04 05:30 |  | Completed |  | 2016-05-09 05:30 |  | 2016-06-30 05:30 | FALSE |  |  |  | Outsourced |  | A phase Ib dose escalation/randomized phase II, multicenter, open-label study of BYL719 in combination with cetuximab in patients with recurrent or metastatic head and neck squamous cell carcinoma | CBYL719X2104 | N7 Oncology - NIBR | [6 empty] | Antonio Silva | [66 empty] | Squamous cell carcinoma of head and neck | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719E1 | CBYL719X2105J | C1200237 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-11-27 05:30 |  | 2012-06-26 05:30 |  | Completed |  | 2017-06-01 05:30 |  | 2017-08-03 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase Ib/II open-label, single arm study of the combination therapy of BYL719 plus ganitumab in adult patients with solid tumors having mutant or amplified PIK3CA who have progressed despite prior standard treatment. | CBYL719X2105J | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Maria Amparo Buigues Vila | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719C_MA | CBYL719X2402 | C3000226 | Phase II | NCDS | OC RDC - Inhouse | 2017-05-12 05:30 | 2017-05-12 05:30 |  | DB Conduct | Final DBL | 2023-09-08 05:30 | 2017-08-14 05:30 |  | 2017-02-06 05:30 |  | Active | 2023-07-17 05:30 |  | 2023-09-08 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | A phase II multicenter, open-label, two-cohort, non-comparative study to assess the efficacy and safety of alpelisib plus fulvestrant or letrozole in patients with PIK3CA mutant hormone receptor (HR) positive, HER2-negative advanced breast cancer (aBC), who have progressed on or after CDK 4/6 inhibitor treatment | CBYL719X2402 BYLieve | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Shedge, Vijay | Bagayatkar, Rupali Sudesh | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh |  | Heather Patino | TEMBHARE, HITESH | Katam, Veera Nagendra | [13 empty] | Girvasiya, Shaili |  | Sai Krishna Mettugari | [12 empty] | XS domain rebuild is required after implementing the PPC | 97 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | ICON | External Full | 2017-05-16 05:30 | 2017-05-16 05:30 | Killamsetty, Nanari Ram | Meda, Sreelakshmi | NA | [7 empty] | 91 | 0 |  |  | 0 |  |  |  | 768 | 5 | 0 |  | Breast cancer | No | Global | Open | Yes | [14 empty] | Interim-Analysis | Mettugari, Sai Krishna | None of the above | Yes
CBYL719A0 | CBYL719Z2101 | C1001084 | Phase I | NCDS | [7 empty] | 2014-03-05 05:30 |  | 2013-10-23 05:30 |  | Completed |  | 2016-08-19 05:30 |  | 2016-09-30 05:30 | FALSE |  |  |  | InHouse |  | A phase Ib dose finding study of BYL719 in combination with paclitaxel in advanced solid tumors followed by two expansion phases in locally advanced/metastatic chemotherapy naive HER2-breast cancer patients and recurrent or metastastic head-and-neck squamous cell carcinoma patients pre-treated with platinum based therapy | CBYL719Z2101 Ph I solid tumors L-2 C(paclitaxel) | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Valerie Donnet | Valerie Donnet | [15 empty] | Ghate, Dhananjay | [50 empty] | Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CBYL719A0 | CBYL719Z2102 | C1001082 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-05-14 05:30 |  | 2013-12-19 05:30 |  | Completed | 2019-04-12 05:30 | 2019-04-12 05:30 | 2019-05-17 05:30 | 2019-05-20 05:30 | FALSE | Priority not assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase Ib dose-finding study of BYL719 plus everolimus and BYL719 plus everolimus plus exemestane in patients with advanced solid tumors, with dose-expansion cohorts in renal cell cancer (RCC), pancreatic neuroendocrine tumors (pNETs), and advanced breast cancer (BC) patients. | CBYL719Z2102 NET-kidn-HR+ mBC-RAD001/exemestane | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Marchand, Matthieu | Vavasseur, Celine | Regula, Ramakrishna | Hiriyanna, Srinivas | Sandrine Bach-Berkowicz | Laurence Bourdeau | Bakka, Sandeep | [14 empty] | Gandikota, Sree Lakshmi |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse |  | 2014-03-10 05:30 |  |  | NA | [7 empty] | 157 | 0 |  |  | 0 |  |  |  | 661 | 6 | 0 |  | Breast cancer; Pancreatic neuroendocrine tumour; Renal cell carcinoma; Solid tumour | No | Global | Completed | Yes | [14 empty] | DBL | Mettugari, Sai Krishna | None of the above | Yes
CBYM338B | CBYM338B2203 | C1001089 | Phase III | NCDS | [7 empty] | 2013-09-26 05:30 |  | 2013-06-18 05:30 |  | Completed |  | 2016-01-06 05:30 |  | 2016-04-14 05:30 | FALSE |  |  |  | IDMA |  |  | RESILIENT_CBYM338B2203 | P4 Neuroscience | [6 empty] | Shad Razac | [15 empty] | Kadam, Sandeep | [16 empty] | OCRDC - Inhouse | [33 empty] | Myositis | No | Global | Completed | [17 empty] | None of the above
CBYM338B | CBYM338B2203E1 | C1001088 | Phase III | NCDS | [7 empty] | 2015-11-02 05:30 |  | 2015-06-19 05:30 |  | Completed |  | 2017-02-13 05:30 |  | 2017-03-21 05:30 | FALSE |  |  |  | IDMA |  | Extension of the CBYM338B2203 Phase IIB/III study to evaluate the long-term efficacy, safety and tolerability of intravenous BYM338 in patients with sporadic inclusion body myositis | CBYM338B2203E1 | P4 Neuroscience | [5 empty] | Lisa Jimmink_TAP; Shad Razac | Shad Razac | [66 empty] | Muscle degeneration | Yes | Global | Completed | Yes | [16 empty] | None of the above
CBYM338D | CBYM338D2201 | C1001092 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-09-16 05:30 |  | 2013-11-14 05:30 |  | Completed | 2018-10-25 05:30 | 2018-10-25 05:30 | 2018-12-06 05:30 | 2018-12-07 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | ICON | DF NS | A 24-week double blind treatment and 24-week follow up, randomized, multi-center, placebo-controlled, phase IIa/IIb study to evaluate the safety and efficacy of i.v. bimagrumab on total lean body mass and physical performance in patients after surgical treatment of hip fracture | CBYM338D2201 | P4 Neuroscience | Ball, Michael | Rangegowda, Shwetha | Venugopal, Vijay | Sharma, Atul | Nair, Sreesha | Shad Razac | Shad Razac | Meda, Sreelakshmi | [14 empty] | P, Meghanath |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  | 2014-04-24 05:30 |  |  | ICON | [7 empty] | 89 | 0 |  |  | 0 |  |  |  | 1088 | 14 | 0 |  | Muscle degeneration | Yes | Global | Completed | Yes | [16 empty] | None of the above
CBYM338E | CBYM338E2202 | C1001094 | Phase II | NCDS | OC RDC - Inhouse |  | 2015-01-15 05:30 |  | DB Locked | Final DBL Achieved |  | 2014-12-09 05:30 |  | 2014-09-30 05:30 |  | Completed | 2018-10-16 05:30 | 2018-06-28 05:30 | 2018-10-31 05:30 | 2018-11-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A 28 week, randomized, double-blind, placebo-controlled, multi-center, parallel group dose range finding study to assess the effect of monthly doses of bimagrumab 70, 210, and 700 mg on skeletal muscle strength and function in older adults with sarcopenia | CBYM338E2202 DRF study in Sarcopenia | P4 Neuroscience | Langlo, Francois | Soni, Kushal | Hirlekar, Minal Vivek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Lee Anne Filosa | Lee Anne Filosa | Sama, Ashok | [14 empty] | Bothe, Dnyanesh |  | Rohit Varate | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2015-01-15 05:30 | 2015-01-15 05:30 |  |  | NA | [7 empty] | 127 | 0 |  |  | 0 |  |  |  | 274 | 19 | 0 |  | Sarcopenia | No | Global | Completed | Yes | [16 empty] | None of the above
CBYM338E | CBYM338E2202E1 | C1001095 | Phase II | NCDS | OC RDC - Inhouse |  | 2015-08-18 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-07-22 05:30 |  | 2015-05-27 05:30 |  | Completed | 2018-12-11 05:30 | 2018-12-03 05:30 | 2019-01-22 05:30 | 2019-01-18 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 24 week off drug extension, parallel group, study assessing durability of effect on skeletal muscle strength and function following a 6-month double-blind, placebo controlled study evaluating bimagrumab in older adults with sarcopenia (InvestiGAIT extension) | CBYM338E2202E1 24 weeks extension to Sarcopenia | P4 Neuroscience | Ball, Michael | Amrutham, Subhash | Venugopal, Vijay | Sharma, Atul | Nair, Sreesha | Shad Razac | Shad Razac | Sama, Ashok | [14 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2015-08-17 05:30 | 2015-08-17 05:30 |  |  | NA | [7 empty] | 113 | 0 |  |  | 0 |  |  |  | 573 | 10 | 0 |  | Muscle degeneration | Yes | Global | Completed | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CBYM338D | CBYM338X2110 | C1001093 | Phase I | [8 empty] | 2015-05-19 05:30 |  | 2015-02-17 05:30 |  | Completed |  |  |  | 2016-11-23 05:30 | FALSE |  |  |  | IDMA Shared |  |  | BA in healthy elderly_CBYM338X2110 | P4 Neuroscience | [6 empty] | Sylvie Adam | [66 empty] | Hip fracture | No | Global | Completed | [17 empty] | None of the above
CBYM338B | CBYM338X2205E1 | C1001091 | Phase II | [8 empty] | 2014-03-11 05:30 |  | 2014-01-10 05:30 |  | Completed |  | 2016-08-23 05:30 |  | 2016-12-15 05:30 | FALSE |  |  |  | IDMA Shared |  |  | sIBM Open Label Extension CBYM338X2205E1 | P4 Neuroscience | [6 empty] | Birgitte Sloth | [66 empty] | Sporadic inclusion body myositis | No | Global | Completed | Yes | [16 empty] | None of the above
CBYM338F1 | CBYM338X2211 | C1200449 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-02-01 05:30 |  | 2016-10-12 05:30 |  | Completed | 2019-05-08 05:30 | 2019-05-08 05:30 | 2019-06-21 05:30 | 2019-06-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A randomized, subject- and investigator-blinded, placebo controlled study to assess the safety, pharmacokinetics and efficacy of intravenous bimagrumab in overweight and obese patients with type 2 diabetes | CBYM338X2211 PoC to assess effect of BYM338 on dia | N4 MSD - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Therese Swan | Katherine Hayes | [15 empty] | Nidamanuru, Kalyan Kumar |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Diabetes mellitus; Obesity | No | Global | Completed | Yes | [16 empty] | None of the above
CCAD112A | CCAD112A2201 | C1001804 | Phase II | [10 empty] | 2017-05-29 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE |  |  |  | Undecided Sourcing |  |  | RETIRED CCAD112A2201_PoC_RA_PsA | P7 Immunology Hepatology and Dermatology | [5 empty] | Thomas Salko | Thomas Salko | [66 empty] | Psoriatic arthropathy; Rheumatoid arthritis | No | Global | Wind Down | No | [16 empty] | None of the above
CCDZ173A0 | CCDZ173X2104 | C1001097 | Phase I | NCDS | [7 empty] | 2016-03-01 05:30 |  | 2016-01-19 05:30 |  | Completed |  |  |  | 2016-06-14 05:30 | FALSE |  |  |  | ED Full Outsourced |  | An open-label, two-period, fixed sequence study to evaluate the effects of multiple oral doses of CDZ173 on the pharmacokinetics of a monophasic oral contraceptive in healthy female subjects | CCDZ173X2104 DDI with hormonal contraceptives | N0 ATI - NIBR | [5 empty] | Cathy Gray | Catherine Gray | [68 empty] | Global | Completed | Yes | [16 empty] | None of the above
CCDZ173A | CCDZ173X2201 | C1200731 | Phase III | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2015-08-24 05:30 |  | 2014-11-13 05:30 |  | Completed | 2022-03-01 05:30 | 2021-08-16 05:30 | 2021-10-25 05:30 | 2021-09-07 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | An open-label, non-randomized, within-patient dose-finding study followed by a randomized, subject, investigator and sponsor-blinded placebo controlled study to assess the efficacy and safety of CDZ173 in patients with APDS/PASLI (Activated phosphoinositide 3-kinase delta syndrome/p110Â¿-activating mutation causing senescent T cells, lymphadenopathy and immunodeficiency) | CCDZ173X2201 Efficacy in APDS pts | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Barbora Hrochova; Olga Jurcikova | Kath Radford | [15 empty] | Polavarapu, Vanaja |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Immunodeficiency | No | Global | Open | Yes | [16 empty] | None of the above
CCDZ173A | CCDZ173X2201E1 | C1200443 | Phase III | NCDS | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2027-03-26 05:30 | 2016-09-08 05:30 |  | 2016-04-18 05:30 |  | Active | 2027-01-21 05:30 |  | 2027-03-26 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | An open-label, non-randomized extension study to evaluate the long term safety, tolerability, efficacy and pharmacokinetics of CDZ173 in patients with APDS/PASLI (Activated phosphoinositide 3-kinase delta syndrome/p110d-activating mutation causing senescent T cells, lymphadenopathy and immunodeficiency). | CCDZ173X2201E1 Long term safety & efficacy in APDS | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Amit Kaushik Padadharia; Kathryn Radford; Olga Jurcikova | Kath Radford | [15 empty] | Polavarapu, Vanaja |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Immunodeficiency | No | Global | Open | Yes | [16 empty] | None of the above
CCDZ173C1 | CCDZ173X2203 | C1001099 | Phase II | NCDS |  |  |  | 2018-06-29 05:30 |  |  |  | 2016-06-01 05:30 | 2018-01-19 05:30 | 2016-01-28 05:30 |  | Completed | 2017-10-31 05:30 | 2017-05-17 05:30 | 2017-12-05 05:30 | 2017-07-13 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A randomized, double-blind, placebo-controlled, parallel group study to assess the safety, tolerability, pharmacokinetics and preliminary efficacy of CDZ173 in patients with primary Sjoegren's syndrome | CCDZ173X2203 | N0 ATI - NIBR | [5 empty] | Ute Laessing | Ute L��ssing | [15 empty] | Kumar, Herin | [50 empty] | Sjogren's syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CCEE321A0 | CCEE321A12101 | C4004017 | Phase I | Other | CRO - EDC |  |  | 2020-02-28 05:30 | DB Locked | Final DBL Achieved |  | 2020-02-27 05:30 | 2019-12-27 05:30 | 2019-12-17 05:30 |  | Completed | 2021-05-14 05:30 | 2021-05-16 05:30 |  | 2021-07-23 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A first-in-human study to determine safety, tolerability and systemic exposure of topically applied CEE321 cream in adult subjects | CCEE321A12101 FIH | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Martina Zambianchi | Marta Zambianchi | [15 empty] | R, Harini |  | Rohit Varate | [13 empty] | 0 | [14 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Atopic dermatitis | No | Global | Open | Yes | [16 empty] | None of the above
CCFZ533A | CCFZ533A2101 | C4010284 | Phase I | Other | CRO - EDC |  |  | 2021-06-17 05:30 | DB On hold | Final DBL | 2021-12-29 05:30 |  | 2021-05-03 05:30 |  |  | Stopped (with patients) | 2021-11-18 05:30 |  | 2021-12-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI |  | CCFZ533A2101 Bioequivalence Study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti |  | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Renal transplant | No | Global | Wind Down | Yes | [16 empty] | None of the above
CCFZ533A | CCFZ533A2201 | C3003900 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-05 05:30 | 2018-11-30 05:30 | DB Conduct | Final DBL Achieved |  | 2018-11-28 05:30 | 2018-03-20 05:30 | 2018-05-02 05:30 |  | Active | 2026-03-04 05:30 | 2021-10-29 05:30 | 2022-01-31 05:30 | 2022-02-15 05:30 | TRUE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A partially-blinded, active-controlled, multicenter, randomized study evaluating efficacy, safety, tolerability, pharmacokinetic (PK) and pharmacodynamic (PD) of an anti-CD40 monoclonal antibody, CFZ533, in de novo and maintenance kidney transplant recipients | CCFZ533A2201 DRF in de novo & maintenance KTx | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kocharekar, Prasheela Chetan | Kocharekar, Prasheela Chetan | Sarkhel, Biswadip | Ninan, Esther | Susan Kuranoff | Susan Kuranoff | Govula, Shashikanth | Kashyap, Sandeep |  |  | Shashi Govula transition studies to maintenance lead Giftson J after initial release. Study transitioned from Giftson to Sandeep Kashyap - 28-Oct-2021 |  | DRM (DIAL) | Govula, Shashikanth | Choppadandi, Kranthikumar | Completed | 14-Apr-2021: RF_V9.0 is finalized for PPC15 updates 6JAN2021: SG: No pending/upcoming tasks. 20Oct2020 : QS1L, QS2L DTSs reflecting in the report 06Oct2020. Rule file finalized and SNOW ticket raised 15Sep | None | None | 2018-12-26 05:30 | Legacy Process | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2019-01-03 | Completed | 2019-06-18 05:30 |  |  | 2019-01-03 05:30 | 2019-01-03 05:30 |  | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | EC;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 22 | 33 | 78 | 0 | 316 | 1120 | 0 | 231 | 37 | 296 | 1453 | 5 | 0 |  | Renal transplant | No | Global | Open | Yes | [10 empty] | 2019-06-17 05:30 |  |  |  | Interim-Analysis |  | GDD annual target;#Pioneer | Yes
CCFZ533C | CCFZ533A2202 | C4002221 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-05-24 05:30 | 2019-08-08 05:30 | 2019-10-11 05:30 | DB Conduct | Interim DBL | 2022-05-16 05:30 | 2019-10-07 05:30 | 2018-11-19 05:30 | 2018-11-22 05:30 |  | Active | 2026-08-21 05:30 |  | 2024-02-08 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A 12-month, open-label, multicenter, randomized, safety, efficacy, pharmacokinetic (PK) and pharmacodynamic (PD) study of two regimens of anti-CD40 monoclonal antibody, CFZ533 vs. standard of care control, in adult de novo liver transplant recipients with a 12-month additional follow-up (CONTRAIL I) | CCFZ533A2202 Ph 2a PK/PD Study LTx | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Amrutkar, Pushpendra Sudhakar | Kocharekar, Prasheela Chetan | Sarkhel, Biswadip | Ninan, Esther |  | Carine Lemouzy | Govula, Shashikanth | Kashyap, Sandeep |  |  | Nov-2021 : Giftson Transitioned to Sandeep Kashyap Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 24May2019 |  | DRM | Govula, Shashikanth | Choppadandi, Kranthikumar | Completed | 03-May-2021: Updated the PHS001 form logic in RF as per the updated SDTM annotations and released for peer review 25-Mar-2021: ZES001 form included in RF and updated the FAMH RF logic as per SDTM/Stats programmer request 15Feb2021 : LC - ZES001 form reflecting in 09Feb2021 Missing forms Report. 6JAN2021: SG: No pending/upcoming tasks. 23-Jun-2020 (SHRIVNI5): ZWS002_1, ZWS003_1 forms are mentioned in the 'Excluded' forms' tab of the rule file as these two pages are not being used in the study however these CRF's are still not inactivated in study. DTS MI1L and PR1L are also already included in the Rule file V8.0 and LSH test transfer is ongoing. 22Jun2020 : ZWS002_1, ZWS003_1 forms are flagged in missing forms report but as per 09Mar2020 comment both are included in RF. Need to check why its flagging in report. requested Praveen to look into in Shashi's Absence. 27May2020 : MI: DTS MI1L added. PR: DTS PR1L added. LB: Updated constants EBCIGGAB, EBCIGMAB and sent for peer review 19-Mar-2020: all issues identified in DDPASS meetings have been addressed and Rule file shared for LSH setup. SNOW raised on 18-Mar-2020. 09Mar2020 : All pending forms ZWS001_1 ZWS002_1 ZWS003_1 which are fixed via PPC are included in RF and raised the Snow ticket for SMT and LSH setup today. 02Mar2020 : PPC pending for pending forms. Tentative to be completed by 06Mar2020. 12Feb2020 : Included LBG002_TR form and LBL DTS included in RF and sent for LSH setup. Also fixed PR and FAPR as per DDPASS comments. 10Feb2020: LBG002_TR ZWS001_1, ZWS002_1, ZWS003_1 - DB updated required via PPC to fix the issues. LBL DTS to be included received on 20Jan2020 | None | None | 2019-10-21 05:30 | Transition Study and Legacy process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2019-10-24 | Completed | 2019-10-24 05:30 |  |  | 2019-10-24 05:30 | 2019-10-24 05:30 | Pre-requisites not met | 2019-10-24 05:30 | 2019-10-24 05:30 |  |  |  | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 11 | 52 | 79 | 0 | 456 | 1143 | 0 | 256 | 36 | 346 | 1525 | 4 | 0 |  | Liver transplant | No | Global | Open | Yes | [10 empty] | 2019-10-22 05:30 | [5 empty] | Pioneer
CCFZ533B | CCFZ533B2201 | C4002521 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-06-13 05:30 | 2019-08-30 05:30 | 2019-10-03 05:30 | DB Conduct | Interim DBL | 2022-03-15 05:30 | 2019-10-01 05:30 | 2019-03-06 05:30 | 2019-02-21 05:30 |  | Active | 2023-02-22 05:30 |  | 2023-06-08 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A 48-week, 6-arm, randomized, double-blind, placebo controlled multicenter trial to assess the safety and efficacy of multiple CFZ533 doses administered subcutaneously in two distinct populations of patients with SjÃ¶grenâs Syndrome (TWINSS) | CCFZ533B2201 Ph2b DRF Study in SjS | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Amrutkar, Pushpendra Sudhakar | Kocharekar, Prasheela Chetan | Sarkhel, Biswadip | Ninan, Esther | Cornelia Scheurer | Cornelia Scheurer | Govula, Shashikanth | Kashyap, Sandeep |  |  | Nov-2021 : Giftson transitioned to Sandeep Kashyap Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 13Jun2019 |  | DRM | Govula, Shashikanth | Choppadandi, Kranthikumar | Completed | 21JN2021:Kranthi: RF update is not required for PPC06. However, requested lead DBP to provide clarification on few PPC updates, so that SNOW ticket will be raised for LSH update due to metadata updates 6JAN2021: SG: PPC6 implemented. ALS and required documents for Rulefile update will be shared by 8Jan2021. Rulefile update required. 17Sep2020 : ZW1L domain updated and snow raised. 8SEP2020: Dropped an email to check if any issue with LSH for ZWS003_1 and DSG005 page. 02Sep2020 : ZWS003_1 included in RF and finalized on 02 sep20 and DSG005 already in RF need to followup why its flagging in report 11AUG2020: Received updated SDTM annotations for pending ZW pages. Planned to release updated RF for review by 13AUG. Plan to finalize by 14AUG2020. 09Jul2020 : Added Protocol amendment log - DSG005 CRF to DS domain by Praveen in Shahsi's Absence and finlaized. For ZWS003_1 as per DBD "As the team is focused on DMC 2 deliverable, team decided to look into ZW domain once the data extraction is completed. (1st week of August)" 06Jul2020: Followup email sent to DBD for pending forms 22Jun2020: Shashi on personal emergency and asked Praveen to be backup. sent a followup email for pending forms 29Apr2020 : Praveen worked on V3.0 (Updated analyte name from CRYBL to CRYOGLBN in LBG002_TR_11 and LBG002_TR_12. Added B11L DTS). and raised snow ticket. ZWS003_1 form is pending and sent a followup email for PPC status 03Apr2020 : Checked with Giftson DBD there is DMC and this page is not required. Study team planning to have a PPC. 02Mar2020 : PPC pending for pending forms. 12Feb2020 : Cognitive Test, EQ5D5L, FACIT,HADS, IDEEL, PGADA, PROFAD, Central Lab, Sjogrens Syndrome, ESSDAI, ESSPRI, IDEEL, PHQ, PHGADA, ZW Mobility, ZW Two back. All DTSs included in RF and sent for LSH setup on 11Feb2020. 10-Jan-2020: ZWS003_1-Design issue, will be fixed through PPC. DTS's send on 6-Dec. Will be included in next version. | None | None | 2019-08-21 05:30 |  | Kadam, Sandeep | Varate, Rohit | Sandeep Kadam | Completed | 2019-11-26 | Completed | 2019-12-02 05:30 | LB, ZW have issues in DRM - working on resolution, Blinded domain information will receive in updated DQP, so DRM is pending for blinded domains | System or Application issues (RAVE/LSH/JReview/GPS) | 2019-12-05 05:30 | 2019-12-05 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-03-19 05:30 |  |  | B1 - Blinded domain as per latest DQP, one more round of review from Independant TP needed. QS - review pending ZW - review post recent PPC is pending | 86 | RaveX - Inhouse | Yes | EC;#ZK;#ZK03;#YR;#YD;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 10 | 31 | 63 | 0 | 299 | 733 | 0 | 232 | 36 | 147 | 916 | 4 | 0 |  | Sjogren's syndrome | Yes | Global | Open | Yes | [10 empty] | 2019-11-26 05:30 | [5 empty] | Pioneer
CCFZ533B | CCFZ533B2201E1 | C4003093 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-09-01 05:30 | 2020-11-30 05:30 | 2020-12-18 05:30 | DB Conduct | Final DBL | 2024-09-02 05:30 | 2021-01-05 05:30 | 2020-06-22 05:30 | 2020-07-14 05:30 |  | Active | 2024-07-23 05:30 |  | 2024-09-02 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A TWINSS extension trial to evaluate the safety and tolerability of CFZ533 (iscalimab) at two dose levels administered subcutaneously in patients with SjÃ¶grenâs Syndrome | CCFZ533B2201E1 Ph2b DRF Ext. Study in SjS | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kocharekar, Prasheela Chetan | Kocharekar, Prasheela Chetan | Sarkhel, Biswadip | Ninan, Esther | Amit Ranjan | Amit Ranjan | Bonam, Rajesh Babu | Thomas, Ankit | Completed |  | Nov-2021 : Giftson Transitioned to Ankit Thomas Golive moved from 01sep to 21sep2020 Initial golive as 01Sep2020. |  | DRM | Shafiudeen, Rehana Banu | R, Pratheeksha K | Completed | 01Dec2021: Rule File for PPC03 finalized and SNOW51 ticket raised on 30Nov2021 (SNOW51 Ticket Number - RITM3242553). RF Checklist finalized on 01Dec2021. 19Oct2021: PPC 02 implemented on 07Oct2021 and CMG001_2 and PRG001_2 forms have been added in the RF, RF finalized on 18Oct2021 and SNOW51 ticket raised (RITM3090964 ) on 18Oct2021. RF Checklist finalized on 19Oct2021. 31-Aug-2021 : The study is transitioned to R, Pratheeksha. 31-Aug-2021 : No Pending tasks. 15Jul2021 : Rule file V 6.0 is finalized in CREDI including the YDL table. SNOW 51 ticket is raised and the LSP us notified. 28Jun2021 : The Rule file V5.0 and the checklist is finalized in CREDI and the LSP is notified. 10Jun2021 : The Rule file V4.0 and the checklist is finalized in CREDI and the LSP is notified. 07Jun2021 : The Rule file V4.0 is updated as per the PPC 01 form and sent for peer review. 6Apr2021 : Included ZW2L,QS1L,QS2L,QS3L,QS4L,QS10L,QS11L,QS6L,QS5L,QS8L,LBL DTS in the RF and V 3.0 is finalized in CREDI 30Nov2020 : RF Final and Snow05 raised. 11Nov2020 : Awaiting for the final draft of the DTSs. 9Oct2020 : The study GoLive is postpone to 2Nove2020. Requested for the date change in Master tracker and DM BOW. 1Oct2020 : Peer review completed for the study working on oeer review commnets 28Sep2020 : Recieved the SDTM annotation from the DBD 25Sep2020 : Sent the rulefile for peer review. 14Sep2020 : SRF from core study will be used. Awaiting to recieve the SDTM annottaions for the 2 SS forms. RF development ongoing 1Sep2020: Completed the review for global forms. 14Aug2020: Contacted DBD to share documents. Peer review is ongoing. DBD will share the documents post peer review. | None | None | 2020-11-30 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sandeep Kadam | Completed | 2020-12-17 | Completed | 2020-12-20 05:30 |  |  | 2020-12-21 05:30 | 2020-12-21 05:30 |  | 2021-02-05 05:30 | 2020-12-21 05:30 |  | The DDPASS is on-going. | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 4 | 28 | 57 | 0 | 207 | 636 | 0 | 183 | 35 | 151 | 822 | 4 | 0 |  | Sjogren's syndrome | No | Global | Open | Yes | [10 empty] | 2020-12-20 05:30 | [5 empty] | None of the above
CADPT12A1 | CCFZ533H12201BC | C4000297 | Phase II | NCDS | CRO - EDC |  |  | 2019-03-11 05:30 | DB Conduct | Final DBL | 2023-11-06 05:30 | 2019-02-27 05:30 | 2018-10-16 05:30 | 2018-10-16 05:30 |  | Active | 2023-08-18 05:30 |  | 2023-11-06 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, subject and investigator blinded, placebo-controlled and multi-center platform study, to assess efficacy and safety of different investigational drugs in patients with moderate to severe hidradenitis suppurativa | CCFZ533H12201BC Platform HS | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Andrew Joyson; Frederique Chaperon; Patrycja Misiolek | Andrew Joyson | [15 empty] | Adi, Vishnupriya |  | Rohit Varate | [14 empty] | CRO |  | Y1;#Y5 | [11 empty] | CMED | [19 empty] | Hidradenitis suppurativa | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CCFZ533K1 | CCFZ533K12201 | C4012856 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-06-23 05:30 | Study Planned | DB Go-live | 2022-11-22 05:30 |  | 2023-02-23 05:30 |  |  | Planned | 2026-05-23 05:30 |  | 2026-07-03 05:30 |  |  | Clin-Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI |  | CCFZ533K12201 Ph2 Ulcerative colitis | N0 ATI - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Emma Hakansson | Louise Mooney | [17 empty] | Rohit Varate | [36 empty] | 60 | [7 empty] | 800 | 6 |  |  | Colitis ulcerative | No | Global | Open | Yes
CCFZ533M1 | CCFZ533M12201 | C4011073 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-03-13 05:30 | Study Planned | Final DBL | 2025-04-04 05:30 |  | 2022-10-28 05:30 |  |  | Planned | 2025-01-13 05:30 |  | 2025-04-04 05:30 |  |  | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A multi-center, randomized, patient and investigator-blinded, parallel group study to evaluate the safety and efficacy of iscalimab versus adalimumab in patients with Rheumatoid Arthritis. | CCFZ533M12201 CFZ533 PoC in early RA | N0 ATI - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Malika Hanser; Nasri Abdallah | Nasri Abdallah | [17 empty] | Rohit Varate | [36 empty] | 60 | [7 empty] | 800 | 6 |  |  | Rheumatoid arthritis | No | Global | Open | Yes
CCFZ533A0 | CCFZ533X2101 | C1200225 | Phase I | NOVDD | Other |  |  |  | DB Locked |  |  | 2013-01-07 05:30 |  | 2012-09-26 05:30 |  | Completed |  | 2017-02-03 05:30 |  | 2017-04-26 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, double-blind, placebo-controlled, single ascending dose first-in-human study to assess the safety, tolerability, pharmacokinetics, and pharmacodynamics of CFZ533 in healthy subjects and rheumatoid arthritis patients | CCFZ533X2101 SAD FIH in HVs and RA Patients | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Phil Koo | Phillip Koo | [17 empty] | Rohit Varate | [48 empty] | Rheumatoid arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CCFZ533A0 | CCFZ533X2201 | C1001121 | Phase II | NCDS | OC RDC - Inhouse |  | 2016-08-26 05:30 | 2018-06-29 05:30 | DB Locked |  |  | 2015-02-05 05:30 | 2018-01-19 05:30 | 2014-04-15 05:30 |  | Completed | 2019-10-18 05:30 | 2017-11-29 05:30 | 2018-02-23 05:30 | 2018-02-23 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A 12-month randomized, multiple dose, open-label, study evaluating safety, tolerability, pharmacokinetics/pharmacodynamics (PK/PD) and efficacy of an anti-CD40 monoclonal antibody, CFZ533, in combination with mycophenolate mofetil (MMF) and corticosteroids (CS), with and without tacrolimus (Tac), in de novo renal transplant recipients | CCFZ533X2201 PoC de novo renal transplant | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Bhoite, Raviraj Vijay | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Ute Laessing | Ute L��ssing | Samuel, Giftson | [14 empty] | Ramu, Harikrishnan |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2016-04-04 05:30 | 2016-04-04 05:30 |  |  | NA | [7 empty] | 211 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Transplant rejection | No | Global | Completed | Yes | [16 empty] | None of the above
CCFZ533D1 | CCFZ533X2202 | C1200586 | Phase II | NCDS | CRO - EDC |  |  | 2018-09-17 05:30 | DB Conduct | Final DBL | 2023-10-20 05:30 | 2018-09-12 05:30 | 2017-11-02 05:30 | 2017-12-19 05:30 |  | Active | 2023-06-22 05:30 |  | 2023-10-20 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, placebo-controlled, patient and investigator blinded study investigating the safety, tolerability, pharmacokinetics and preliminary efficacy of multiple doses of CFZ533 in patients with moderately active proliferative lupus nephritis | CCFZ533X2202 Safety, PK & efficacy in LN | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Sarka Mala | Sarka Mala | [15 empty] | Varate, Rohit |  | Rohit Varate | [13 empty] | 0 | [14 empty] | CMED | [19 empty] | Lupus nephritis | No | Global | Open | Yes | [16 empty] | None of the above
CCFZ533B | CCFZ533X2203 | C1200737 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-10-22 05:30 |  | 2014-01-30 05:30 |  | Completed | 2018-06-29 05:30 | 2018-06-29 05:30 | 2018-09-25 05:30 | 2018-09-26 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A multi-center, randomized, double-blind, placebo-controlled, parallel group study to assess the safety, tolerability, pharmacokinetics and preliminary efficacy of CFZ533 in patients with primary SjÃ¶gren's syndrome. | CCFZ533X2203 Primary Sjogren's Syndrome Study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Amanda Nguyen | Amanda Nguyen | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED |  | AP21 | CMED Clinical services | [16 empty] | Sjogren's syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CCFZ533E1 | CCFZ533X2204 | C1200683 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-09-29 05:30 |  | 2015-03-23 05:30 |  | Completed | 2018-02-01 05:30 | 2017-12-19 05:30 | 2018-02-28 05:30 | 2018-02-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A multi-center, randomized, double-blind, placebo-controlled, parallel group study to preliminarily evaluate the safety, tolerability, pharmacokinetics and efficacy of CFZ533 in patients with moderate to severe myasthenia gravis | CCFZ533X2204 CFZ533 in myasthenia gravis | N0 ATI - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Emilie Francoise Armelle Voltz | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Autoimmune disorder | No | Global | Completed | Yes | [16 empty] | None of the above
CCFZ533F1 | CCFZ533X2205 | C1200432 | Phase I | NCDS | Other |  |  |  | DB Locked |  |  | 2016-04-19 05:30 |  | 2015-12-15 05:30 |  | Completed |  | 2017-04-24 05:30 |  | 2017-07-24 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - CVM | An open label study to evaluate the safety and efficacy of 12 week treatment with CFZ533 in patients with Graves' disease. | CCFZ533X2205 | N1 CVM - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Brian Flannery | Brian Flannery | [17 empty] | Rohit Varate | [48 empty] | Graves' disease | No | Global | Completed | Yes | [16 empty] | None of the above
CCFZ533G1 | CCFZ533X2207 | C1200033 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-10-01 05:30 | 2019-11-14 05:30 | DB Conduct | Interim DBL | 2022-12-01 05:30 | 2019-11-08 05:30 | 2018-12-21 05:30 | 2019-03-26 05:30 |  | Active | 2027-06-09 05:30 |  | 2027-11-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM |  | CCFZ533X2207 PoC in adult and pediatric Type I Dia | N0 ATI - NIBR | Langlo, Francois | Donta, Alekhya Balaiah | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Aruna Vedala; Larissa Aguiar de Almeida; Noemi Giglioli | Aruna Vedala | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022. |  | DRM | Oguri, Praveen | Shrivastava, Nikhil | Completed | 15-Dec-2021: RF V7.0 updated and finalized WRT PPC#05 and DDPASS comments for FAREFID in FAAE domain. SNOW-51 (RITM3297567) raised and LSP is notified. 13-Jul-2021: Waiting for the inputs and confirmation from TDM, DBD and SDTM programmer. 23-Jun-2021: Sent mail to TDM to confirm if there is any other issue or to proceed with just FAREFID update in Rule File. 26May2021 : Reassigned the study from Praveen Oguri to Nikhil. 26-May-2021: DDPASS comment in LB domain needs to be updated. latest RF Version 6.0 30-Mar-2021: Added ZJG006, ZJG006_2, ZJG006_3, ZJG006_4, ZJG006_5, ZJG006_6 and ZJG006_7 forms and raised SNOW ticket (RITM2415171). 15-Feb-2021: RF is pending as CMS001 page SDTM annotations were in discussion. 15Feb2021 : LC - DSG005, LBG002_TR, CMS001_1 forms reflecting in 09Feb2021 missing form Report 21Jan2021: Received finalized DTS, will update RF today. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 LB3L DTS listed. Please check 05Nov2020: Sent follow up email to DBD Ramakanth to provide SDTM annotations from SDTM programmer on 04Nov2020. 16-Oct-2020: LB2LDTS will be included along with PPC03 updates. I will try to finalize by 21-Oct-2020 11Sep2020: Included FA1L DTS and raised SNOW ticket on 08Sep2020. 02Sep2020 : As per 02Sep2020 missing forms DTS report FA1L DTS pending 06Jul2020: Rule file V2.0 is the latest one. 02Dec2019: Rule file V2.0 finalized. 18Nov2019: RF v1.0 finalized. Pending forms/DTS: No DTS finalized yet. | None | None | 2019-11-22 05:30 | Transition Study and Legacy process | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2019-12-03 | Completed | 2019-12-03 05:30 | Study setup completed, except for FAAE domain, awaiting SMT file for the same from DBP. 30th Jan 2020 : LSH setup completed for FAAE domain. | Pre-requisites not met | 2019-12-04 05:30 | 2019-12-04 05:30 | Pre-requisites not met | 2020-05-05 05:30 |  |  | Awaiting inputs from DBD. Delayed as PPC3 implementation is in progress. [RAMACHA1, 5th Feb, 2021] Yet to receive updated rule file for PPC3. ZJ,ML,FAAE domain issues are pending resolution. DDPASS Success Rate = 86% [RAMACHA1, 10JUN2021] PPC3 and PPC4 DDPASS was conducted on 26th April, 2021. DDPASS Success Rate = 81%. FACM,ZJ,FAAE,LB issues identified. FACM issue requires PPC fix. Next follow up meeting scheduled on 15th June, 2021 | 81 | RaveX - Inhouse | Yes | LB(Masked), Y1, Y5 | [11 empty] | NA | [5 empty] | 7 | 27 | 67 | 0 | 289 | 865 | 0 | 184 | 36 | 248 | 1149 | 4 | 0 |  | Diabetes | No | Global | Open | Yes | [10 empty] | 2019-12-03 05:30 |  |  |  |  | Adi, Vishnupriya | Pioneer | Yes
CCGF166A1 | CCGF166X2201 | C1200254 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2014-06-23 05:30 |  | 2013-12-20 05:30 |  | Completed | 2020-01-06 05:30 | 2019-12-09 05:30 | 2020-04-06 05:30 | 2020-03-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A three-part, multicenter, open label, single dose study to assess the safety, tolerability, and efficacay of intra-labyrinthine (IL) CGF166 in patients with severe-to-profound hearing loss | CCGF166X2201 Hearing Restoration PoC study | N5 DAx - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:cmot@cmedresearch.com | [15 empty] | Sensorineural hearing loss | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CCGF166A1 | CCGF166X2202 | C1200723 | Phase II | NCDS | OC RDC - Inhouse |  | 2016-10-03 05:30 |  | DB Conduct | Final DBL | 2024-07-02 05:30 | 2015-12-21 05:30 |  | 2015-06-22 05:30 |  | Active | 2024-04-30 05:30 |  | 2024-07-02 05:30 |  | FALSE | RAINBOW | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - DAx | Long-term safety and efficacy follow-up study of CGF166 treated patients | CCGF166X2202 Long term safety follow-up | N5 DAx - NIBR | Langlo, Francois | Palav, Mahesh | Bhatkar, Priyanka | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | Samuel, Giftson | Meda, Sreelakshmi | [13 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | ICON | 2015-09-30 05:30 | 2015-09-30 05:30 | Meda, Sreelakshmi |  | NA | [7 empty] | 59 | 0 |  |  | 0 |  |  |  | 153 | 1 | 0 |  | Sensorineural hearing loss | No | Global | Open | Yes | [16 empty] | None of the above
CCGM097A1 | CCGM097X2101 | C1200242 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-03-20 05:30 |  | 2012-10-18 05:30 |  | Completed | 2020-07-01 05:30 | 2020-07-24 05:30 | 2020-09-04 05:30 | 2020-09-07 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A Phase I, open-label, multi-center, dose escalation study of oral CGM097, a p53/HDM2-interaction inhibitor, in adult patients with selected advanced solid tumors | CCGM097X2101 TCO Ph 1 advanced solid tumors study | N7 Oncology - NIBR | Langlo, Francois | Maritz, Henri | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Nicolas Carlo Blanco | Martin Klumpp |  | Gupta, Anshu | [15 empty] | Rohit Varate | [28 empty] | Syneos Health | Oncology | BP21 | INC | donna.cockram@incresearch.com | Earlier DBD: Jugnu Kumari |  |  | 293 | 0 | [10 empty] | Solid tumour | No | Global | Wind Down | Yes | [16 empty] | None of the above
CCJM112D | CCJM112X2202 | C1200682 | Phase I | NOVDD | [7 empty] | 2015-04-13 05:30 |  | 2014-12-08 05:30 |  | Completed |  | 2016-11-23 05:30 |  | 2017-01-27 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A randomized, double-blind, placebo controlled, multiple dose study to evaluate the clinical efficacy, safety, tolerability, dose relation, pharmacokinetics and pharmacodynamics of CJM112 in moderate to severe chronic hidradenitis suppurativa patients | CCJM112X2202 | N0 ATI - NIBR | [5 empty] | Kathryn Radford; Nicole Davis | Kath Radford | [67 empty] | No | Global | Completed | Yes | [16 empty] | None of the above
CCJM112E1 | CCJM112X2203 | C1001101 | Phase II | NCDS | CRO - EDC |  |  | 2018-02-20 05:30 | DB Locked |  |  | 2016-12-22 05:30 | 2017-11-28 05:30 | 2016-06-23 05:30 |  | Completed | 2019-06-28 05:30 | 2018-08-01 05:30 | 2018-10-15 05:30 | 2018-10-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, subject and investigator blinded, placebo-controlled, multi-center study in parallel groups to assess the efficacy and safety of CJM112 in patients with moderate to severe inflammatory acne. | CCJM112X2203 PIE PoC moderate severe inflam acne | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Maria Berkheimer | Maria Berkheimer | [15 empty] | Bothe, Dnyanesh |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | [12 empty] | CMED | [19 empty] | Acne; Acne aggravated; Acne comedonal; Acne follicular papular pustular etc; Acne papular | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCJM112F1 | CCJM112X2204 | C1200368 | Phase II | NCDS | CRO - EDC |  |  | 2017-11-10 05:30 | DB Locked |  |  | 2017-11-06 05:30 |  | 2017-06-15 05:30 |  | Completed | 2019-07-01 05:30 | 2019-07-08 05:30 | 2019-10-11 05:30 | 2019-10-11 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, subject- and investigator-blinded, placebocontrolled,\nmulti-center, multiple dose study to assess the\nefficacy and safety of CJM112 in patients with inadequately\ncontrolled moderate to severe asthma | CCJM112X2204 POC in Severe Asthma (low IgE/eos) | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Therese Swan | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | -NA-;#ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CCLG561A1 | CCLG561X2201A | C1200536 | Phase II | RAVE_RAW | [7 empty] | 2015-09-25 05:30 |  | 2015-06-09 05:30 |  | Completed | 2017-11-30 05:30 | 2017-12-01 05:30 | 2018-01-12 05:30 | 2018-01-16 05:30 | FALSE |  |  |  | Alcon InHouse |  | A randomized, multi-center, single masked, sham controlled, proof-of- concept study of intravitreal CLG561 as a monotherapy and in combination with LFG316 in subjects with geographic atrophy\n | CCLG561X2201A | N8 Ophthalmology - NIBR | [5 empty] | Jen Watts | Jen Watts | [66 empty] | Geographic atrophy | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCLL442A1 | CCLL442X2201 | C1200399 | Phase I | NCDS | CRO - EDC |  |  | 2018-03-01 05:30 | DB Locked |  |  | 2017-12-15 05:30 |  | 2017-09-06 05:30 |  | Completed | 2018-11-02 05:30 | 2018-11-01 05:30 | 2019-01-10 05:30 | 2019-01-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, Investigator-and patient-blind, placebo-controlled, parallel group first in human and proof of concept study to evaluate the safety, tolerability, and efficacy of CLL442 in patients with Cutaneous Squamous Cell Carcinoma in situ (SCCis) | CCLL442X2201 - FIH/PoC Squamous Cell Carcinoma | N5 DAx - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | [15 empty] | Sahu, Ahallad |  | Rohit Varate | [28 empty] | CMED | [19 empty] | Squamous cell carcinoma of skin | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCLR325A | CCLR325X2202 | C1200389 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-05-17 05:30 |  | 2015-10-01 05:30 |  | Completed | 2019-01-14 05:30 | 2019-01-14 05:30 | 2019-04-15 05:30 | 2019-04-17 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A randomized, subject and investigator-blind, placebocontrolled study of CLR325 in stable heart failure patients | CCLR325X2202 TM_Stable Heart Failure | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Diego Albrecht | Julie Mabille | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:amotrea@cmedresearch.com | [15 empty] | Heart failure | No | Global | Completed | Yes | [16 empty] | None of the above
CCMK389A0 | CCMK389A01101 | C4010835 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2022-01-21 05:30 | 2022-01-21 05:30 | 2022-02-05 05:30 | DB Conduct | Final DBL | 2022-09-26 05:30 | 2022-02-05 05:30 | 2021-10-05 05:30 | 2021-10-05 05:30 | 2022-01-05 05:30 | Active | 2022-08-08 05:30 |  | 2022-09-26 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | A randomized, participant and investigator-blinded, placebo-controlled, single ascending intravenous and single subcutaneous dose study to assess the safety, tolerability and pharmacokinetics of CMK389 in Japanese healthy participants | CCMK389A01101 ESS Japan | N5 DAx - NIBR | Langlo, Francois | SAKAKI, SAYAKA | Soni, Kushal | Tanada, Miyako | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | Suzuki, Hiroko | KADAM, NAVINA VIJAY | In Progress |  |  | 1. One Lab parameter is needed to raise new metadata request. However, it took time for confirming with CTT. Then, request raised by TDM on end of December. And then, Screen UAT and Rule file could be finalized. 2. DOA tool was not working as expected. DB setup initiation was delayed. |  | Bai, Chandrakala | Bai, Chandrakala | Completed | 21Jan-2022: RF v1.0 is finalized and the SNOW#05 ticket- RITM3407305 has been raised for LSH-PROD setup by Pratiksha(back-up). 12Jan2022: SNOW#05 - RITM3374493 for LSH-Test is created. 05-Jan-2022: Rule File version_1.0 has been finalized in Subway but since DQP is not finalized, SNOW#05 for LSH-Test is delayed. 29-Dec-2021: Initial Rule file is ready for finalization but since DQP is not finalized, SNOW#05 for LSH-Test is delayed. | None | None | 2022-01-21 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2022-02-02 | Completed | 2022-02-04 05:30 |  |  | 2022-02-04 05:30 | 2022-02-07 05:30 |  | 2022-02-08 05:30 |  |  |  | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 15 | 73 | 0 | 300 | 765 | 0 | 202 | 38 | 258 | 1061 | 0 | 0 |  | Pulmonary sarcoidosis | No | Global | Open | Yes | 2022-01-12 05:30 | Completed | 2022-01-27 05:30 | Completed | 2022-02-01 05:30 | 2022-02-02 05:30 |  |  |  |  | 2022-01-28 05:30 | [5 empty] | None of the above
CCMK389B1 | CCMK389B12201 | C4008946 | Phase II | Other | CRO - EDC |  |  | 2021-04-20 05:30 | DB Conduct | Final DBL | 2023-01-30 05:30 | 2021-04-20 05:30 | 2020-09-18 05:30 | 2020-09-21 05:30 |  | Active | 2022-11-01 05:30 |  | 2023-01-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, subject and investigator blinded, placebo-controlled multicenter study to assess the efficacy and safety of CMK389 in patients with moderate to severe atopic dermatitis | CCMK389B12201 Atopic Dermatitis PoC | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Navin Mahajan | Navin Mahajan | [15 empty] | Varate, Rohit |  | Rohit Varate | [13 empty] | 0 | [14 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Atopic dermatitis | No | Global | Open | Yes | [16 empty] | None of the above
CCMK389A1 | CCMK389X2201 | C1200686 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-11-08 05:30 | 2019-11-27 05:30 | 2020-09-24 05:30 | DB Conduct | Interim DBL | 2022-06-03 05:30 | 2020-09-23 05:30 | 2019-05-24 05:30 | 2019-05-23 05:30 |  | Active | 2023-03-13 05:30 |  | 2023-05-17 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A subject and investigator blinded, randomized, placebo-controlled, repeat-dose, multicenter study to investigate efficacy, safety, and tolerability of CMK389 in patients with chronic pulmonary sarcoidosis | CCMK389X2201 Chronic Pulmonary Sarcoidosis | N5 DAx - NIBR | Langlo, Francois | Malik, Arpit | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Julie Mabille; Kathryn Bizzozero | Julie Mabille | Yadav, Priyanka | Thomas, Ankit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 08Nov2019 |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 12Nov2021:RF v70 is finalized in CREDI for PPC#06 updates. 01Jul2021: RF v6.0 is finalized in CREDI for PPC#05 updates. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021: No Activity, latest RF version 5.0 21-Jan-2021: Sent follow-up email to LSP Vishnupriya Adi to confirm whether DTS setup is done in LSH or not. 05Nov2020: No Activity. 11Sep2020: RF updated and raised SNOW ticket on 08Sep2020 for MO1L. 02Sep2020 : As per 02Sep2020 missing forms DTS report MO1L pending . Praveen to update 11Aug2020 : MO1L listed in 20jul report & 04Aug2020 report. Received DTS from DBD on 21stJul2020. Expected to complete by 17thAug. 27Jul2020 : MO1L listed in 20jul report 06Jul2020: Rule File V3.0 is the latest version. 25Feb2020: RF v3.0 finalized with 'RE1L' dts included. 06Jan2020: RFv2.0 finalized with LB dts 18Nov2019: RF v1.0 finalized. Pending Form/DTS: Steriod Titration Form. No DTS finalized yet. Ashok Sama to Praveen to chankrakala | None | None | 2019-11-28 05:30 |  | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2019-11-28 | Completed | 2019-12-03 05:30 |  |  | 2019-12-03 05:30 | 2019-12-03 05:30 |  | 2020-08-26 05:30 |  |  | FPFV Date is yet to be confirmed by the TDM. | 77 | RaveX - Inhouse | Yes | ZK;#Y1 | [11 empty] | NA | [5 empty] | 8 | 13 | 60 | 0 | 162 | 556 | 0 | 183 | 37 | 198 | 791 | 3 | 0 |  | Pulmonary sarcoidosis | Yes | Global | Open | Yes | [10 empty] | 2019-12-02 05:30 |  |  |  |  | Gouni, Harita | None of the above | Yes
CCNP392A1 | CCNP392A12201 | C4011645 | Phase II | [12 empty] | Stopped (with patients) | 2025-02-07 05:30 | [7 empty] | ED Undecided Sourcing |  |  | CCNP392A12201 CNP ssDry Eye POC | N8 Ophthalmology - NIBR | [6 empty] | Valerie Brooks | [66 empty] | Dry eye | No | Global | Terminated | Yes
CCNP520A | CCNP520A2001 | C3003583 | Not Applicable | Other | Other |  |  | 2019-01-31 05:30 | DB Locked |  |  | 2019-01-17 05:30 | 2018-04-25 05:30 | 2018-04-26 05:30 |  | Active | 2025-06-26 05:30 |  | 2025-09-08 05:30 | 2019-08-29 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Prospective observational cohort study on natural disease progression and burden across the entire Alzheimerâs spectrum (iMAP study) | CCNP520A2001 iMAP | P4 Neuroscience | Chaghasbanian, Harut | Dhuri, Sejal | Dhuri, Sejal | Purra, Shashikanth | Nair, Sreesha |  | Matthew Quinn | [17 empty] | Amit Agavekar | [28 empty] | CMED | [19 empty] | Alzheimer's disease | No | Global | Terminated | Yes | [16 empty] | None of the above
CCNP520A | CCNP520A2202J | C1001103 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-06-09 05:30 |  | DB Locked | Final DBL | 2020-06-30 05:30 | 2017-08-03 05:30 |  | 2016-12-22 05:30 |  | Completed | 2020-04-30 05:30 |  | 2020-06-30 05:30 |  | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy of two doses of CNP520 in participants at risk for the onset of clinical symptoms of AD | CCNP520A2202J Pivotal | P4 Neuroscience | Chaghasbanian, Harut | Joglekar, Prajakta | Dhuri, Sejal | Purra, Shashikanth | Nair, Sreesha | Matt Quinn | Matthew Quinn | Narasetty, Indumathi | Meda, Sreelakshmi | [13 empty] | Tidke, Shyam | Tidke, Shyam | Amit Agavekar | [13 empty] | 100 | RaveX - Inhouse | Yes |  | 2021-06-11 05:30 | 2021-06-14 05:30 |  |  | Pharma | Novartis | ICON | 2017-06-09 05:30 | 2017-06-09 05:30 | Meda, Sreelakshmi | Rajhans, Khushbu Kumari | NA | [7 empty] | 204 | 0 |  |  | 0 |  |  |  | 710 | 25 | 0 |  | Alzheimer's disease | Yes | Global | Wind Down | Yes | [16 empty] | None of the above | Yes
CCNP520A0 | CCNP520X1101 | C1001104 | Phase I | NOVDD | [7 empty] | 2015-10-01 05:30 |  | 2015-06-29 05:30 |  | Completed |  | 2016-02-12 05:30 |  | 2016-04-15 05:30 | FALSE |  |  |  | ED Outsourced |  | A randomized, double-blind, placebo-controlled, single ascending and multiple oral dose study, to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of CNP520 in Japanese healthy adult and elderly subjects | CCNP520X1101 JPN MAD/SAD | P4 Neuroscience | [5 empty] | YASUYUKI TABEI | YASUYUKI TABEI | [66 empty] | Alzheimer's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CCNP520A0 | CCNP520X2102 | C1200668 | Phase I | NOVDD | [7 empty] | 2015-08-10 05:30 |  | 2015-05-04 05:30 |  | Completed |  | 2016-03-11 05:30 |  | 2016-05-24 05:30 | FALSE |  |  |  | ED Outsourced |  | A randomized, double-blind, placebo-controlled, parallel-group study to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of multiple oral doses of CNP520 in healthy elderly subjects | CCNP520X2102 | P4 Neuroscience | [5 empty] | Marie-Laure Rouzade-Dominguez | Denise Serra | [66 empty] | Alzheimer's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CCNP520A0 | CCNP520X2103 | C1001105 | Phase I | NOVDD |  |  |  |  | DB Locked |  |  | 2016-01-04 05:30 |  | 2015-10-09 05:30 |  | Completed |  | 2016-03-25 05:30 |  | 2016-05-09 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - NS |  | Rel BA CSF vs MF CCNP520X2103 | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Brian Flannery | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [28 empty] | NA | [19 empty] | Dementia Alzheimer's type | No | Global | Completed | No | [16 empty] | None of the above
CCOA566A | CCOA566A1401 | C1200423 | Phase IV | Other | Paper |  |  | 2018-06-01 05:30 | DB Conduct | Final DBL | 2023-05-31 05:30 | 2018-02-16 05:30 | 2017-01-26 05:30 | 2017-01-26 05:30 |  | Active | 2023-01-31 05:30 |  | 2023-05-31 05:30 |  | FALSE | Japan PMS | Indu Bala | Cluster C (fGSK,IHD,Sandoz) | Outsourced | Rare Diseases |  | CCOA566A1401 JPN PMS | P6 Global Health | YAMADA, KAYO | Ichinowatari, Mihoko | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MAKOTO NAGASAKI | MAKOTO NAGASAKI | [17 empty] | Sai Krishna Mettugari | [28 empty] | Other | [19 empty] | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CCOA566A | CCOA566A2402 | C4004858 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2020-03-10 05:30 | 2020-04-07 05:30 | 2020-10-05 05:30 | DB Locked | Final DBL Achieved |  | 2020-10-13 05:30 | 2019-10-29 05:30 | 2020-04-16 05:30 |  | Completed | 2021-04-01 05:30 | 2021-03-18 05:30 | 2021-05-04 05:30 | 2021-05-04 05:30 | FALSE | Non – Interventional Study | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | Management of Malaria in African Countries: A multicenter, Prospective, non-interventional study | CCOA566A2402 Malaria management in Africa (NIS) | P6 Global Health | Vithala, Srinivas | Mayakrishnan, Amritaraj | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Marc Cousin | Marc Cousin | Sinha, Deepakshi | Thomas, Ankit | Not Started |  | 10Oct2019 : email from DM GH Unni :DBD assignment for the CCOA566A2402- Global Health study. (CCOA566A2402 – DB Go-Live date is 10th Mar 2020, FPFV on 15th Apr 2020.) |  | DRM |  | Patnaik, Angella | Completed | 04-MAY-2021: Final Database Lock for CCOA566A2402 was achieved successfully. 05-APR-2021: SNOW#51 raised for SMT update due to PPC#4. No impact on Rule File. 11-FEB-2021: RF Version 5.0 finalized in CREDI for PPC 2 updates. SNOW# 51 raised for SMT and LSH updates. 26JAN2021: RF Version 4.0 finalzied in CREDI for SDTM annotations update. SNOW# 51 raised for SMT and LSH updates. 25JAN2021: Updated RF Version 4.0 for the SDTM annotations (FACE, SS, MB domains). Released for Peer Review. 05OCT2020: No RF updates required for PPC1. SMT and LSH updates requested to team. 23SEP2020: IA for PPC1 provided. No impact on RF. SMT and LSH updates highlighted to DBD. 07-JUL-2020: No DB updates or DTS received post RF V1.0 finalization. 08Apr2020 : raised snow ticket today for SMT and LSH setup. 3APR2020: RF V1.0 finalized in CREDI. Awaiting PROD ALS for raising the SNOW#05 request. 31MAR2020: RF Peer review comments updated and released for Peer review. 24APR2020: Updated ALS received for RF development. 17MAR2020: Received the RF comments from Peer Reviewer. Study team to add new forms to the DB, hence Go-live is postponed to 27MAR2020. Awaiting updated ALS to re-build RF. 09MAR2020: DB set-up issues sent to DBD for updates. 03MAR2020: SRF and Screen review started. 02MAR2020: ALS, SRFs and SDTM annotations received for RF development. 07Feb2020 : SRFs received on 06Feb2020 Study specific forms reviewed and provided feedback. Yet to start with RF. Screens not final yet. | None | None | 2020-04-08 05:30 |  | Nidamanuru, Kalyan Kumar | Kadam, Sandeep | Sai Krishna Mettugari | Completed | 2020-04-30 | Completed | 2020-05-12 05:30 |  |  | 2020-05-22 05:30 | 2020-05-27 05:30 |  | 2020-08-24 05:30 |  |  | FPFV IS ON 5-COT-2020 |  | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 5 | 3 | 22 | 0 | 31 | 219 | 0 | 63 | 3 | 109 | 331 | 1 | 0 |  | Malaria | No | Global | Open | Yes | [10 empty] | 2020-05-11 05:30 | [5 empty] | None of the above
CCOA566B | CCOA566B2306 | C1200261 | Phase III | NOVDD | [7 empty] | 2012-10-08 05:30 |  | 2012-02-20 05:30 |  | Completed |  | 2014-07-08 05:30 |  | 2014-07-30 05:30 | FALSE |  |  |  | Outsourced |  | Efficacy safety PK study Pf malaria in infants &lt; 5 kg | CCOA566B2306 Coartem dispersible in infants < 5kg | P6 Global Health | [5 empty] | Marc Cousin | Marc Cousin | [66 empty] | Malaria | No | Global | Draft | [17 empty] | None of the above
CCOA566B | CCOA566B2307 | C4003719 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-09-30 05:30 | 2020-08-21 05:30 | 2021-01-07 05:30 | DB Conduct | Final DBL | 2023-04-21 05:30 | 2020-12-21 05:30 | 2019-12-12 05:30 | 2019-12-12 05:30 |  | Active | 2023-12-02 05:30 |  | 2023-04-21 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health |  | CCOA566B2307 new A-L formulation for infants <5kg | P6 Global Health | Vithala, Srinivas | Mayakrishnan, Amritaraj | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Marc Cousin | Marc Cousin | Gupta, Anshu | Kumari, Jyoti |  |  | moved from 27jul2020 to 12-Aug-2020. As there are screen and dynamics update came as new requirement after Screen UAT. 12th Aug DB Live moved to next week due to 1. CCG link not initiated by TDM 2. Co moved to 01Apr2020 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 30Sep2019 |  | DRM |  | Patnaik, Angella | Completed | 22-OCT-2021: RF Version 5.0 finalized for PPC #2 updates. SNOW#51 raised for SMT and LSH updates. 17-JUN-2021: RF Version 4.0 finalized for LB domain updates as per the SMT requirements. SNOW#51 raised for SMT and LSH updates. 23-MAR-2021: RF Version 3.0 finalized for mapping Subject Status information to SS domain as per SDTM team's request. SNOW#51 raised for SMT and LSH updates. 02-MAR-2021: No RF updates for PPC1. SNOW#51 has been raised for SMT and LSH updates. 08-OCT-2020: RF V2.0 finalized for DTS table addition - MB2L, PF1L. SNOW#51 raised and LSP informed on SMT and LSH updates. 21-AUG-2020: RF final in CREDI. SNOW#05 raised for LSH set-up. 10-AUG-2020: Peer Review comments received. Discussion ongoing with TDM, SDTM Programmer. 05-AUG-2020: RF released for Peer Review. 23JUL-2020: Received updated ALS for RF development; 07-JUL-2020: RF creation in progress. DB issues highlighted to DBD. Awaiting updated ALS for completing the RF and initiating the Peer Review. 24-JUN-2020: SRF and ALS Review ongoing. 27-APR-2020: RF not initiated. Go-live pushed to 27-JUL-2020. 14-APR-2020: No documents received from DBD for RF dev. Follow-up email sent to DBD. Provided feedback on SRFs and SS. 18-MAR-2020: Sent a reminder to DBD for UAT status and ref documents to start RF development. | None | None | 2020-08-21 05:30 |  | Praveen kumar, Chakka Giri | Praveen kumar, Chakka Giri | Sai Krishna Mettugari | Completed | 2020-10-28 | Completed | 2020-11-03 05:30 |  |  | 2020-11-03 05:30 | 2020-11-03 05:30 |  | 2020-12-22 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 4 | 11 | 84 | 0 | 98 | 1124 | 1 | 309 | 38 | 401 | 1563 | 3 | 0 |  | Malaria | No | Regional | Open | Yes | [10 empty] | 2020-10-28 05:30 | [5 empty] | None of the above | Yes
CCPK850A1 | CCPK850X2202 | C1200349 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-09-11 05:30 | 2018-08-22 05:30 | DB Conduct | Final DBL | 2028-05-04 05:30 | 2018-08-22 05:30 | 2018-03-28 05:30 | 2017-11-17 05:30 |  | Active | 2027-08-09 05:30 |  | 2028-05-04 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | An open-label first-in-human single ascending dose study to explore the safety, tolerability and efficacy of subretinal administration of CPK850 gene therapy in patients with retinitis pigmentosa caused by mutations in the RLBP1 gene | CCPK850X2202 FIH/POC | N8 Ophthalmology - NIBR | Langlo, Francois | Gundu, Ananth Reddy | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Karen Holopigian | Karen Holopigian | Oguri, Praveen | Thomas, Ankit | In Progress |  |  |  | DRM (DIAL) | Rana, Aamir | Patnaik, Angella | Completed | 22-JUL-2021: RF Version 18.0 finalized for PPC #9 updates. SNOW#51 raised for LSH updates. 21Jul2021 : Forms DSG005, OPS001, QS1S721 reflecting in 21Jul report. 11-FEB2-2021: RF V17.0 finalized for ZW1 intermediate table name update. SNOW#51 raised for LSH updates. 8-FEB-2021: RF V16.0 finalized and SNOW#51 raised for LSH updates. 8-FEB-2021: RF V16.0 updated for re-mapping ZW2L DTS table to ZW1 domain. Released for Peer Review. 24-DEC-2020: RF V15.0 finalized and SNOW#51 raised for LSH updates. 23-DEC-2020: RF V15.0 released for Peer Review for PPC8 updates. 09-OCT-2020: RF V12.0 finalized for LB1L DTS table addition. SNOW#51 raised and LSP notified. 07-JUL-2020: RF up to date for all final DTS and PPPCs implemented in the study. 09APR2020: Rule file finalized for ZXS006 and DTS tables ZW2L, ZW3L. SNOW#51 raised for LSH update. 03APR2020: RF V11.0 updated for DTS and ZXRESN Format issue. Pending SDTM input for ZXS006 form. 07Feb2020 : PPC 4 updates for DS implemented and SNOW 51 raised. 7-JAN-2020: Rule file updated and finalized for ZW domain (Nikhil supported). 2-JAN-2020: SMT comments on missing results variable for ZW Domain. | None | None | 2018-11-22 05:30 |  | Nagalla, Lakshmi Naga Lavanya | Varate, Rohit | Rohit Varate | Completed | 2018-12-03 | Completed | 2019-05-28 05:30 | domains published to DIAL: AE,CM,DM,DS,DV,EC,IE,LB,MH,ODM,PR,SC,VS,ZW,ZX,QS,TV,SV |  | 2018-11-28 05:30 | 2018-11-28 05:30 | SNOW 05 was raised after FPFV, Pre-requisites not met | 2019-07-23 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | AE;#CM;#MH;#PR | [11 empty] | NA | [5 empty] | 13 | 23 | 81 | 0 | 617 | 886 | 0 | 197 | 33 | 354 | 1273 | 10 | 0 |  | Retinopathy | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-05-24 05:30 | [5 empty] | None of the above
CCSJ117A1 | CCSJ117A12201C | C3004595 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-06-15 05:30 | 2020-08-13 05:30 | 2020-09-08 05:30 | DB Conduct | DB Snapshot | 2022-04-11 05:30 | 2020-09-09 05:30 | 2020-01-31 05:30 | 2020-01-28 05:30 |  | Active | 2022-12-15 05:30 |  | 2023-02-02 05:30 |  | FALSE | Pioneer | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 12-week, multicenter, randomized, double-blind, parallel arm, placebo-controlled study to assess the efficacy and safety of CSJ117, when added to existing asthma therapy in patients â¥18 years of age with severe uncontrolled asthma | CCSJ117A12201C CSJ117A1 Ph2b_DRF study | P8 Respiratory | Mahajan, Vinay | Vangara, Soundarya | Dubey, Rohit | Regula, Ramakrishna | Hiriyanna, Srinivas | Elaine Askin | Elaine Louise Askin | Kancharla, Susmita | Iliyas, Mohamed | Completed | 2021-05-20 05:30 | 14-Nov-2021 - Jyoti transitioned study to Iliyas Moved from 07 AUg to 14th Aug Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Jun2020 |  | DRM | Sama, Ashok | Choppadandi, Kranthikumar | Completed | 18-Jun-2021: ECDOSFRM field added as constant as per the CTT(SDTM) request 20-May-2021: RF finalized and raised SNOW ticket for FAMH domain 16-Apr-2021: RF finalized and raised SNOW ticket 14-Apr-2021: RF Updated for PPC02 and released for peer review 11-Feb-2021: SNOW ticket has been raised to update LSh for PPC#01 06-Nov-2020: RF_Version 4.0 is finalized for LB DTS 25-Sep-2020: Updated RF to include DX1L and released for peer review. 13-Aug-2020: RF V1.0 is final in CREDI and raised SNOW05 ticekt for SMT/LSH setup. 06Jul2020 : RF transitioned from Ashok to Kranthi. Ashok to support until he breaks for leave. | None | None | 2020-08-13 05:30 |  | Sundar, N Sushant | Sundar, N Sushant | Sushant Sundar | Completed | 2020-09-10 | Completed | 2020-09-10 05:30 |  | Pre-requisites not met | 2020-09-10 05:30 | 2020-09-10 05:30 | Pre-requisites not met | 2020-09-18 05:30 |  |  |  | 42 |  |  | -NA- | [11 empty] | NA | [5 empty] | 6 | 13 | 48 | 0 | 106 | 728 | 0 | 224 | 37 | 140 | 905 | 12 | 0 |  | Asthma | No | Global | Open | Yes | [10 empty] | 2020-09-04 05:30 | [5 empty] | None of the above
CCSJ117A1 | CCSJ117A12201E1 | C4006566 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-08-10 05:30 | 2021-08-11 05:30 | 2021-09-28 05:30 | DB Conduct | DB Snapshot | 2022-04-11 05:30 | 2021-09-08 05:30 | 2021-06-01 05:30 | 2021-04-14 05:30 |  | Active | 2023-06-02 05:30 |  | 2023-07-14 05:30 |  | FALSE | Pioneer | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CCSJ117A12201E1 Ph2 safety extension | P8 Respiratory | Mahajan, Vinay | Vangara, Soundarya | Dubey, Rohit | Regula, Ramakrishna | Hiriyanna, Srinivas | Michele Valentin | Michele Valentin | Rachakonda, Hima Sailaja | Iliyas, Mohamed |  |  | Nov - Hima transitioned study to Iliyas 29Apr2021: Not yet started initial golive 10Aug2021 when DBD assigned |  | DRM | Kuttoboina, Sujan Kumar | Saha, Saikat | Completed | 11Feb2022: The DBD shared the PPC#1 IA for review. Reviewed and provided the comments and asked for LSPs confirmation. 17Jan2022: Updated the RF with the EG DTS and finalized in CREDI. Both RF and Checklist have been finalized, SNOW51 request raised and notified the LSP. 12Jan2022: Received the updated EG DTS for review and sent back my review comments. 28Dec2021: RF and Checklist finalized with the RE and QS dts. Snow 51 ticket RITM3334116 has been raised and informed the LSP. 23Dec2021: Provided the DTS review comments for EG DTS 20Dec2021: RF updated with the RE, QS DTS details and released for peer review. 13Dec2021: Received RE, QS and EG DTS for review. Reviewed and provided all the comments. 6Dec2021: RF and Checklist finalized in the SubWay. SNOW 51 raised and notified LSP. 3Dec2021: LB1L DTS received and added that into the RF. RF released for peer review. 10Nov2021 : RF and Checklist have been finalized in the CREDI. SNOW 51 request has been raised and notified the LSP. 8Nov2021 : Received the IRT DTS from the DBD for review. Reviewed and sent it back with the comments in it. Released the RF for peer review. 12Aug2021 : Rule file version 1.0 has been finalized and SNOW 05 (RITM2869508) request has been created for LSH set-up. 11Aug2021 : Study has been pushed to production. 10Aug2021 : DBD confirmed that the go-live date has been pushed to 11-Aug-2021. 09Aug2021 : Reassigned from Sujan to Saikat. 05AUG2021 : The go-live date has been pushed to 10AUG2021. 21JUL21: Go-Live is on 4-Aug-2021. RF developed by Saikat and peer review is ongoing. On top of this, New pages have been added on 21-JUL-21 and again RF has to be updated as per latest changes. 06JUL21: The expected DB go-live is on 27JUL2021. Lead DBD shared all the required documents, Saikat is working on Rule file development activities. 09JUN21: Following up with lead DBD about go-live activities 26May2021: RF developer assigned | None | None | 2021-08-12 05:30 |  | Sundar, N Sushant | Sundar, N Sushant | Sushant Sundar | Completed | 2021-08-31 | Completed | 2021-08-31 05:30 |  |  | 2021-08-31 05:30 | 2021-08-31 05:30 |  | 2021-09-06 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 14 | 49 | 0 | 117 | 686 | 0 | 204 | 39 | 131 | 856 | 8 | 0 |  | Asthma | No | Global | Open | Yes | [10 empty] | 2021-08-30 05:30 | [5 empty] | None of the above
CCSJ117A1 | CCSJ117A12204 | C4008408 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-06-20 05:30 | DB On hold | Final DBL | 2024-10-28 05:30 |  | 2023-01-09 05:30 |  |  | Planned | 2024-09-23 05:30 |  | 2024-10-28 05:30 |  | FALSE | No priority assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CCSJ117A12204 CSJ117A1 Profiling study | P8 Respiratory | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas | Therese Swan | Therese Swan | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CCSJ117A1 | CCSJ117A12301C | C4001353 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-06-20 05:30 | Study Planned | Final DBL | 2025-02-12 05:30 |  | 2023-01-30 05:30 |  |  | Planned | 2024-12-30 05:30 |  | 2025-02-12 05:30 |  | FALSE | No priority assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CCSJ117A12301C Ph3 exacerbation study | P8 Respiratory | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Ryan Ayers | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CCSJ117A1 | CCSJ117A12303C | C4001820 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-07-24 05:30 | Study Planned | Final DBL | 2026-02-19 05:30 |  | 2023-03-03 05:30 |  |  | Planned | 2026-01-07 05:30 |  | 2026-02-19 05:30 |  | FALSE | No priority assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CCSJ117A12303C OCS sparing Ph3 study | P8 Respiratory | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Ryan Ayers | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CCSJ117B1 | CCSJ117B12201 | C4010604 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-06-01 05:30 | 2021-08-12 05:30 | 2021-09-15 05:30 | DB Conduct | Final DBL | 2023-10-18 05:30 | 2021-09-24 05:30 | 2021-03-15 05:30 | 2021-04-01 05:30 | 2021-06-15 05:30 | Active | 2023-09-06 05:30 |  | 2023-10-18 05:30 |  | FALSE | Pioneer | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 12-week, randomized, participant-and investigator-blinded, placebo-controlled, parallel group study to explore the efficacy, pharmacodynamics, safety, and pharmacokinetics of two doses of inhaled CSJ117 in adults with Chronic Obstructive Pulmonary Disease (COPD) | CCSJ117B12201 COPD PiEPOC Study | N5 DAx - NIBR | Mahajan, Vinay | Chopra, Pankaj | Dubey, Rohit | Regula, Ramakrishna | Hiriyanna, Srinivas | Ioannis Strigkas | Ioannis Strigkas | Kabra, Pratik Govind | Iliyas, Mohamed | Completed | 2021-09-27 05:30 | 13May2021 : Dynamics programming has not been started yet as confirmations on specs (collation list) are not yet received from the team. Highlighted the risk of delay to TDM/PDM for the timelines. 28Apr2021 : CRF build in progress. Next week plan for Dynamics. FPFV - 19Jul2021 requested TDM to update the same. Go-live date has been pushed to 22-Jun-2021 due to delay in protocol finalization. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 13Aug2021 : Rule File version 1.0 is now finalized in SUBWAY and SNOW-05 Ticket is also raised with ticket number-RITM2872760 for LSH setup. 04Aug2021: Peer review is completed. DBD informed Go-Live shifted to 12th Aug 2021. 8July2021: Communication shared regarding Go-Live shifted to 4th Aug 2021. 7July2021: CCSJ117B12201_Rule file_version 0.1 has been released for Peer Review. 5July2021: Rule file development has been started. 24June2021: DBD shared the remaining two form with SDTM Annotation for review. 11May2021: DBD shared the updated Activity Planner , Approved SRFs, ALS and SDTM Annotation of 3 study specific forms for review. Review ongoing. Two forms are under discussion with study team. It will be shared once specs are received from study team and built in database. 06May2021: Requested the DBD to share the Activity Planner and status of Screen UAT. 03May2021 : DBD contacted for few inputs on CRFs. Yet to receive Study specific forms for review. Following up with DBD 17Feb2021: RF developer assigned. | None | None | 2021-08-13 05:30 |  | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2021-08-27 | Completed | 2021-08-29 05:30 |  |  | 2021-08-30 05:30 | 2021-08-30 05:30 |  | 2021-08-30 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 10 | 59 | 0 | 110 | 668 | 0 | 200 | 41 | 166 | 875 | 13 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [10 empty] | 2021-08-26 05:30 | [5 empty] | None of the above
CCSJ117B1 | CCSJ117B12301 | C4010647 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-06-13 05:30 | Study Planned | Final DBL | 2025-07-30 05:30 |  | 2023-01-27 05:30 |  |  | Planned | 2025-06-25 05:30 |  | 2025-07-30 05:30 |  |  | No priority assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CCSJ117B12301 COPD Ph3 Study | N5 DAx - NIBR | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Ryan Ayers | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 60 | [7 empty] | 1000 | 8 |  |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes
CCSJ117A0 | CCSJ117X1101 | C3004119 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-28 05:30 | 2018-07-11 05:30 | DB Locked | Final DBL Achieved |  | 2018-07-04 05:30 | 2018-04-23 05:30 | 2018-04-25 05:30 |  | Completed | 2018-09-07 05:30 | 2018-09-07 05:30 | 2018-10-19 05:30 | 2018-10-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, subject and investigator-blind, placebo-controlled, and single ascending dose study to assess the safety, tolerability and pharmacokinetics of CSJ117 in Japanese and Caucasian healthy male subjects. | CCSJ117X1101 Japan ES | P8 Respiratory | Langlo, Francois | Hagiwara, Yayoi | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | Suzuki, Hiroko | Suzuki, Hiroko |  |  |  |  | Pre-DRM | Suzuki, Hiroko | Suzuki, Hiroko | Completed | Study Locked | Study Locked | Study Locked | 2018-07-05 05:30 | Legacy Process | Sahu, Ahallad |  | Rohit Varate | Completed | 2018-07-17 | Not Applicable |  | Ahallad Sahu, LSP for this locked study is currently on leave. The LSH setup request date will be updated as soon as the information is received. |  | 2018-07-24 05:30 | 2018-07-24 05:30 | [6 empty] | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 9 | 68 | -1 | 97 | 467 | 0 | 125 | 32 | 211 | 710 | 1 | 0 |  | Asthma | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCSJ117A0 | CCSJ117X2101 | C1200446 | Phase I | NCDS | [7 empty] | 2016-08-01 05:30 |  | 2016-05-05 05:30 |  | Completed |  | 2017-02-09 05:30 |  | 2017-04-03 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A first-in-human, randomized, subject-blind, placebo controlled, single ascending dose study to assess the safety, tolerability and pharmacokinetics of CSJ117 in adult healthy subjects | CCSJ117X2101 | P8 Respiratory | [5 empty] | Jul Schofield | Jul Schofield | [66 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CCSJ117A1 | CCSJ117X2201 | C1200454 | Phase I | NCDS | CRO - EDC |  |  | 2017-12-22 05:30 | DB Locked |  |  | 2017-12-18 05:30 |  | 2017-05-22 05:30 |  | Completed | 2019-07-16 05:30 | 2019-07-16 05:30 | 2019-11-08 05:30 | 2019-11-08 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CCSJ117X2201 Bronchial Provocation in mild asthma | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Therese Swan | [15 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | [12 empty] | CMED | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CCSJ137A | CCSJ137X2201 | C1200649 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-09-22 05:30 |  | 2015-06-05 05:30 |  | Completed | 2020-05-13 05:30 | 2020-05-13 05:30 | 2020-07-31 05:30 | 2020-07-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A first-in-human, two-part (open label, and randomized/double blind/placebo controlled), single- and repeat-dose study of CSJ137 in erythropoietin-treated chronic hemodialysis patients with functional iron-deficiency anemia | CCSJ137X2201 FIH/PoC | N5 DAx - NIBR | Langlo, Francois | Bhatkar, Priyanka | Bhatkar, Priyanka | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Ewa Kubiak | Ewa Kubiak | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:emitarvatasescu@cmedresearch.com | cmedresearch.com | [14 empty] | Anaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CCSJ148A0 | CCSJ148X2201 | C1200665 | Phase I | NOVDD | [7 empty] | 2015-06-02 05:30 |  | 2014-05-29 05:30 |  | Completed |  | 2016-12-07 05:30 |  | 2017-02-27 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A multi-center, randomized, double-blind, placebo controlled, study to evaluate the efficacy and safety of CSJ148 compared to placebo to prevent human cytomegalovirus (HCMV) replication in stem cell transplant patients | CSJ148X2201 | P6 Global Health | [5 empty] | Kristin Belmore | Kristin Belmore | [67 empty] | No | Global | Completed | Yes | [16 empty] | None of the above
CCSJ148B1 | CCSJ148X2202 | C1200435 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-03-25 05:30 |  | DB On hold | Final DBL | 2022-12-27 05:30 |  |  | 2017-08-14 05:30 |  | Stopped (with patients) | 2022-11-15 05:30 |  | 2022-12-27 05:30 |  | FALSE | Not Applicable | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ID | A multicenter, randomized, patient, investigator and sponsor blinded, placebo-controlled phase II study to evaluate the efficacy and safety of CSJ148 in pregnant women with primary HCMV infection | CCSJ148X2202 | N3 Infectious Diseases - NIBR | Langlo, Francois | Palav, Mahesh | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Natalia Baginski | Shrivastava, Nikhil | Shrivastava, Nikhil |  |  | Study in production and got cancelled | [10 empty] | Sharma, Anju |  | Rohit Varate | [28 empty] | NA | [5 empty] | 1 | 14 | 67 | -1 | 194 | 424 | 0 | 135 | 38 | 299 | 761 | 0 | 0 |  | Cytomegalovirus infection | No | Global | Terminated | Yes | [16 empty] | None of the above
CCTL019A | CCTL019A2201 | C1001107 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-01-02 05:30 |  | 2015-03-05 05:30 |  | Completed | 2017-12-13 05:30 | 2017-12-13 05:30 | 2018-03-15 05:30 | 2018-04-06 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Dose optimization trial of autologous T Cells engineered to express anti-CD19 chimeric antigen receptor (CART-19) in patients with relapsed or refractory CD19+ chronic lymphocytic leukemia (CLL) | CCTL019A2201 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Hemnani, Nisha | Sarkhel, Biswadip | Rengarao, Sanjai Kumar Surya | Nair, Sreesha |  | Renata Zieba |  | Gandla, Prashanth | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | BP21 | PPD | mailto:Christopher.Floyd@ppdi.com | Earlier DBD: Asha Rajanna | [14 empty] | Leukaemia | Yes | Local | Completed | Yes | [16 empty] | None of the above
CCTL019A0 | CCTL019A2205B | C1001108 | Not Applicable | NCDS | OC RDC - Inhouse | 2015-05-08 05:30 | 2015-05-08 05:30 |  | DB Conduct | DB Snapshot | 2022-06-14 05:30 | 2015-11-02 05:30 |  | 2014-10-03 05:30 |  | Active | 2036-02-22 05:30 |  | 2036-04-04 05:30 |  | FALSE | LTFU study, submission once in 5 years. Every year there will be a ASR (Annual Safety report) snapshot | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Long Term Follow-Up of Patients Exposed to Lentiviral-based CAR T-Cell Therapy | CCTL019A2205B_Long Term Follow Up | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kambal, Sundeep | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Vishal Mishra | Vishal Mishra | Tadiparthy, Ramakanth | Mareedu, Vasu |  | 2020-01-02 05:30 | [11 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [12 empty] | Planned DDPASS in Q2 | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2015-05-08 05:30 | 2015-05-08 05:30 | Mareedu, Vasu |  | NA | [7 empty] | 45 | 0 |  |  | 0 |  |  |  | 770 | 5 | 0 |  | Acute lymphatic leukaemia; Chronic lymphocytic leukaemia; Diffuse large B-cell lymphoma; Follicular B-cell non-Hodgkin's lymphoma; Leukaemia; Multiple myeloma; Non-Hodgkin's lymphoma; T-cell lymphoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CCTL019B | CCTL019B1401 | C4001762 | Phase IV | Other | Other |  |  | 2021-02-26 05:30 | DB Conduct | Final DBL | 2028-02-28 05:30 | 2019-10-30 05:30 | 2019-04-30 05:30 | 2019-04-10 05:30 |  | Active | 2028-02-28 05:30 |  | 2028-02-28 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology |  | CCTL019B1401 Japan PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | KASAHARA, TETSUYA | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | HARUKA NISHIOKA | KEIKO FUJINO | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Acute lymphoblastic leukaemia; Diffuse large B-cell lymphoma | No | Global | Open | Yes | [16 empty] | None of the above
CCTL019B | CCTL019B2101J | C1001113 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-03-15 05:30 |  | 2010-12-15 05:30 |  | Completed | 2018-06-15 05:30 | 2018-05-07 05:30 | 2018-08-10 05:30 | 2018-09-20 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A Phase I/IIA Study of Redirected Autologous T Cells Engineered to Contain Anti-CD19 Attached to TCR zeta and 4-1BB Signaling Domains in Patients with Chemotherapy Resistant or Refractory CD19+ Leukemia and Lymphoma | CCTL019B2101J PI Ped r/r ALL/L3-M (Penn/CHOP959) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Mohapatra, Ruchi | Sarkhel, Biswadip | Rengarao, Sanjai Kumar Surya | Nair, Sreesha |  | Renata Zieba |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | BP21 | PPD | mailto:Aditi.Shah@ppdi.com | Earlier DBD: Asha Rajanna | [14 empty] | Acute lymphoblastic leukaemia | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCTL019B | CCTL019B2202 | C1001114 | Phase II | NCDS | OC RDC - Inhouse | 2015-01-03 05:30 | 2015-01-03 05:30 |  | DB Conduct | Final DBL | 2023-01-16 05:30 | 2015-04-08 05:30 |  | 2014-08-27 05:30 |  | Active | 2022-11-28 05:30 |  | 2023-01-16 05:30 |  | FALSE | Yearly 1 to 2 IRC snapshot | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multicenter trial to determine the efficacy and safety of CTL019 in pediatric patients with relapsed and refractory B-cell acute lymphoblastic leukemia | CCTL019B2202 PII Pediatric r/r ALL/L3-M | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | NARAYANAN, AKHILA JAYA | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Lauren Smith | Lauren Smith | Gehlawat, Priya | Ahuja, Mohit | [13 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [12 empty] | Old OC Study. Will conduct DDPASS before any milestone |  | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2015-03-30 05:30 | 2015-03-30 05:30 | Gehlawat, Priya |  | NA | [7 empty] | 199 | 0 |  |  | 0 |  |  |  | 557 | 11 | 0 |  | Acute lymphoblastic leukaemia | Yes | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CCTL019B | CCTL019B2203J | C1001115 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-02-27 05:30 |  | 2013-09-30 05:30 |  | Completed | 2018-03-23 05:30 | 2017-10-26 05:30 | 2018-04-03 05:30 | 2018-04-26 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Phase II Study of Redirected Autologous T Cells Engineered to Contain Anti-CD19 Attached to TCR and 4-1BB Signaling Domains in Patients With Chemotherapy Resistant or RefractoryAcute Lymphoblastic Leukemia | CCTL019B2203J PII Adult ALL/L3-M (Penn 21413) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Yerva, Kiran | Sarkhel, Biswadip | Rengarao, Sanjai Kumar Surya | Nair, Sreesha |  | Uday Deore |  | Gandla, Prashanth | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | BP21 | PPD | Manpreet Singh <Manpreet.Singh@ppdi.com> | Earlier DBD: Asha Rajanna | [14 empty] | Acute lymphoblastic leukaemia | Yes | Global | Completed | Yes | [16 empty] | None of the above
CCTL019B | CCTL019B2205J | C1001116 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-08-14 05:30 |  | 2016-05-05 05:30 |  | Completed | 2019-05-24 05:30 | 2019-05-24 05:30 |  |  | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multicenter trial to determine the efficacy and safety of CTL019 in pediatric patients with relapsed and refractory B-cell acute lymphoblastic leukemia | CCTL019B2205J PII Pediatric r/rALL/L3-M ENSIGN | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Mohapatra, Ruchi | Mitra, Kaustav | Rengarao, Sanjai Kumar Surya | Nair, Sreesha |  | Lauren Smith | Ahuja, Mohit | [14 empty] | Sundar, N Sushant |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse |  | 2014-07-15 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 163 | 0 |  |  | 0 |  |  |  | 585 | 7 | 0 |  | Acute lymphatic leukaemia | Yes | Global | Completed | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CCTL019B | CCTL019B2206 | C1001117 | Phase II | NCDS | OC RDC - Inhouse |  | 2014-06-04 05:30 |  | DB Locked |  |  | 2014-11-18 05:30 |  | 2014-05-14 05:30 |  | Completed | 2019-05-01 05:30 | 2019-04-29 05:30 | 2019-06-12 05:30 | 2019-07-31 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | IDMA Transaction | Hematology | A multicenter study of apheresis collection of peripheral blood mononuclear cells (PBMC) in patients with CD19 expressing malignancies who could be eligible for a CTL019 clinical research trial | CCTL019B2206 PII Apheresis | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Qian, Celia | Mitra, Kaustav | Rengarao, Sanjai Kumar Surya | Nair, Sreesha | Lauren Smith | Lauren Smith | Nikhare, Aparna | [14 empty] | Varate, Rohit |  | Amit Agavekar | [12 empty] | This is a OC study and 1st DDPASS schduled for 18th Mar 2019. | 0 | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse |  | 2014-06-12 05:30 | Gehlawat, Priya | Kanchi, Pavan kumar | NA | [7 empty] | 94 | 0 |  |  | 0 |  |  |  | 368 | 2 | 0 |  | Acute lymphatic leukaemia | No | Global | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CCTL019B | CCTL019B2210 | C4002385 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-05-01 05:30 |  | 2021-11-30 05:30 | DB On hold | Final DBL | 2027-12-29 05:30 |  | 2019-08-30 05:30 | 2019-08-18 05:30 |  | Planned | 2027-11-30 05:30 |  | 2027-12-29 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multi-center trial to evaluate the efficacy and safety of tisagenlecleucel in Chinese pediatric and young adult patients with relapsed or refractory B-cell acute lymphoblastic leukemia | CCTL019B2210 CHINA PhII Ped r/r ALL | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Qian, Celia | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | HIROMI TAKEUCHI | HIROMI TAKEUCHI | Sinha, Deepakshi | Sinha, Deepakshi |  |  | 29Apr2021 : DB golive moved to 03Sep2021. DB build activities to start from 20May2021. iBOW to be updated Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 01May2020 |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Ongoing | 06Sep2021: Followed up with the DBD for the updated ALS. Have still not received the updated ALS 02Sep2021: DBD informed that There has been multiple updates in the SSD, which are being addressed currently. Those will be implemented in the study and the updated ALS be shared with me by 3 Sept, 2021 EOB. 30Aug2021: Have been following up with the DBD for the updated ALS 23Aug2021: ALS Review completed and shared my comments with the DBD 20Aug2021: DBD shared the ALS for my initial review. 11Aug2021: DBD confirmed the Go-Live date: 10-Sep-2021. SRF Review completed and comments have been shared. 04Aug2021: DBD shared the rest of the SRFs for review. Review ongoing. 30Jul2021: Rehana supported in reviewing the SRFs and shared her comments with the DBD 21Jul2021: DBD shared 10 SRFs with SDTM annotation among 17 SRFs. Also shared the status of other SRFs. Review ongoing. 14Jul2021: DBD informed regarding the Go-live date. The DBD informed that the study is planned for Go-live on 20 Aug, 2021. But due to some issues in DO accelerate the study activities are delayed and hence the Go-live date will be altered. 08Jul2021:Requested the DBD to share the study status and share the SRFs, ALS for initial review. 26May2021: Reassigned the study from Kranthi to Arpita. 07-Jul-2020: Go-Live postponed 05Feb2020 : followed-up with DBD, Awaiting documents. Assignment done on 14an2020 | [6 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Acute lymphoblastic leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CCTL019B_MA | CCTL019B2302 | C4004988 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2019-09-11 05:30 | 2019-11-21 05:30 | DB Conduct | Final DBL | 2023-05-26 05:30 | 2019-11-21 05:30 | 2019-04-12 05:30 | 2019-04-12 05:30 |  | Active | 2023-04-14 05:30 |  | 2023-05-26 05:30 |  | FALSE | GMA- NEO NovRave | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | A phase IIIb study of the safety and efficacy of tisagenlecleucel out of specification for commercial release in patients who are consistent with the label indication | CCTL019B2302 OOS Final Product | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Dorepalli, Saidulu | Sadhu, Soumen Kumar | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Linda Voice | Linda Voice | Bora, Deepthi Reddy | Thomas, Ankit | Completed | 2021-07-20 05:30 |  |  | DRM | Pilli, Bhaskar | Shrivastava, Nikhil | Completed | 21-Jan-2022: Rule File V4.0 finalized WRT PPC#05 finalized in CREDI. SNOW-51 is raised and LSP is notified. 19-Feb-2021: Rule File V3.0 finalized WRT PPC#03 finalized in CREDI. SNOW-51 is raised and LSP is notified. 16-Jan-2021: Rule File is updated WRT PP#03 and sent to team for peer review. 12-Jan20201: DBD informed that PPC#03 will be implemented by this week. 9DEC2020 (Angella): PPC3 is still in UAT stage. RF updates will be initiated post PPC3 implementation. 9-DEC-2020 (Angella): Awaiting pre requisite (ALS, UAT SOD) for RF updates. 26Nov2020: Backup: Angella Whats planned: PPC#03 is in draft state. PPC form is reviewed and shared the comments. Need to include in RF once database is updated. 13-Nov-2020: Received the PPC form (PPC#03) from DBD. Reviewed from RF perspective and sent the comments. 23Oct2020: Followup email sent to DBD for PPC status 29-Sep-2020 (SHRIVNI5): TDM informed that in addition to 2 missing forms, there are some other changes also that needs to be implemented in the database and some of those might require Standards approval. Hence, they are trying to implement all in one PPC. TDM informed that he will keem me informed after following up with CTT. 31-Aug-2020 (SHRIVNI5): DBP informed that PPC 03 is planned to be drafted by 1st week of Sep2020 for fixing pending forms (CMS001 and CVS001) issue. 10Jul2020: Followed up with DBD on PPC for fixing pending forms (CMS001 and CVS001) issue. DBD has not received the PPC form. 04-Jun-2020 (SHRIVNI5): Study DBD confirmed that updates related to CMS001 and CVS001 will be done in the next upcoing PPC3 (mostly end of Jul). RF updates will be done post that. 03-Jun-2020 (SHRIVNI5): 10 forms (CMO006, CMO006_1, CMH001, ZRO005, ZRS001_1, CMG001_1, CMG001_2, QS1H12, QS1H13 and CMS002) have been included in the RF V2.0 and SNOW-51 ticket raised for LSH setup. 27May2020 : CMS001, CVS001,CMO006, CMO006_1 were peding due to inputs from DBD as per below comments. Below forms CMS001, CVS001, CMO006, CMO006_1, CMH001, ZRO005, ZRS001_1, CMG001_1, CMG001_2, QS1H12, QS1H13, CMS002 are part of the missing forms/DTS report. Included in PPC. Following up with DBD 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. RF is finalized with outstanding issues: 1.) CMS001 - CMCAT does not have dictionary associated with it. Please update in next PPC. Also please provide SRF for this CRF. 2.) Please provide SRFs for CMO006 and CMO006_1 and also provide SOD (.csv) with output standards 3.) CVS001, there are two results (CVRESN,CVRESCD) where one test field (CVTSTLG) as log line and also other specify is also used for test as separate field. Can you please check with TAPOD/TDM about this screen design. 4.) Can you please confirm if TDM has requested to create lab analyte in rave metadata as ‘COLOR or ‘CSFCOLOR’ as both are not present. 5.) Length of B1TEST_STD abbreviated value is more than 8 characters in B1S002 and also form design needs to be updated in next PPC. | None | None | 2019-11-19 05:30 | Transition Study and Legacy process | Polavarapu, Vanaja | Polavarapu, Vanaja | Sai Krishna Mettugari | Completed | 2020-02-27 | Completed | 2020-02-28 05:30 |  | Study Transition | 2020-02-28 05:30 | 2020-02-28 05:30 | Pre-requisites not met | 2020-06-09 05:30 |  |  | DDPASS is from next week | 10 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 6 | 9 | 72 | 0 | 150 | 683 | 0 | 190 | 40 | 264 | 987 | 1 | 0 |  | Acute lymphoblastic leukaemia; Diffuse large B-cell lymphoma | No | Global | Open | Yes | [10 empty] | 2020-02-13 05:30 | [5 empty] | None of the above
CCTL019B | CCTL019B2401 | C1001118 | Phase IV | Other | Other |  |  | 2018-12-20 05:30 | DB Conduct | Final DBL | 2039-02-22 05:30 | 2018-12-20 05:30 |  | 2017-09-07 05:30 |  | Active | 2038-12-14 05:30 |  | 2039-02-22 05:30 |  | FALSE | Registry trial, receiving data from CIBMTR and EBMT | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Prospective registry to assess the long term safety of patients with B lymphocyte malignancies treated with tisagenlecleucel | CTL019B2401 PIV-Pt Registry | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bathini, Murali Krushna | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Karine Nail | Karine Nail | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Acute lymphoblastic leukaemia; Chronic lymphocytic leukaemia; Diffuse large B-cell lymphoma; Follicular B-cell non-Hodgkin's lymphoma; Non-Hodgkin's lymphoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CCTL019C | CCTL019C2201 | C1001119 | Phase II | NCDS | OC RDC - Inhouse |  | 2014-09-30 05:30 |  | DB Conduct | Final DBL | 2023-04-03 05:30 | 2015-07-29 05:30 |  | 2014-09-08 05:30 |  | Active | 2023-02-20 05:30 |  | 2023-04-03 05:30 |  | FALSE | Submission study in LTFU stage now. Full DBL expected in 2022/2023 | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multicenter trial to determine the efficacy and safety of CTL019 in adult patients with relapsed or refractory diffuse large B-cell lymphoma (DLBCL) | CCTL019C2201 PII r/r DLBCL/L3-M (Juliet) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Sehrawat, Ram Singh | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Clemence Hustache | Kristina Stangl | Maricherla, Vijayroshan | Mareedu, Vasu |  | 2020-03-09 05:30 | [11 empty] | Sundar, N Sushant |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2015-07-24 05:30 | 2015-07-24 05:30 | Mareedu, Vasu | Iliyas, Mohamed | NA | [7 empty] | 218 | 0 |  |  | 0 |  |  |  | 686 | 9 | 0 |  | T-cell lymphoma | Yes | Global | Open | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CCTL019C | CCTL019C2202 | C3000949 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-23 05:30 | 2019-02-01 05:30 | DB Conduct | Final DBL | 2023-06-15 05:30 | 2019-02-15 05:30 | 2018-05-14 05:30 | 2018-06-13 05:30 |  | Active | 2023-04-07 05:30 |  | 2023-06-15 05:30 |  | TRUE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multicenter trial to determine the efficacy and safety of CTL019 in pediatric Non-Hodgkin lymphoma | CCTL019C2202 PII CTL019 in Non-Hodgkin Lymphoma | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Qian, Celia | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Lauren Smith; Victoria Ahmed | Lauren Smith | Bakka, Sandeep | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 19NOV2021: RF 8.0 is final and SNOW 51 RITM3207760 request has been created for to rebuild FACE domain 26OCT2021: RF V7.0 is final and SNOW request RITM3044235 has been created. requested LSP to rebuild LB, XM, AE, ZT and DV domains as per ppc changes. 31MAY2021: RF V6.0 is final and SNOW 51 RITM2622979 request has been created with below change. 25MAY2021: B18L DTS reviewed and added in Rule file V6.0. Peer review is ongoing. 01Feb2021 : No rule file update the PPC 09 only SMT update. Raised snow Ticket for the same. 6Jan2021: PPC9 shared by DB lead for review on 6Jan2021. PPC review and subsequent Rulefile update needs to be done. 22Jun2020: In shashi's Absence updates done by Ashok to QS, VS, CM, DS, FACE, ZI Domains as per the PPC and teams request and raised SNOW51. 13Jun19 : Except 3rd party rest all domains covered in Rule file. | None | None | 2019-01-28 05:30 | Transition Study and Legacy process | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2019-07-02 | Completed | 2019-05-15 05:30 |  |  | 2019-02-07 05:30 | 2019-02-07 05:30 |  | 2019-08-26 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2021-12-24 05:30 | 2021-12-27 05:30 | [9 empty] | NA | [5 empty] | 12 | 23 | 135 | 0 | 371 | 1351 | 0 | 254 | 35 | 542 | 1928 | 8 | 0 |  | Non-Hodgkin's lymphoma; Non-Hodgkin's lymphoma refractory | Yes | Global | Open | Yes | [10 empty] | 2019-06-27 05:30 |  |  |  | Interim-Analysis | R, Harini | HA Commitment | Yes
CCTL019C | CCTL019C2203 | C4002685 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-07-01 05:30 |  | 2022-01-31 05:30 | DB On hold | Final DBL | 2027-10-29 05:30 |  | 2019-08-09 05:30 | 2019-09-12 05:30 |  | Planned | 2027-09-27 05:30 |  | 2027-10-29 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single-arm, multicenter trial to evaluate the efficacy and safety of tisagenlecleucel in Chinese adult patients with relapsed or refractory diffuse large B-cell non-Hodgkin lymphoma (DLBCL) | CCTL019C2203 China stand alone DLBCL r/r 3rd line | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Qian, Celia | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Robert Ma | Zheyong Ma | Gupta, Anshu | Gupta, Anshu |  |  | 28Apr2021 : Requested TDM to wait for couple of weeks . Until then request to continue on the activities which are required from DO accelerate perspective. DDB can be on-boarded at later point. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 01Jul2020 |  | DRM | Bairagi, Arpita | R, Pratheeksha K | Ongoing | 22Sept2021: RF development started. 12Aug2021 : Reassigned from Arpita to Pratheeksha. 11Aug2021: Go-Live date is confirmed on 10-Sep-2021. 06Aug2021: Reviewed and shared the comments for rest of the SRFs. 03Aug2021: Reviewed the SRFs and shared the comments with the DBD. DBD shared rest of the SRFs for initial review. 21Jul2021: DBD informed that there has been discussion ongoing to reschedule the Go-live date, and thus the DBD will share the communication once updated. DBD shared 4 SRFs with SDTM Annotation out of 7 for initial review. 12Jul2021: Requested DBD to update on the study status and share the SRFs and ALS for initial review. 6JAN2021: SG: DB activities have not begun yet. No upcoming task for Rulefile. 31Mar2020 : Study on Hold 10Feb2020 : No development activities started yet |  |  |  |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Diffuse large B-cell lymphoma refractory | No | Global | Open | Yes | [16 empty] | None of the above
CCTL019C_MA | CCTL019C2401 | C4005962 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2019-08-30 05:30 | 2019-10-11 05:30 | DB Conduct | Final DBL | 2022-12-30 05:30 | 2019-10-22 05:30 | 2019-06-28 05:30 | 2019-06-21 05:30 |  | Active | 2022-11-18 05:30 |  | 2022-12-30 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology |  | CCTL019C2401 DLBCL NIS (SHIELD) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Buditi, Sandhya | Sadhu, Soumen Kumar | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Jimmy Lee | James Lee | Patnaik, Angella | Rao, S Shashikanth |  |  |  |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 11-FEB-2022: PPC #3 implemented in PROD on 8-FEB-2022. No impact on RF. SNOW #51 (RITM3484677) raised for SMT/LSH updates. 1-JUL-2021: RF Version 4.0 finalized. SNOW#51 (RITM2730171) has been raised for the LSH Integration for Discoverant Data. 27-APR-2021: RF Version 3.0 finalized. SNOW#51 raised for SMT and LSH updates. 20-APR-2021: RF Version 3.0 is released for Peer Review. 14-APR-2021: SDTM annotations confirmed for FAMH. 22-SEP-2020: RF V2.0 finalized for FAMH domain as per the updated SDTM annotations provided. SNOW#51 raised for SMET and LSH updates. 07-JUL-2020: RF up to date. No DTS, No PPC yet. 02DEC2019: Rule file V1.0 final in CREDI. SMT request raised. 17DEC2019: Still not received the SMT files for raising the SNOW ticket. Have followed up with the SMT Team. | None | None | 2019-12-17 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2019-12-23 | Completed | 2019-12-27 05:30 | Rule file V1.0 final in CREDI. SMT request raised. | Pre-requisites not met | 2019-12-27 05:30 | 2019-12-30 05:30 | Pre-requisites not met | 2020-06-09 05:30 |  |  | Rule file update need | 84 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 3 | 5 | 30 | 0 | 39 | 278 | 0 | 76 | 4 | 132 | 414 | 1 | 0 |  | Diffuse large B-cell lymphoma | No | Global | Open | Yes | [10 empty] | 2019-12-26 05:30 | [5 empty] | None of the above
CCTL019E | CCTL019E1401 | C4013308 | Phase IV | Other |  |  |  | 2022-11-30 05:30 |  | Final DBL | 2026-09-15 05:30 |  | 2022-09-30 05:30 |  |  | Planned | 2026-09-15 05:30 |  | 2026-09-15 05:30 | [5 empty] | Outsourced |  |  | CCTL019E1401 CTL019E JAPAN PMS / Registry | PA Oncology (Hematology not for MA projects) | [6 empty] | KEIKO FUJINO | [66 empty] | Follicular B-cell non-Hodgkin's lymphoma | No | Global | Open | Yes
CCTL019E | CCTL019E2202 | C3001732 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-03 05:30 | 2018-11-26 05:30 | DB Conduct | Interim DBL | 2022-05-10 05:30 | 2018-11-12 05:30 | 2018-03-28 05:30 | 2018-04-10 05:30 |  | Active | 2025-05-22 05:30 |  | 2025-07-17 05:30 |  | TRUE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase II, single arm, multicenter open label trial to determine the efficacy and safety of CTL019 in adult patients with refractory or relapsed follicular lymphoma. | CCTL019E2202 PII_Adult_r/r_FollicularLymphoma/ L-3 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kotamarthi, Jyothi | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Lauren Smith | Katja Lehnhoff | Choppadandi, Kranthikumar | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 07-May-2021: RF updated and finalized for discoverent DTS update and LPARM updates 21-Apr-2021: RF updated for XM configuration file updates 03-Mar-2021: RF_V16.0 finalized to include ZI2L DTS table 21Jan2021: Kranthi: B17L DTS is included in RF_V14.0 and raised SNOW ticket for LSH set-up. LSh setup is in progress and will be completed by 22-Jan-2021 as per the LSP's confirmation 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B17L DTS listed. Please check 10-Nov-2020: V13.0 creaed for Project level DTS implementation 22-Oct2020: V10.0 finalized for the screen updates of PPC#11 06-Jul-2020: No pending issues. | None | None | 2018-09-05 05:30 |  | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2018-09-06 | Completed | 2019-07-19 05:30 |  | Retrospective DRM studies | 2018-09-10 05:30 | 2018-09-12 05:30 |  | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 15 | 35 | 132 | 0 | 333 | 1471 | 0 | 355 | 39 | 501 | 2011 | 11 | 0 |  | Non-Hodgkin's lymphoma | Yes | Global | Open | Yes | [10 empty] | 2019-07-19 05:30 |  |  |  | Interim-Analysis | Gouni, Harita | None of the above | Yes
CCTL019G | CCTL019G2201J | C1001579 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-15 05:30 | 2019-06-28 05:30 | DB Conduct | DB Snapshot | 2022-06-07 05:30 | 2019-06-24 05:30 | 2018-03-28 05:30 | 2018-03-29 05:30 |  | Active | 2027-07-21 05:30 |  | 2027-09-01 05:30 |  | TRUE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A single arm phase II trial in first line high risk (HR) pediatric and young adult patients with B-cell acute lymphoblastic leukemia (ALL) who are minimal residual disease (MRD) positive at end of consolidation (EOC) therapy | CCTL019G2201J pALL High Risk/L1-M/ Cassiopeia | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | A, Mohamed Noorul | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Aleksandra Wlasenko | Aleksandra Wlasenko | Bakka, Sandeep | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 19NOV2021: RF V11.0 final and snow 51 RITM3100150 created for the addition B17L and XM_CCTL019G2201J DTS 26MAR2021: RF has been finalized as part of PPC8 and SNOW 51 request RITM2402918 has been created Changes: Added new forms 'DSG005', 'B2O004', 'FAMHS004_TR' 6JAN2021: SG: No upcoming tasks. 02Sep2020 : QS2L DTS incluuded in RF and finalized on 01sep2020 11AUG2020: QS2L DTS will be included in RF by 14AUG2020. 29Jul2020 : As per 20Jul report CEH001 and CEH001_1 are listed but these are removed and new form CEH001_2 has been added. QS2L is pending. 03JUL20: RF final and SNOW 51 request RITM1566286 has been created. QS2L DTS update is ongoing, as of today not final: Converting DRM to PREDRM. 01JUL20: RF developed and peer review is ongoing with following changes. QS domain: QS1S13_TR form has been added. CM domain: CMH001 form has been added CE domain: 1. CEH001, CEH001_1 forms have been removed 2. CEH001_2 form has been added EC and FAEC domain: Forms ECH001,ECH001_1 has been mapped to EC and FAEC domains as per new standard SDTM annotations Note: QS1L, QS2L updates are ongoing. 22Jun2020 : As per pending DTS report dated 22may QS1L and QS2L flagged. Had a meeting with DM recently to discuss on different DTS template being used across QS DTS’s. DB lead is aware of the issue and possible solution(update DTS). 27May2020 : As per pending DTS report dated 22may QS1L and QS2L flagged. 30Mar2020 : included pending 4B1 and ZW DTS and sent for LSH setup 27Mar2020 : 4 B1 & ZW DTS received to incldue in RF, will released for Peer review on 30th. 19-Mar-2020: Received DTS updates for B1 and ZW on 17-Mar-2020. 02Mar2020 : Shashi to provide the update. RF for pending (QS, B1, ZW DTS) not final 12Feb2020 : QS, B1, ZW DTS included in RF and sent for peer review (Nikhil). The FPFV for the study is in the last week of Feb 2019. 13Jun19 : Except 3rd party rest all domains covered in Rule file. | None | None | 2019-05-16 05:30 |  | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2019-06-10 | Completed | 2019-07-23 05:30 | ​ |  | 2019-06-10 05:30 | 2019-06-10 05:30 |  | 2020-05-06 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 10 | 50 | 145 | 0 | 581 | 1181 | 0 | 250 | 37 | 702 | 1920 | 11 | 0 |  | Acute lymphoblastic leukaemia | Yes | Global | Open | Yes | [10 empty] | 2019-07-23 05:30 |  |  |  |  | Praveen kumar, Chakka Giri | None of the above | Yes
CCTL019H | CCTL019H2301 | C1001120 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-04-16 05:30 | 2019-05-03 05:30 | DB Conduct | Final DBL | 2026-12-15 05:30 | 2019-05-07 05:30 | 2018-06-18 05:30 | 2018-07-11 05:30 |  | Active | 2026-10-27 05:30 |  | 2026-12-15 05:30 |  | TRUE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Tisagenlecleucel versus standard of care in adult patients with relapsed or refractory aggressive B-cell non-Hodgkin lymphoma: A randomized, open label, phase III trial (BELINDA) | CCTL019H2301 PIII 2L aNHL_Belinda | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bathini, Murali Krushna | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Clemence Hustache | Cl��mence Julia Hustache | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR |  |  |  |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 08Jul2021:RF v12.0, 13.0 is finalized with XM DTS and ZI2L DTS. 07Jul2021: RF v12.0 is ready for finalization awaiting confirmation from LSP for 'XM(Discoverant) dts' test set-up by (Praveen). 06Jul2021 : ZI2L reflecting in missing form DTS report again. 04-June-2021: As flagged in 'Missing dts' report added 'ZI2L' table to RF v12.0 and sent for review/finalization. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021: Discoverant XM1L DTS discussion is in progress. 26-Apr-2021: Added B18L DTS in RF and finalized, raised SNOW51 ticket RITM2483470. 19-Apr-2021: B18L DTS finalized and working on RF update. 15Feb2021: Sent follow up email to Vtssr Prasanna to confirm on DTS finalization status. 05Nov2020: RF Version 8.0 shared with team for peer review on 02Nov2020. 11Sep2020: QS1L,QS2L,QS3L and B17L DTS's were added in RF and raised SNOW ticket on 08Sep2020. 02Sep2020 : As per 02Sep2020 missing forms DTS report QS1L, QS2L, QS3L, B17L pending. Praveen to update status 11Aug2020 : QS DTS metadata need sto be added in sharepoint following up with TDM, DBD. DTS updated required. 28Jul2020: SRF has been raised by TDM to add QS metadata to sharepoint reference metadata. once SRF is approved, TDM will initiate draft DTS's for QS1L, QS2L and QS3L. LSP's require the finalized DTS document to setup the DTS in LSH. 18Jun20 : Include the 3 DTS and don't wait for Metadata to be updated in SP. Ask the DBD and TDM to get it updated in SP. From RF perspective we will update it as there is no impact on RF 12May2020 : Following up with DBD on pending DTS QS1L, QS2L, QS3L 05May2020: Rule File Finalized and SNOW51 ticket raised on 27-Apr-2020. Updated CEH001 and FAMHO001 as per the latest SDTM Annotations. Added B12L,B13L,B14L and B15L DTS to B1 Domain. 08Apr2020 : yet to receive updated pending DTSs. 01Apr2020 : Reassigned RF from Roshan to Praveen 01Apr2020: No response from Lead DBD inspite of multiple emails. Rule file to be updated for the finalized DTSs after DTS issues are fixed. 26MAR2020: Awaiting response from DBD on the issues raised on DTS. 10Mar20 : DTS for B15L final and shared to include in RF on 06Mar. QS1L, QS2L, QS3L, B12L & B13L not processed as there is update required for All QS DTS. 03MAR2020: LSH setup completed 07Feb2020 : Received 5 DTSs this week to include in RF 14 Jan 20: SMT generated and informed LSP to work on LSH rebuild on 13 Jan 20 with ticket RITM1012999 | None | None | 2019-06-03 05:30 | Transition Study | Kommu, Ranjith Kumar | Agavekar, Amit | Amit Agavekar | Completed | 2019-06-03 | Completed | 2019-06-03 05:30 |  | Pre-requisites not met | 2019-06-14 05:30 | 2019-06-14 05:30 | Pre-requisites not met | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1 | [11 empty] | NA | [5 empty] | 15 | 97 | 143 | 0 | 454 | 1556 | 0 | 308 | 39 | 572 | 2167 | 13 | 0 |  | Diffuse large B-cell lymphoma; Diffuse large B-cell lymphoma refractory; Follicular B-cell non-Hodgkin's lymphoma; Non-Hodgkin's lymphoma; Non-Hodgkin's lymphoma refractory | Yes | Global | Open | Yes | [10 empty] | 2019-06-14 05:30 |  |  |  | Interim-Analysis | Pagolu, Sahithi Venkata | GDD annual target | Yes
CCTL019J | CCTL019J2101 | C3003428 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-24 05:30 | 2018-09-04 05:30 | DB Locked | Final DBL Achieved |  | 2018-10-09 05:30 | 2018-03-21 05:30 | 2018-03-08 05:30 |  | Completed | 2021-07-20 05:30 | 2021-07-20 05:30 | 2021-09-20 05:30 | 2021-09-03 05:30 | TRUE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Ph1/2 POC study of concurrent CTL019 and pembrolizumab in relapsed/refractory DLBCL population, single arm design including dose timing finding run-in | CCTL019J2101 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | A, Mohamed Noorul | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Karine Nail | Karine Nail | Maricherla, Vijayroshan | Tadiparthy, Ramakanth |  |  |  |  | DRM (DIAL) | Oguri, Praveen | Bai, Chandrakala | Completed | CB,13Sep2021: As per confirmation from study LSP-I don’t think there is any need to add this table to Rule file as this is post lock biomarker data. Third party table will be published directly to GPS. 07Jul2021: RF v7.0 finalized for XM dts in CREDI. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021: Discoverant XM1L DTS discussion is in progress. 05Nov2020: RF Vesion 6.0 finalized on 09Oct2020. 11Sep2020: No Activity. 06Jul2020 : Rule File V5.0 is the latest version in CREDI and no modifications done after the transition from Roshan. Study will be transitioned to Praveen to Ashok 01Apr2020: Rule file v5.0 is finalized in CREDI by Roshan. 01Apr2020 : Reassigned RF from Roshan to Ashok 01Apr2020: No pending activity 03MAR2020: LSH setup completed for all pending forms. 09Jul19: Pending updates are CE, FACE, FAEC. SDTM confirmation whether SSG003 is being used for SDTM as SSTEST Column is not present for SSG003 09 jan 20: Initiated rule file development for the pending forms | None | B17L, B18L | 2018-10-10 05:30 | Legacy Process | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2018-10-29 | Completed | 2019-06-12 05:30 | LSH refresh raised with ticket RITM0091453. | Retrospective DRM studies | 2018-10-30 05:30 | 2018-10-30 05:30 | Pre-requisites not met | 2019-07-22 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes |  | 2021-09-24 05:30 | 2021-09-29 05:30 | Updated third party data received after the Post Lock request has been raised | [8 empty] | NA | [5 empty] | 13 | 50 | 115 | 0 | 256 | 1249 | 0 | 242 | 36 | 408 | 1693 | 10 | 0 |  | Diffuse large B-cell lymphoma | No | Global | Open | Yes | [10 empty] | 2019-07-16 05:30 |  |  |  | DBL | Nidamanuru, Kalyan Kumar | None of the above | Yes
CCTL019L1 | CCTL019L12101C | C4000392 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-12-06 05:30 | 2019-05-15 05:30 | DB Conduct |  |  | 2019-06-11 05:30 | 2018-06-01 05:30 | 2018-05-22 05:30 |  | Active | 2021-11-01 05:30 | 2021-11-01 05:30 | 2022-01-10 05:30 | 2021-12-22 05:30 | TRUE | No Priority | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase Ib, multicenter study to determine the safety and tolerability of tisagenlecleucel in combination with ibrutinib in adult patients with relapsed and/or refractory diffuse large B-cell lymphoma. | CCTL019L12101C combo with ibrutinib in DLBCL | N7 Oncology - NIBR | Molander, Lei Ann | Rocha, Gabriela | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | David Hynds | David Hynds | Maricherla, Vijayroshan | Tadiparthy, Ramakanth |  |  |  |  | DRM (DIAL) | Oguri, Praveen | Bai, Chandrakala | Completed | 06Dec2021: RF v5.0 is finalized for LB and B16L dts updates. 07Jul2021: Re-confirmation mail sent to DBD, TDM and LSP for 'ZI1L' prod transfer. LSP confirmed-production transfer is not completed yet. 08-Jun-2021: RF v4.0 finalized in CREDI with addition of ZI1L dts. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021 : Following up with Study DBD to get an update on ZIL DTS. flagged in report dated 19May2021 25-May-2021: Sent email to Ramakanth to confirm on ZIL DTS finalization status. 05Nov2020: No Activity. 11Sep2020: No Activity. 06Jul2020: Rule file V3.0 is the latest version. RF will be transitioned from Ashok to Praveen 16Jun2020 : Rule file V3.0 is finalized in CREDI. 01Apr2020 : Reassigned RF from Roshan to Ashok 01Apr2020: No pending activity 03MAR2020: LSH setup completed for pending forms 23Jan2020: Rule file updated for LBG001_1_TR and sent for peer review 14 Jan 20: Pending Lab domain. 09 Jan 20: initiated rule file updation | None | None | 2019-02-20 05:30 |  | Tidke, Shyam | Sahu, Ahallad | Rohit Varate | Completed | 2019-02-25 | Completed |  | DRM setup is ongoing(AE and MH is pending.) |  | 2019-02-25 05:30 | 2019-02-25 05:30 |  | 2020-05-08 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | IQVIA | [5 empty] | 6 | 23 | 140 | 0 | 392 | 1078 | 0 | 236 | 38 | 567 | 1683 | 6 | 0 |  | Diffuse large B-cell lymphoma refractory | No | Global | Open | Yes | [10 empty] | 2019-11-29 05:30 | [5 empty] | None of the above
CDDA945A0 | CDDA945X2101 | C1200411 | Phase I | NCDS | CRO - EDC |  |  | 2017-12-15 05:30 | DB Locked |  |  | 2017-11-13 05:30 | 2017-05-31 05:30 | 2017-05-30 05:30 |  | Completed | 2018-11-05 05:30 | 2018-10-29 05:30 | 2019-08-19 05:30 | 2019-08-13 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CDDA945X2101 | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Jen Watts | Jen Watts | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK02;#ZK | [11 empty] | CMED | [19 empty] | Asthma | No | Global | Terminated | Yes | [14 empty] | DMC/Dry-Run/Snapshot | Kumar, Ranjeet | None of the above | Yes
CDDO001B | CDDO001B2001 | C4004631 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-11-30 05:30 | 2020-12-11 05:30 | 2020-09-29 05:30 | DB Conduct | Final DBL | 2022-07-06 05:30 | 2020-10-14 05:30 | 2020-09-03 05:30 | 2021-09-23 05:30 |  | Active | 2022-06-08 05:30 |  | 2022-07-06 05:30 |  | FALSE | Feasibility | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CDDO001B2001 Feasibility Trial | P5 Ophthalmology | Navarro, Christelle |  | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Daniele Dolis | Daniele Jacqueline Dolis | Kabra, Pratik Govind | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Kabra Pratik Govind transitioned the study to Chandana Sarasani on 26-Feb-2021. Initial go live as 30Nov2020 when RF developer assigned on 23Oct2020. 07Oct2020 : DBD assignment request. |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 11DEC20: RF has been finalized on 11DEC20 and SNOW 51 request RITM2083691 has been created. 07DEC20: Rule file has been developed and sent for peer review. Expected date of Rule file finalization is 11DEC20. 10NOV20: •There will be direct data mapping by using the rule file to transfer data from RAVEx to LSH •This is pre-DRM study, no data aggregation (processing) will happen in LSH. DDPASS will not be applicable as data is not going through normal process •No validation is needed in pinnacle validator as data is not fully SDTM compliant at this moment •LSP will provide details if see any challenge in direct data transfer through RAVEx to LSH to GPS 06NOV20: Scheduled meetings with all stake holders for to identify risk for this new requirement of RF development. 09NOV20: Unique requirement for this study, no SRF and no transformation will be applied as per study team requiement and deviations have been filed for the same. FPFV already achieved and DB golive has been planned 07DEC20. | None | None | 2020-12-11 05:30 | RF finalized within golive + 5 days | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2020-12-28 | Not Applicable |  |  | there is no DRM for this study as this study is Rave - outsourced study as per TDM confirmation | 2021-01-27 05:30 | 2021-01-27 05:30 | [5 empty] | 100 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 4 | 4 | 33 | 0 | 68 | 200 | 0 | 52 | 2 | 155 | 357 | 1 | 0 |  | Wet age-related macular degeneration | No | Global | Open | Yes | [10 empty] | 2021-01-27 05:30 | [5 empty] | None of the above
CDDO001B | CDDO001B2002 | C4011054 | Not Applicable | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-16 05:30 | Study Planned | DB Go-live | 2022-02-28 05:30 |  | 2022-05-13 05:30 |  |  | Planned | 2023-09-16 05:30 |  | 2024-04-30 05:30 |  |  | NA | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CDDO001B2002 nAMD/DME Validation Trial | P5 Ophthalmology | Navarro, Christelle |  | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Godelieve Convents | Godelieve Convents | [17 empty] | Sai Krishna Mettugari | [36 empty] | 30 | [7 empty] | 450 | 2 |  |  | Age-related macular degeneration; Macular oedema | No | Global | Open | Yes
CDDO001E | CDDO001E2001 | C4011096 | Not Applicable | [9 empty] | 2020-05-01 05:30 | 2020-11-16 05:30 |  | Active | [8 empty] | InHouse |  | A retrospective adjudication study based on HAWK and HARRIER clinical trials to evaluate the accuracy of the intelligent precision dosing algorithm (IPDA) in predicting disease activity in patients with neovascular age-related macular degeneration treated with Brolucizumab | CDDO001E2001 IPDA Adjudication Trial | P5 Ophthalmology | [5 empty] | Godelieve Convents | Godelieve Convents | [66 empty] | Age-related macular degeneration | No | Global | Open | No
CDDO001F1 | CDDO001F12201 | C4007662 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-10-31 05:30 | 2021-05-18 05:30 | 2021-06-30 05:30 | DB Conduct | Final DBL | 2023-06-02 05:30 | 2021-06-30 05:30 | 2020-10-22 05:30 | 2020-10-28 05:30 |  | Active | 2023-04-21 05:30 |  | 2023-06-02 05:30 |  | FALSE | POC | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 52 Week Randomized, Single-masked, Multicenter Proof of Concept Study of Binocular Videogames Versus Patching for Amblyopia in Children 4-7 Years of Age With an Open-label Substudy of Binocular Videogames in Children 8-12 Years of Age | CDDO001F12201 POC | P5 Ophthalmology | Navarro, Christelle | Reddyvari, Hima Bindu | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Volker Moeckel | Volker M��ckel | Sinha, Deepakshi | Sinha, Deepakshi | Not Started |  | 29Apr2021 : DB golive moved to 04May2021. iBOW to be updated Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 31Oct2020 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 05Aug2021 : FADX001not in report 21Jul2021: CB-Form is removed from draft but the 'ALS repository ' has the Prod ALS versions. Hence need to await for any PPC for this study. As confirmed by DBD no PPC is planned as of now. 21Jul2021 : Form FADX001 again reflecting in 21Jul report. 07Jul2021: Sent a reminder to the DBD for updating ALS. 06Jul2021 : FADX001reflecting in missing form DTS report. 18June2021: Same status, DBD is analysing the impact for FADX001. 04-June-2021: This was created for Gaming DTS form demo , hence asked the DBD to remove it from the Rave architect as it is not included in any 'Matrix'. 18Jun2021: RF v2.0 for YD,YR,QS1L to QS7L dts tables finalized. 19May2021: Rule file version 1.0 is finalized in Subway for the initial DB release and SNOw#05(RITM2582177) raised . 30Apr2021: RF for DB initial version 1.0 in review 6JAN2021: Rulefile update completed for Gaming DTS setup. Rulefile activity for DB has to be initiated. 5Nov2020: Rule file update ongoing for setting up the Gaming page. 05Oct2020 : Few meeting on this study. Few fields are collection item to setup page. Data fo gaming is coming from device. Plan to have rule file validation with test data (DTS / Rave ). | None | None | 2021-05-19 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2021-05-28 | Completed | 2021-06-08 05:30 |  |  | 2021-06-09 05:30 | 2021-06-09 05:30 |  | 2021-06-16 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 13 | 56 | 0 | 117 | 568 | 0 | 152 | 39 | 173 | 780 | 5 | 0 |  | Eye disorder | No | Global | Open | Yes | [10 empty] | 2021-06-08 05:30 | [5 empty] | None of the above | No
CDDO001F1 | CDDO001F12301 | C4009099 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-01-19 05:30 | Study Planned | DB Go-live | 2022-12-01 05:30 |  | 2022-07-28 05:30 |  |  | Planned | 2024-11-14 05:30 |  | 2024-12-26 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CDDO001F12301 Pivotal 1 (Children) | P5 Ophthalmology | Navarro, Christelle | Mohanty, Pujita | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Duvvuri Krishna | Duvvuri Krishna | [6 empty] | DRM | Bai, Chandrakala | Bai, Chandrakala | Not Started | 21Jul2021 : FPFV for these studies will be in Q2 2022 (May’2022), go live will be tentatively in Apr’2022. vendor had already started developing the gaming APP & they would need the DTS during their development phase of the APP. Assigned RF Developer. | None | none |  |  |  |  | Sai Krishna Mettugari | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Eye disorder; Eye disorder | No | Global | Open | Yes
CDDO001F1 | CDDO001F12302 | C4009101 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-29 05:30 | Study Planned | DB Go-live | 2022-08-08 05:30 |  | 2022-04-08 05:30 |  |  | Planned | 2024-08-08 05:30 |  | 2024-09-19 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 52 week prospective, randomized, single-masked, controlled, multicenter study of binocular videogames in children â¥8 years old and adults with amblyopia | CDDO001F12302 Pivotal 2 (Adults) | P5 Ophthalmology | Molander, Lei Ann | Dubey, Anjali | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Mojdeh Maboudian | Mojdeh Maboudian | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar |  |  |  |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Not Started | 21Jul2021 : FPFV for these studies will be in Q2 2022 (May’2022), go live will be tentatively in Apr’2022. vendor had already started developing the gaming APP & they would need the DTS during their development phase of the APP. Assigned RF Developer. | None | none |  |  |  |  | Sai Krishna Mettugari | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Eye disorder | No | Global | Open | Yes
CDDO799A0 | CDDO799A02101 | C4012361 | Phase I |  |  |  |  | 2023-04-17 05:30 |  | Final DBL | 2024-01-18 05:30 |  | 2023-01-22 05:30 |  |  | Planned | 2023-11-23 05:30 |  | 2024-01-18 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CDDO799A02101 FIH_SAD | N1 CVM - NIBR | [6 empty] | Emma Healy | [66 empty] | Obesity | No | Global | Open | Yes
CDFF332A1 | CDFF332A12101 | C4008421 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-02-26 05:30 | 2021-09-02 05:30 | 2021-11-18 05:30 | DB Conduct | Final DBL | 2025-05-19 05:30 | 2021-11-30 05:30 | 2021-03-08 05:30 | 2021-03-05 05:30 |  | Active | 2025-02-24 05:30 |  | 2025-05-19 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/Ib, open-label, multi-center study of DFF332 as a single agent and in combination with Everolimus or IO agents in patients with advanced/relapsed ccRCC and other malignancies with HIF2Î± stabilizing mutations | CDFF332A12101 Phase I Renal cell carcinoma study | N7 Oncology - NIBR | Langlo, Francois | Muthappa, Helen | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Bala Bharathi Mannava; Victoria Nesbitt | Victoria Nesbitt | Rachakonda, Hima Sailaja | Rao, S Shashikanth | Completed | 2021-09-14 05:30 | 29Apr2021 : Go live has postponed to 6-Jun-2021 and still we are expecting date to push as there is amendment in the protocol, Team is in discussion will update the date once I get confirmation on this. Started with global form build activities Moved from 26feb21 to may21 Initial go live as 26Feb2021 when RF developer assigned on 28Oct2020. |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 03-Sep-2021: CDFF332A12101_Rule File version 1.0 has been finalized in SUBWAY and SNOW-05 Ticket is also raised with ticket number-RITM2943731 for LSH Set-up. 05Aug2021: Requested the DBD to update few database issues as identified in Renderer. DBD is yet to provide the updated ALS. Once received, Rule file will be released for Peer review. 02Aug2021: DBD shared the UAT SODs. Requested DBD to brief on the updates done in the latest Database 21July2021: DBD informed that Go live for the study has pushed to “26-Aug-2021” and screen completion to “30-Jul-2021”. 1July2021: Rule file development started. Waiting for DBD to share the UAT SODs. 25June2021: DBD shared the updated ALS. Go-Live shifted to 30July2021 18June2021: Initial Review comments is shared with DBD and updated ALS is requested. 14June2021: DBD shared the Approved SRF, ALS and SDTM annotations for initial review. 26May2021: Reassigned from Kranthi to Arpita. 28Oct2020 : RF Developer assigned with planned golive as 26Feb2021. | B1S001 | None | 2021-09-03 05:30 |  | Ramayanam, Vinay | Tidke, Shyam | Rohit Varate | Completed | 2021-09-16 | Completed | 2021-10-05 05:30 |  |  | 2021-10-07 05:30 | 2021-10-07 05:30 |  | 2021-10-07 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | IQVIA | [5 empty] | 2 | 32 | 118 | 0 | 413 | 1267 | 0 | 397 | 55 | 259 | 1581 | 9 | 0 |  | Renal cell carcinoma | Yes | Global | Open | Yes | [10 empty] | 2021-10-18 05:30 | [5 empty] | None of the above
CDFV890B1 | CDFV890A01101 | C4010044 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-05-31 05:30 | DB On hold | Final DBL | 2022-11-29 05:30 |  | 2022-01-30 05:30 |  |  | Planned | 2022-10-25 05:30 |  | 2022-11-29 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI |  | CDFV890A01101 Japanese Ethnic Sensitivity Study | N4 MSD - NIBR | Langlo, Francois | Hagiwara, Yayoi | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | TAKAHIRO MURAMOTO | TAKAHIRO MURAMOTO | Suzuki, Hiroko | Suzuki, Hiroko | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 26 Jan 2022: RF programmer assigned | [6 empty] | Rohit Varate | [48 empty] | Microangiopathy | No | Global | Open | Yes
CDFV890A0 | CDFV890A02101 | C4006694 | Phase I | Other | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved | [5 empty] | Completed | 2021-04-25 05:30 |  |  | 2021-06-02 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A phase I, double-blind, placebo-controlled, single and multiple ascending dose study of the safety, tolerability, pharmacokinetics, pharmacodynamics and food effects of IFM-2427 in healthy subjects | CDFV890A02101 FIH SAD-MAD-FE in HV | N0 ATI - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Emma Hakansson | Beata Mehes | [17 empty] | Rohit Varate | [28 empty] | PRA Health | [19 empty] | Autoimmune disorder | No | Global | Open | Yes | [16 empty] | None of the above
CDFV890A1 | CDFV890A12201 | C4006228 | Phase II | Other | CRO - EDC | 2021-03-15 05:30 |  | 2021-09-17 05:30 | DB Conduct | Final DBL | 2022-09-23 05:30 | 2021-09-20 05:30 | 2021-01-26 05:30 | 2021-02-01 05:30 |  | Active | 2022-08-18 05:30 |  | 2022-09-23 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | PoC in FCAS patients. | CDFV890A12201 PoC in CAPS | N0 ATI - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Emma Hakansson | Beata Mehes | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Familial cold autoinflammatory syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CDFV890B1 | CDFV890B12201 | C4006229 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-06-07 05:30 | 2021-06-21 05:30 | 2021-09-20 05:30 | DB Conduct | Final DBL | 2023-10-25 05:30 | 2021-09-20 05:30 | 2021-03-01 05:30 | 2021-03-01 05:30 |  | Active | 2023-09-20 05:30 |  | 2023-10-25 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A randomized, two-arm, placebo-controlled, participant and investigator-blinded study investigating the efficacy, safety and tolerability of DFV890 in patients with symptomatic knee osteoarthritis | CDFV890B12201 PoC in knee OA | N4 MSD - NIBR | Langlo, Francois | Prasanna, Snehalata | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Simon Badoud | Simon Badoud | Das, Devashish | Das, Devashish |  |  | 03May2021: Screens are ready, OSRM 1 next week. Initial golive 07Jun2021 | Clinical Operational Challenges | DRM | Shafiudeen, Rehana Banu | R, Pratheeksha K | Completed | 8Feb2022: RF Version 3.0 Finalized in subway after adding LBL DTS on 8Feb2022 and SNOW Ticket raised (RITM3468616). 31-Aug-2021 : The study is transitioned to R, Pratheeksha. 31-Aug-2021 : No Pending tasks. 30Jul2021 : Rule file 2.0 is finalized in SUBWAY. LSP's comment was addressed in this version. 22Jun2021 : The Rule file 1.0 is finalized in SUBWAY and the LSP is Notified. 21Jun2021 : The study is live. 18Jun2021 : The rule file peer review is completed 16Jun2021 : The Rule file is updated and sent for Peer review. 10Jun2021 : All the comments were addressed by the DBD 03Jun2021 : I have completed the review and sent my comments to the DBD. 27May2021 : Few changes were made and the latest ALS was sent for review. 12May2021 : We have received the ALS for review 05May2021 : The SSD and SRFs sent to me for review. 24Apr2021 : RF developer assigned. | None | None | 2021-06-22 05:30 |  | Tidke, Shyam | Gouni, Harita | Rohit Varate | Completed | 2021-07-23 | Completed | 2021-07-23 05:30 |  |  | 2021-07-25 05:30 | 2021-11-18 05:30 | KPI met - incorrect source date entry (example FPFV) | 2021-11-18 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Osteoarthritis; Osteoarthritis knee | No | Global | Open | Yes | [10 empty] | 2021-07-23 05:30 | [5 empty] | None of the above
CDFV890C1 | CDFV890C12201 | C4008573 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-08-21 05:30 | Study Planned | Final DBL | 2024-12-30 05:30 |  | 2023-03-13 05:30 |  |  | Planned | 2024-11-25 05:30 |  | 2024-12-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - DAx |  | CDFV890C12201 PoC in COPD | N5 DAx - NIBR | Langlo, Francois | Bhatkar, Priyanka | Bhatkar, Priyanka | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Pascale Emilie Genevi��ve Pinot | [17 empty] | Rohit Varate | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDFV890D1 | CDFV890D12201 | C4009186 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-05-13 05:30 | 2020-05-13 05:30 | 2020-05-27 05:30 | DB Locked | Final DBL Achieved |  | 2020-05-27 05:30 | 2020-04-22 05:30 | 2020-04-27 05:30 |  | Completed | 2020-12-25 05:30 | 2020-12-24 05:30 | 2021-02-10 05:30 | 2021-02-10 05:30 | TRUE | Pioneer | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A Phase 2, randomized, controlled, open-label multi-center study to assess the safety and efficacy of DFV890 in patients with COVID-19 pneumonia and impaired respiratory function | CDFV890D12201 PoC study in patients with COVID-19 | N0 ATI - NIBR | Langlo, Francois | Bhatkar, Priyanka | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Beata Mehes | Beata Mehes | Bonam, Rajesh Babu | Kurella, Rakesh Reddy | Not Started |  |  |  | DRM |  | Shrivastava, Nikhil | Completed | 01-Feb-2021: Rule File V5.0 updated and finalized in Subway to remove the form 'LBG002_TR' as this form is now pure qualitative form. SNOW-51 is raised . LSP and SMT programmer are notified. 26Nov2020: Backup: Chandrakala Whats planned: (Covid 19 study) Nothing planned as of now. 24-Nov-2020: RF V4.0 finalized for update to LB domain WRT PPC#05. SNOW-51 raised and LSP notified. 14-Aug-2020: RF V3.0 finalized for update to LB and DS domain. SNOW-51 raised and LSP notified. 15-Jun-2020 (SHRIVNI5): RF V2.0 finalized to map REDAT to CMS001 form in CM domain. SNOW-51 raised to rebuild CM domain in LSH. 15-May-2020 (SHRIVNI5): RF was finalized on 13th night and SNOW-05 was raised along with all the required documents. LSH setup completed on 14th May. 14May2020 : RF final and raised Snow ticket 24Apr2020: Screen designing ongoing, DBD has not shared the documents. Following up on the same. | None | None | 2020-05-14 05:30 | RF finalized within Go-live + 5 days | Mettugari, Sai Krishna | Varate, Rohit | Rohit Varate | Completed | 2020-05-14 | Completed | 2020-05-14 05:30 |  |  | 2020-05-14 05:30 | 2020-05-14 05:30 |  | 2020-08-25 05:30 |  |  |  | 85 | RaveX - Inhouse | No | Y1 | 2021-02-11 05:30 | 2021-02-12 05:30 | [9 empty] | NA | [5 empty] | 8 | 19 | 59 | 0 | 290 | 554 | 0 | 196 | 37 | 168 | 759 | 1 | 0 |  | Corona virus infection | Yes | Global | Open | Yes | [10 empty] | 2020-05-14 05:30 | [5 empty] | COVID19
CDFV890G1 | CDFV890G12101 | C4014607 | Phase I |  | Rave EDC - Inhouse |  |  | 2022-09-01 05:30 | DB Set-Up | DB Go-live | 2022-08-16 05:30 |  | 2022-03-11 05:30 |  |  | Planned | 2024-05-10 05:30 |  | 2024-06-07 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase 1/1b open label, multi-center, dose escalation study to assess the safety and efficacy of DFV890 as single agent and combination in adult patients with myeloid diseases | CDFV890G12101 Global Phase I PoC | N7 Oncology - NIBR | Langlo, Francois | BabuP, Anand | Thorat, Swapnil | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Liza Morgan | Liza Morgan | Chiranjeevi, Priyanka Boya | Chiranjeevi, Priyanka Boya | [15 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Chronic myelomonocytic leukaemia; Myelodysplastic syndrome | No | Global | Open | Yes
CDKY709A1 | CDKY709A12101C | C4001940 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-03-12 05:30 | 2019-04-16 05:30 | 2019-05-07 05:30 | DB Conduct | Final DBL | 2023-05-18 05:30 | 2019-05-07 05:30 | 2018-11-28 05:30 | 2019-01-10 05:30 |  | Active | 2024-04-15 05:30 |  | 2023-05-18 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I, open-label, multi-center, study of DKY709 as a single agent and in combination with spartalizumab PDR001 in patients with advanced solid tumors | CDKY709A12101C a study of DKY709 in Solid Tumors | N7 Oncology - NIBR | Langlo, Francois | Barnard, Carol | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Debby Long | Debby Long | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 12Mar2019 Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022. |  | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 19-Oct-2019: Rule file 13.0 got finalized in CREDI, as there is an issue with B1 domain. 14-Oct-2021: Rule file 12.0 got finalized in CREDI as per PPC#7 changes 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 26May2021 : Reassigned the study from Praveen Oguri to Rehana Banu. 26-May-2021: No activity, latest RF Version 11.0 28Apr2021 : Pratheeksha added B13L DTS and sent for peer review. 26-Apr-2021: Received finalized B13L DTS on 20-Apr-2021, working on RF update. 19-Apr-2021: Sent email to Study DBD to confirm on DTS finalization status. 11Feb2021: RF Version 10.0 Finalized (Updated B1TESTCD for PD-L1 Status CRF) and raised SNOW ticket (RITM2259435). 26JAN2021: RF Version 9.0 is finalized with PPC06 updates, SNOW51 ticket raised on 26JAN2021. 05Nov2020: RF Version 8.0 is updated and shared with Sujan for peer review, planning to finalize by 06Nov2020. 11Sep2020: All missing TU forms included in RF and raised SNOW ticket on 03Sep2020. 02Sep2020 : As per 02Sep2020 missing forms DTS report below forms pending. Praveen to update status 19 Aug 2020 : ZJG006_7, ZJG006_8, ZJG006_9, ZJG006_10, ZWS001 included in RF and Final 11Aug2020: ZJG006_7, ZJG006_8,ZJG006_9,ZJG006_10, ZWS001 added in PPC. expected to complte by 14th Aug. 22Apr2020: Rule File updated to include finalized DTSs B11L & B12L and SNOW51 ticket raised on 22Apr2020. 01Apr2020 : Reassigned RF from Roshan to Praveen 01Apr2020: No pending activity 03MAR2020: LSH rebuild completed SMT generated. 14 Jan 20: SMT rebuild and LSH rebuild requested for PPC updates made. Awaiting updates from SMT developer | None | None | 2019-05-02 05:30 | Transition Study | Nagalla, Lakshmi Naga Lavanya | Garje, Sagar | Rohit Varate | Completed | 2019-05-03 | Completed | 2019-06-06 05:30 | PREDRM was completed in 05 MAY 2019, DRM in 06 JUN 2019..DRM was published to JREVIEW and GPS | " Study transitioned SMT support delayed since SMEs occupied with other priority work." | 2019-06-07 05:30 | 2019-06-07 05:30 | transitioned study, Study Transition | 2019-08-22 05:30 |  |  | There are many queries received more of Clarifications, ZTINDC variable missing is the major issue, which was fixed | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 9 | 51 | 153 | 0 | 955 | 1309 | 0 | 302 | 43 | 763 | 2115 | 5 | 0 |  | Colorectal cancer; Melanoma; Nasopharyngeal cancer; Non-small cell lung cancer; Triple negative breast cancer | No | Global | Open | Yes | [10 empty] | 2019-06-04 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Polagoni, Bharghavi | None of the above | Yes
CDRB436A | CDRB436A2102 | C1001582 | Phase I | GSK | CRO - EDC |  |  | 2013-02-27 05:30 | DB Locked |  |  | 2013-11-05 05:30 |  | 2018-09-25 05:30 |  | Completed | 2020-12-31 05:30 | 2019-06-26 05:30 | 2021-02-11 05:30 | 2021-01-19 05:30 | FALSE | None | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | Phase I/IIa, 2-part, Multi-Center, Single-Arm, Open-Label Study to Determine the Safety, Tolerability and Pharmacokinetics of Oral Dabrafenib in Children and Adolescent Subjects with Advanced BRAF V600-Mutation Positive Solid Tumors | CDRB436A2102 Ph I/IIa Ped in HGG LGG and LCH | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Shevate, Pravinkumar | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Derryn Friend | C��cile Blin | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Glioma; Solid tumor | Yes | Global | Open | Yes | [16 empty] | None of the above
CDRB436A | CDRB436A2104 | C1001584 | Phase I | GSK | [7 empty] | 2015-02-19 05:30 |  |  |  | Completed |  |  |  | 2017-01-18 05:30 | FALSE |  |  |  | Outsourced |  | An open-label phase 1 study to evaluate the effects of\ndabrafenib (GSK2118436) on the single dose\npharmacokinetics of an OATP1B1/1B3 substrate and of a\nCYP3A4 substrate in subjects with BRAF V600 mutation\npositive tumors | PhI OATP1 and CYP3A4 subst effect (CDRB436A2104) | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Nathalie Force-Lambert | [66 empty] | Solid tumor | No | Local | Completed | Yes | [16 empty] | None of the above
CDRB436A | CDRB436A2106 | C1001123 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-12-19 05:30 |  | 2016-07-18 05:30 |  | Completed | 2019-09-30 05:30 | 2019-09-27 05:30 | 2019-11-01 05:30 | 2019-10-21 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A phase I, open label, multicenter, single dose study to evaluate the pharmacokinetics of dabrafenib in healthy subjects with normal renal function and subjects with impaired renal function | CDRB436A2106 PhI PK HV Renal Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Chelsea Kosecki; Elizabeth Miles | Chelsea Kosecki | Tadiparthy, Ramakanth | [14 empty] | Sundar, N Sushant |  | Sandeep Kadam | [12 empty] | Old CRO Study. Will conduct DDPASS before any milestone |  | FSOM - Outsourced | No | [5 empty] | ONC | PPD | Outsourced | 2016-12-13 05:30 |  | Mareedu, Vasu | Shewane, Roshni | PPD | [19 empty] | Renal impairment | No | Global | Open | Yes | [16 empty] | None of the above
CDRB436A | CDRB436A2107 | C1001124 | Phase I | NCDS | CRO - EDC |  | 2016-12-20 05:30 |  | DB Locked |  |  | 2016-12-20 05:30 |  | 2016-07-28 05:30 |  | Completed | 2019-04-08 05:30 | 2019-04-08 05:30 | 2020-05-12 05:30 | 2019-06-21 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A phase I, open label, multicenter, single dose study to evaluate the pharmacokinetics of dabrafenib in healthy subjects with normal hepatic function and subjects with impaired hepatic function | CDRB436A2107 PhI PK HV Hepatic Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther | Chelsea Kosecki | Chelsea Kosecki | Goyal, Rishu | [14 empty] | Varate, Rohit |  | Sandeep Kadam | [14 empty] | CRO | [6 empty] | ONC | PPD | Outsourced | 2016-12-13 05:30 |  |  |  | PPD | [19 empty] | Hepatic impairment | No | Global | Wind Down | Yes | [14 empty] | DBL | Mettugari, Sai Krishna | None of the above | No
CDRB436A | CDRB436A2201 | C1001585 | Phase II | GSK | [7 empty] | 2010-08-09 05:30 |  |  |  | Completed |  |  |  | 2016-09-02 05:30 | FALSE |  |  |  | Outsourced |  | A Phase II (BRF113710) single-arm, open-label study of\ndabrafenib (GSK2118436) in previously treated BRAF\nmutant metastatic melanoma | PhIIa in BRAFmut mel(BREAK2) (CDRB436A2201) | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Nathalie Force-Lambert | Nathalie Force-Lambert | [66 empty] | Metastatic melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
CDRB436A | CDRB436A2301 | C1001125 | Phase III | GSK | [7 empty] | 2010-12-23 05:30 |  |  |  | Completed |  |  |  | 2017-01-10 05:30 | FALSE |  |  |  | Outsourced |  | A Phase III randomized, open-label study comparing\nGSK2118436 to DTIC in previously untreated subjects with\nBRAF mutation positive advanced (Stage III) or metastatic\n(Stage IV) melanoma | PhIII DvsDTIC BRAFmut mel(BREAK3) (CDRB436A2301) | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Nathalie Force-Lambert | Nathalie Force-Lambert | [66 empty] | Metastatic melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
CDRB436A_MA | CDRB436A2X01B | C1001586 | Phase IV | GSK | CRO - EDC |  |  |  | DB Locked |  |  | 2010-11-02 05:30 |  | 2009-09-01 05:30 |  | Completed |  | 2018-04-09 05:30 |  | 2018-05-25 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | PhIV rollover of D for BRAFmut (CDRB436A2X01B) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Chinchansure, Basavraj | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Ankur Modi | Ankur Modi | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Solid tumor | No | Global | Completed | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B1401 | C1001589 | Phase IV | Other | CRO - EDC |  |  | 2019-06-24 05:30 | DB Conduct | Final DBL | 2022-08-31 05:30 | 2016-07-26 05:30 | 2019-04-29 05:30 | 2016-04-01 05:30 |  | Active | 2022-04-30 05:30 |  | 2022-08-31 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | The special drug use surveillance of Tafinlar 50 mg and 75 mg capsules and Mekinist 0.5 mg and 2 mg tablets | CDRB436B1401 Japan PMS_Melanoma | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | IROKAWA, TAKURO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | NOBUTAKA NAKAGAWA | NOBUTAKA NAKAGAWA | [17 empty] | Sushant Sundar | [28 empty] | Other | [19 empty] | Malignant melanoma | No | Global | Open | Yes | [16 empty] | None of the above
CDRB436A0 | CDRB436B2102 | C3001948 | Phase I | Other |  |  |  | 2020-03-10 05:30 |  |  |  | 2020-03-11 05:30 | 2020-07-01 05:30 | 2020-01-30 05:30 |  | Completed | 2020-12-25 05:30 | 2020-12-24 05:30 | 2021-02-18 05:30 | 2021-02-17 05:30 | FALSE |  |  |  | FULL Outsourced |  | A randomized, open-label, two-period crossover study to assess the relative bioavailability of dabrafenib in combination with trametinib administered with a low-fat low-calorie meal compared to under fasting condition in healthy subjects | CDRB436B2102 PhI Food Effect | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Jenni Featherstone | Amanda Taylor | [66 empty] | Food interaction | No | Global | Open | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2201 | C1001126 | Phase II | GSK | CRO - EDC |  |  | 2019-01-04 05:30 | DB Locked | Final DBL Achieved |  | 2010-03-26 05:30 |  |  |  | Completed | 2020-07-17 05:30 | 2018-02-27 05:30 | 2020-09-25 05:30 | 2018-05-08 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An Open-Label, Dose-Escalation, Phase I/II Study to Investigate the Safety, Pharmacokinetics, Pharmacodynamics and Clinical Activity of the BRAF Inhibitor GSK2118436 in Combination with the MEK Inhibitor GSK1120212 in Subjects with BRAF Mutant Metastatic Melanoma | CDRB436B2201 PhI/II Safety PK PD Clin in mMel | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sharma, Anurag | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther | Severine Niglis | Andrea Westervelt | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Malignant melanoma; Melanoma; Skin melanoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDRB436B_MA | CDRB436B2202 | C1001595 | Phase II | GSK | CRO - EDC |  |  |  | DB Locked |  |  | 2014-08-06 05:30 | 2018-10-25 05:30 | 2015-08-14 05:30 |  | Completed | 2020-05-15 05:30 | 2017-04-26 05:30 | 2020-06-30 05:30 | 2017-07-31 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | An open-label, multicenter, corollary study of pre-operative therapy with dabrafenib and the combination of dabrafenib with trametinib in subjects with BRAF mutation-positive metastatic melanoma to the brain | CDRB436B2202 PhII preOp PK in BRAFmut mMel Brain | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Maritz, Henri | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Tara Glynos | Tara Glynos | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Metastatic malignant melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2204 | C1001127 | Phase II | GSK | CRO - EDC |  |  | 2019-01-04 05:30 | DB Locked | Final DBL Achieved |  | 2014-02-21 05:30 | 2018-08-17 05:30 | 2013-07-26 05:30 |  | Completed | 2020-07-17 05:30 | 2018-02-14 05:30 | 2020-09-25 05:30 | 2018-04-12 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase II, Open-Label, Multicentre Study of Dabrafenib\nplus Trametinib in Subjects with BRAF Mutation- Positive\nMelanoma that has Metastasized to the Brain | CDRB436B2204 COMBI-MB PhII D and T in Mel BM | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vankayala, Vijay | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther | Qian Xia | Nathalie Force-Lambert | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Metastatic melanoma | Yes | Global | Open | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2205 | C1001592 | Phase II | GSK | CRO - EDC |  |  | 2019-01-07 05:30 | DB Locked | Final DBL Achieved |  | 2015-06-12 05:30 | 2018-08-20 05:30 | 2013-07-08 05:30 |  | Completed | 2021-04-09 05:30 | 2019-08-08 05:30 | 2021-05-07 05:30 | 2021-05-13 05:30 | FALSE | Non critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An Open-Label, Multi-Center Study to Investigate the Objective Response Rate of Dabrafenib in Combination with Trametinib in Subjects with BRAF V600 Mutation-Positive Melanoma | CDRB436B2205 PhIIa mel ORR Acral CN PanAsia | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Basani, Sravan | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Stephanie Savary | Stephanie Savary | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 2 | 0 |  | Melanoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2301 | C1001128 | Phase III | GSK | Other |  |  | 2018-06-08 05:30 | DB Locked | Final DBL Achieved |  | 2012-05-04 05:30 | 2018-07-20 05:30 | 2012-02-08 05:30 |  | Completed | 2019-02-28 05:30 | 2019-02-28 05:30 | 2019-05-13 05:30 | 2019-03-19 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase III, randomized, double-blinded study\ncomparing the combination of the BRAF inhibitor,\ndabrafenib and the MEK inhibitor, trametinib to\ndabrafenib and placebo as first-line therapy in\nsubjects with unresectable (Stage IIIC) or metastatic\n(Stage IV) BRAF V600E/K mutation-positive cutaneous\nmelanoma | CDRB436B2301 PhIII 1L V600E/Kmut cut mel COMBI-D | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Shevate, Pravinkumar | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther |  | Andrea Westervelt | [17 empty] | Sandeep Kadam | [28 empty] | Other | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 1 | 0 |  | Metastatic malignant melanoma; Metastatic melanoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2302 | C1001129 | Phase III | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2012-06-04 05:30 |  | 2012-02-15 05:30 |  | Completed | 2019-03-15 05:30 | 2019-04-25 05:30 | 2020-01-10 05:30 | 2019-06-21 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase III, randomised, open-label study comparing the\ncombination of the BRAF inhibitor dabrafenib and the\nMEK inhibitor trametinib to the BRAF inhibitor\nvemurafenib in subjects with unresectable (stage IIIc) or\nmetastatic (stage IV) BRAF V600E/K mutation positive\ncutaneous melanoma | CDRB436B2302 PhIII D_T vs D_V in cut mel COMBI-V | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sharma, Anurag | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther | Andrea Westervelt | Andrea Westervelt | [17 empty] | Sandeep Kadam | [28 empty] | TCS | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 2 | 0 |  | Metastatic malignant melanoma; Metastatic melanoma | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDRB436B_MA | CDRB436B2401 | C1001593 | Phase II | GSK | [7 empty] | 2013-12-24 05:30 |  | 2013-04-15 05:30 |  | Completed |  | 2017-01-19 05:30 |  | 2017-04-11 05:30 | FALSE |  |  |  | Outsourced |  | Phase II biomarker study evaluating the upfront combination of BRAF inhibitor dabrafenib with MEK inhibitor trametinib versus the combination after eight weeks of monotherapy with dabrafenib or trametinib in patients with metastatic and unresectable stage III or IV melanoma harbouring an activating BRAF mutation | CDRB436B2401 PhII biomarker D_T in malMel COMBAT | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Tara Glynos | Tara Glynos | [66 empty] | Metastatic malignant melanoma | No | Global | Assumed Completed | Yes | [16 empty] | None of the above
CDRB436B_MA | CDRB436B2404 | C1001594 | Phase IV | NCDS | OC RDC - Inhouse |  | 2017-07-07 05:30 | 2017-11-09 05:30 | DB Locked | Final DBL Achieved |  | 2017-11-09 05:30 |  | 2016-11-18 05:30 |  | Completed | 2018-12-14 05:30 | 2018-12-14 05:30 | 2019-02-08 05:30 | 2019-02-15 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | Describe III: Dabrafenib Monotherapy and Dabrafenib-Trametinib Combination Metastatic Melanoma Therapy Named Patient Program (NPP), retrospective chart review to characterise patients with long term benefit | CDRB436B2404 PhIV D T BRAFmut mel DESCRIBE3 | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Varshney, Kapil | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Flora Miranda | Flora Miranda | Pilli, Bhaskar | [14 empty] | Nagalla, Lakshmi Naga Lavanya |  | Sandeep Kadam | [13 empty] | 100 |  | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-07-07 05:30 | 2017-07-07 05:30 |  |  | NA | [7 empty] | 29 | 0 |  |  | 0 |  |  |  | 299 |  |  |  | Metastatic melanoma |  | Global | Completed | Yes | [16 empty] | None of the above
CDRB436B | CDRB436B2407 | C4013549 | Phase IV | [12 empty] | Planned | [8 empty] | Outsourced |  |  | CDRB436B2407 China Mucosal Melanoma Ph IV RWE PMC | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Robert Ma | Xuhua Qiu | [66 empty] | Melanoma | No | Global | Open | Yes
CDRB436C | CDRB436C2201 | C1001130 | Phase II | GSK | CRO - EDC |  |  | 2019-01-07 05:30 | DB Locked | Final DBL Achieved |  | 2012-12-19 05:30 |  | 2012-10-10 05:30 |  | Completed | 2020-06-18 05:30 | 2020-06-18 05:30 | 2020-09-28 05:30 | 2020-11-02 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An Open-Label, Four-Part, Phase I/II Study to Investigate the Safety, Pharmacokinetics, Pharmacodynamics, and Clinical Activity of the MEK Inhibitor GSK1120212, BRAF Inhibitor GSK2118436 and the anti-EGFR Antibody Panitumumab in Combination in Subjects with BRAF-mutation V600E Positive Colorectal Cancer and in Subjects with CRC With Secondary Resistance to Prior Anti-EGFR Therapy. | CDRB436C2201 DRB,TMT,Panitumumab BRAFV600E Pos CRC | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Padigela, Hari | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther |  | Mimi Leung | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Colorectal cancer metastatic | Yes | Global | Wind Down | Yes | [16 empty] | None of the above
CDRB436E | CDRB436E1402 | C1001133 | Phase IV | Other | CRO - EDC |  |  | 2018-08-31 05:30 | DB Conduct | Final DBL | 2024-02-29 05:30 | 2018-07-31 05:30 | 2018-03-30 05:30 | 2018-03-30 05:30 |  | Active | 2023-10-31 05:30 |  | 2024-02-29 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Special drug use observational study of dabrafenib and trametinib in the patients with BRAF V600 mutation positive non-small cell lung cancer (NSCLC) | CDRB436E1402 Japan PMS_NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | INOUE, YUSUKE | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | NOBUTAKA NAKAGAWA | NOBUTAKA NAKAGAWA | [17 empty] | Sushant Sundar | [28 empty] | Other | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CDRB436E | CDRB436E2201 | C1001134 | Phase II | GSK | CRO - EDC |  |  | 2021-06-24 05:30 | DB Locked | Final DBL Achieved |  | 2011-06-20 05:30 |  | 2017-08-21 05:30 |  | Completed | 2020-12-30 05:30 | 2021-01-07 05:30 | 2021-03-17 05:30 | 2021-02-24 05:30 | FALSE | None | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase II study of the BRAF inhibitor dabrafenib as a single agent and in combination with the MEK inhibitor trametinib in subjects with BRAF V600E mutation positive metastatic (stage IV) non-small cell lung cancer | CDRB436E2201 PhII DvsDT in BRAFV600Emut NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sharma, Mokshitaa | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Christina Kim | Christina Kim | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 4 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CDRB436E | CDRB436ECN01 | C4004550 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-06-26 05:30 | 2020-06-26 05:30 | 2020-08-31 05:30 | DB Conduct | Final DBL | 2025-01-07 05:30 | 2020-08-19 05:30 | 2019-08-05 05:30 | 2019-06-27 05:30 |  | Active | 2024-11-15 05:30 |  | 2025-01-07 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An Open-Label, Single-arm Study to Evaluate the Safety and Efficacy of Dabrafenib in Combination with Trametinib in Chinese Patients with BRAF V600 Mutation-Positive Metastatic NSCLC | CDRB436ECN01 PhII NSCLC study in China | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Gorla, Krishna Sagar Reddy | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Stephanie Savary | Stephanie Savary | Gandla, Prashanth | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 |  |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 07-Apr-2021: RF V6.0 finalized in CREDI for FAMHO001 form as per updated SDTM annotation. SNOW-51 is raised. LSP and SMT programmer have been notified. 10-Feb-2021: RF V5.0 finalized in CREDI WRT B11L DTS. SNOW-51 is raised and LSP is notified. 28-Jan-2021: TU, TR and RS DTS included in Rule File V4.0 and finalized in CREDI. LSP and SMT developer are notified. 28-Dec-2020: RF V3.0 updated and finalized WRT PPC#01. SNOW-51 is raised. LSP and SMT developer are notified. 26Nov2020: Backup: Chandrakala Whats planned: Nothing planned as of now. 03-Aug-2020 (SHRIVNI5): This form was already included by Ashok in the initial version of rule file V1.0 27Jul2020 : QS2G7 is listed in 20jul report 15Jul2020: Rule File V2.0 is finalized in CREDI which is the latest one. 06Jul2020: RF will be transitioned from Ashok to Nikhil. 26Jun2020 : RF finalized in CREDI and SNOW-05 request (RITM1545409) has been raised with all the required documents 25Jun2020 : RF peer review completed and awaiting for golive. post which RF can be finalized 30Apr2020: Received ZX domain SRFs and I have reviewed and provided my comments to DBD. Waiting for the SDTM annotations. | None | None | 2020-06-26 05:30 |  | Polavarapu, Vanaja | Polavarapu, Vanaja | Sandeep Kadam | Completed | 2020-07-16 | Completed | 2020-08-03 05:30 |  |  | 2020-08-05 05:30 | 2020-08-25 05:30 | Study Transition | 2020-09-24 05:30 |  |  | The initial DDPASS was conducted in Sep-2020 with 100% success rate. 2nd round of DDPASS is ongoing for upcoming IA: DDPASS meeting 1 : 24-Mar-2021 DDPASS meeting 2 : 25-Mar-2021 | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 3 | 71 | 81 | 0 | 890 | 960 | 0 | 294 | 41 | 219 | 1220 | 8 | 0 |  | Non-small cell lung cancer | No | Local | Open | Yes | [10 empty] | 2020-08-03 05:30 | [5 empty] | None of the above | Yes
CDRB436F | CDRB436F2301 | C1001135 | Phase III | GSK | CRO - EDC |  |  | 2019-01-04 05:30 | DB Conduct | Final DBL | 2023-02-28 05:30 | 2013-01-08 05:30 | 2018-08-17 05:30 |  |  | Active | 2022-12-30 05:30 |  | 2023-02-28 05:30 |  | FALSE | Non critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CDRB436F2301 PhIII DT in Adjuvant Melanoma | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sharma, Mokshitaa | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Christina Kim | Christina Kim | [17 empty] | Sandeep Kadam | [28 empty] | NA | [11 empty] | 0 |  |  |  | 1586 | 1 | 0 |  | Melanoma | Yes | Global | Open | Yes | [16 empty] | None of the above
CDRB436F_MA | CDRB436F2410 | C3003261 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-06 05:30 | 2018-08-29 05:30 | DB Locked | Final DBL Achieved |  | 2018-08-29 05:30 | 2018-04-04 05:30 | 2018-04-04 05:30 |  | Active | 2021-10-22 05:30 | 2021-09-16 05:30 | 2021-12-03 05:30 | 2021-11-18 05:30 | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | COMBI-APlus: Open-label, phase IIIb study of dabrafenib in COMBInation with trametinib in the Adjuvant treatment of stage III BRAF V600 mutation-positive melanoma after complete resection to evaluate the impact on pyrexia related outcomes of an adapted pyrexia AE-management algorithm (Plus) | CDRB436F2410 adjuvant Interventional Trial | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Joshi, Amruta | Padigela, Hari | Sonmale, Pravin | Ninan, Esther | Flora Miranda | Flora Miranda | Munukutla, Valli | Iliyas, Mohamed | Completed | 2021-06-22 05:30 | 22Jun2021 : Transition from Valli Munukutla to Iliyas, Mohamed (Ext) PPC-10 eSAE PPC Completed. No PPC ongoing Transition from Santosh Yadav to Valli Munukutla |  | DRM (DIAL) | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 26OCT2021: RF V5.0 is final and SNOW 51 request RITM3123475 has been created for to rebuild RS domain. 05AUG2021: DM placed a request order for to add new study test codes. Once test codes are available in Reference metadata, data will flow to downstream. 05JUN2021: RSTEST codes are not available in Reference Metadata. Following up with Transitioned DBD and DM. 28Apr2021 : Sujan to followup on below comment. 6JAN2021: Rule file update is requested for updating RSTEST value. Rule file update is required. | None | None | 2018-12-20 05:30 | Transition Study and Legacy process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2018-12-28 | Completed | 2019-06-19 05:30 | JReview and GPS publish dates are as per LSH, could not find the correct LSH request date |  | 2018-12-06 05:30 | 2018-12-06 05:30 | Retrospective DRM studies | 2019-12-16 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 11 | 23 | 56 | 0 | 222 | 784 | 0 | 218 | 35 | 191 | 1010 | 2 | 0 |  | Melanoma | Yes | Global | Open | Yes | [10 empty] | 2019-06-19 05:30 |  |  |  | Interim-Analysis | Mettugari, Sai Krishna | None of the above | No
CDRB436F | CDRB436FCN01 | C4004800 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2020-12-02 05:30 | 2020-12-02 05:30 | 2020-12-29 05:30 | DB Conduct | DB Snapshot | 2023-02-22 05:30 | 2020-12-31 05:30 | 2020-06-30 05:30 | 2020-01-08 05:30 |  | Active | 2026-12-31 05:30 |  | 2027-02-11 05:30 |  | FALSE | NA | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CDRB436FCN01 PhIV RWE study Adj Mel China | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Shevate, Pravinkumar | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Stephanie Savary | Stephanie Savary | R, Ankit | Rapaka, Sindhuja | Not Started |  |  |  | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 6JAN2021: SG: No upcoming tasks. 02Dec2020 : RF final and Snow 05 raised 5Nov2020: RF update started. DB Golive planed for 18Nov2020. 05Oct2020 : had discussion on Study specific forms. Followup with DBD on current status. 8Sep2020: Following up with Lead DBD to know the status of screen design. 04Sep2020 : Followup with DBD on study. | None | None | 2020-12-02 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2021-01-08 | Completed | 2021-01-11 05:30 | LSH set up was delayed due to resource unavailability and 2-3 studies went live in same period. | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-01-11 05:30 | 2021-01-11 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-01-11 05:30 |  |  |  | 5 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 12 | 43 | 0 | 106 | 481 | 0 | 132 | 14 | 144 | 639 | 1 | 0 |  | Metastatic melanoma | No | Global | Open | Yes | [10 empty] | 2021-01-08 05:30 | [5 empty] | None of the above | Yes
CDRB436G | CDRB436G1401 | C4016698 | Phase IV | [6 empty] | Final DBL | 2027-02-26 05:30 |  | 2023-09-29 05:30 |  |  | Planned |  |  | 2027-02-26 05:30 | [5 empty] | Outsourced |  |  | CDRB436G1401 JPN PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | NOBUTAKA NAKAGAWA | [66 empty] | Glioma | No | Global | Open | Yes
CDRB436G | CDRB436G2101 | C1001136 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-07-07 05:30 |  | 2016-07-06 05:30 |  | Completed | 2018-05-28 05:30 |  | 2018-06-21 05:30 | 2018-06-21 05:30 | FALSE | NA | Rao, Sreekanth | Cluster C (fGSK,IHD,Sandoz) | Outsourced | Immuno-Oncology | A randomized, open-label, three-period cross-over study to investigate the relative bioavailability of two new oral suspension formulations of dabrafenib (10 x 10 mg dispersible tablets reconstituted in water) in comparison to dabrafenib HPMC capsules (2 x 50 mg) following a single oral dose of 100 mg in healthy adult volunteers | CDRB436G2101 PhI relBA for T Ped Form | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Chinchansure, Basavraj | Sonmale, Pravin | Purra, Shashikanth | Hiriyanna, Srinivas |  | Christina Kim | Yadav, Santosh | [14 empty] | Varate, Rohit |  | Sushant Sundar | [14 empty] | CRO | [6 empty] | ONC | Novartis | InHouse | 2017-02-03 05:30 |  |  |  | PPD | [19 empty] | Malignant melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
CDRB436G | CDRB436G2201 | C1001137 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-09-30 05:30 | 2018-01-31 05:30 | DB Conduct | Final DBL | 2023-07-12 05:30 | 2017-12-28 05:30 |  | 2015-11-07 05:30 |  | Active | 2023-05-30 05:30 |  | 2023-07-12 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | Phase II open-label global study to evaluate the effect of dabrafenib in combination with trametinib in children and adolescent patients with BRAF V600 mutation positive Low Grade Glioma (LGG) or relapsed or refractory High Grade Glioma (HGG) | CDRB436G2201 PhII Pediatric LGG HGG | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Juneja, Twinkle | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Karine Roiffe | Karine Roiffe | Bai, Chandrakala | Mareedu, Vasu |  | 2020-01-24 05:30 | [11 empty] | Kadam, Sandeep |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | Y1;#Y5;#YD;#ZJ |  |  |  |  | ONC | Novartis | ICON | 2017-09-30 05:30 | 2017-09-30 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 162 | 0 |  |  | 0 |  |  |  | 922 | 8 | 0 |  | Astrocytoma; Glioblastoma multiforme; Glioma; Medulloblastoma; Meningioma; Solid tumour | Yes | Global | Open | Yes | [16 empty] | None of the above
CDRB436G | CDRB436G2401 | C3003997 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2019-04-24 05:30 | 2019-06-27 05:30 | 2019-10-14 05:30 | DB Conduct | Final DBL | 2026-08-31 05:30 | 2019-11-04 05:30 | 2019-02-27 05:30 | 2019-03-13 05:30 |  | Active | 2026-07-20 05:30 |  | 2026-08-31 05:30 |  | FALSE | non critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An open label, multi-center roll-over study to assess long-term effect in pediatric patients treated with Tafinlar (dabrafenib) and/or Mekinist (trametinib) | CDRB436G2401 Long Term Follow up Study | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Joshi, Amruta | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Chelsea Kosecki | Chelsea Kosecki | Bakka, Sandeep | Bakka, Sandeep |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 24Apr2019 |  | DRM | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 03JUN2021: RF V4.0 is final and SNOW 51 RITM2636388 request has been created ZNO002 - Target Domain changed to CV domain from ZN domain as per the SDTM annotations and confirmation from SDTM programmer. 28May2021 : SDTM annotations received for pending form for PPC04 on 26th to work on Rule file. 22APR2021: PPC4 completed on 14APR21 but SDTM annotations have not been shared. Lead DBD following up with SDTM programmer. Note: SNOW 51 RITM2494709 request has been created which are not having dependency on Rule file. 6JAN2021: SG: No upcoming tasks. 22Jun2020 : In SHashi's absence Ashok updated RF V3.0 to include the PRG001 updates and raised SNOW51 request (RITM1526844) 23Apr2020: RF v2.0 is Finalized and included DSG005, EGG001_1, QSS001, RSS001, FAMH, ZTO003, ZTO003_1, ZPO001, ZPO003, ZBO001, ZBO002, ZTO001, ZTO001_1, PES001_1, PES002, ZXS001_1, ZXS002, ZXS003, ZXS005, PES001 (ZN) all the forms in this version. 14Apr2020 : Included RF for PPC changes and pending forms and sent for peer review (Angella) 03Apr2020: RF updates for PPC changes assigned to Ashok. 31mar2020 : Received PPC and all required docs for RF update on 31-Mar. 19-Mar-2020: PPC being implemented. Planned for PPC go-live in the week of 23-Mar. 10Mar2020: Followed up with DBD on PPC1. there are regular updates to PPC due to new requirments from study team. PPC will be worked upon from 16th march. 02Mar2020 : Same as below status and PPC ongoing 10Feb2020 : PES001Clarification pending from TAPOD and SDTM programmer on the Domain to be used. QSS001 Questionnaire not available in Reference metadata. EGG001 Interpretation should be included as part of test. DB update required. RSS001 Response assessment short name(RPTEST) needs to have Dictionary attached with appropriate abbreviated value(OVRLRESP). DB update required. ZP,ZT,ZB.SDTM annotations requested. LBG001_TR_3Analytes to be assigned for Triglycerides FAMH SDTM annotations requested. 18-Dec-2019: Rule file finalized. Shared for LSH Setup. Pages not included :OPG001,OPS001,PES001,QSS001,EGG001,RSS001,ZP,ZT,ZB,LBG001_TR_3,FAMH. 17-Dec-2019: Rule file peer review comments will be addressed and released for Final Review by EOB. Pages excluded as below. OPG001,OPS001,PES001,QSS001,EGG001,LBG003_TR,RSS001,RPG002,ZP,ZT,ZB,LBG001_TR_3 6-Dec-2019: Released for Peer QC (Chandrakala) | None | None | 2019-12-18 05:30 | Transition Study and Legacy process | Kadam, Sandeep | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-01-29 | Completed | 2020-01-29 05:30 | SNOW05 recevied on 18 Dec 2019. SMT development in progress |  | 2020-01-29 05:30 | 2020-01-29 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2020-05-07 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 7 | 21 | 68 | 0 | 232 | 648 | 0 | 202 | 40 | 283 | 971 | 1 | 0 |  | Cancer | No | Global | Open | Yes | [10 empty] | 2020-01-29 05:30 | [5 empty] | HA Commitment
CDRB436H | CDRB436H1403 | C3001319 | Phase IV | Paper |  |  |  | 2023-12-30 05:30 |  | Final DBL | 2024-07-15 05:30 |  | 2022-11-30 05:30 |  |  | Planned | 2024-07-13 05:30 |  | 2024-07-15 05:30 |  | FALSE |  |  |  | Undecided Sourcing |  | Special drug use surveillance of DRB436 for ATC | CDRB436H1403 JPN PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | ERI ASAYAMA | YUKIE YOSHIZAWA | [54 empty] | 40 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Anaplastic thyroid cancer | No | Global | Open | Yes | [16 empty] | None of the above
CDRB436J1 | CDRB436J12301 | C4007162 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-03-31 05:30 |  | 2021-11-22 05:30 | DB Conduct | Final DBL | 2026-11-19 05:30 | 2021-11-15 05:30 | 2020-12-16 05:30 | 2021-02-05 05:30 |  | Active | 2026-10-30 05:30 |  | 2026-11-19 05:30 |  | FALSE | Non-Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A randomized, double-blind, placebo-controlled Phase III study to evaluate the efficacy and safety of dabrafenib plus trametinib in previously treated patients with locally advanced or metastatic, radio-active iodine refractory BRAFV600E mutation-positive Differentiated Thyroid Cancer | CDRB436J12301 PhIII Study in DTC | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Karine Roiffe | Karine Roiffe | Moses, Leah | Moses, Leah | Not Started |  | 29Apr2021 : The 9 weeks KPI was intended to be followed, but this is not possible. This is a DO Accelerate pilot study. We faced initial delays owing to technical issues in the tool. Awaiting the clean ALS from TDM to upload in RAVE and initiate the DB build. As per TDM email dated 27Oct2020 with regards to Database developer assignment for study CDRB436J12301. the planned protocol finalization date is 04Dec2020 and the planned study Go-live date is end of March 2021. Though the FPFV is planned in Aug2021, we are planning to complete study go-live by end of March 2021 as this study is being considered as a pilot for DO Accelerate tool. Thanks. The DB Go live has been postponed to 03AUG2021 owing to delays related to technical issues in the DO Accelerate tool. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 13Oct2021: CDRB436J12301_Rule file_version 1.0 finalized in Subway and SNOW-05 LSH- New study Setup (TEST) request is also raised with ticket number- RITM3080843. 07Sep2021: DBD informed that the DB Go Live date has been postponed to 28SEP2021. 23Aug2021: Released CDRB436J12301_Rule file V0.1 for peer review. Peer review ongoing 09Aug2021: TDM shared the DTS for review. DTS reviewed and shared the comments 02Aug2021: After discussion with DBD, TDM and CDS, the DBD confirmed that the QS IDNUM will be confirmed after the Governance discussion. 02Aug2021: Requested DBD to confirm on QS IDNUM to be used for one of the QS form in the study, as the IDNUM and QSCAT values are mismatching with the Reference metadata. 27July2021: DBD informed that the Go-Live pushed to 7th Sep 2021 and Screen UAT will be completed by 3rd Aug 2021 22July2021: TDM shared QS DTS for review. Reviewed and shared the comments with TDM. Requested DBD to share the Screen UAT Status. 16July2021: DTS Review was completed and shared the comments with TDM. 15July2021: TDM shared ZX, RS TR and TU DTS for review. 09July2021: Updated ALS was shared by DBD. Rule file development is initiated 8July2021: Initial Review comments are shared with the DBD. Waiting for updated ALS. 7July2021: DBD shared the ALS, Approved SRFs and SDTM Annotation for initial review. 6June2021: Requested DBD to share the study status. The DBD informed that the CRFs are developed in the database and the dynamics development is ongoing. The planned DB Go live will be postponed considering the initial delays in finalizing the specs through DO Accelerate tool. 11May2021: Review of approved SRF completed. Waiting for DBD to share the ALS for review. 10May2021: Received SRFs for review from DBD. Review ongoing. 03May2021 : Not received SS forms for review. Follow up with DBD 27Jan2021 : Study assigned to Arpita with mentoring support from Kranthi. | None | None | 2021-10-13 05:30 |  | Kokane, Swapnil | Kokane, Swapnil | Sandeep Kadam | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Papillary thyroid cancer | No | Global | Open | Yes | [10 empty] | 2021-12-24 05:30 | [5 empty] | None of the above
CDRB436H | CDRB436X2201 | C1001588 | Phase II | GSK | CRO - EDC |  |  | 2014-03-12 05:30 | DB Locked |  |  | 2014-03-12 05:30 | 2013-07-09 05:30 | 2013-07-09 05:30 |  | Active | 2021-12-09 05:30 | 2021-12-10 05:30 | 2022-01-17 05:30 | 2022-02-09 05:30 | FALSE | Non priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase II, Open-label, Study in Subjects with BRAF V600E-Mutated Rare Cancers with Several Histologies to Investigate the Clinical Efficacy and Safety of the Combination Therapy of Dabrafenib and Trametinib | CDRB436X2201 PhII ROAR rare indications | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sharma, Mokshitaa | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther |  | Katharine Mary Hazell | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Anaplastic thyroid cancer; Bile duct cancer; Gastrointestinal stromal tumour; Germ cell neoplasm; Glioblastoma; Leukaemia | Yes | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CDRB436A | CDRB436X2X02B | C1001598 | Phase IV | NCDS | OC RDC - Inhouse |  | 2017-11-20 05:30 | 2018-01-01 05:30 | DB Conduct | Final DBL | 2028-01-28 05:30 | 2017-12-28 05:30 |  | 2017-06-26 05:30 |  | Active | 2027-12-21 05:30 |  | 2028-01-28 05:30 |  | FALSE | Roll over study | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An open label, multi-center, Phase IV roll-over protocol for patients who have completed a prior global Novartis sponsored Tafinlar (dabrafenib) and/or Mekinist (trametinib) study and are judged by the investigator to benefit from continued treatment. | CDRB436X2X02B PhIV Rollover all indications | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Shevate, Pravinkumar | Mali, Astik | Sonmale, Pravin | Ninan, Esther | Andrea Westervelt | Andrea Westervelt | Bai, Chandrakala | Mareedu, Vasu |  | 2019-12-11 05:30 | [11 empty] | Kommu, Ranjith Kumar |  | Sandeep Kadam | [13 empty] | 64 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-11-17 05:30 | 2017-11-17 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 18 | 0 |  |  | 0 |  |  |  | 150 | 1 | 0 |  | Solid tumor | No | Global | Open | Yes | [16 empty] | None of the above
CDSUU001_MA | CDSUU0012401 | C1001140 | Phase IV | RAVE_RAW | [7 empty] | 2016-07-29 05:30 |  | 2016-03-29 05:30 |  | Completed | 2017-11-22 05:30 | 2017-11-22 05:30 | 2018-08-10 05:30 | 2018-07-31 05:30 | FALSE |  |  |  | Alcon InHouse |  | Clinical evaluation following use of Systane Balance in Patients with Lipid deficient dry eye (Systane Balance vs. Optive Advance Study) | Systane Balance v Optive Advance Stu_CDSUU0012401 | P5 Ophthalmology | [5 empty] | Ajit Patil; Sarah Flynn | Ajit Patil | [66 empty] | Dry eye | No | Global | Completed | Yes | [16 empty] | None of the above
CDVH112A1 | CDVH112A12101 | C4006489 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-08-02 05:30 | Study Planned | Final DBL | 2027-08-27 05:30 |  | 2023-04-25 05:30 |  |  | Planned | 2027-05-28 05:30 |  | 2027-08-27 05:30 |  | FALSE | NIBR RACE | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA |  | CDVH112A12101 LSC FIH and POC | N8 Ophthalmology - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Karen Holopigian | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Dry eye | No | Global | Open | Yes | [16 empty] | None of the above
CDYP688A1 | CDYP688A12101 | C4013592 | Phase I+II |  | Rave EDC - Inhouse |  |  | 2022-05-25 05:30 | DB Set-Up | DB Go-live | 2022-03-24 05:30 |  | 2021-12-17 05:30 | 2022-01-03 05:30 |  | Planned | 2025-12-19 05:30 |  | 2026-03-13 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase I/II, multi-center, open label study of DYP688 in patients with metastatic uveal melanoma and other GNAQ/11 mutant melanomas | CDYP688A12101 Trial | N7 Oncology - NIBR | Langlo, Francois | Jain, Rahul | Kocharekar, Poonam Vilas | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Mary Ising | Mary Ising | Das, Devashish | Das, Devashish | [15 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Malignant melanoma; Uveal Melanoma | No | Global | Open | Yes
CECF843A | CECF843A2201 | C3002728 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-09-14 05:30 | 2020-08-28 05:30 | 2020-10-01 05:30 | DB Locked | Final DBL Achieved |  | 2020-10-06 05:30 | 2020-04-01 05:30 | 2020-04-06 05:30 |  | Completed |  | 2021-05-13 05:30 | 2021-10-08 05:30 | 2021-10-11 05:30 | FALSE | DCN Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | Double blind, double masked multicenter study to evaluate the safety and efficacy of ECF843 vs Vehicle | CECF843A2201 Phase 2 Safety and Efficacy trial | P5 Ophthalmology | Navarro, Christelle | Bangera, Payal | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Liza Svoboda | Liza Svoboda | Sinha, Deepakshi | Kurella, Rakesh Reddy |  |  | moved from 10Jun2020 moved to 30Dec2019 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 14Sep2019 |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 01OCT21: RF V4.0 is final and SNOW 51 request RITM3041045 has been created. Request you to add MO domain and rebuild AE domain 01MAR21: RF V3.0 has been finalized and SNOW 51 request RITM2314415 has been created 24FEB21: QS4L DTS received. RF development is ongoing. 26NOV20: RF has been finalized and SNOW 51 request RITM2031762 has been created. Change: QS1L, QS2L and QS3L DTS have been added. 02SEP20: RF has been finalized and SNOW 05 request is created. Note: no pending forms and DTS 26AUG20: RF has been released for peer review 19AUG20: Received new ALS for RF development and it will be rework for RF developer. Rule file will be released for Peer review today. 04AUG20: During RF development it has been noticed that inconsistency between SDTM annotations and variables used in the database and also data is not available for few fields and form. Waiting response from DBD. 03AUG20: RF development is ongoing. All study specific pages review has been completed. 24JUL20: Study specific pages have been reviewed and provided comments. Requested for updated ALS. 07JUL20: For few study specific pages inputs have been provided on 01JUL20. Today requested DBD for the SDTM annotations. 26JUN2020: As per DBD confirmation, golive timelines might change. 12 study specific pages will be shared for review on 29JUN20 25JUN2020: No updates from DBD even after several followups offline and emails. 28MAY2020: The Go-live timelines has been pushed to 10 August, 2020. 26May2020 : no update from DBD . Sent a followup email. 24MAR2020: No Rule file activities have been started and screens are not final yet. Golive has been planned on 10AUG2020. 02MAR2020: Screens are not finalized yet and expected date of completion is MAY2020. 29-NOV-2019: Screens are not finalized yet | None | None | 2020-09-02 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2020-09-28 | Completed | 2020-09-28 05:30 |  |  | 2020-09-28 05:30 | 2020-09-28 05:30 |  | 2021-01-29 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes |  | 2021-10-13 05:30 | 2021-10-18 05:30 | [9 empty] | NA | [5 empty] | 5 | 6 | 46 | 0 | 101 | 433 | 0 | 153 | 32 | 108 | 573 | 3 | 0 |  | Dry eye | No | Global | Open | Yes | [10 empty] | 2020-09-28 05:30 |  |  |  |  | Manoharan, Vivek | GDD annual target | Yes
CEDI048A0 | CEDI048A02101 | C4010237 | Phase I | Other |  |  |  | 2022-04-12 05:30 |  | Final DBL | 2023-01-03 05:30 |  | 2021-12-04 05:30 | 2021-12-01 05:30 |  | Planned | 2022-11-29 05:30 |  | 2023-01-03 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CEDI048A02101 FIH SAD/MAD in Crypto | R4 NITD - NIBR | [5 empty] | Robert Beecham | Robert Beecham | [66 empty] | Cryptosporidiosis | Yes | Global | Open | Yes | [16 empty] | None of the above
CEGA230B | CEGA230B2102 | C4005031 | Phase I | NCDS |  |  |  | 2020-01-24 05:30 |  |  |  | 2020-01-24 05:30 | 2019-11-18 05:30 | 2019-11-20 05:30 |  | Completed | 2020-08-28 05:30 | 2020-08-28 05:30 | 2020-10-21 05:30 | 2020-10-26 05:30 | FALSE |  |  |  | FULL Outsourced |  | A randomized, partially blinded, placebo- and positive controlled 4-period cross-over study to assess the effects of triclabendazole on the heart rate-corrected QT intervals in healthy volunteers | CEGA230B2102 TQT | P6 Global Health | [5 empty] | Cathy Gray | Amanda Taylor | [66 empty] | Proarrhythmic effect | No | Global | Open | Yes | [16 empty] | None of the above
CEGA230B | CEGA230B2404 | C4005133 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2020-02-28 05:30 | 2020-12-15 05:30 | 2022-02-28 05:30 | DB Conduct | Final DBL | 2026-04-23 05:30 | 2022-02-11 05:30 | 2019-11-06 05:30 | 2019-11-06 05:30 |  | Active | 2026-03-19 05:30 |  | 2026-04-23 05:30 |  | FALSE | PMC to FDA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | An open-label, single-arm study to assess the treatment outcome with Egaten 20mg/kg in approx. 300 patients with fascioliasis. | CEGA230B2404 PMC 20mg Safety Reporting Study | P6 Global Health | Vithala, Srinivas | Khatua, Sandeep | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Kanan Jhala | Kanan Jhala | R, Ankit | Rapaka, Sindhuja | Not Started |  | DB golive moved from 8/31/2020 to 10Oct2020 as per DBD Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 28Feb2020 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 17-Feb-2021: finalized RF_V2.0 as the latest LB guidance 21-Dec-2020: RF is final on 15-Dec-2020 and SNOW ticket raised 27-Nov-2020: RF draft version 0.2 is released for peer review. 14Aug2020 : Supporting DBD on SS forms 05Feb2020 : Study assignment email sent to DB 21-Dec-2020: RF is final on 15-Dec-2020 27-Nov-2020: RF draft version 0.2 is released for peer review. 14Aug2020 : Supporting DBD on SS forms 05Feb2020 : Study assignment email sent to DB |  |  | 2020-12-15 05:30 | RF finalized within Go-live + 5 days | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2020-12-28 | Completed | 2021-07-06 05:30 |  | DRM setup on hold due to updates in pre-requisite documents. | 2021-07-07 05:30 | 2021-07-07 05:30 |  | 2021-07-09 05:30 |  |  |  | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 3 | 11 | 47 | 0 | 113 | 551 | 0 | 173 | 34 | 146 | 731 | 0 | 0 |  | Infection parasitic | No | Global | Open | Yes | [10 empty] | 2021-07-06 05:30 | [5 empty] | HA Commitment
CEGF816A | CEGF816A2302 | C3003664 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2018-06-15 05:30 |  | 2021-06-11 05:30 | DB On hold | Final DBL Achieved |  |  | 2019-11-29 05:30 | 2018-03-09 05:30 |  | Completed | 2027-04-21 05:30 |  | 2027-06-30 05:30 | 2019-11-13 05:30 | FALSE | Study cancelled | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Randomized, Open-label, Phase III Study of single agent Nazartinib Versus Investigatorâs choice (Erlotinib or Gefitinib) as First-Line Treatment in Patients with locally advanced or metastatic Non-Small Cell Lung Cancer harboring EGFR Activating Mutations | CEGF816A2302 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vaishnav, Deepti | Majumder, Sabarni | Sahu, Vandana | Hiriyanna, Srinivas | Sarah Kenny | Leslie O'Sullivan-Djentuh | K S, Suneeth Kumar | K S, Suneeth Kumar |  |  | Changed status from On hold to Cancelled as per DM BOW. 21Jun2018 : The study CEGF816A2302 is now suspended and no development activities needed for this study. | [10 empty] | Challa, Nandini |  | Sushant Sundar | [15 empty] | No | [12 empty] | NA | [7 empty] | 94 | 0 |  |  | 0 |  |  |  | 975 |  |  |  | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CEGF816A | CEGF816X2101 | C1001209 | Phase I | NCDS | OC RDC - Inhouse | 2014-04-16 05:30 | 2014-04-16 05:30 |  | DB Conduct | Final DBL | 2023-12-14 05:30 | 2014-06-06 05:30 |  | 2014-02-05 05:30 |  | Active | 2023-10-28 05:30 |  | 2023-12-14 05:30 |  | FALSE | Not Applicable | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase l/ll, multicenter, open-label study of EGFRmut-TKI EGF816, administered orally in adult patients with EGFRmut solid malignancies | CEGF816X2101 EGF816 in EGFRmut–TKI NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Medisetti, Yugeshwar | Girme, Abhijit | Sahu, Vandana | Hiriyanna, Srinivas | Brinda Sharma | Brinda Sharma | Oguri, Praveen | Oguri, Praveen | [13 empty] | Challa, Nandini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse |  | 2014-04-11 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 215 | 0 |  |  | 0 |  |  |  | 717 | 9 | 0 |  | Malignant tumour | No | Global | Open | Yes | [14 empty] | Interim-Analysis | Adi, Vishnupriya | None of the above | Yes
CEGF816C1 | CEGF816X2102 | C1200698 | Phase I | NCDS | OC RDC - Inhouse | 2017-11-29 05:30 | 2017-11-29 05:30 | 2018-01-29 05:30 | DB Conduct | Final DBL | 2023-01-02 05:30 | 2018-01-29 05:30 |  | 2017-07-26 05:30 |  | Active | 2022-11-04 05:30 |  | 2023-01-02 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase Ib, open label, multi-center study to characterize the safety, tolerability and preliminary efficacy of EGF816 in combination with selected targeted agents in EGFR mutant NSCLC | CEGF816X2102 Phase Ib NSCLC study | N7 Oncology - NIBR | Langlo, Francois | Beukes, Ellouise | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sergio Vicente Gabarda | Sergio Vicente Gabarda | Tadiparthy, Ramakanth | Gehlawat, Priya |  |  | Ramkanth transitioned study to Priya. | [10 empty] | Tidke, Shyam |  | Rohit Varate | [13 empty] | 93 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-11-29 05:30 | 2017-11-29 05:30 |  | Gehlawat, Priya | IQVIA | [7 empty] | 216 | 0 |  |  | 0 |  |  |  | 666 | 8 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CEGF816B1 | CEGF816X2201C | C1200693 | Phase II | NCDS | OC RDC - Inhouse | 2015-01-05 05:30 | 2015-01-05 05:30 |  | DB Locked |  |  | 2015-02-09 05:30 |  | 2014-10-20 05:30 |  | Completed | 2021-12-31 05:30 | 2021-02-05 05:30 | 2021-04-15 05:30 | 2021-04-20 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase II, multicenter, open-label study of EGF816 in combination with Nivolumab in adult patients with EGFR mutated non-small cell lung cancer and of INC280 in combination with Nivolumab in adult patients with cMet positive non-small cell lung cancer | CEGF816X2201C | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Kiki Gao | Qiqi Gao | Joshi, Alekhya | Mareedu, Vasu | Completed | 2020-05-21 05:30 | [11 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Quintiles | ICON | 2015-01-05 05:30 | 2015-01-05 05:30 | Mareedu, Vasu | Shewane, Roshni | IQVIA | [7 empty] | 106 | 0 |  |  | 0 |  |  |  | 557 | 4 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above | Yes
CEGT710A0 | CEGT710A02101 | C4016382 | Phase I |  |  |  |  | 2022-10-17 05:30 |  | Final DBL | 2023-11-06 05:30 |  | 2022-09-16 05:30 |  |  | Planned | 2023-09-11 05:30 |  | 2023-11-06 05:30 | [5 empty] | InHouse |  |  | CEGT710A02101 FIH SAD/MAD in SARS-CoV-2 | R4 NITD - NIBR | [5 empty] | Emma Hakansson | Emma Hakansson | [66 empty] | Corona virus infection | No | Global | Open | No
CEJE514C | CEJE514C1401 | C3001189 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2011-07-01 05:30 | 2019-04-29 05:30 |  |  | Completed | 2023-04-10 05:30 | 2014-12-17 05:30 | 2023-04-10 05:30 | 2014-12-17 05:30 | FALSE |  |  |  | Outsourced |  |  | CEJE514C1401 JPN PMS | P5 Ophthalmology | [6 empty] | CHIHIRO KATO | [66 empty] | Eye pain | No | Global | Completed | Yes | [16 empty] | None of the above
CELC200B | CELC200B1401 | C1001141 | Phase IV | Other |  |  |  | 2015-07-14 05:30 |  |  |  | 2015-07-14 05:30 | 2015-03-30 05:30 | 2015-03-30 05:30 |  | Completed | 2018-07-26 05:30 | 2018-08-31 05:30 | 2018-10-30 05:30 | 2018-07-25 05:30 | FALSE |  |  |  | Outsourced |  | Drug use observational study of Stalebo in ParkinsonÂ¿s disease | JPN PMS_CELC200B1401 | P6 Global Health | [5 empty] | MARIKO YAMADA | MARIKO YAMADA | [66 empty] | Parkinson's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CEMA401A0 | CEMA401A1101 | C1001144 | Phase I | Other |  |  |  |  | DB Locked |  |  | 2017-03-17 05:30 |  | 2017-01-13 05:30 |  | Completed |  | 2017-05-11 05:30 | 2017-10-31 05:30 | 2017-09-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Outsourced | NIBR - NS | A randomized, placebo-controlled, single ascending and multiple oral doses study to assess the safety, tolerability and pharmacokinetics of EMA401 in Japanese healthy adult and elderly subjects and Caucasian healthy adult subjects. | CEMA401A1101 EMA401A J_ESS and CSF PK | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | SATORU SHINMYO | SATORU SHINMYO | [15 empty] | Suzuki, Hiroko |  | Rohit Varate | [28 empty] | NA | [19 empty] | Neuropathic pain | No | Global | Completed | Yes | [16 empty] | None of the above
CEMA401A0 | CEMA401A2101 | C1001145 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-07-27 05:30 |  | 2017-05-17 05:30 |  | Completed |  | 2017-08-30 05:30 | 2018-01-08 05:30 | 2017-12-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED InHouse | NIBR - NS | A single-center, open-label, single oral dose study to investigate the absorption, distribution, metabolism, and excretion (ADME) and pharmacokinetics of EMA401 after a single dose of [14C] EMA401 in healthy male subjects | CEMA401A2101 EMA401A hADME study in hv's | P4 Neuroscience | Langlo, Francois | Bhoite, Raviraj Vijay | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Chiara Pazzagli | Chiara Pazzagli | [15 empty] | Kumar, Ranjeet |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Neuropathy peripheral | No | Global | Completed | Yes | [16 empty] | None of the above
CEMA401A0 | CEMA401A2102 | C3000988 | Phase I | NCDS |  |  |  | 2019-01-23 05:30 | DB Locked |  |  | 2019-01-23 05:30 | 2018-10-19 05:30 | 2018-07-30 05:30 |  | Completed | 2019-07-04 05:30 | 2019-07-04 05:30 | 2019-10-07 05:30 | 2019-07-30 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CEMA401A2102 DDI with midazolam | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Anxiety | No | Global | Completed | Yes | [16 empty] | None of the above
CEMA401A | CEMA401A2201 | C1001142 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-06-09 05:30 |  | DB Locked |  |  | 2017-06-27 05:30 |  | 2017-02-01 05:30 |  | Completed | 2020-08-28 05:30 |  | 2019-07-11 05:30 | 2019-06-11 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | IDMA Transaction | DF NS | A double-blind, placebo-controlled, randomized dose ranging trial to determine the safety and efficacy of three dose levels of EMA401 in reducing 24-hour average pain intensity score in patients with post-herpetic neuralgia (EMPHENE) | CEMA401A2201 Ph II PHN | P4 Neuroscience | Ball, Michael | Bhardwaj, Puneet | Ghosh, Sourya | Sharma, Atul | Nair, Sreesha | Christie Doerr; Fiona O'Riain | Christie Doerr | Narasetty, Indumathi | [14 empty] | Polagoni, Bharghavi |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | Y1;#Y5;#YR;#ZK |  |  |  |  | Pharma | Novartis | InHouse | 2017-06-09 05:30 | 2017-06-09 05:30 | Kanchi, Pavan kumar | Mareedu, Vasu | NA | [7 empty] | 117 | 0 |  |  | 0 |  |  |  | 645 | 13 | 0 |  | Post herpetic neuralgia | Yes | Global | Completed | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | No
CEMA401A | CEMA401A2202 | C1001143 | Phase II | NCDS | OC RDC - Inhouse |  | 2018-02-02 05:30 | 2018-03-15 05:30 | DB Locked |  |  | 2018-03-14 05:30 |  | 2017-09-18 05:30 |  | Completed |  | 2019-03-25 05:30 | 2019-07-01 05:30 | 2019-06-21 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | IDMA Transaction | DF NS | A double-blind, placebo-controlled, randomized trial to determine the safety and efficacy of EMA401 100 mg b.i.d. in reducing 24-hour average pain intensity score in patients with painful diabetic neuropathy (EMPADINE) | CEMA401A2202 Ph II PDN | P4 Neuroscience | Ball, Michael | Shalini, Syamala | Ghosh, Sourya | Sharma, Atul | Nair, Sreesha | Christie Doerr; Laurent Ecochard | Christie Doerr | Narasetty, Indumathi | Samuel, Giftson | [13 empty] | Sahu, Ahallad |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse |  | 2018-02-02 05:30 | Kanchi, Pavan kumar | Mareedu, Vasu | NA | [7 empty] | 118 | 0 |  |  | 0 |  |  |  | 644 | 15 | 0 |  | Diabetic neuropathy | Yes | Global | Completed | Yes | [16 empty] | None of the above
CENA713D | CENA713D1401 | C1001146 | Phase IV | Other | [7 empty] | 2011-08-05 05:30 | 2018-01-18 05:30 | 2011-06-10 05:30 |  | Completed | 2014-01-31 05:30 | 2018-12-07 05:30 | 2018-11-30 05:30 | 2018-12-07 05:30 | FALSE |  |  |  | Outsourced |  | Drug use observational study of Exelon in Dementia | CENA713D1401 Japan PMS_Drug use study | P6 Global Health | [5 empty] | Lisa Jimmink_TAP | NOBUTAKA NAKAGAWA | [66 empty] | Dementia Alzheimer's type | No | Global | Open | Yes | [16 empty] | None of the above
CENA713D | CENA713D1402 | C1001147 | Phase IV | Other | [7 empty] | 2012-09-29 05:30 | 2017-12-08 05:30 | 2012-05-15 05:30 |  | Completed | 2018-11-30 05:30 | 2018-12-07 05:30 | 2018-11-30 05:30 | 2018-12-07 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of Exelon in Dementia | CENA713D1402 Japan PMS_Special drug use study | P6 Global Health | [5 empty] | KAZUHARU MIURA; Lisa Jimmink_TAP | NOBUTAKA NAKAGAWA | [66 empty] | Dementia Alzheimer's type | No | Global | Open | Yes | [16 empty] | None of the above
CENV396A0 | CENV396A02101 | C4012910 | Phase I | Other |  |  |  | 2021-04-01 05:30 |  |  |  | 2020-09-08 05:30 | 2022-04-03 05:30 | 2020-08-25 05:30 |  | Completed | 2022-06-24 05:30 | 2020-10-28 05:30 | 2022-07-26 05:30 | 2021-01-12 05:30 |  |  |  |  | FULL Outsourced |  |  | CENV396A02101 legacy trial 9303-102 | N6 Neuroscience - NIBR | [5 empty] | Denise Serra | Fernanda Do Valle Duraes | [66 empty] | Schizophrenia | No | Global | Open | Yes
CENV396A1 | CENV396A12101 | C4012909 | Phase I | Other | Other |  |  | 2021-07-12 05:30 | DB Locked |  |  | 2020-02-28 05:30 | 2021-05-30 05:30 | 2019-12-17 05:30 |  | Active | 2021-10-07 05:30 |  |  |  |  | Cadent | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - NS |  | CENV396A12101 legacy trial Cadent 9303-101 | N6 Neuroscience - NIBR | Langlo, Francois | Momin, Suhail | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Siobhan ONeill | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Schizophrenia | No | Global | Open | Yes
CEOH507A0 | CEOH507A02101 | C4011575 | Phase I |  |  |  |  | 2023-06-28 05:30 |  | Final DBL | 2024-07-17 05:30 |  | 2023-03-01 05:30 |  |  | Planned | 2024-05-22 05:30 |  | 2024-07-17 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CEOH507A02101 FIH study - population tbd | N5 DAx - NIBR | [6 empty] | Martha Watkins | [54 empty] | 50 | [7 empty] | 700 | 2 |  |  | Liver transplant | No | Global | Open | Yes
CERL080A | CERL080A2424 | C1001150 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2009-11-08 05:30 |  | 2009-07-10 05:30 |  | Completed | 2018-03-15 05:30 | 2018-03-26 05:30 | 2018-05-22 05:30 | 2018-05-22 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | Multicenter, prospective cohort study of the usage, effectiveness, tolerability and patient compliance of immunosuppressive regimens using Myfortic (mycophenolate sodium) to treat recent renal transplant recipients in routine clinical practice in China. (Authors: Primatesta P, Rothenbacher D, Dong G, Xu J ) | CERL080A2424 Myfortic PAC in China (NIS) | P6 Global Health | Vithala, Srinivas | Syed, Fayaz | Bhabhe, Nikhil | Regula, Ramakrishna | Krishnan, Kripesh | Marc Cousin | Marc Cousin | Tripathi, Shakuntala | R, Ankit | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA |  | AP21 | [17 empty] | Renal impairment |  | Global | Open | Yes | [16 empty] | None of the above
CETB115A_MA | CETB115A2409 | C1001153 | Phase IV | GSK | [7 empty] | 2015-06-18 05:30 |  | 2014-07-16 05:30 |  | Completed |  | 2016-12-31 05:30 |  | 2017-02-24 05:30 | FALSE |  |  |  | Outsourced |  | A global, prospective cohort study to evaluate the real-world use of eltrombopag in adult patients with chronic Hepatitis C Virus infection who are unable to initiate or maintain optimal interferon-based therapy due to thrombocytopenia | CETB115A2409 Epidemiolog/HcV GSK201111 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Beata Mehes | Linda Voice | [66 empty] | Hepatitis C | No | Global | Wind Down | Yes | [16 empty] | None of the above
CETB115A | CETB115A2X01B | C1001600 | Phase IV | GSK | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2022-04-01 05:30 | 2013-10-15 05:30 |  | 2013-05-07 05:30 |  | Active |  |  | 2022-04-01 05:30 |  | FALSE | Roll over study | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CETB115A2X01B fGSK200170 Rollover Study | PA Oncology (Hematology not for MA projects) | Paigaonkar, Gargi | Sharma, Mokshitaa | Mali, Astik | Sonmale, Pravin | Ninan, Esther | Lambert Asuagbor | Lambert Besemtabe Asuagbor | [17 empty] | Sandeep Kadam | [28 empty] | NA | [19 empty] | Thrombocytopenia | No | Global | Open | Yes | [16 empty] | None of the above
CETB115G | CETB115AUS01T | C1001160 | Phase I | Other | CRO - EDC |  |  | 2012-07-02 05:30 | DB On hold |  |  | 2012-07-02 05:30 |  |  |  | Active | 2023-02-24 05:30 |  |  |  | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | Eltrombopag added to standard immunosuppresion in treatment-naive severe aplastic anemia anemia | CETB115AUS01T 1L SAA/L1-C (hATG) NIH0150-US CRADA | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Juneja, Twinkle | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther |  | Parveen Yadav | [17 empty] | Sandeep Kadam | [28 empty] | NA | [16 empty] | 5 | 0 |  | Aplastic anaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CETB115B | CETB115B1401 | C1001601 | Phase IV | Other | Paper |  |  | 2010-12-21 05:30 | DB Locked |  |  | 2010-12-21 05:30 | 2010-10-27 05:30 | 2010-11-02 05:30 |  | Completed | 2016-04-15 05:30 | 2016-03-31 05:30 | 2020-10-16 05:30 | 2020-10-16 05:30 | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology |  | CETB115B1401 Japan PMS_ Ph IV/ITP/ITP | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | INOUE, YUSUKE | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO |  | MASAYUKI SATO | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Thrombocytopenia | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CETB115B | CETB115B2301 | C1001154 | Phase III | GSK | CRO - EDC |  |  |  | DB Locked |  |  | 2013-02-18 05:30 |  |  |  | Completed | 2018-11-14 05:30 |  | 2019-02-15 05:30 | 2019-03-08 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CETB115B2301(GSK ID#113765) | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | Chinchansure, Basavraj | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | Lambert Besemtabe Asuagbor | [17 empty] | Sandeep Kadam | [28 empty] | IQVIA | [22 empty] | Open | Yes | [16 empty] | None of the above
CETB115D | CETB115D2202 | C1001156 | Phase II | GSK |  |  |  | 2018-03-01 05:30 |  |  |  | 2013-09-05 05:30 |  |  |  | Completed |  |  | 2018-04-02 05:30 | 2017-03-10 05:30 | FALSE |  |  |  | Outsourced |  |  | CETB115D2202 (GSK#117146) | PA Oncology (Hematology not for MA projects) | [6 empty] | Lambert Besemtabe Asuagbor | [66 empty] | Thrombocytopenia | Yes | Global | Completed | Yes | [16 empty] | None of the above
CETB115E | CETB115E1201 | C1001157 | Phase II | GSK | Other |  |  |  | DB Locked |  |  | 2014-07-23 05:30 |  | 2014-03-31 05:30 |  | Completed |  | 2017-09-05 05:30 |  | 2017-11-30 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | Japan_ETB115E1201_IIB/SAA/SAA/L2-M_(GSK ID#200926) | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | Ohtaka, Masahiro | Pai, Ujwala | Tanada, Miyako | Ninan, Esther |  | RIE NAGAHARI | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Anaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CETB115E | CETB115E1202 | C1001158 | Phase II | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2015-05-12 05:30 |  |  |  | Completed |  | 2017-09-06 05:30 | 2018-05-01 05:30 | 2018-03-22 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | Japan_ETB115E1202_B/SAA/SAA/L1-C (ATG)_GSK#201793 | PA Oncology (Hematology not for MA projects) | Breton, Guillaume | Ohtaka, Masahiro | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | MASAYUKI ITO | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Aplastic anaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CETB115E | CETB115E1402 | C3001432 | Phase IV | Other | CRO - EDC |  |  | 2018-04-10 05:30 | DB Conduct | Final DBL | 2022-07-29 05:30 | 2018-04-10 05:30 | 2021-11-01 05:30 | 2017-07-24 05:30 |  | Active | 2021-11-04 05:30 | 2021-10-31 05:30 | 2022-07-29 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Special drug use study of Revolade for Aplastic anemia | CETB115E1402 Japan PMS_AA | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | TSURUTA, MIKANO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MASAYUKI SATO | MASAYUKI SATO | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Aplastic anaemia | No | Global | Open | Yes | [16 empty] | None of the above
CETB115E | CETB115E2201 | C1001159 | Phase II | NCDS | OC RDC - Inhouse | 2017-07-07 05:30 | 2017-07-07 05:30 |  | DB Conduct | Interim DBL | 2022-06-18 05:30 | 2017-09-30 05:30 |  | 2017-01-04 05:30 |  | Active | 2025-05-26 05:30 |  | 2025-07-07 05:30 |  | FALSE | non critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A phase II, open-label, non-controlled, intra-patient doseescalation study to characterize the pharmacokinetics after oral administration of eltrombopag in pediatric patients with refractory, relapsed or treatment naÃ¯ve severe aplastic anemia or recurrent aplastic anemia | CETB115E2201 (OCD200936 GSK_PIP) | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Shevate, Pravinkumar | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Lambert Asuagbor | Lambert Besemtabe Asuagbor | Tadiparthy, Ramakanth | Iliyas, Mohamed |  |  | Ramakanth transitioned to Iliyas | [10 empty] | Manoharan, Vivek |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | Y5 |  |  |  |  | ONC | Novartis | ICON | 2017-07-07 05:30 | 2017-07-07 05:30 | Iliyas, Mohamed | Gehlawat, Priya | NA | [7 empty] | 122 | 0 |  |  | 0 |  |  |  | 450 | 4 | 0 |  | Anaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CETB115E | CETB115E2202 | C3004538 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-08-14 05:30 | 2019-09-19 05:30 | 2019-12-09 05:30 | DB Conduct | Final DBL | 2023-05-15 05:30 | 2019-12-09 05:30 | 2019-04-18 05:30 | 2019-01-25 05:30 |  | Active | 2023-04-18 05:30 |  | 2023-05-15 05:30 |  | FALSE | Non-Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A non-randomized, open-label, phase II study to assess the safety and efficacy of eltrombopag in Chinese patients with refractory, severe aplastic anemia | ETB115E2202 China Refractory SAA | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Yuanxi Shi | Yuanxi Shi | Suzuki, Hiroko | Rapaka, Sindhuja |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 14Aug2019 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 06-Jul-2020(Kranthi): No pending issues 04Mar2020 : All pending forms included in RF V2.0 and released for LSH setup. 02-Mar-2020: Included XG001, B2O001 and B2O003 forms in V1.1 and released for Peer review. 05Feb2020: Follwed up with DBD for SDTM annotations for pending 3 forms. 09-Jan-2020: XGO001, B2O001 and B2O003 forms are excluded due to unavailability of SDTM annotations | None | None | 2020-01-27 05:30 | SDTM annotations delayed | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2020-01-28 | Completed | 2020-01-29 05:30 | Rulefile created and Sent for Peer review. DQP - received on 06-JAN-2019. Setup is in Progressnow. | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2020-01-29 05:30 | 2020-01-29 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2020-08-24 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 8 | 58 | 62 | 0 | 527 | 635 | 0 | 162 | 35 | 205 | 875 | 1 | 0 |  | Aplastic anaemia | No | Global | Open | Yes | [10 empty] | 2020-01-23 05:30 | [5 empty] | None of the above | Yes
CETB115E_MA | CETB115E2403 | C1001603 | Phase II | NCDS | OC RDC - Inhouse | 2017-05-11 05:30 | 2017-05-11 05:30 |  | DB Conduct | Final DBL | 2022-08-03 05:30 | 2017-05-11 05:30 |  | 2016-10-18 05:30 |  | Active | 2022-06-22 05:30 |  | 2022-08-03 05:30 |  | FALSE | Not a submission study | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | Phase II, open label, single-arm, two-stage design trial to assess efficacy and safety of Eltrombopag combined with cyclosporine as first line therapy in patients with severe acquired aplastic anemia | CETB115E2403 SOAR PhII SAA SAA Cyclosporine | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Begari, Swathi | Mali, Astik | Sonmale, Pravin | Ninan, Esther | Anne Ruault | Anne Ruault | Samuel, Giftson | Gehlawat, Priya | [13 empty] | Kadam, Sandeep |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | ZK |  |  |  |  | ONC | Novartis | ICON | 2017-03-07 05:30 | 2017-03-07 05:30 | Gehlawat, Priya | Iliyas, Mohamed | NA | [7 empty] | 117 | 0 |  |  | 0 |  |  |  | 495 | 7 | 0 |  | Aplastic anaemia | No | Global | Open | Yes | [16 empty] | None of the above
CETB115G | CETB115G2201 | C4005101 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-04-17 05:30 | 2020-07-13 05:30 | 2020-11-27 05:30 | DB Conduct | Interim DBL | 2022-07-12 05:30 | 2020-11-04 05:30 | 2019-12-11 05:30 | 2019-12-10 05:30 |  | Active | 2024-12-09 05:30 |  | 2025-01-20 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A non-randomized, open label, multi-center, Phase II study to assess the safety and efficacy of eltrombopag in combination with rabbit anti-thymocyte globulin (r-ATG) and cyclosporine A (CsA) in East-Asian patients with treatment naive severe aplastic anemia (REACTS) | CETB115G2201 Pan Asian | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Matthias Scharenberg | Matthias Alexander Scharenberg | Lingampalli, Rohit | Iliyas, Mohamed | Completed | 2021-07-21 05:30 | Moved from 05jun to 10jun2020. CETB115G2201 go-live has been postponed due to Protocol amendment . Initial go-live was planned on 19th JUN 2020 Initial go live as 17Apr2020 when RF developer assigned on 21Jan2020. |  | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 16Jul2021 : Rule file 2.0 is finalized in CREDI and LSP is also notified. DDPASS comments were addressed in this version. 26May2021 : Reassigned the study from Praveen Oguri to Rehana Banu. 26-May-2021 : Received DDPASS comments in LB, CM and B2 domains, have to review and confirm whether RF update is required or not. 05Nov2020: No Activity. 11Sep2020: No Activity. 14Jul2020 : RF final and Snow ticket raised. Shashi performed QC. 18Jun2020 : Awating 2 pages XGS001 & XGO001annotations have followed up with DBD on 17th. WIll be sent for peer review today excluding these 2 forms. 05Jun2020 : Received SDTM annotations and screen UAT finalization as per DBD email 03Jun2020. working on RF. golive planned on 10Jun2020 12May2020 : As per DBD teher are upadtes to dynamics and screens and planned golive is 05Jun. looks like potential risk and notified GHs. 19Mar2020 : Sent an followup email to DBD. 17Feb2020 : Followed up with DBD and yet to receive study specific forms for review. No RF activity started | None | None | 2020-07-14 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2020-09-08 | Completed | 2020-09-08 05:30 |  |  | 2020-09-08 05:30 | 2020-09-08 05:30 |  | 2020-09-14 05:30 |  |  | There is no data as of now because FPFV is on 29th Sep 2020 | 0 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 2 | 62 | 72 | 0 | 519 | 678 | 0 | 197 | 33 | 210 | 921 | 1 | 0 |  | Aplastic anaemia | No | Global | Open: Reapproval | Yes | [10 empty] | 2020-09-01 05:30 | [5 empty] | None of the above | Yes
CETB115I | CETB115I2101 | C3003982 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2024-11-14 05:30 | DB On hold | Final DBL | 2025-04-09 05:30 |  | 2024-08-21 05:30 |  |  | Planned | 2025-03-05 05:30 |  | 2025-04-09 05:30 |  | FALSE | NA | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CETB115I2101 Healthy Volunteers study | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Bellamkonda, Vamsi Krishna | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Farida Souami | Farida Souami | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 5 | 0 |  | Acute radiation syndrome | Yes | Global | Open | Yes | [16 empty] | None of the above
CETB115I | CETB115I2102 | C3003981 | Phase I | Other | CRO - EDC |  |  | 2020-12-15 05:30 | DB Conduct |  |  | 2020-12-14 05:30 | 2020-08-31 05:30 | 2020-09-15 05:30 |  | Active | 2022-03-21 05:30 | 2021-05-16 05:30 | 2022-04-29 05:30 | 2021-07-09 05:30 | FALSE | non critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A randomized, single center, open-label, two-period, crossover study to evaluate the relative bioavailability of eltrombopag as crushed and dispersed tablets versus tablets administered intact in healthy adult volunteers | CETB115I2102 Relative Bioavailability study | PA Oncology (Hematology not for MA projects) | Navarro, Christelle | Joshi, Amruta | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Neha Ruparelia | Neha Ruparelia | [17 empty] | Sandeep Kadam | [28 empty] | Celerion | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Acute radiation syndrome | Yes | Global | Open | Yes | [16 empty] | None of the above
CETB115J_MA | CETB115J2411 | C3001342 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-10 05:30 | 2018-11-19 05:30 | DB Conduct | Final DBL | 2022-03-02 05:30 | 2018-11-02 05:30 | 2018-05-16 05:30 | 2018-04-23 05:30 |  | Active | 2022-01-03 05:30 |  | 2022-03-02 05:30 |  | FALSE | Submission for Label update | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A phase II, open-label, prospective, single-arm, study to assess ability of eltrombopag to induce sustained remission in subjects with ITP who are refractory or relapsed after first line steroids \n\n | CETB115J2411 GMA Study Early Relapse in ITP | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Basani, Sravan | Mali, Astik | Sonmale, Pravin | Ninan, Esther | Jimmy Lee | James Lee | Akula, Raghavender | Rapaka, Sindhuja |  |  |  |  | DRM (DIAL) | Akula, Raghavender | Shrivastava, Nikhil | Completed | 26-Oct-2021: Raised SNOW-51 request for LSH rebuild WRT PPC#09 and notified LSP. RF is not impact for this PPC. 11-Feb-2021: B12L DTS finalized by TDM today and hence included in the Rule File. RF V7.0 finalized in CREDI and SNOW-51 is raised. LSP is notified. 12-Jan-2021: Sent 3 reminder to TDM and followed up to provide the response on the previously given comments. 27Nov2020: Backup: Rehana Whats planned: B12L DTS has been uploaded in CREDI but not yet finalized. Included in the Rule file and released for peer Review. Once TDM provide satisfactory response on provided comments and when DTS get final then RF needs to be finalized. 13-Nov-2020: Received the PPC form (PPC#03) from DBD. Reviewed from RF perspective and sent the comments. 11-Aug-2020 (SHRIVNI5): This DTS (B11L) was already included in V6.0 which was finalized on 20th May 2020. Prod load has not yet happened. 27Jul2020 : B11L is listed in 20jul report 20-May-2020(SHRIVNI5): ‘B11L’ DTS has been added in rule file version 3.0 and the same has been finalized in CREDI. SNOW-51 ticket raised for LSH setup. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 13Jan2020 (SHRIVNI5): All forms and DTS are included. | None | None | 2018-09-10 05:30 |  | Kadam, Sandeep | Chitransh, Arpit | Sandeep Kadam | Completed | 2018-12-26 | Completed | 2019-07-04 05:30 |  |  | 2018-10-04 05:30 | 2018-10-04 05:30 |  | 2019-07-02 05:30 |  |  |  | 95 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 36 | 48 | 0 | 259 | 447 | 0 | 168 | 36 | 220 | 703 | 7 | 0 |  | Thrombocytopenia | No | Global | Open | Yes | [10 empty] | 2019-07-04 05:30 | [5 empty] | None of the above
CETB115K1 | CETB115K12101 | C4004758 | Phase I | Other | CRO - EDC |  |  | 2020-02-06 05:30 | DB Locked |  |  | 2020-02-13 05:30 | 2019-11-15 05:30 | 2020-06-16 05:30 |  | Active | 2022-06-16 05:30 | 2021-05-09 05:30 | 2022-07-13 05:30 | 2021-10-29 05:30 | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CETB115K12101 Healthy Volunteers study | PA Oncology (Hematology not for MA projects) | Molander, Lei Ann | Varma, Viswanadha | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Raquel Merino Herranz | Raquel Merino Herranz | [17 empty] | Sandeep Kadam | [28 empty] | PRA Health | [19 empty] | Anaemia | No | Global | Wind Down | Yes | [16 empty] | None of the above
CETB115L1 | CETB115L11201 | C4008579 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-02-17 05:30 | 2021-04-09 05:30 | 2021-05-31 05:30 | DB Conduct | DB Snapshot | 2022-04-11 05:30 | 2021-05-25 05:30 | 2020-11-30 05:30 | 2020-11-30 05:30 |  | Active | 2024-10-15 05:30 |  | 2024-11-18 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A randomized, double-blind, placebo-controlled, Japan local phase II clinical study comparing the eltrombopag monotherapy versus placebo in adult lower risk MDS patients with platelet transfusion dependence | CETB115L11201 LR MDS Japan registration trial | PA Oncology (Hematology not for MA projects) | Paigaonkar, Gargi | Amano, Kana | Bellamkonda, Vamsi Krishna | Tanada, Miyako | Ninan, Esther | MASAE KAI | MASAE KAI | Suzuki, Hiroko | Rana, Aamir | Not Started |  | 15-Dec-2021 : Vinay Pamula will be backup for Aamir till 15-Mar-2022 |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 21Jan2022: Rule file and its checklist 7.0 finalized in SUBWAY for the B2 domain issue fix and the SNOW#51-RITM3407587 for LSH has been created. 21Dec2021:PPC#01 updates do not have any impact on the Rule file, therefore Snow#51- RITM3315460 created directly. 03Dec2021: RF v6.0 finalized-updated the logic for FAAA1L table mapping. 06Sep2021: RF v5.0 finalized-Added B11L dts table. 24Aug2021: RF v4.0 finalized for DTS table -FAAA1L. 16Jun2021: RF v3.0 finalized in Subway for Yx(dts) update, ZJ, MH, FAMH and ZJ domain updates due to SDTM annotations update. 26Apr2021: RF version 2.0 finalized in subway for the 'STGVER' issue. Angella worked on it in Chandrakala's absence 09Apr2021 : RF verion 1.0 finalized in subway , Snow #05 raised. Angella worked on it in Chandrakala's absence. 01Feb2021: The Go-live date has been pushed to March 17, 2021. The Screen UAT is planned for 5 Feb, 2021. 07Jan2021: SS crfs and SRFS to be received from DBD. 04Dec2020: Development yet to start, SRF are in d iscussion-confirmed by DBD. | None | None | 2021-04-09 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2021-04-20 | Completed | 2021-04-29 05:30 |  |  | 2021-04-29 05:30 | 2021-04-29 05:30 |  | 2021-04-29 05:30 |  |  |  | 100 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 2 | 85 | 75 | 0 | 851 | 955 | 0 | 206 | 38 | 203 | 1196 | 4 | 0 |  | Myelodysplastic syndrome | Yes | Global | Open | Yes | [10 empty] | 2021-04-28 05:30 | [5 empty] | None of the above | Yes
CEXE844B | CEXE844B2101 | C1001161 | Phase I | RAVE_RAW | [7 empty] | 2015-11-30 05:30 |  | 2015-06-29 05:30 |  | Completed |  | 2016-06-24 05:30 |  | 2016-07-13 05:30 | FALSE |  |  |  | Alcon InHouse |  | An Open-Label, Single-Dose, Pharmacokinetic Study of AL-60371 Sterile Otic Suspension, 0.3% in Pediatric Subjects Following Tympanostomy Tube Surgery | PK Sterile Otic Susp in Peds_ALCON_CEXE844B2101 | P5 Ophthalmology | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Bacterial infection; Other bacterial diseases |  | Global | Completed | [17 empty] | None of the above
CEXE844B | CEXE844B2301 | C1001162 | Phase III | RAVE_RAW | [7 empty] | 2015-06-25 05:30 |  | 2015-04-15 05:30 |  | Completed |  | 2016-06-15 05:30 |  | 2016-06-28 05:30 | FALSE |  |  |  | Alcon InHouse |  | Safety and Efficacy of EXE844 Otic Suspension in the Treatment of Otitis Media at the Time of Tympanostomy Tube Insertion | Phase 3_CEXE844B2301 | P5 Ophthalmology | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Bacterial infection; Other bacterial diseases |  | Global | Completed | Yes | [16 empty] | None of the above
CEXE844B | CEXE844B2302 | C1001163 | Phase III | RAVE_RAW | [7 empty] | 2015-06-19 05:30 |  | 2015-04-20 05:30 |  | Completed |  | 2016-08-04 05:30 |  | 2016-08-24 05:30 | FALSE |  |  |  | Alcon InHouse |  | Safety and Efficacy of EXE844 Otic Suspension in the Treatment of Otitis Media at the Time of Tympanostomy Tube Insertion | Phase 3_CEXE844B2302 | P5 Ophthalmology | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Bacterial infection; Other bacterial diseases |  | Global | Completed | Yes | [16 empty] | None of the above
CEYU688A0 | CEYU688A02101 | C4005157 | Phase I | Other | Other |  |  | 2021-07-13 05:30 | DB Conduct | Final DBL | 2022-04-06 05:30 | 2021-07-13 05:30 | 2021-04-02 05:30 | 2021-03-29 05:30 |  | Active | 2022-03-02 05:30 |  | 2022-04-06 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CEYU688A02101 FIH SAD/MAD for Dengue | R4 NITD - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Robert Beecham | Robert Beecham | [17 empty] | Rohit Varate | [28 empty] | Celerion | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Dengue fever | No | Global | Open | Yes | [16 empty] | None of the above
CEYU688A1 | CEYU688A12201 | C4008932 | Phase II |  |  |  |  | 2022-09-06 05:30 |  | Final DBL | 2023-06-05 05:30 |  | 2022-05-12 05:30 |  |  | Planned | 2023-04-10 05:30 |  | 2023-06-05 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CEYU688A12201 PoC in Dengue | R4 NITD - NIBR | [5 empty] | Patricia Wagner | Patricia Wagner | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Dengue fever | Yes | Global | Open | Yes | [16 empty] | None of the above
CFAZ053A1 | CFAZ053X2101 | C1001605 | Phase I | NCDS | OC RDC - Inhouse | 2016-09-23 05:30 | 2016-09-23 05:30 |  | DB Conduct | Final DBL | 2022-09-02 05:30 | 2016-10-20 05:30 |  | 2016-06-16 05:30 |  | Active | 2022-07-22 05:30 |  | 2022-09-02 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I, open-label, multi-center dose escalation study of FAZ053 as single agent and in combination with PDR001 in adult patients with advanced malignancies | CFAZ053X2101 TCO-Ph I FAZ053-PD-L1-immuno-2101 | N7 Oncology - NIBR | Langlo, Francois | John, Christina | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Carolyn McGarry | Carolyn McGarry | Joshi, Alekhya | Meda, Sreelakshmi | Completed | 2021-07-16 05:30 | [11 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2016-09-23 05:30 | 2016-09-23 05:30 | Shewane, Roshni | Gehlawat, Priya | IQVIA | [7 empty] | 171 | 0 |  |  | 0 |  |  |  | 775 | 7 | 0 |  | Anaplastic thyroid cancer; Endometrial cancer; Non-small cell lung cancer; Solid tumour; Triple negative breast cancer | No | Global | Open | Yes | [16 empty] | None of the above | Yes
CFGF401A1 | CFGF401X2101 | C1001608 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-12-29 05:30 |  | 2014-08-07 05:30 |  | Completed | 2020-03-30 05:30 | 2019-05-30 05:30 | 2019-06-28 05:30 | 2019-07-16 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I/II, multicenter, open-label study of oral FGF401 in adult patients with hepatocellular carcinoma or solid malignancies characterized by positive FGFR4 and KLB expression | CFGF401X2101 TCO-FIH0-w dose-expan-HCC-Pts | N7 Oncology - NIBR | Langlo, Francois | Thorat, Swapnil | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Vasiliki Katsanou | Vasiliki Katsanou | Ahuja, Mohit | [14 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | ZK;#ZK02 |  |  |  |  | ONC | Novartis | InHouse |  | 2014-11-27 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 11 | 0 |  | Hepatocellular carcinoma; Solid tumour | No | Global | Completed | Yes | [14 empty] | DBL | Girvasiya, Shaili | None of the above | Yes
CFIA586A0 | CFIA586A02101 | C4010149 | Phase I | Other |  |  |  | 2021-12-10 05:30 |  | Final DBL | 2022-06-28 05:30 | 2021-12-10 05:30 | 2021-07-30 05:30 | 2021-07-30 05:30 |  | Active | 2022-05-20 05:30 |  | 2022-06-28 05:30 |  | FALSE |  |  |  | FULL Outsourced |  | Pliant Hepatic Impairment | CFIA586A02101 Pliant Hepatic Impairment | N5 DAx - NIBR | [5 empty] | Amanda Taylor | Amanda Taylor | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [16 empty] | None of the above
CFIA586A1 | CFIA586A12201 | C4010146 | Phase II |  |  |  |  | 2022-10-20 05:30 |  | Final DBL | 2025-02-14 05:30 |  | 2022-07-27 05:30 |  |  | Planned | 2025-01-10 05:30 |  | 2025-02-14 05:30 | [5 empty] | ED Undecided Sourcing |  | Pliant PoC cirrhotic NASH | CFIA586A12201 Pliant PoC cirrhotic NASH | N5 DAx - NIBR | [5 empty] | Prafulla Bhad | Phillip Koo | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Open | Yes
CFLB298A0 | CFLB298A02101 | C4009418 | Phase I |  | CRO - EDC |  |  | 2022-06-02 05:30 | DB Set-Up | DB Go-live | 2022-05-03 05:30 |  | 2022-03-02 05:30 |  |  | Planned | 2023-03-24 05:30 |  | 2023-05-19 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CFLB298A02101 | N6 Neuroscience - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Patricia Wagner | Patricia Wagner | [17 empty] | Rohit Varate | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Depression | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CFOR258D | CFOR258D2416 | C1001164 | Phase IV | Other | [7 empty] | 2013-06-04 05:30 |  | 2013-03-05 05:30 |  | Stopped (with patients) |  | 2016-04-19 05:30 |  | 2016-06-24 05:30 | FALSE |  |  |  | Outsourced |  |  | CLINICAL PM_CFOR258D2416 Post CSR Submis Activit | P6 Global Health | [6 empty] | Sarita Gajendrapratap Barsainya | [66 empty] | Asthma | No | Global | Wind Down | [17 empty] | None of the above
CFTY720D | CFTY720D1401 | C1001174 | Phase IV | Other | Paper |  |  |  | DB Locked |  |  | 2011-12-16 05:30 |  | 2011-12-22 05:30 |  | Completed | 2020-09-30 05:30 | 2020-08-27 05:30 | 2021-02-26 05:30 | 2021-02-19 05:30 | FALSE | Japan PMS | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Special drug use observational Study of Fingolimod in multiple sclerosis | CFTY720D1401 Japan PMS | P4 Neuroscience | YAMADA, KAYO | MORI, YUMIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | KUMI TAKAMIYA | YOSHIHISA SATOU | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Relapsing-remitting multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CFTY720K | CFTY720D2311 | C1001176 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked | Final DBL | 2028-12-13 05:30 | 2013-07-26 05:30 |  | 2011-11-27 05:30 |  | Active | 2028-11-02 05:30 |  | 2028-12-13 05:30 |  | FALSE | Extension of CFTY720D2311E1 safety studies | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A two year, double-blind, randomized, multicenter, active-controlled Core Phase study to evaluate the safety and efficacy of fingolimod administered orally once daily versus interferon Ã-1a i.m. once weekly in pediatric patients with multiple sclerosis with five-year fingolimod Extension Phase | Paediatrics RRMS _CFTY720D2311 | P4 Neuroscience | Chaghasbanian, Harut | Ananth, Anusha | Almeida, Snehal | Chitre, Vrushali | Nair, Sreesha | Mia DeBarros | Mia DeBarros | [17 empty] | Amit Agavekar | [28 empty] | IQVIA | [19 empty] | Multiple sclerosis | Yes | Global | Open | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2312 | C1001168 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-08-09 05:30 |  | 2011-09-26 05:30 |  | Completed | 2018-07-23 05:30 | 2018-04-30 05:30 | 2018-10-01 05:30 | 2018-10-01 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A 12-month, randomized, rater- and dose-blinded study to compare the efficacy and safety of fingolimod 0.25 mg and 0.5 mg administered orally once daily with glatiramer acetate 20 mg administered subcutaneously once daily in patients with relapsing-remitting multiple sclerosis | ASSESS Low Dose _CFTY720D2312 | P4 Neuroscience | Ball, Michael | Khan, Akhtar Ghous | Ghosh, Sourya | Sharma, Atul | Nair, Sreesha | Daniel Sienkiewicz | Daniel Sienkiewicz | [17 empty] | Amit Agavekar | [28 empty] | PPD | [19 empty] | Multiple sclerosis | No | Global | Wind Down | Yes | [16 empty] | None of the above
CFTY720D_MA | CFTY720D2319 | C1001609 | Phase III | NOVDD | [7 empty] | 2012-05-29 05:30 |  | 2011-03-29 05:30 |  | Completed |  | 2017-07-24 05:30 | 2018-05-11 05:30 | 2017-11-14 05:30 | FALSE |  |  |  | FULL Outsourced |  | A 3-year, multi-center study to evaluate optical coherence tomography as an outcome measure in patients with multiple sclerosis | CFTY720D2319 GMA OCT | P4 Neuroscience | [5 empty] | Moreshwar Patwardhan | Wojciech Smoron | [66 empty] | Relapsing-remitting multiple sclerosis | No | Global | Completed | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2399 | C1001165 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-09-13 05:30 |  | 2010-05-26 05:30 |  | Completed | 2018-10-19 05:30 | 2018-10-19 05:30 | 2019-01-10 05:30 | 2018-12-14 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A single arm, open-label, multicenter study evaluating the long-term safety and tolerability of 0.5 mg fingolimod (FTY720) administered orally once daily in patients with relapsing forms of multiple sclerosis | LONGTERMS_FTY720D2399 | P4 Neuroscience | Ball, Michael | Khan, Akhtar Ghous | Ghosh, Sourya | Sharma, Atul | Nair, Sreesha | Mia DeBarros | Mia DeBarros | [17 empty] | Amit Agavekar | [28 empty] | IQVIA | [11 empty] | 0 |  |  |  | 575 |  |  |  | Multiple sclerosis | No | Global | Completed | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2403 | C1001169 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2011-08-01 05:30 |  | 2011-01-27 05:30 |  | Completed | 2020-03-16 05:30 | 2020-07-10 05:30 | 2020-08-31 05:30 | 2020-09-01 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Long term, prospective, multinational, parallel-cohort study monitoring safety in patients with multiple sclerosis newly started with fingolimod once daily or treated with another approved disease-modifying therapy. | US PASSAGE _CFTY720D2403 | P4 Neuroscience | Chaghasbanian, Harut | Khan, Akhtar Ghous | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Mia DeBarros | Kamin Personett | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Pharma | AP21 |  |  | novartis.com | [14 empty] | Multiple sclerosis | No | Global | Wind Down | Yes | [16 empty] | None of the above
CFTY720D_MA | CFTY720D2405 | C1001610 | Phase IV | NOVDD | [7 empty] | 2012-09-25 05:30 |  | 2014-10-14 05:30 |  | Completed |  | 2017-01-31 05:30 |  | 2017-04-06 05:30 | FALSE |  |  |  | Outsourced |  | TRANSITION: A two years observational study to evaluate the safety profile of fingolimod in patients with multiple sclerosis who switched from natalizumab to fingolimod | CFTY720D2405 GMA stu | P4 Neuroscience | [5 empty] | Daniel Sienkiewicz; Diane Bonagura | Daniel Sienkiewicz | [66 empty] | Multiple sclerosis |  | Global | Completed | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2406 | C1001171 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-05-08 05:30 |  | 2011-12-20 05:30 |  | Completed | 2020-06-01 05:30 | 2020-03-17 05:30 | 2020-08-31 05:30 | 2020-08-28 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Long-term, prospective, observational, multinational, parallel-cohort study monitoring safety in patients with MS recently started with fingolimod once daily or treated with another approved disease-modifying therapy | EU PASSAGE _CFTY720D2406 | P4 Neuroscience | Chaghasbanian, Harut | Khan, Akhtar Ghous | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Kamin Personett | Kamin Personett | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Pharma | AP21 | [17 empty] | Multiple sclerosis | No | Global | Wind Down | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2409 | C1001172 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-09-29 05:30 |  | 2014-04-22 05:30 |  | Completed | 2020-03-16 05:30 | 2020-01-24 05:30 | 2020-05-26 05:30 | 2020-03-31 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Long-term, open-label, multicenter study assessing long-term cardiovascular risks in patients treated with fingolimod | CARDIAC MONITORING _CFTY720D2409 | P4 Neuroscience | Chaghasbanian, Harut | Khan, Akhtar Ghous | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Kamin Personett | Kamin Personett | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Pharma | AP21 | [17 empty] | Multiple sclerosis | No | Global | Completed | Yes | [16 empty] | None of the above
CFTY720D | CFTY720D2419 | C4006803 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2021-01-07 05:30 | 2021-01-08 05:30 | 2021-02-26 05:30 | DB Conduct | Interim DBL | 2022-10-12 05:30 | 2021-02-20 05:30 | 2020-02-28 05:30 | 2020-03-09 05:30 | 2020-11-25 05:30 | Active | 2024-12-28 05:30 |  | 2025-02-28 05:30 |  | FALSE | Product license renewal in China | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 24-month, open-label, prospective, multicenter interventional, single-arm study assessing the efficacy and safety of fingolimod (Gilenya) 0.5 mg in relapsing multiple sclerosis (RMS) patients in China | CFTY720D2419 | P4 Neuroscience | Chaghasbanian, Harut | Ananth, Anusha | Almeida, Snehal | Chitre, Vrushali | Nair, Sreesha | Dora Weng | Chiaching Weng | Gandla, Prashanth | TEMBHARE, HITESH | Not Started |  |  |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 20Sep2021: RF-V 3.0 finalized for MO1L dts. 07Jul2021:RF v2.0 for QS1L, QS2L, QS3L and QS4L dts tables addition was finalized on 17Jun2021 already, sent a re-confirmation mail to DBD,TDM and LSP for prod transfer. Production transfer is expected on 28Jul2021. 06Jul2021 : QS1L, QS2L, QS3L, QS4L reflecting in missing form DTS report 18June2021: ALS is replaced in the repository by DBD today for 'DUMMY_LONG_FORMOID' issue. 17Jun2021:RF v2.0 finalized for QS1L, QS2L, QS3L and QS4L dts tables addition. 09Jun2021:DBD confirmed the ALS in repository has 'DUMMY_LONG_FORMOID' which is inconsistent with CREDI hence will delete the current copy present in ALS repository and upload one present in CREDI. So that in future this will not highlight in reports. 04-June-2021:Rave architect has no such 'FormOID' confirmed by DBD, checking with LSP. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 26-May-2021: MO1L DTS is in discussion and sent follow up email to study DBD on DUMMY_LONG_FORMOID issue. 26-Apr-2021: I will check with Study DBD and find out more information about this issue. 06Apr2021 : LC: DUMMY_LONG_FORMOID form in missing forms and DTS Report. 15-Jan-2021: RF Version 1.0 finalized and raised SNOW05 ticket(RITM2172043). RF finalization was delayed by 5 working days as UAT SOD's were not available for RF validation. 02-Dec-2020: Received SRF's and ALS. Screen UAT is not completed. I will start RF development activity on 07-Dec-2020. 11Aug2020 : SS forms shared by DBD for review. provided feedback. | None | None | 2021-01-15 05:30 | RF finalization was delayed by 5 working days as UAT SOD's were not available for RF validation. DB Go-Live : 08-Jan-2021 RF Finalization : 15-Jan-2021 Planned FPFV : 29-Jan-2021 | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Amit Agavekar | Completed | 2021-02-02 | Completed | 2021-02-04 05:30 | till now didn't get RAVE SOD access for this study |  | 2021-02-05 05:30 | 2021-02-05 05:30 |  | 2021-03-23 05:30 |  |  | no data in study |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 2 | 14 | 105 | 0 | 190 | 665 | 0 | 206 | 35 | 371 | 1071 | 5 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2021-02-03 05:30 |  |  |  |  | Manoharan, Vivek | None of the above | Yes
C2311 | CFTY720I2201 | C1001175 | Phase III | NOVDD | [7 empty] | 2012-12-20 05:30 |  | 2012-05-22 05:30 |  | Completed |  | 2016-09-01 05:30 |  | 2016-11-30 05:30 | FALSE |  |  |  | FULL Outsourced |  | A double-blind, randomized, multicenter, placebo-controlled, parallel-group study to evaluate the efficacy and safety of 0.5 mg fingolimod administered orally once daily versus placebo in patients with chronic inflammatory demyelinating polyneuropathy (CIDP) | CIDP_CFTY720I2201 | P4 Neuroscience | [6 empty] | Tilak Mohapatra | [66 empty] | Polyneuropathy chronic | No | Global | Completed | Yes | [16 empty] | None of the above
CFXT508A0 | CFXT508A02101 | C4008080 | Phase I | Other |  |  |  | 2022-10-03 05:30 |  | Final DBL | 2023-07-28 05:30 |  | 2022-07-01 05:30 |  |  | Planned | 2023-07-28 05:30 |  | 2023-07-28 05:30 | [5 empty] | FULL Outsourced |  |  | CFXT508A02101 FIH SAD/MAD | N5 DAx - NIBR | [6 empty] | Danielle Spera | [66 empty] | Asthma | No | Global | Open | Yes
CFYQ722A1 | CFYQ722A12101 | C4014518 | Phase I |  | CRO - EDC |  |  | 2022-03-07 05:30 | DB Set-Up | DB Go-live | 2022-02-25 05:30 |  | 2021-12-02 05:30 | 2022-01-13 05:30 |  | Planned | 2022-08-02 05:30 |  | 2022-09-01 05:30 |  |  | Submission | Rao, Sreekanth | Cluster C (fGSK,IHD,Sandoz) | Outsourced | Solid Tumor | A single-center, open-label, randomized single-dose crossover study to evaluate the effects of eltrombopag/remibrutinib co-administration, in fasted and fed conditions, on the relative bioavailability of eltrombopag and remibrutinib in healthy adult participants | CFYQ722A12101 PhI HV PK/FE | P0 Oncology (Solid Tumors all MA Onc projects) | Paigaonkar, Gargi | Sharma, Harish | Sharma, Harish | Bhabhe, Nikhil | Ninan, Esther | Robert Beecham | Robert Beecham | [17 empty] | Sushant Sundar | [28 empty] | Parexel | [19 empty] | Immune thrombocytopenic purpura | No | Global | Open | Yes
CFYQ722A1 | CFYQ722A12102 | C4015179 | Phase I |  |  |  |  | 2022-03-07 05:30 |  | Final DBL | 2022-06-20 05:30 |  | 2022-04-04 05:30 |  |  | Planned | 2022-04-25 05:30 |  | 2022-06-20 05:30 | [5 empty] | FULL Outsourced |  |  | CFYQ722A12102 PhI HV Site Absorption | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Robert Beecham | Robert Beecham | [66 empty] | Immune thrombocytopenic purpura | No | Global | Open | Yes
CFYQ722A1 | CFYQ722A12201 | C4013852 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-04-28 05:30 | Study Planned | DB Go-live | 2023-03-24 05:30 |  | 2022-12-22 05:30 |  |  | Planned | 2024-11-07 05:30 |  | 2024-12-19 05:30 |  |  | Submission | Rao, Sreekanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Solid Tumor |  | CFYQ722A12201 PhII_ITP | P0 Oncology (Solid Tumors all MA Onc projects) | Paigaonkar, Gargi | Kulkarni, Manish | Sharma, Harish | Bhabhe, Nikhil | Ninan, Esther |  | Farida Souami | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 105 | [7 empty] | 1250 | 6 |  |  | Immune thrombocytopenic purpura | No | Global | Open | Yes
CGBA401A1 | CGBA401A12101 | C4011773 | Phase I |  |  |  |  | 2023-06-30 05:30 |  | Final DBL | 2029-03-30 05:30 |  | 2023-01-20 05:30 |  |  | Planned | 2029-02-23 05:30 |  | 2029-03-30 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CGBA401A12101 GBA401A1 IRD FIH and POC | N8 Ophthalmology - NIBR | [6 empty] | Karen Holopigian | [66 empty] | Retinitis pigmentosa | No | Global | Open | Yes
CGHZ339A0 | CGHZ339A02101 | C4011590 | Phase I |  |  |  |  | 2023-10-03 05:30 |  | Final DBL | 2025-01-23 05:30 |  | 2023-07-04 05:30 |  |  | Planned | 2024-11-28 05:30 |  | 2025-01-23 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CGHZ339A02101 FIH with HV | N0 ATI - NIBR | [6 empty] | Izabela Rozenberg | [66 empty] | Atopic dermatitis | No | Global | Open | Yes
CGJG057A0 | CGJG057A02101 | C4012292 | Phase I |  | Rave EDC - Inhouse |  |  | 2022-10-18 05:30 | Study Planned | DB Go-live | 2022-09-14 05:30 |  | 2022-06-07 05:30 |  |  | Planned | 2023-08-10 05:30 |  | 2023-09-21 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - ATI |  | CGJG057A02101 GJG057 FIH SAD/MAD study | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Marta Zambianchi | [17 empty] | Rohit Varate | [48 empty] | Atopic dermatitis | No | Global | Open | Yes
CGP2013_MA | CGP13-501 | C3001502 | Not Applicable | Other | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2017-10-19 05:30 |  | 2017-07-21 05:30 |  | Completed | 2021-03-29 05:30 | 2021-03-31 05:30 | 2021-04-26 05:30 | 2021-05-20 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A prospective multi-center non-interventional study describing the effectiveness and safety of biosimilar rituximab (RixathonÂ®) administered in combination with CHOP chemotherapy for treatment of patients with previously untreated CD20 positive Diffuse Large B-Cell Lymphoma in current clinical practice | CGP13-501 GP2013 NIS | P2 SZ Biopharma | Marshall, Lee | Halfaf-Schwientek, Ewa-Maria | Stoeckmann, Niklas | Marshall, Lee | Marshall, Lee | Stefan Sell | Stefan Sell | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 41 | 0 |  |  | 0 |  |  |  | 229 | 0 | 0 |  | Diffuse large B-cell lymphoma | No | Global | Open | No | [16 empty] | None of the above
CGP2015_MA | CGP15-501 | C3001527 | Not Applicable | Other | Other |  |  | 2018-07-24 05:30 | DB Locked | Final DBL Achieved |  | 2017-10-11 05:30 | 2018-01-26 05:30 | 2017-06-26 05:30 |  | Active | 2022-09-05 05:30 | 2021-04-30 05:30 | 2021-07-23 05:30 | 2021-07-27 05:30 | FALSE | NIS | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A multicenter, prospective, observational cohort study to evaluate the real-world safety and effectiveness of Erelziâ¢, an etanercept biosimilar (COMPACT) | CGP15-501 GP2015 GMA NIS | P2 SZ Biopharma | Marshall, Lee | Saha, Sagar | Stoeckmann, Niklas | Gracey Sugunan, Unni Krishnan | Ninan, Esther | Martins Acha | [18 empty] | Sandeep Kadam | [28 empty] | NA | [11 empty] | 0 |  |  |  | 299 | 1 | 0 |  | Rheumatic disorder | No | Global | Open | Yes | [16 empty] | None of the above
CGP2018 | CGP18-101 | C1050228 | Phase I | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2016-10-25 05:30 |  | 2016-05-13 05:30 |  | Completed |  | 2017-06-20 05:30 |  | 2017-09-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | Outsourced | Biosimilars/ Sandoz | A randomized, double-blind, three-arm parallel group study to compare the pharmacokinetics and safety of GP2018, EU-authorized Remicade and US-licensed Remicade following a single intravenous infusion in healthy male subjects | CGP18-101 GP2018 Phase I Study | P2 SZ Biopharma | Marshall, Lee | Maier, Martina | Machado, Sundeep | Machado, Sundeep | Ninan, Esther | [19 empty] | Sandeep Kadam | [28 empty] | PPD | [19 empty] | Pharmacokinetic study | No | Global | Completed | [17 empty] | None of the above
CGP2411 | CGP24112101 | C1050024 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-10-22 05:30 | 2020-01-17 05:30 | 2020-02-05 05:30 | DB Conduct | Final DBL | 2022-07-25 05:30 | 2020-01-27 05:30 | 2019-05-22 05:30 | 2019-05-24 05:30 |  | Active | 2022-06-10 05:30 |  | 2022-07-25 05:30 |  | FALSE | Submission | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A double-blind, randomized, three-arm parallel group phase 1 study to compare the pharmacokinetics, pharmacodynamics, safety and immunogenicity of GP2411 (proposed biosimilar denosumab), EU-authorized XgevaÂ® and US-licensed XgevaÂ® after a single subcutaneous injection of 35 mg in healthy male subjects | CGP24112101 GP2411 Phase I Study (Xgeva trial) | P2 SZ Biopharma | Marshall, Lee | Juvatkar, Tanvi Navneet | Machado, Sundeep | Bhabhe, Nikhil | Ninan, Esther | Christine Schober; Franziska Handmann | Christine Schober | Kuttoboina, Sujan Kumar | TEMBHARE, HITESH |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 22Oct2019 |  | DRM | Choppadandi, Kranthikumar | Kuttoboina, Sujan Kumar | Completed | 10JAN22: Rule file Version 7.0 and SNOW 51 request RITM3353844 has been created, requested to rebuild VS, QS, PR and DV (new codes added) domains as per below PPC 8 changes. 25NOV21: RF V6.0 final and SNOW 51 request RITM3205368 has been created on 19NOV21, requested to rebuild EC1 domain as part of PPC. 25FEB21: RF finalized and SNOW 51 request RITM2301172 has been created Updates: EG domain: EGG001 form: Renamed variables from 'EGRESN and EGRESN_STD' to 'EGRESCD and EGRESCD_STD' since result is a coded value 17AUG20: RF was finalized and SNOW 51 RITM1657087 request was raised . DSG005 form was added as part of PPC. 27JUL20: SV domain has been updated as per recent DT communication. 07JUL20: As of today, no pending forms and no pending DTS. 30Mar2020 : LBL pending DTS incldued in RF and sent for LSH setup 27Mar2020 : LBL is flagged in Missing DTS report, follwing up with DBD, So far DTS is not shared by DBD with RF developer. 02-MAR-2020: LSH setup was completed on 30JAN2020 27-JAN-2020: Rule file completed, SMT file generation is ongoing 22-JAN-2020: Working on peer review comments and expected date of Rule file completion is 23-JAN-20. 29-Nov-2019: Study golive has been pushed to 17-Jan-20 and there is a changes in the screens as per new protocol amendment | None | None | 2020-01-24 05:30 | RF finalized within golive + 5 days | Sultana, Salma | Varate, Rohit | Sandeep Kadam | Completed | 2020-01-31 | Completed | 2020-02-03 05:30 | completed | MANOHVI3 :Resource Crunch | 2020-02-03 05:30 | 2020-02-03 05:30 | Pre-requisites not met | 2020-05-01 05:30 |  |  | Comments are currently being fixed for the study | 71 | RaveX - Inhouse | No | -NA-;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 9 | 18 | 49 | 0 | 140 | 475 | 0 | 167 | 32 | 118 | 625 | 2 | 0 |  | Osteolytic bone metastases; Pharmacokinetic study | No | Global | Open | Yes | [10 empty] | 2020-01-31 05:30 | [5 empty] | None of the above
CGP2411 | CGP24112301 | C1050025 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-05-10 05:30 | 2019-06-07 05:30 | 2019-07-23 05:30 | DB Conduct | Final DBL | 2022-09-13 05:30 | 2019-07-02 05:30 | 2018-09-28 05:30 | 2018-09-28 05:30 |  | Active | 2022-08-05 05:30 |  | 2022-09-13 05:30 |  | FALSE | Submission | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A randomized, double-blind, multicenter integrated phase I/III study in postmenopausal women with osteoporosis to compare the pharmacokinetics, pharmacodynamics, efficacy, safety and immunogenicity of GP2411 (proposed biosimilar denosumab) and Prolia (EU-authorized) | CGP24112301 GP2411 Phase III Study (Prolia trial) | P2 SZ Biopharma | Marshall, Lee | Khanke, Neha | Machado, Sundeep | Bhabhe, Nikhil | Ninan, Esther | Agnieszka Niedziolka; Maria Halfen; Stefan Sell | Stefan Sell | Rao, S Shashikanth | Rao, S Shashikanth |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 10May2019 |  | DRM | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 07-Feb-2022: Rule file updates are not required for PPC 12. SNOW #RITM3463794 has been raised for SMT/LSH update 27-Aug-2020: RF V4.0 finalized 11Aug2020 : SSS003, DSG005 has Includeed in RF on 30th JUl 2020 and snow 51 raised. 06-Jul-2020: No pending issues. 09Mar2020 : DVG002 form, MO,LB DTSs included in RF V2.0. Released for LSH setup 02-Mar-2020: Rule File drafted to include DVG002 form, MO,LB DTSs and awaiting for UAT SODs to review and release for RF peer review 05Feb2020 : RF needs to be updated to include DVG002, MO & LB. Traget to complete by this week. 21-Jan-2020(Kranthi): Shashi confirmed that the DTSs are not yet finalized29th Nov 19- (Shashi) MO and LB third party data to be included in RF. Both of DTS are not finalized yet. | None | None | 2019-07-05 05:30 | Legacy Process | Tidke, Shyam | Garje, Sagar | Sandeep Kadam | Completed | 2019-08-05 | Completed | 2019-08-12 05:30 |  | Pre-requisites not met | 2019-08-12 05:30 | 2019-08-12 05:30 | Pre-requisites not met | 2020-05-07 05:30 |  |  |  |  | RaveX - Inhouse | No | -NA- | [11 empty] | Parexel | [5 empty] | 10 | 36 | 42 | 0 | 139 | 730 | 0 | 204 | 33 | 131 | 894 | 3 | 0 |  | Osteoporosis postmenopausal | No | Global | Open | Yes | [10 empty] | 2019-08-12 05:30 | [5 empty] | None of the above
CGP2017_MA | CGPN017A2001 | C3001506 | Not Applicable | NCDS_2 | Rave EDC - Inhouse |  | 2019-03-22 05:30 | 2019-06-28 05:30 | DB Locked | Final DBL Achieved |  | 2019-06-24 05:30 | 2018-11-12 05:30 | 2018-11-29 05:30 |  | Completed | 2025-06-30 05:30 | 2020-05-08 05:30 | 2020-07-17 05:30 | 2020-07-03 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | GIANT - A multicenter, prospective, post-marketing observational study to evaluate the effectiveness (PAES) of GP2017 (adalimumab biosimilar) and GP1111 (infliximab biosimilar) in patients with Crohnâs Disease | CGPN017A2001 GP17-501 NIS | P2 SZ Biopharma | Marshall, Lee | Halfaf-Schwientek, Ewa-Maria | Mayekar, Meera | Gracey Sugunan, Unni Krishnan | Ninan, Esther | Denys Zaitsev | Denys Zaitsev | Kuttoboina, Sujan Kumar | Rao, S Shashikanth |  |  |  |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 07-JUL-2020: Study has been locked. 13-MAY-2020: No pending forms or DTS, LSH setup has been completed. 30Apr2020: QS and MO included and RF final. SNOW request has been created. 27APR2020: QS and MO domains have been updated and sent for peer review 15Apr2020 : Will be sent for peer review by today post including pending QS forms 08Apr2020 : Had meeting with TA pod. Seperate discussion with SME, SMT programmer and DBD to see if any possibity to handle it in SMT and RF without PPC as there is a milestone. This study may get early terminated. 02MAR2020: PPC has to be implemented for fixing the issue . Post which RF needs to be updated. 13Feb2020 : For Pending QS the reference metadata needs to be added in sharepoint. Sujan to followeup with CDS, TDM and loop DBD. QS needs to be added in RF 09-JAN-20 : QS domain is Pending. Study was put on hold from recruitment for approx. 9 months post FPFV 06JUN2019: PPC ongoing for QS domain since QS test not found in global library. Only one subject enrolled and study will be on hold for sometime | None | None | 2019-03-28 05:30 |  | Nagalla, Lakshmi Naga Lavanya | Kadam, Sandeep | Sandeep Kadam | Completed | 2019-05-28 | Completed | 2019-07-18 05:30 | study is locked | " Study transitioned SMT support delayed since SMEs occupied with other priority work." | 2019-07-18 05:30 | 2019-07-18 05:30 | transitioned study,Study Transition | 2020-07-07 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-07-03 05:30 | 2020-07-07 05:30 | [9 empty] | NA | [5 empty] | 5 | 6 | 29 | -1 | 115 | 237 | 0 | 69 | 5 | 150 | 392 | 1 | 1 |  | Crohn's disease | No | Global | Terminated | Yes | [10 empty] | 2019-04-18 05:30 |  |  |  | DBL |  | None of the above | Yes
CGPN017B1 | CGPN017B12101 | C4001030 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-01-11 05:30 | 2021-01-21 05:30 | 2021-05-07 05:30 | DB Locked | Final DBL Achieved |  | 2021-02-23 05:30 | 2020-03-06 05:30 | 2020-02-18 05:30 | 2020-12-29 05:30 | Active | 2021-12-21 05:30 | 2021-12-13 05:30 | 2022-01-21 05:30 | 2022-01-27 05:30 | FALSE | Submission | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A randomized, double-blind, parallel, two-arm study to compare pharmacokinetics, safety and immunogenicity of GPN017B1 (HyrimozÂ® high concentration formulation; 100 mg/mL) with GP2017 (HyrimozÂ® low concentration formulation; 50 mg/mL) after a single dose of 40 mg subcutaneous injection in healthy male subjects | CGPN017B12101 HCF PK bridging | P2 SZ Biopharma | Marshall, Lee | Juvatkar, Tanvi Navneet | Machado, Sundeep | Bhabhe, Nikhil | Ninan, Esther | Steven Schussler | Steven Schussler | Bora, Deepthi Reddy | Bora, Deepthi Reddy | Completed | 2021-06-24 05:30 | Initial transition was from Deepthi to Valli. 22Jun2021 : Transition from Valli Munukutla to Deepthi Bora Current Status : PPC-02 endorsed and development ongoing. 26 completed by Valli, 9 to be taken over by Deepthi. |  | DRM | Govula, Shashikanth | Shrivastava, Nikhil | Completed | 19-Aug-2021: LB1L ZK4L and ZK5L DTS have been included in the RF V5.0. SNOW-51 raised and notified the LSP. 06-Aug-2021: ZK4 andZK5 are ongoing and near finalization. Once those are finalized, they will be included in the Rule File. 23-Jun-2021: RF V4.0 finalized with updates to YR and YD table names and adhoc request to add TPTTXT in 3 Vital Signs forms. SNOW-51 raised and LSP is notified. 22-June-2021: Updated RF V3.1 and shared with team for peer review. 18-May-2021: Sent mail to TDM to update the table name of IRT DTS for YR and YD domains. Post DTS updated, RF will be updated. 15-Apr-2021: PPC#01 is currently ongoing but no impact to RF and LSH. 02-Feb-2021: EC1 domain created in the Rule File V3.0 and finalized in Subway. Attached to same SNOW-5 ticket. LSP is notified. 28-Jan-2021: YR and YD domains included in the Rule File V2.0 and finalized in Subway. LSP is notified. 21-Jan-2021: Rule File V1.0 created and finalized in Subway. Raised the SNOW-05 request and notified LSP programmer. 15-Jan-2021: Got some comments from peer reviewer. Sent mail to DBD to provide clarification on them. Waiting for DBD response. 13-Jan-2021: Created the Rule File V0.1. Reviewed from my end and released for peer review. Waiting for peer review comments. 12-Jan-2021 (SHRIVNI5): Study was assigned to me on 12th Jan 2021 and study documents were shared. Reviewed the study documents from RF perspective and provided the comments to DBD. 6JAN2021: SG: Rule file to be created for the study. Planned golive 20Jan2021. Screen updates ongoing. ALS will be shared on 11Jan as per DB lead confirmation. 5Nov2020: Planned Golive 11Jan2021. Rohit working on PA1 changes. 8Sep2020: Sent a followup mail to Lead DBP Rohit Lingampally for status of screens. 04Sep2020 : Followup with DBD as no update on study 22Jun2020 : Asked Ashok to support in Shashi's absence | None | None | 2021-01-21 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2021-02-09 | Completed | 2021-02-11 05:30 |  |  | 2021-02-11 05:30 | 2021-02-11 05:30 |  | 2021-02-23 05:30 |  |  |  | 90 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 5 | 19 | 56 | 0 | 146 | 607 | 0 | 177 | 35 | 128 | 770 | 3 | 0 |  | Pharmacokinetic study | No | Global | Open | Yes | [10 empty] | 2021-02-11 05:30 | [5 empty] | None of the above | Yes
CGWN323A1 | CGWN323X2101 | C1200393 | Phase I | NCDS | OC RDC - Inhouse |  | 2016-06-08 05:30 |  | DB Locked |  |  | 2016-07-22 05:30 | 2016-03-02 05:30 | 2016-02-03 05:30 |  | Completed | 2020-04-01 05:30 | 2020-03-03 05:30 |  | 2020-05-06 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/Ib open-label, multi-center, dose escalation study of GWN323 (anti-GITR) as a single agent and in combination with PDR001 (anti-PD-1) in patients with advanced solid tumors and lymphomas | CGWN323X2101 | N7 Oncology - NIBR | Langlo, Francois | Barnard, Carol | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon | Daniel Carreon | Mokhamatam, Madhu Purnachandra Rao | TEMBHARE, HITESH | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | I will schedule DDPASS session for this study soon. | 100 | OCRDC - Inhouse | Yes | -NA- | 2020-07-07 05:30 | 2020-07-08 05:30 |  |  | ONC | Novartis | InHouse | 2016-06-08 05:30 | 2016-06-08 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | IQVIA | [7 empty] | 155 | 0 |  |  | 0 |  |  |  | 751 | 8 | 0 |  | Lymphoma NOS; Solid tumour | No | Global | Completed | Yes | [14 empty] | DBL |  | None of the above | Yes
CGXV813A0 | CGXV813A02101 | C4009335 | Phase I | Other | CRO - EDC |  |  | 2022-02-11 05:30 | DB Set-Up | Final DBL | 2022-10-12 05:30 |  | 2021-10-01 05:30 | 2021-09-29 05:30 |  | Planned | 2022-06-15 05:30 |  | 2022-10-12 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A first-in-human, randomized, participant- and investigator-blinded, placebo controlled, single and multiple ascending dose study to assess the safety, tolerability, and pharmacokinetics of oral GXV813 in healthy participants | CGXV813A02101 | N6 Neuroscience - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Catherine Gray | [17 empty] | Rohit Varate | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Schizophrenia | No | Global | Open | Yes | [16 empty] | None of the above
CGXV813A0 | CGXV813A02102 | C4011594 | Phase I |  |  |  |  | 2022-10-20 05:30 |  | Final DBL | 2023-02-22 05:30 |  | 2022-07-21 05:30 |  |  | Planned | 2023-01-18 05:30 |  | 2023-02-22 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CGXV813A02102 RO | N6 Neuroscience - NIBR | [6 empty] | Denise Serra | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Psychotic disorder | No | Global | Open | Yes | [16 empty] | None of the above
CGXV813A0 | CGXV813A02103 | C4011677 | Phase I |  |  |  |  | 2024-05-15 05:30 |  | Final DBL | 2024-09-17 05:30 |  | 2024-01-17 05:30 |  |  | Planned | 2024-08-06 05:30 |  | 2024-09-17 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CGXV813A01101 Japan - Ethnic Sensitivity Study | N6 Neuroscience - NIBR | [6 empty] | TAKAHIRO MURAMOTO | [66 empty] | Psychotic disorder | No | Global | Open | Yes
CGXV813A1 | CGXV813A12201 | C4011596 | Phase II |  |  |  |  | 2023-06-05 05:30 |  | Final DBL | 2025-01-29 05:30 |  | 2023-02-19 05:30 |  |  | Planned | 2024-12-11 05:30 |  | 2025-01-29 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CGXV813A12201 PoC | N6 Neuroscience - NIBR | [6 empty] | Denise Serra | [66 empty] | Psychotic disorder | No | Global | Open | Yes
CHDM201A | CHDM201A2101 | C3003080 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2019-03-01 05:30 |  | DB On hold |  |  |  | 2018-10-12 05:30 | 2018-10-18 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | Study has been terminated | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A Phase I/II multi-center study of HDM201 added to chemotherapy in adult patients with relapsed/refractory (R/R) and newly diagnosed acute myeloid leukemia (AML) | CHDM201A2101_PIb/II_AML Rel/Ref & 1L fit CT combo | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Panda, Bidyuta Prabhat | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Ursula Loechner | Ursula Loechner | Bakka, Sandeep | Bakka, Sandeep |  |  | Study in production and got cancelled |  | DRM | Bakka, Sandeep | Bakka, Sandeep | Completed | 25th June: Received Peer review comments. Will work on the updates and will release again for Peer Review by 27th Jun.&nbsp; Will request for LSH setup once done. 13Jun19: 2 study specific forms pending to be included in Rule file. DRM setup is onhold as SMT file generation is on hold 15 APr2020; Study has been terminated. | Study Cancelled | Study Cancelled | 2019-04-17 05:30 |  | Kommu, Ranjith Kumar | Varate, Rohit | Amit Agavekar | Completed | 2019-04-18 | Completed | 2019-04-18 05:30 | Study is going for termination and No FPFV happened and the FPFV is being pulled from another tracker |  | 2019-04-18 05:30 | 2019-04-18 05:30 |  | 2019-04-19 05:30 |  |  |  | 0 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 1 | 155 | 93 | -1 | 909 | 1192 | -280 | 280 | 35 | 376 | 1603 | 3 | 3 |  | Acute myeloid leukaemia | No | Global | Terminated | Yes | [10 empty] | 2019-04-18 05:30 | [5 empty] | None of the above
CHDM201H1 | CHDM201H12101C | C4002980 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-03-15 05:30 | 2019-05-16 05:30 | 2019-06-11 05:30 | DB Conduct | Final DBL | 2023-02-14 05:30 | 2019-06-24 05:30 | 2018-12-05 05:30 | 2018-12-03 05:30 |  | Active | 2022-12-06 05:30 |  | 2023-02-14 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase Ib, multi-arm, open-label, study of HDM201 in combination with MBG453 or venetoclax in adult subjects with acute myeloid leukemia (AML) or high-risk myelodysplastic syndrome (MDS) | CHDM201H12101C novel/novel combination AML/MDS | N7 Oncology - NIBR | Langlo, Francois | Jain, Rahul | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Brigitte Kuenzle | Brigitte K��nzle | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 15Mar2019 Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022. |  | DRM | Tadiparthy, Ramakanth | Kuttoboina, Sujan Kumar | Completed | 04JAN21: Rule file has been finalized and SNOW 51 RITM2132812 request has been created as part of PPC5. 31DEC20: Rule file has been updated with new ZJ forms as part of PPC 5. Peer review is ongoing. 16SEP20: B13L DTS has been added in RF and finalized. SNOW 51 request RITM1801221 has been created. As of today no pending forms and no pending DTS. 04SEP20: RF finalized and SNOW 51 Request RITM1765900 has been raised. As of today no pending forms and no pending DTS. 02SPEP20: RF updated with B12L DTS , peer review is onoging 25AUG20: Change request was shared on 24AUG20 end of the day and change request is not clear and requested for DBD inputs for to proceed RF development. 07JUL20: As of today, no pending forms and no pending DTS. 04JUN2020: No pending forms and DTS. Rule file has been finalized and snow 51 request has been raised for the addion of new Time variable in ZJ domain for preadvance data flow. 06MAY2020: As part of PPC new form VSG001_2 has been added in Rule file and finalized. SNOW 51 request has been created. 09Mar2020 : Included B11L DTS and sent for LSH setup. 02MAR2020: TDM has confirmed that Biomarker has been finalized and is included in RF will be sent for peer review on 03Mar2020. Also there is plan to have PPC and form not received yet. 13Feb2020 : Yet to receive the final DTS B11L from DBD. Its flagged in the report and followed up with DBD 20-JAN-20: B11L DTS is pending and EG1L DTS added in Rule file. 29-NOV-2019: Rule file update is ongoing. Will be finalized by 03-DEC-19. | None | None | 2019-08-16 05:30 | Transition Study and Legacy process | Tidke, Shyam | Varate, Rohit | Rohit Varate | Completed | 2019-08-26 | Completed | 2019-08-27 05:30 |  | Pre-requisites not met | 2019-08-28 05:30 | 2019-08-28 05:30 | Pre-requisites not met | 2019-10-30 05:30 |  |  |  |  | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 7 | 139 | 111 | 0 | 675 | 1013 | 0 | 231 | 37 | 297 | 1347 | 6 | 0 |  | Acute myeloid leukaemia; Myelodysplastic syndrome | No | Global | Open | Yes | [10 empty] | 2019-08-27 05:30 | [5 empty] | None of the above
CHDM201I1 | CHDM201I12201 | C4010923 | Phase I+II | NCDS_2 | Rave EDC - Inhouse | 2022-01-14 05:30 |  | 2022-05-16 05:30 | Study Planned | Final DBL | 2026-02-06 05:30 |  | 2021-08-26 05:30 | 2021-09-06 05:30 | 2021-12-27 05:30 | Planned | 2025-12-26 05:30 |  | 2026-02-06 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase Ib/II open label dose confirmation, proof of concept study of siremadlin in combination with venetoclax plus azacitidine in unfit adult AML participants who responded sub-optimally to first-line venetoclax plus azacitidine treatment and in participants with newly diagnosed unfit AML presenting with high-risk clinical features | CHDM201I12201 - Ph2 HDM+VEN+AZA in AML | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Yadav, Kanika | Mitra, Kaustav | Bhartendu, Rishav | Nair, Sreesha | Stephanie Grzesiak | Stephanie Marie Fabienne Grzesiak | Kabra, Pratik Govind | Kabra, Pratik Govind |  |  | 09 Dec 2021: Go-Live date has been moved to 31 Jan 2022 (New addition of 6 CRFs receieved) |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 19-Jan-2022: Peer Review is completed. CHDM201I12201_Rule File_version 1.0 is finalized in Subway. SNOW-05 LSH (TEST) ticket is also raised with ticket number-RITM3396496 for LSH setup. SNOW-05 LSH (PROD) ticket will be raised once Go-live is achieved. 3-Jan-2022: RF is released for peer Review 28-Dec-2021: RF Development is started 15-Dec-2021: DBD share the ALS, SRF and annotation for initial review. Comments were shared with DBD. 9-Dec-2021: DBD informed new Go-live date: 31-jan-2022 19Aug2021 : RF developer Assigned with golive as 29NOv2021. | None | None |  | LSH TEST Ticket raised on 19-Jan-2022, missed the KPI because of delay in Rule File finalization due to delay in finalization of DQP which is a pre-requisite document for LSH-TEST setup and also due to unavailability of the Rule file developer and Peer reviewer because of Health issues. | CHILUKESHWARAM, AKHIL | Agavekar, Amit | Amit Agavekar | [13 empty] | 0 | [14 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1174 | 12 | 0 |  | Acute myeloid leukaemia | Yes | Global | Open | Yes |  | Completed | 2022-02-09 05:30 | Ongoing | [12 empty] | None of the above
CHDM201I1 | CHDM201I12202 | C4015261 | Phase II | NCDS_2 |  |  |  | 2022-11-15 05:30 |  | Final DBL | 2025-06-23 05:30 |  | 2022-07-15 05:30 |  |  | Planned | 2025-05-12 05:30 |  | 2025-06-23 05:30 | [5 empty] | InHouse |  |  | CHDM201I12202 Ph2 HDM+VEN in R/R AML | PA Oncology (Hematology not for MA projects) | [5 empty] | Flavia Kiertsman | Flavia Kiertsman | [54 empty] | 105 | [7 empty] | 1250 | 6 |  |  | Acute myeloid leukaemia | No | Global | Open | Yes
CHDM201K1 | CHDM201K12201 | C4010927 | Phase I+II | NCDS_2 | Rave EDC - Inhouse | 2022-04-08 05:30 |  | 2022-07-05 05:30 | DB Set-Up | DB Go-live | 2022-04-15 05:30 |  | 2021-12-17 05:30 | 2021-12-17 05:30 |  | Planned | 2028-01-17 05:30 |  | 2028-02-28 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology |  | CHDM201K12201 - Ph2 HDM+DLI in AML post-aHSCT | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kambal, Sundeep | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Stephanie Grzesiak | Stephanie Marie Fabienne Grzesiak | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | [6 empty] | Bairagi, Arpita | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Acute myeloid leukaemia | Yes | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CHDM201A0 | CHDM201X1102 | C1200289 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-09-28 05:30 |  | 2017-06-14 05:30 |  | Completed | 2017-12-12 05:30 | 2017-12-12 05:30 | 2017-12-29 05:30 | 2017-12-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase I, single-center, open-label, two-period, fixedsequence DDI study to evaluate the effect of CYP3A4 inhibitor or inducer on the pharmacokinetics of HDM201 in healthy volunteers | CHDM201X1102 | PA Oncology (Hematology not for MA projects) | Langlo, Francois | SATO, RYUSUKE | Kansagara, Sachinkumar | Tanada, Miyako | Gupta Bhaya, Soumya Kanti |  | YU TANI | [15 empty] | Shah, Manasi |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CHDM201F1 | CHDM201X2101 | C1200596 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-07-07 05:30 |  | 2014-02-25 05:30 |  | Completed | 2021-01-27 05:30 | 2020-06-09 05:30 | 2020-07-20 05:30 | 2020-07-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase I, open label, multicenter, dose-escalation study of oral HDM201 in adult patients with advanced solid and hematological tumors characterized by wild-type TP53 | CHDM201X2101 | N7 Oncology - NIBR | Langlo, Francois |  | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Audrey Kaag | Audrey Kaag |  | Gupta, Anshu | [15 empty] | Rohit Varate | [28 empty] | Syneos Health | Oncology | AP21 | INC | Anne Bone (anne.bone@incresearch.com) | Earlier DBD: Brinda Shree |  |  | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Haematological malignancy; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CHDM201G1 | CHDM201X2103C | C1200759 | Phase I+II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-03-13 05:30 |  | 2014-10-31 05:30 |  | Completed | 2019-11-19 05:30 | 2019-10-16 05:30 | 2019-12-25 05:30 | 2019-12-03 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib/II, open-label, multicenter study of oral HDM201 in combination with oral LEE011 in adult patients with liposarcoma | CHDM201X2103C | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Emilie Bossuge | Emilie Bossuge | Oguri, Praveen | Oguri, Praveen | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse | 2015-02-09 05:30 | 2015-02-09 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | IQVIA | [7 empty] | 148 | 0 |  |  | 0 |  |  |  | 493 | 5 | 0 |  | Liposarcoma | No | Global | Completed | Yes | [16 empty] | None of the above
CHDM201A0 | CHDM201X2104 | C3001760 | Phase I | NCDS | CRO - EDC |  |  | 2020-07-28 05:30 | DB Locked |  |  | 2020-07-13 05:30 | 2019-04-26 05:30 | 2019-04-23 05:30 |  | Completed | 2020-09-30 05:30 | 2020-08-10 05:30 | 2020-10-12 05:30 | 2020-10-09 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A single-center, open-label study to investigate the absorption, distribution, metabolism and excretion (ADME) of HDM201 after a single oral dose of 25 mg [14C]HDM201 in healthy subjects | CHDM201X2104 hADME | PA Oncology (Hematology not for MA projects) | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | IQVIA | [19 empty] | Acute myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CHDM201A0 | CHDM201X2105 | C3003952 | Phase I | Other | Rave EDC - Inhouse |  |  | 2022-09-15 05:30 | DB On hold | Final DBL | 2023-06-02 05:30 |  | 2022-05-19 05:30 |  |  | Planned | 2023-03-31 05:30 |  | 2023-06-02 05:30 |  | FALSE | Study cancelled | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | FULL Outsourced | Hematology | HDM201 in subjects with mild, moderate and severe hepatic impairment and matching healthy volunteers | CHDM201X2105_Hepatic_Impairment | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Donthineni, Kalyan | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Amanda Taylor | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CHDM201A0 | CHDM201X2106 | C3003953 | Phase I | Other | Rave EDC - Inhouse |  |  | 2022-02-11 05:30 | DB On hold | Final DBL | 2022-08-02 05:30 |  | 2021-09-03 05:30 | 2021-09-29 05:30 |  | Planned | 2022-10-26 05:30 |  | 2022-08-02 05:30 |  | FALSE | Study cancelled. | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | FULL Outsourced | Hematology | A phase I, randomized, open-label, cross-over study to evaluate the food effect on the pharmacokinetics of siremadlin (HDM201) in healthy subjects | CHDM201X2106_Relative BAV & Food effect | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Tripathi, Gaurav Jagdish | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Melissa Hackling | Melissa Hackling | [17 empty] | Amit Agavekar | [28 empty] | Parexel | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 300 | 0 | 0 |  | Solid tumor |  | Global | Open | Yes | [16 empty] | None of the above
CHDM201A0 | CHDM201X2110 | C3003958 | Phase I | NCDS_2 |  |  |  | 2023-02-14 05:30 |  | Final DBL | 2024-06-03 05:30 |  | 2022-11-28 05:30 |  |  | Planned | 2024-03-25 05:30 |  | 2024-06-03 05:30 |  | FALSE |  |  |  | InHouse |  | HDM201 in subjects with severe renal impairment and matching healthy volunteers | CHDM201X2110_Renal Impairment | PA Oncology (Hematology not for MA projects) | [6 empty] | Charisse Kemp | [54 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Acute renal insufficiency | No | Global | Open | Yes | [16 empty] | None of the above
CHKT288A1 | CHKT288X2101 | C1200464 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-12-01 05:30 |  | 2016-07-21 05:30 |  | Completed | 2018-06-13 05:30 | 2017-09-14 05:30 | 2018-10-26 05:30 | 2018-03-23 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase I, multicenter, open-label dose escalation and expansion study of HKT288, administered intravenously in adult patients with advanced solid tumors, including epithelial ovarian cancer and renal cell carcinoma | CHKT288X2101 | N7 Oncology - NIBR | Langlo, Francois | Danisiewicz, Aleksandra | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sarah DiDominick | Sarah DiDominick | Bakka, Sandeep | [14 empty] | Gandikota, Sree Lakshmi |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2016-10-21 05:30 | 2016-10-21 05:30 |  |  | ICON | [19 empty] | Fallopian tube cancer; Ovarian cancer; Renal cell carcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CHLS459A1 | CHLS459A12101 | C4009266 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-12-04 05:30 |  | 2022-04-04 05:30 | DB On hold | Final DBL | 2025-01-06 05:30 |  | 2020-11-09 05:30 | 2020-11-10 05:30 |  | Planned | 2024-10-25 05:30 |  | 2025-01-06 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO |  | CHLS459A12101 Clinical Trial | N7 Oncology - NIBR | Langlo, Francois | OMEYER, Delphine | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Adonai Fessehatsion | Adonai Fessehatsion | Kancharla, Susmita | Kancharla, Susmita | Not Started |  | 04May2021 : As per TDM (Duffin, Anastasia) HLS459 program remains on pause while the organization continues to focus effort and resources on generating more data from current anti-BCMA assets that would further support a better assessment/understanding of the role of dual targeting BCMA and CD19 in preventing MM relapses. There is no precise timeframe to resume the HLS459 program at this time. currently study is on hold and database setup activities have not been initiated. |  | DRM |  | Kuttoboina, Sujan Kumar | Not Started | 09JUN21: Study was put on hold 10NOV20: No updates from study team about db golive timelines. Will update once I've information from the team. 28OCT20: Protocol not yet finalized and study might post poned and requested Lead DBD to provide updated timelines. 20OCT20: Following up with lead DBD on the progress of the study. 12OCT20: SSD is in review, once Lead DBD got the initial SSD and SRF's approved, will start review of Study specific page modeling. 11SEP20: No activities started at this point of time | [6 empty] | Rohit Varate | [28 empty] | IQVIA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 5 | 0 |  | Multiple myeloma | No | Global | Open | Yes | [16 empty] | None of the above
CLFU835A0 | CHSC835A2204 | C1200700 | Phase II | NCDS | OC RDC - Inhouse | 2015-11-17 05:30 | 2015-11-17 05:30 |  | DB Locked | Final DBL Achieved |  | 2014-11-24 05:30 |  | 2015-04-08 05:30 |  | Completed | 2021-12-18 05:30 | 2021-01-21 05:30 | 2021-05-18 05:30 | 2021-05-24 05:30 | FALSE | No priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A follow-up study that evaluates the safety and clinical outcomes of patients that have undergone hematopoietic stem cell transplantation with HSC835 (expanded umbilical cord blood hematopoietic stem cells) | CHSC835A2204 Safety follow up of all pts who recei | P6 Global Health | Paigaonkar, Gargi | Doshi, Pranav | Doshi, Pranav | Sarkhel, Biswadip | Ninan, Esther | Prafulla Bhad | Prafulla Bhad | Meda, Sreelakshmi | Iliyas, Mohamed | [13 empty] | Garje, Sagar |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | -NA- | 2021-05-25 05:30 | 2021-05-26 05:30 |  |  | Pharma | ICON | ICON | 2015-11-17 05:30 | 2015-11-17 05:30 | Iliyas, Mohamed | Meda, Sreelakshmi | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 1 | 0 |  | Haematological malignancy | No | Global | Open | Yes | [16 empty] | None of the above
CHSY244A0 | CHSY244X2101 | C1200283 | Phase I | NCDS | CRO - EDC |  |  | 2019-10-21 05:30 | DB Locked |  |  | 2019-10-21 05:30 | 2019-07-15 05:30 | 2019-07-16 05:30 |  | Completed | 2020-02-20 05:30 | 2020-02-17 05:30 | 2020-06-08 05:30 | 2020-06-05 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A first-in-human, randomized, investigator and subject blind, placebo-controlled, single ascending dose study to assess the safety, tolerability and pharmacokinetics of intravenously administered HSY244 in healthy subjects. | CHSY244X2101 AFib FIH | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Jul Schofield | Jul Schofield | [15 empty] | Varate, Rohit |  | Rohit Varate | [28 empty] | CMED | [19 empty] | Atrial fibrillation | No | Global | Completed | Yes | [16 empty] | None of the above
CHSY244A1 | CHSY244X2201 | C1200377 | Phase II | NCDS | CRO - EDC |  |  | 2020-12-18 05:30 | DB Conduct | Final DBL | 2023-01-03 05:30 | 2020-11-30 05:30 | 2020-09-04 05:30 | 2020-09-08 05:30 |  | Active | 2022-11-08 05:30 |  | 2023-01-03 05:30 |  | FALSE | NIBR-Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A randomized, placebo-controlled, investigator- and participant-blinded study to evaluate the efficacy, safety, tolerability, and pharmacokinetics of HSY244 in participants with atrial fibrillation | CHSY244X2201 POC in AF | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Lee Anne Filosa | Lee Anne Filosa | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Atrial fibrillation | No | Global | Open | Yes | [16 empty] | None of the above
CHX575 US | CHX575-307 | C3000273 | Phase III | Other | [7 empty] | 2012-09-05 05:30 |  | 2011-04-29 05:30 |  | Completed |  | 2015-03-20 05:30 |  | 2015-09-28 05:30 | FALSE |  |  | Cluster C (fGSK,IHD,Sandoz) | Outsourced |  | Randomized, double-blind, parallel-group, multicenter study to evaluate the efficacy and safety of HX575 epoetin alfa vs. US-licensed epoetin alfa (EpogenÂ®/ProcritÂ®) in the treatment of anemia associated with chronic kidney disease | CHX575-307 HX575 US | P2 SZ Biopharma |  |  |  | Gracey Sugunan, Unni Krishnan | Ninan, Esther |  | Paul Lupo | [66 empty] | Anaemia; Chronic kidney disease | No | Regional | Completed | [17 empty] | None of the above
CIAG933A1 | CIAG933A12101 | C4008364 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-07-20 05:30 | 2021-09-08 05:30 | 2021-10-18 05:30 | DB Conduct | Final DBL | 2024-07-04 05:30 | 2021-10-21 05:30 | 2021-04-26 05:30 | 2021-04-09 05:30 |  | Active | 2024-05-23 05:30 |  | 2024-07-04 05:30 |  | FALSE | TCO RACE | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | An open-label, multi-center, Phase I study of oral IAG933 in adult patients with advanced Mesothelioma and other solid tumors | CIAG933A12101 Clinical Trial | N7 Oncology - NIBR | Langlo, Francois | Talisetty, Kedarinath | Thorat, Swapnil | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Stephanie Garnick | Stephanie Garnick | Porandla, Swapna | Porandla, Swapna | Not Started |  | 06May2021 : Swapna to Co-lead. 30Apr201 : No activity performed from DBD perspective. DO acct study and access is pending. Need to check on timelines Initial golive 20jul2021. |  | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 13-Oct-2021: Rule file v3.0 is finalized in SUBWAY for the DTS (EG1L) addition. 24Sep2021: LB domain changes have been updated in Rule file 2.0. As LSP got an issue in the LSH setup. 09Sep2021: Rule File Version 1.0 finalized in subway. SNOW#05 (RITM2961738) Request raised for new study setup in LSH. 03Sep2021: Rule file peer review is completed. 25Aug2021: Released the CIAG933A12101_Rule file_version 0.1 for Peer Review. 15Aug2021: Rule file development has been started. Go-live is pushed to 08Sep2021 12Aug2021: Review of SRFs, ALS, SDTM Annotations are completed and comments are shared with DBD. 11Aug2021: Go-live is pushed to 26Aug2021 9Aug2021: Received ALS, SRFs, SDTM Annotations. 9Aug2021 : Reassigned from Angella to Satwik. Satwik developed RF and Review by Angella. 9-Aug-2021: Screen UAT completion confirmed by Lead DBD. Pre-requisite documents shared for review. 26May2021: RF developer assigned. | None | None | 2021-09-09 05:30 |  | Ramayanam, Vinay | R, Harini | Rohit Varate | Completed | 2021-09-21 | Completed | 2021-09-29 05:30 |  |  | 2021-09-30 05:30 | 2021-09-30 05:30 |  | 2021-09-30 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 35 | 133 | 0 | 620 | 1406 | 0 | 316 | 45 | 353 | 1804 | 1 | 0 |  | Mesothelioma; Solid tumor | No | Global | Open | Yes | [10 empty] | 2021-09-29 05:30 | [5 empty] | None of the above | Yes
CICL670A | CICL670A2302 | C1001178 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-03-22 05:30 |  | 2009-07-15 05:30 |  | Completed | 2018-03-26 05:30 | 2018-02-27 05:30 | 2018-06-07 05:30 | 2018-04-27 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A multi-center, randomized, double-blind, placebocontrolled clinical trial of deferasirox in patients with myelodysplastic syndromes (low/int-1 risk) and transfusional iron overload (TELESTO) | CICL670A2302_(TELESTO)_IO/low-int1 MDS/L1-M (pcb) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kunte, Nahush | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Janet Lasher | Janet Lasher |  | Sinha, Deepakshi | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | Oncology | BP21 | Quintiles | Christopher.Waters@quintiles.com | Earlier DBD: Asha Rajanna | [14 empty] | Myelodysplastic syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CICL670A_MA | CICL670A2421 | C1001612 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-01-28 05:30 |  | 2013-04-29 05:30 |  | Completed |  | 2017-04-05 05:30 |  | 2017-06-22 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | An open-label, phase II, randomized, pilot study to assess the effect in term of erythroid improvement of deferasirox combined with erythropoietin compared to erythropoietin alone in patients with low- and int-1-risk myelodysplastic syndrome | CICL670A2421 KALLISTO IO/low risk MDS/L1-C | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sardesai, Pallavi Sharad | Sardesai, Pallavi Sharad | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Geralyn Gilotti | Geralyn Gilotti | [17 empty] | Sai Krishna Mettugari | [28 empty] | ICON | [19 empty] | Myelodysplastic syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CICL670A | CICL670A2428 | C4010617 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-08-23 05:30 | Study Planned | DB Go-live | 2022-07-05 05:30 |  | 2022-03-15 05:30 |  |  | Planned | 2025-08-25 05:30 |  | 2025-10-06 05:30 |  |  | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Drug Utilization Study-Evaluation of the use of EXJADEÂ® (deferasirox) film-coated tablets and biological monitoring as described in the EU Summary of Product Characteristics and Educational Materials in Selected European Countries | CICL670A2428 DUS | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Deshpande Dubey, Aditi | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Anne Zuse | Anne Zuse | [17 empty] | Sai Krishna Mettugari | [36 empty] | 50 | [7 empty] | 600 | 3 |  |  | Chronic iron overload | No | Global | Open | Yes
CICL670E | CICL670E2419 | C1001617 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-12-06 05:30 |  | 2012-05-23 05:30 |  | Completed | 2019-01-17 05:30 | 2019-01-17 05:30 | 2019-02-27 05:30 | 2019-04-09 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | An open label, single arm, efficacy and safety study of deferasirox in iron overloaded patients with non-transfusion dependent thalassemia | CICL670E2419 (THETIS) IO/NTDT/L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Pawar, Sagar Chandrakant | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Fabian Romen | Fabian Romen |  | Gandla, Prashanth | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | mailto:Gary.Lock@ppdi.com | Earlier DBD: Asha Rajanna |  |  | 36 | 0 |  |  | 0 |  |  |  | 463 | 3 | 0 |  | Thalassaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CICL670E | CICL670E2422 | C1001618 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2025-02-14 05:30 | 2014-07-28 05:30 |  | 2013-11-19 05:30 |  | Active | 2025-01-04 05:30 |  | 2025-02-14 05:30 |  | FALSE | DCN Priority | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | An observational, multicenter study to evaluate the safety and tolerability of deferasirox in the treatment of pediatric patients with non-transfusion-dependent iron overload | CICL670E2422 (NESO) IO/NTDT/L1-M Ped Registry | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Poul, Sushant | Sadhu, Soumen Kumar | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Janet Ng-Sikorski | Janet Ng-Sikorski |  | Sinha, Deepakshi | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | Oncology | AP21 | Quintiles | Christopher.Waters@quintiles.com | Earlier DBD: Jugnu Kumari; CRF amendment going on aCRF and DB spec relkeased. |  |  | 29 | 0 |  |  | 0 |  |  |  | 663 |  |  |  | Iron overload | No | Global | Open | Yes | [16 empty] | None of the above
CICL670F | CICL670F2108 | C3003292 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  |  | Study Planned |  |  |  |  | 2017-09-23 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A 24 week, open label, multi-center study to assess pharmacokinetics, efficacy and safety of ICL670 film-coated tablet (FCT) in comparison with deferasirox dispersal tablet (DT) in Chinese anemia patients with transfusional hemosiderosis | CICL670F2108 “Short description of study” | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle |  | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | MASAYUKI ITO | MASAE KAI | [17 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Aplastic anaemia | No | Global | Terminated | Yes | [16 empty] | None of the above
CICL670F | CICL670F2202 | C1001180 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2024-02-05 05:30 | 2015-10-21 05:30 |  | 2015-02-06 05:30 |  | Active | 2023-12-19 05:30 |  | 2024-02-05 05:30 |  | FALSE | HA commitment | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A randomized, open-label, multicenter, two arm, phase II study to evaluate treatment compliance, efficacy and safety of an improved deferasirox formulation (granules) in pediatric patients with iron overload | CICL670F2202 Iron Overload Pediatric (CALYPSO) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Rastogi, Anisha | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Nayia Gkolfi | Panagiota Gkolfi |  | Gupta, Anshu | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | Oncology | AP21 | Quintiles | mailto:carla.real@iqvia.com | Earlier DBD: Brinda Shree |  |  | 174 | 0 |  |  | 0 |  |  |  | 850 | 4 | 0 |  | Chronic iron overload | Yes | Global | Open | Yes | [16 empty] | None of the above
CICL670F | CICL670F2203 | C1001181 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-10-03 05:30 | 2018-01-31 05:30 | DB Conduct | Final DBL | 2023-05-02 05:30 | 2018-01-11 05:30 |  | 2017-06-13 05:30 |  | Active | 2023-03-18 05:30 |  | 2023-05-02 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Ocular study in Hereditary Hemochromatosis | CICL670F2203_IO/Anemia/L1M (Exjade FCT) Safety HH | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Painuly, Vandana | Sadhu, Soumen Kumar | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Sumerah Bakhsh | Janet Lasher | Mokhamatam, Madhu Purnachandra Rao | Shewane, Roshni | Completed | 2020-05-21 05:30 | Study Transitioned to Roshni Shewane on 21-May-2020. | [10 empty] | Sundar, N Sushant | Sundar, N Sushant | Sai Krishna Mettugari | [13 empty] | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-10-16 05:30 | 2017-10-16 05:30 | Shewane, Roshni | Iliyas, Mohamed | NA | [7 empty] | 76 | 0 |  |  | 0 |  |  |  | 627 | 4 | 0 |  | Chelation therapy; Hereditary haemochromatosis | No | Global | Open | Yes | [16 empty] | None of the above
CICL670F | CICL670F2429 | C1001182 | Phase IV | NCDS | OC RDC - Inhouse |  | 2017-06-29 05:30 | 2018-01-25 05:30 | DB Locked | Final DBL Achieved |  | 2018-01-16 05:30 |  | 2017-06-15 05:30 |  | Completed | 2019-12-30 05:30 | 2019-12-05 05:30 | 2020-02-10 05:30 | 2020-01-13 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase IV, open-label, single-arm, interventional, prospective safety study evaluating pediatric patients with transfusional hemosiderosis treated with crushed deferasirox FCT | CICL670F2429_IO/NTDT/L1-M (EXJADE FCT Crushed) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Pawar, Sagar Chandrakant | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Vanessa Giannone | Vanessa Giannone | Maricherla, Vijayroshan | Rana, Aamir | [13 empty] | Polagoni, Bharghavi |  | Sai Krishna Mettugari | [12 empty] | Data was not extracted by team during initial DDPASS meetings. | 17 | OCRDC - Inhouse |  | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-10-16 05:30 | 2017-10-16 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 44 | 0 |  |  | 0 |  |  |  | 541 | 2 | 0 |  | Haemosiderosis | No | Global | Open | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CIDD001D | CIDD001D2402 | C1200232 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-04-03 05:30 | 2018-07-16 05:30 | DB Locked | Final DBL Achieved |  | 2018-07-11 05:30 |  | 2017-11-14 05:30 |  | Completed | 2019-02-28 05:30 | 2019-01-22 05:30 | 2019-03-22 05:30 | 2019-03-22 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 24 week randomized, multi-center, open-label study to evaluate the effect of reminder notifications and motivational/adaptive messaging on treatment adherence of COPD subjects receiving Ultibro Breezehaler treatment using the Concept2 inhaler for dose administration and tracking | CIDD001D2402 | P8 Respiratory | Mahajan, Vinay | Rajguru, Gaurav | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Mojdeh Maboudian | Mojdeh Maboudian | Patnaik, Angella | Patnaik, Angella |  |  |  | DB Go-live planned with respect to FPFV Date. | Pre-DRM | Patnaik, Angella | Patnaik, Angella | Completed | 07-JUL-2020: Study Locked. 21May18 : Sent for LSHTST setup 05Jun18: Pre-drm LSH Test output pending 27Jun18: PPC 1 updates pending in Rule file post which Pre-drm data to be reviewed 18Jul18: Same as above 26Jul18: Test Predrm output shared for review 03Aug18: List of domains PREDRM output provided = CM, DM, DS, EC, FAMH, IE, MH, PR, SU, SV, VS, ODM (verification ongoing, 4 panels left) Blinded domain PREDRM pending = AE, DE, DV (verification done) LSP working on it TPD domain not to be processed in LSH Test = QS, DX, DT, SS (done) - test transfers receieved from vendor. 03DEC2019: Study Locked. | None | None | 2018-09-12 05:30 |  | Kadam, Sandeep |  | Sushant Sundar | Completed | 2018-09-19 | Not Applicable |  |  |  | 2018-09-24 05:30 | 2018-09-24 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) |  |  |  | DXL, SSL, QS4L third party set up completed, prod data loaded and reviewed by TDM/TP | 100 | RaveX - Inhouse |  |  | 2019-03-25 05:30 | 2019-03-27 05:30 | [9 empty] | NA | [5 empty] | 7 | 10 | 40 | 0 | 60 | 448 | 0 | 153 | 30 | 124 | 602 | 7 | 0 |  | Chronic obstructive airways disease | No | Global | Wind Down | Yes | [15 empty] | Sahu, Ahallad | None of the above | Yes
CIDD001E1 | CIDD001E12101 | C4004987 | Phase I | Other |  |  |  | 2019-09-30 05:30 |  |  |  | 2019-04-28 05:30 | 2019-09-09 05:30 | 2019-04-18 05:30 |  | Active | 2019-12-19 05:30 | 2019-12-19 05:30 | 2020-01-10 05:30 | 2020-01-20 05:30 | FALSE |  |  |  | FULL Outsourced |  |  | CIDD001E12101 Sensor Pilot Study | P8 Respiratory | [5 empty] | Mojdeh Maboudian | Mojdeh Maboudian | [66 empty] | Asthma; Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CIDD001E1 | CIDD001E12201 | C4003896 | Phase II | NCDS_2 |  |  |  | 2022-10-21 05:30 |  | Final DBL | 2024-07-11 05:30 |  | 2022-06-02 05:30 |  |  | Planned | 2024-05-02 05:30 |  | 2024-07-11 05:30 |  | FALSE |  |  |  | InHouse |  |  | CIDD001E12201 Poc Sensor Study in Asthma/COPD/IPF | P8 Respiratory | [6 empty] | Mojdeh Maboudian | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CIDD001E1 | CIDD001E12202 | C4003897 | Phase II | NCDS_2 |  |  |  | 2020-03-30 05:30 |  |  |  |  | 2019-12-18 05:30 |  |  | Stopped (with patients) | 2020-12-18 05:30 |  | 2021-02-26 05:30 | 2021-02-26 05:30 | FALSE |  |  |  | InHouse |  | Prospective multi-centric (US focused), 4 months, non-investigational, observational study in symptomatic asthma patients at risk of asthma exacerbations | CIDD001E12202 PoC SensorStudy_Asthma | P8 Respiratory | [6 empty] | Mojdeh Maboudian | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Asthma | No | Global | Terminated | Yes | [16 empty] | None of the above
CIDH305A0 | CIDH305X2101 | C1200746 | Phase I | Other | CRO - EDC | 2015-02-20 05:30 | 2015-02-20 05:30 |  | DB Conduct | Final DBL | 2025-01-03 05:30 | 2015-01-06 05:30 |  | 2014-10-31 05:30 |  | Active | 2024-10-25 05:30 |  | 2025-01-03 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A Phase I study of IDH305 in patients with advanced malignancies that harbor IDH1R132 mutations | CIDH305X2101 FIH in Advanced Malignancies | N7 Oncology - NIBR | Langlo, Francois | HernÃ¡ndez, Fernanda | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | JoAnne Coop | Douglas Bootle | Ahuja, Mohit | Iliyas, Mohamed | [13 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | CRO | [6 empty] | ONC | Novartis | Outsourced | 2015-02-27 05:30 |  | Kanchi, Pavan kumar | Shewane, Roshni | PPD | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Acute myeloid leukaemia; Cholangiocarcinoma; Glioma; Myelodysplastic syndrome; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above | Yes
CIDH305A0 | CIDH305X2102 | C1200475 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-08-15 05:30 |  | 2016-03-29 05:30 |  | Completed | 2020-04-24 05:30 | 2016-11-29 05:30 | 2020-06-03 05:30 | 2017-12-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase I, open label, multicenter, dose finding study of IDH305 with standard of care in IDH1 mutant acute myeloid leukemia | CIDH305X2102 IDH305 in combination in AML | N7 Oncology - NIBR | Langlo, Francois | Danisiewicz, Aleksandra | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Jessica O'Keeffe | Joanne Randolph | Tadiparthy, Ramakanth | [14 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2016-07-01 05:30 | 2016-07-01 05:30 |  |  | ICON | [19 empty] | Acute myeloid leukaemia; Myelodysplastic syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CIGE025A | CIGE025A2455 | C1001183 | Phase IV | Other |  |  |  | 2019-12-27 05:30 |  |  |  | 2019-12-27 05:30 | 2018-11-19 05:30 | 2018-11-19 05:30 |  | Completed | 2021-07-02 05:30 | 2021-07-08 05:30 | 2021-08-06 05:30 | 2021-09-22 05:30 | FALSE |  |  |  | Outsourced |  | Post Approval Safety Study (PASS) for s.c. injection 150mg XolairÂ® (Omalizumab) in Chinese Patients with Moderate to Severe Allergic Asthma | CIGE025A2455 China PASS Study | P8 Respiratory | [5 empty] | Keira Ding | Liju Ding | [66 empty] | Allergic asthma | No | Global | Open | Yes | [16 empty] | None of the above
CIGE025B | CIGE025B1401 | C1001185 | Phase IV | Other |  |  |  | 2013-09-25 05:30 |  |  |  | 2013-10-09 05:30 | 2013-08-29 05:30 | 2013-08-29 05:30 |  | Completed | 2019-06-14 05:30 | 2019-01-31 05:30 | 2019-06-14 05:30 | 2019-05-31 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of Xolair in pediatric allergic asthma | CIGE025B1401 JPN PMS | P8 Respiratory | [5 empty] | YOHEI SHINFUKU | MAKOTO NAGASAKI | [66 empty] | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CIGE025D | CIGE025D1401 | C1001186 | Phase IV | Other |  |  |  | 2013-09-13 05:30 |  |  |  | 2013-09-13 05:30 | 2013-08-29 05:30 | 2013-08-29 05:30 |  | Completed | 2018-11-30 05:30 | 2018-05-31 05:30 | 2018-11-30 05:30 | 2018-11-14 05:30 | FALSE |  |  |  | Outsourced |  | Special Investigation of Xolair(DTE/DTR) | CIGE025D1401 JPN PMS | P8 Respiratory | [5 empty] | KOICHI MORITA | MAKOTO NAGASAKI | [66 empty] | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CIGE025E | CIGE025E1401 | C1001188 | Phase IV | Other | [7 empty] | 2017-09-21 05:30 | 2018-01-19 05:30 | 2017-02-23 05:30 |  | Completed | 2020-03-27 05:30 | 2020-03-13 05:30 | 2020-09-07 05:30 | 2020-08-17 05:30 | FALSE |  |  |  | Outsourced |  | Observational study to investigate the safety and efficacy for 52 weeks in patients with chronic spontaneous urticaria (CSU) treated with Xolair (omalizumab) | CIGE025E1401 JPN PMS | P8 Respiratory | [5 empty] | MINE KIMURA | MINE KIMURA | [66 empty] | Urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CIGE025E | CIGE025E2305 | C1001187 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-04-26 05:30 |  | 2016-08-12 05:30 |  | Completed | 2019-10-01 05:30 | 2019-09-24 05:30 | 2019-11-19 05:30 | 2019-11-14 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | External Full | DF ID | A multicenter, randomized, double-blind, placebocontrolled phase III study to evaluate the efficacy and safety of Xolair® (omalizumab) in Chinese patients with chronic spontaneous urticaria who remain symptomatic despite antihistamine treatment | IGE025E_2305 Pivotal CSU study in China | P8 Respiratory | Paigaonkar, Gargi | Muraleedharan Thampy Santhanalekshmy, Karthika | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Moreshwar Patwardhan | Moreshwar Ramchandra Patwardhan | Killamsetty, Nanari Ram | Killamsetty, Nanari Ram | [13 empty] | Gandikota, Sree Lakshmi |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | Y1;#Y5;#ZK |  |  |  |  | Pharma | ICON | ICON | 2017-02-14 05:30 | 2017-02-14 05:30 | Killamsetty, Nanari Ram | Meda, Sreelakshmi | ICON | [7 empty] | 65 | 0 |  |  | 0 |  |  |  | 553 | 5 | 0 |  | Urticaria | No | Global | Open | Yes | [14 empty] | DMC/Dry-Run/Snapshot | Shanmugam, Sharmila | None of the above | Yes
CIGE025F | CIGE025F1301 | C3000743 | Phase III | Other | CRO - EDC |  |  | 2017-12-15 05:30 | DB Locked |  |  | 2017-12-15 05:30 |  | 2017-06-08 05:30 |  | Completed | 2018-10-19 05:30 | 2018-10-20 05:30 | 2018-12-26 05:30 | 2018-12-24 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | DF RESP |  | Phase III Severe Cedar Pollinosis CIGE025F1301 | P8 Respiratory | Mahajan, Vinay | Ushijiama, Sachiko | P M, Prasanth Kumar | Soni, Suchitra | Hiriyanna, Srinivas | HANAE SATOU; RYOHEI IWASAKI | HANAE SATOU | [15 empty] | Garje, Sagar |  | Sushant Sundar | [14 empty] | FSOM - Outsourced | No | -NA- | [11 empty] | Other | [19 empty] | Seasonal rhinitis | Yes | Global | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | No
CIGE025F | CIGE025F1401 | C3001108 | Phase IV | Other | Other |  |  | 2021-01-29 05:30 | DB Conduct | Final DBL | 2023-05-31 05:30 | 2021-01-27 05:30 | 2020-05-29 05:30 | 2020-05-29 05:30 |  | Active | 2023-01-31 05:30 |  | 2023-05-31 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | DF RESP | The special drug use observational study to investigate the safety and efficacy in patients aged 12 years to &lt; 18 years old with seasonal allergic rhinitis treated with Xolair | CIGE025F1401 JPN PMS | P8 Respiratory | YAMADA, KAYO | INOUE, YUSUKE | YAMADA, KAYO | YAMADA, KAYO | Hiriyanna, Srinivas | YUKIE YOSHIZAWA | YUKIE YOSHIZAWA | [17 empty] | Sushant Sundar | [28 empty] | Other | [19 empty] | Rhinitis allergic | No | Global | Open | Yes | [16 empty] | None of the above
CIGE025K1 | CIGE025K12101 | C4005811 | Phase I | NCDS |  |  |  | 2020-11-16 05:30 |  |  |  | 2020-11-09 05:30 | 2020-10-02 05:30 | 2020-09-30 05:30 |  | Completed | 2021-06-04 05:30 | 2021-07-06 05:30 |  | 2021-08-12 05:30 | FALSE |  |  |  | FULL Outsourced |  |  | CIGE025K12101 BE | P8 Respiratory | [5 empty] | Paola Paganoni | Paola Paganoni | [66 empty] | Allergic asthma | No | Global | Open | Yes | [16 empty] | None of the above
CIMJ995A1 | CIMJ995A12101 | C4006700 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-05-21 05:30 |  | 2022-07-04 05:30 | DB Set-Up | Final DBL | 2025-11-26 05:30 |  | 2021-04-09 05:30 | 2021-04-08 05:30 |  | Planned | 2025-10-15 05:30 |  | 2025-11-26 05:30 |  | FALSE | None | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase I, open label, multicenter, dose escalation and expansion study of IMJ995 in Acute Lymphoblastic Leukemia | CIMJ995A12101 Phase I dual CD19/CD22 CART | N7 Oncology - NIBR | Langlo, Francois | De Kock, Antoinette | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sabine Gutzwiller; Stavros Milatos | Stavros Milatos | Chiranjeevi, Priyanka Boya | Chiranjeevi, Priyanka Boya | Not Started |  | 29Apr2021: Not yet started initial golive when study assigned 21May2021. |  | DRM | Mopuru, Satwik | Mopuru, Satwik | Not Started | 06Jul2021 : RF Developer assigned with Golive as 22Sep2021. | [6 empty] | Rohit Varate | [28 empty] | IQVIA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 5 | 0 |  | Acute lymphocytic leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2102 | C1001192 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-02-01 05:30 |  | 2016-10-17 05:30 |  | Completed |  | 2017-05-30 05:30 |  | 2017-10-09 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase I, open label, two-arm drug-drug interaction study to assess the effect of itraconazole (a CYP3A4 inhibitor) and rifampicin (a CYP3A4 inducer) on the pharmacokinetics of a single dose of INC280 in healthy subjects | CINC280A2102 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Boyapati, Karthik | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Nathalie Pognan | Jean-Rene Basque | Choppadandi, Kranthikumar | [14 empty] | Agavekar, Amit |  | Sushant Sundar | [14 empty] | CRO | No | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-02-01 05:30 |  |  |  | Parexel | [19 empty] | Drug interaction; Pharmacokinetic study | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2103 | C1001193 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-12-10 05:30 |  | 2015-04-21 05:30 |  | Completed |  | 2017-09-12 05:30 | 2017-12-04 05:30 | 2017-12-04 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase I, multicenter, open-label, single-sequence drug-drug interaction study to assess the effect of INC280 on the pharmacokinetics of midazolam and caffeine in patients with cMET-dysregulated advanced solid tumors | CINC280A2103 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Dubey, Mahesh | Varatharaj, Sathiyaraj | Soni, Suchitra | Hiriyanna, Srinivas | Lucian Popa; Nathalie Pognan | Jean-Rene Basque | [15 empty] | Mettugari, Sai Krishna |  | Sushant Sundar | [28 empty] | NA | [19 empty] | Drug interaction; Pharmacokinetic study; Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2105 | C1001195 | Phase I | NCDS | [7 empty] | 2015-12-08 05:30 |  | 2015-07-09 05:30 |  | Completed |  | 2017-04-28 05:30 |  | 2017-07-13 05:30 | FALSE |  |  |  | InHouse |  | A phase I, multicenter, open-label, single-sequence drug-drug interaction study to assess the effect of INC280 on the pharmacokinetics of digoxin and rosuvastatin in patients with cMET-dysregulated advanced solid tumors | CINC280A2105 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Nathalie Pognan | Jean-Rene Basque | [15 empty] | Gandikota, Sree Lakshmi | [16 empty] | OCRDC - Inhouse | [33 empty] | Drug interaction; Pharmacokinetic study; Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2106 | C1001196 | Phase I | NOVDD | [7 empty] | 2015-06-12 05:30 |  | 2015-01-13 05:30 |  | Completed |  | 2017-09-12 05:30 |  | 2017-11-02 05:30 | FALSE |  |  |  | Outsourced |  | An open label, single-dose, multi-center, parallel-group, two-staged study to evaluate the pharmacokinetics of the oral cMET inhibitor INC280 in non-cancer subjects with impaired hepatic function and non-cancer subjects with normal hepatic function | CINC280A2106 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Nathalie Pognan | Jean-Rene Basque | [66 empty] | Hepatic impairment; Pharmacokinetic study | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2108 | C1001197 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-12-14 05:30 |  | 2016-08-10 05:30 |  | Completed | 2018-08-21 05:30 | 2018-05-16 05:30 | 2018-09-26 05:30 | 2018-06-21 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A multicenter, open label, phase 1 dose escalation study to evaluate the pharmacokinetics, safety, and tolerability of INC280 tablet formulation with food in patients with cMET dysregulated advanced solid tumors | CINC280A2108 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Juneja, Twinkle | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Jean-Rene Basque | Jean-Rene Basque | Goyal, Rishu | [14 empty] | Shah, Manasi |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2016-10-28 05:30 | 2016-10-28 05:30 |  |  | NA | [7 empty] | 90 | 0 |  |  | 0 |  |  |  | 753 | 4 | 0 |  | Solid tumour | Yes | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280A2109 | C3000351 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-09-29 05:30 |  | 2017-06-07 05:30 |  | Completed | 2019-04-11 05:30 | 2018-01-05 05:30 | 2019-06-20 05:30 | 2018-03-07 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase 1, randomized, open-label, three-period, six-sequence crossover study to evaluate the bioequivalence of two batches of INC280 150 mg tablet (2x150 mg) in comparison to INC280 100 mg tablet (3x100 mg) following a single oral dose of 300 mg in healthy subjects | CINC280A2109 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Boyapati, Karthik | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Jean-Rene Basque | Jean-Rene Basque | Bai, Chandrakala | [14 empty] | Varate, Rohit |  | Sushant Sundar | [14 empty] | CRO | [6 empty] | ONC | Parexel | Outsourced | 2017-08-10 05:30 |  |  |  | Parexel | [19 empty] | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280A | CINC280A2201 | C1001189 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Conduct | Final DBL | 2023-04-06 05:30 | 2015-06-11 05:30 |  | 2015-01-23 05:30 |  | Active | 2023-03-23 05:30 |  | 2023-04-06 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II, multicenter study of oral cMET inhibitor INC280 in adult patients with EGFR wild-type (wt), advanced non-small cell lung cancer (NSCLC) | CINC280A2201 METmut/METamp NSCLC 1-3L | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Masood Khan, Owais Ahmed | Ravi, Sapna | Soni, Suchitra | Hiriyanna, Srinivas | Brinda Sharma | Brinda Sharma | Samuel, Giftson | Samuel, Giftson | [13 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2015-05-14 05:30 | 2015-05-14 05:30 | Shewane, Roshni | Mareedu, Vasu | NA | [7 empty] | 97 | 0 |  |  | 0 |  |  |  | 632 | 19 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [14 empty] | Interim-Analysis | Varate, Rohit | None of the above
CINC280A | CINC280A2202 | C1001190 | Phase II | NCDS | OC RDC - Inhouse |  |  | 2018-06-29 05:30 | DB On hold | Final DBL | 2020-03-20 05:30 |  |  | 2015-03-30 05:30 |  | Stopped (with patients) | 2020-01-10 05:30 |  | 2020-03-20 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II multicenter study of oral cMET inhibitor INC280 in adult patients with EGFR wild-type (wt), cMET- amplified, advanced non-small cell lung cancer (NSCLC) who have received one or two prior lines of systemic therapy for advanced/metastatic disease | CINC280A2202 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Satoor, Deepti | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Jean-Rene Basque | Jean-Rene Basque | Marx, Karl | [16 empty] | Sushant Sundar | [21 empty] | ONC | Novartis | InHouse |  |  |  |  | NA | [19 empty] | Non-small cell lung cancer | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CINC280A | CINC280A2203 | C4007689 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-10-05 05:30 | 2020-10-05 05:30 |  | DB On hold |  |  |  | 2020-06-02 05:30 | 2020-06-12 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | Study on hold | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase II, Open-Label, Multicenter Study of Capmatinib in Subjects with MET mutation positive, advanced, Non Small-Cell Lung Cancer that has Metastasized to the Brain | CINC280A2203 INC280 in Brain Mets NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Yamjala, Karthik | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Carrie Ben Said | Carrie Ben Said | Gandla, Prashanth | Gandla, Prashanth | Not Started |  | Initial go live as 05Oct2020 when RF developer assigned on 06Jun2020. |  | DRM |  | Kuttoboina, Sujan Kumar | Ongoing | 24SEP20: Study on-hold due to US has declined feasibility for this study which contributes approximately 40% of the total study allocation 22SEP20: Expecting some more changes in database and it will have an impact on RF. Will come to know changes on 23SEP20. 11SEP20: Received all required documents and RF development is ongoing and expected date of RF devlopemnt is 15-SEP-20. 31AUG20: Received ALS, SRF and SDTM annotations for review and review is ongoing 19AUG20: Study team is working on dynamics. I've requested for study specific for review. 17AUG20: Following up with DBD for the status of the study 07JUL20: No RF activities ongoing at the moment. 25-Jun-2020: Requested DBD if there is any changes with DB Golive and FPFV dates. | Study on Hold | Study on Hold |  |  | Manoharan, Vivek | Sundar, N Sushant | Sushant Sundar | [16 empty] | -NA- | [11 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1200 | 8 | 0 |  | Non-small cell lung cancer | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CINC280A | CINC280A2204 | C4007688 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-04-01 05:30 | 2021-04-01 05:30 | 2021-04-30 05:30 | DB Conduct | Interim DBL | 2022-05-30 05:30 | 2021-05-17 05:30 | 2020-05-06 05:30 | 2020-04-30 05:30 | 2021-02-24 05:30 | Active | 2024-01-23 05:30 |  | 2024-03-05 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II, multicenter, two-cohort study of oral MET inhibitor INC280 in Chinese adult patients with EGFR wild-type (wt), ALK rearrangement negative, MET-mutated, advanced non-small cell lung cancer (NSCLC) who are treatment naive or failed one or two prior lines of systemic therapy | CINC280A2204 phase II MET mutation in Chinese pts | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Yamjala, Karthik | Satoor, Deepti | Soni, Suchitra | Hiriyanna, Srinivas | Larry Qiu | Xuhua Qiu | Mokhamatam, Madhu Purnachandra Rao | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | LSH/JReview Test Set-up Pilot trial |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 23-JUN-2021: RF Version 5.0 finalized for B11L DTS table addition. SNOW#51 raised for LSH updates. 22-JUN-2021: RF Peer Review completed. RF uploaded for approval. SNOW#51 request pending. 19May2021 : LSH set-up pending due to TR1L, TR2L, RS1L, RS2L, TU1L TU2L DTS updates. 11-MAY-2021: RF Version 4.0 finalized for YD logic (based on recent global communication). SNOW#51 raised for SMT/LSH updates. 5-MAY-2021: RF is up to date. LSH status: Setup is Completed for QS1L, QS2L, QS3L, QS4L Awaiting Test Transfer. There are updates to DTS - TR1L, TR2L, RS1L, RS2L, TU1L TU2L - Awaiting DTS update. 20-APR-2021: RF Version 3.0 finalized for 11 DTS table addition (QS1L,QS2L,QS3L,QS4L,RS1L,RS2L,TR1L,TR2L,TU1L,TU2L,YD). SNOW#51 (RITM2482671) raised for SMT and LSH updates. 1-APR-2021: SNOW#05 has been raised for LSH PROD set-up with the final pre-requisite documents. 17-MAR-2021: RF Version 2.0 finalized for VE domain update. 10-MAR-2021: RF Version 1.0 finalized and request raised for LSH test set-up via email (RF, SSD, DQP, UAT ALS). 3-MAR-2020: RF released for Peer Review. 24-FEB-2021: Screen UAT completed. RF activities initiated. 18-FEB-2021: Received first draft ALS for review. 01-FEB-2021 : RF developer assigned. | None | None | 2021-04-01 05:30 |  | Challa, Nandini | Challa, Nandini | Sushant Sundar | Completed | 2021-04-13 | Completed | 2021-04-13 05:30 | Rule file Was updates as ALS Was updated after LSH setup was initiated | Mutiple Updates To ALS , But met the KPI | 2021-04-30 05:30 | 2021-04-30 05:30 |  | 2021-04-30 05:30 |  |  | FAMH Unique Study Specific Issue , Took longer time to resolve than Usual | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 1 | 45 | 79 | 0 | 509 | 988 | 0 | 279 | 46 | 237 | 1271 | 12 | 0 |  | Non-small cell lung cancer | No | Global | Open: Reapproval | Yes | [10 empty] | 2021-04-13 05:30 |  |  |  | Interim-Analysis |  | None of the above | Yes
CINC280A | CINC280A2301 | C1001191 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-08-06 05:30 | 2020-08-14 05:30 | 2020-09-29 05:30 | DB Conduct | DB Snapshot | 2022-06-22 05:30 | 2020-09-25 05:30 | 2020-07-17 05:30 | 2020-04-30 05:30 |  | Active | 2024-10-21 05:30 |  | 2024-12-02 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase III randomised, controlled, open-label, multicentre, global study of capmatinib versus SoC docetaxel chemotherapy in previously treated patients harboring METâex14 mutation, EGFR wild-type, ALK negative, locally advanced or metastatic non-small cell lung cancer (NSCLC) | CINC280A2301 Phase III MET mut 1/2L NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Jagani, Dhara Bhupendra | Ravi, Sapna | Soni, Suchitra | Hiriyanna, Srinivas | Aline Jary | Aline Jary | Mokhamatam, Madhu Purnachandra Rao | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | DB Live date moved by a day from 13th to 14th Aug due to some updates in DB by Standards Initial go live as 06Aug2020 when RF developer assigned on 01Jun2020. |  | DRM | Govula, Shashikanth | Shrivastava, Nikhil | Completed | 29-Dec-2021: SNOW-51 request raised (RITM3336194) for LSH and SMT updates as per PPC#04. Rule File is not impacted. Notified the LSP. 15-Apr-2021: Updated version of QS1L, QS2L and QS3L have been reviewed. Those are already included in the RF. No action required. 26-Feb-2021: TU2L, TR2L and RS2L DTS included in the Rule File V4.0 and finalized in CREDI. SNOW-51 is raised and LSP is notified. 23-Feb-2021: As per Missing form and DTS report, TU2L, TR2L and RS2L DTS finalized in CREDI but RF programmer was not informed. 02-Feb-2021 (SHRIVNI5): The CRF forms (B1S001_TR_1, B1S001_TR_2 and B1S001_TR_3) have been added in the Rule File V3.0 and finalized in CREDI. SNOW-51 is raised and LSP is notified. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 QS2L, LBL, TU1L, RS1L, TR1L, QS1L, QS3L, B11L, B12L DTSs listed. Please check 6JAN2021: B1 pages with updated annotations, Rulefile to be updated to add the B1 pages. Reviewed the B1 annotations, no transformations required at Rulefile end, B1 pages to be union'ed directly with existing B1 DTS's. 9Dec2020: RF with DTS updates released for review. SDTM programmer to share the updated annotations by today EOB. WIll include B1 pages once I receive the annotations. 5Nov2020: Queries could not be answered by SDTM team. They need TAPOD and Clinical inputs. TDM is working with on getting the info for the same. PPC has been implemented to make some updates which impact Rulefile. DTS's will be included along with PPC changes. Plan to release RF updates for review on 10Nov. 05Oct2020 : follow up with Lead and SDTM programmer 25Sep2020: Study SDTM programmer getting inputs from Senior SP regarding issues raised for the B1 pages. For pednung DTS as per report 22Sep2020 ..DB lead has not informed of the DTS finalization. Dropped an email to DB lead requesting to share the DTS. 8Sep2020: Planned to have a meeting with SDTM programmer and DB lead to discuss this issue. 02Sep2020 : As per 02Sep2020 missing forms DTS report "B1S001_TR_3, B1S001_TR_1, B1S001_TR_2" forms pending. Forms were not incldued in inital release due to not having clarity on SDTM annotations and DB. Need to followup with DBD 19Aug2020 : RF final and raised Snow ticket 12AUG2020: Rule file under development. Some updates made to DB. Updated ALS shared on 11AUG2020. 22Jun2020 : Asked Sujan to support in Shashi's Absence | None | None | 2020-08-19 05:30 |  | Challa, Nandini | Challa, Nandini | Sushant Sundar | Completed | 2020-08-28 | Completed | 2020-09-21 05:30 | Blinding Level is not yet confirmed , SMT is in progress.FPFV on 22nd sep 2020 |  | 2020-09-23 05:30 | 2020-09-24 05:30 | Due to delay in the Blinding requirements in the DQP. PPC after the finalisation of the DQP. | 2020-09-24 05:30 |  |  | First DDPASS was closed due to less data and as per the communication with all team members |  | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 77 | 93 | 0 | 579 | 1167 | 0 | 336 | 49 | 245 | 1461 | 9 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [10 empty] | 2020-09-21 05:30 |  |  |  |  | Sultana, Salma | None of the above | Yes
CINC280A | CINC280A2X02B | C1001198 | Phase II | NCDS | OC RDC - Inhouse | 2017-06-20 05:30 | 2017-06-20 05:30 |  | DB Conduct | Final DBL | 2027-09-09 05:30 | 2017-07-04 05:30 |  | 2016-12-21 05:30 |  | Active | 2027-07-30 05:30 |  | 2027-09-09 05:30 |  | FALSE | Rollover | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | An open-label, multi-center, long-term safety roll-over study in patients who have completed a prior Novartis-sponsored capmatinib (INC280) study and are judged by the investigator to benefit from continued treatment with capmatinib | CINC280A2X02B INC280 Rollover study | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Rasegaonkar, Sneha Nitin | Ravi, Sapna | Soni, Suchitra | Hiriyanna, Srinivas | Brinda Sharma | Brinda Sharma | Gehlawat, Priya | Ambati, Purnachander | [13 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | ICON | 2017-06-20 05:30 | 2017-06-20 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 22 | 0 |  |  | 0 |  |  |  | 161 | 0 | 0 |  | Non-small cell lung cancer; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CINC280A | CINC280AJP01 | C4006454 | Phase IV | Other | CRO - EDC |  |  | 2020-11-30 05:30 | DB Conduct | Final DBL | 2025-07-31 05:30 | 2020-11-02 05:30 | 2020-09-18 05:30 | 2020-09-09 05:30 |  | Active | 2023-09-30 05:30 |  | 2025-07-31 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Special drug use-results surveillance of Tabrecta Tablets (MET exon 14 skipping mutation-positive unresectable advanced/recurrent non-small cell lung cancer) | CINC280AJP01 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | TSUKIMOTO, IZUMI | YAMADA, KAYO | YAMADA, KAYO | Hiriyanna, Srinivas | HARUKA NISHIOKA | HARUKA NISHIOKA | [17 empty] | Sushant Sundar | [28 empty] | Other | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CINC280B | CINC280B2201 | C1001204 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-09-23 05:30 |  | 2015-04-27 05:30 |  | Completed | 2019-08-09 05:30 | 2018-12-05 05:30 | 2019-04-08 05:30 | 2019-02-05 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase Ib/II, open-label, multicenter trial with oral cMET inhibitor INC280 alone and in combination with erlotinib versus platinum/pemetrexed in adult patients with EGFR mutated, cMET-amplified, locally advanced/metastatic nonsmall cell lung cancer (NSCLC) with acquired resistance to prior EGFR tyrosine kinase inhibitor (EGFR TKI | CINC280B2201 INC280/erlotinib EGFR mut NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Boyapati, Karthik | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Nathalie Smith | Nathalie Smith | Govula, Shashikanth | [14 empty] | Gandikota, Sree Lakshmi |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2015-07-17 05:30 | 2015-07-17 05:30 |  |  | NA | [7 empty] | 127 | 0 |  |  | 0 |  |  |  | 652 | 4 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | No
CINC280D | CINC280D2201 | C3002904 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-09 05:30 | 2018-11-19 05:30 | DB Locked | Final DBL Achieved |  | 2018-12-26 05:30 | 2018-07-27 05:30 | 2018-07-24 05:30 |  | Completed | 2021-01-25 05:30 | 2020-09-07 05:30 | 2020-10-07 05:30 | 2020-10-19 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II, multicenter, randomized, two-arm study of the combination of capmatinib (INC280, an oral MET inhibitor) and spartalizumab (PDR001, a PD-1 inhibitor) versus docetaxel in pretreated adult patients with EGFR wild-type, ALK rearrangement negative locally advanced/metastatic non-small cell lung cancer | CINC280D2201 NSCLC study PDR001+INC280 vs Docetal | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Jayavaram, Pavan | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Carrie Ben Said | Carrie Ben Said | Pilli, Bhaskar | Munukutla, Valli |  |  |  |  | DRM (DIAL) | Pilli, Bhaskar | Shrivastava, Nikhil | Completed | 07-Oct-2020 (SHRIVNI5): RF V10.0 finalized WRT PPC#08. Sent for LSH build. 27-Apr-2020 (SHRIVNI5): B13L DTS included in RF and V9.0 finalized. Sent for LSH build. 01Apr2020 : Reassigned RF from Bhaskar to Nikhil 14Jan2020 (SHRIVNI5): The pending forms EGG001_1 and DSG005 included in the rule file version 7.0 and rule is finalized. SNOW-51 ticket also raised. Only metadata is published into jreview and GPS for programming because LSH unable to process 185 forms. | None | None | 2018-11-12 05:30 |  | Sahu, Ahallad | Chitransh, Arpit | Sushant Sundar | Completed | 2018-12-26 | Completed | 2019-07-16 05:30 | Rule file version 6 is done |  | 2018-11-26 05:30 | 2018-12-24 05:30 |  | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 12 | 46 | 187 | 0 | 590 | 1111 | 0 | 372 | 45 | 573 | 1729 | 9 | 0 |  | Non-small cell lung cancer | Yes | Global | Completed | Yes | [10 empty] | 2019-07-11 05:30 | [5 empty] | None of the above
CINC280I1 | CINC280I12201 | C4005905 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-12-16 05:30 | 2020-02-10 05:30 | DB Conduct | Final DBL | 2023-04-26 05:30 | 2020-01-22 05:30 | 2019-10-07 05:30 | 2019-09-13 05:30 |  | Active | 2023-02-16 05:30 |  | 2023-04-26 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | INC280 plus Pembrolizumab in NSCLC with PD-L1 &gt;=50% | CINC280I12201 Capmatinib+Pembrolizumab in NSCLC | N7 Oncology - NIBR | Langlo, Francois | Sayyed, Ashique | Kocharekar, Poonam Vilas | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Xuan Zhao | Xuan Zhao | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Ramakanth Tadiparthy has transitioned the study to Navina Kadam on 6-JAN-2022 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 11-Nov-2021: RF v5.0 finalized for B13L dts addition and SNOW#51 has been raised. 21-Apr-2021: Rule File V4.0 has been updated and finalized WRT PPC#04. SNOW-51 has been raised and both LSP & SMT programmer have been notified. 09Feb2021: New EG pages EGG001_1, EGG001_4_1, EGG001_7_1, EGG001_6_1 were already added in RF v3.0, existing old pages are not inactivated yet. 6JAN2021: SG: No upcoming tasks for this study. 23Jun2020 : In Shashi's Absence Ashok supported for DD: Added DDG002 & EC: Added ECG003, ECG003_1, ECG003_2, ECG006_1, ECG006_2 in RF V2.0 EG pages EGG001_1, EGG001_4_1, EGG001_7_1, EGG001_6_1 in this rule file v3.0 22Jun2020 : PPC ongoing to fix EG page design issue. Once PPC is completed RF to be updated. Ashok/ Kranthi (Peer review) in shashi's absence. 03Apr2020: PPC not implemented Yet 19-Mar-2020: PPC not yet initiated. As per email from TDM dated 04Mar2020. these changes will be included along with Protocol Amendment. 02Mar2020 : PPC pending for pending forms. 21-Jan-2020: Rule file finalized, sent for LSH setup. 10-Jan-2020: EG-Design issue. 27-Dec-2019: Released for Peer review on 18-Dec-2019. 17-Dec-2019: Planned for Peer review release by 18-Dec EOB. 9-Dec-2019: Started. | None | B14L- 06Dec-2021: No confirmation on the B14L DTS finalization received from TDM/DBD neither is it available in 'Subway'. 15Dec2021: B14L DTS is not yet finalised. | 2020-01-21 05:30 | DB Set-up Issues | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-01-22 | Completed | 2020-01-29 05:30 |  | Pre-requisites not met | 2020-01-29 05:30 | 2020-01-29 05:30 | Pre-requisites not met | 2020-05-01 05:30 |  |  | DDPASS has been completed for 11 domains and clean patients as mentioned in the safety DMC. Other domains and subjects will be reviewed shortly as there is another DMC awaiting and PPC also. | 84 | RaveX - Inhouse | Yes | ZK;#Y1;#Y5;#YD | [11 empty] | NA | [5 empty] | 6 | 44 | 96 | 0 | 531 | 1012 | 0 | 271 | 41 | 285 | 1338 | 3 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [10 empty] | 2020-01-29 05:30 |  |  |  |  | R, Harini | None of the above | Yes
CINC280J1 | CINC280J12201 | C4006311 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-04-15 05:30 | 2020-07-03 05:30 | 2020-09-07 05:30 | DB Conduct | Final DBL | 2023-02-17 05:30 | 2020-08-19 05:30 | 2020-02-13 05:30 | 2020-02-13 05:30 |  | Active | 2022-12-16 05:30 |  | 2023-02-17 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A double-blind, placebo controlled, randomized, phase II study evaluating the efficacy and safety of capmatinib (INC280) and spartalizumab (PDR001) combination therapy versus capmatinib and placebo as first line treatment for locally advanced or metastatic non-small cell lung cancer patients with MET exon 14 skipping mutations | CINC280J12201 Phase II INC280 in combo w/ PDR001 | N7 Oncology - NIBR | Langlo, Francois | Kubade, Shrikant | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Elisa Leo; Maria Cintrao Dos Santos Rosa | Elisa Leo | R, Ankit | Gehlawat, Priya | Not Started |  | Jan-2022 - Study to be transitioned to Priya from Prasanna Oct-2021 - Priya managing backup for Prasanna. 28Nov2019 : initial golive planned as 15Apr2020 when DBD assigned. |  | DRM | Shrivastava, Nikhil | Saha, Saikat | Completed | 15Nov2021 : RF and Checklist have been finalized in the SubWay. SNOW 51 ticket has been raised and notified the LSP. 12Nov2021 : TDM confirmed we can go ahead with RF finalization without the missing field as it will make no impact. 29Sep2021 : Field is missing in the ALS as per the SRF. Provided the comments to the DBD to make the updates. RF is pending. 28Sep2021 : Received the ALS, SOD and SRF from the backup DBD. 18Sep2021 : Provided the review comments and asked for the updated ALS and SOD to proceed with the RF development. 17Sep2021 : Received PPC notification from the DBD. 13-Aug-2021 (Nikhil): Transition activities completed. Informed the Study Team. 12-Aug-2021: For 4 Biomarker forms (B1S001_TR, B1S001_TR_1, B1S001_TR_2 and B1S001_TR_3), SDTM programmer has updated the annotation. But for one form (B1S001_TR) discussion between DBD, TDM and SDTM programmer currently ongoing. Post discussion and alignment, either database or SDTM annotation will be updated. Rule File should be updated post discussion and final alignment among the team. 11Aug2021 : Reassigned the study from Nikhil to Saikat. 25-Jun-2021: RF V6.0 finalized WRT PPC#02 for including the new fields in B1 and ZJ forms. SNOW-51 raised and LSP has been notified. 22-Jun-2021: PPC#02 was implemented but RF programmer was not informed by DBD. Following up with DBD and SDTM programmer to get the input documents. 21-May-2021: B14L DTS is included in Rule File V5.0 and finalized in Subway. Raised SNOW-51 ticket and notified LSP. 15-Apr-2021: B14L has been drafted and getting reviewed. Need to include in the Rule File. 10-Feb-2021: RF V4.0 finalized in Subway WRT 3 QS DTS (QS1L, QS2L and QS3L) and some updates for MH and FAMH domain as per SDTM programmer's request. SNOW-51 is raised and LSP is notified. 01-Feb-2021: TU, TR and RS DTS included in RF V3.0 and finalized in Subway. SNOW-51 is raised and LSP is notified. 6JAN2021: TU,TR and RS DTS's to be reviewed and added to Rulefile. 24Sep2020 : OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, B11L included in RF and final. 8Sep2020: OPG pages are LOINC pages. Will be mapped to ODM. Received a request to update FAMH as per updated annotations. Rule file will be updated to include the all these updates. Awaiting Ankit's confirmation before proceeding. 02Sep2020 : In report OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, pages are flagged need to check with DBD and incldue in RF 11AUG2020: OPG pages are operational pages. 27Jul2020: As per 20th JUl report OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, page are missing and no comments. 03Jul2020: RF final and raised Snow ticket. Krnathi supported the RF development and Sujan Peer review in Shashi's Absence 22Jun2020 : Asked Kranthi to support in Shashi's absence 18May2020: Received draft ALS, PDR on 12 May. Provided initial review comments on 14May. | PPC#6 ongoing, will update the RF after receiving the updated ALS. | None | 2020-07-03 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-07-06 | Completed | 2020-07-10 05:30 | ​LSH Setup request was raised on 3rd July, 2020. LSH setup initiated and SMT request raised on 6th July, 2020. Awaiting clinical views refresh to initiate PREDRM setup. ​PREDRM setup was completed on 6th July, 2020. ​Received SMT files on 9th July, 2020. Completed the LSH setup by 10th July, 2020. |  | 2020-07-10 05:30 | 2020-07-10 05:30 |  | 2020-08-25 05:30 |  |  | SDTM programmer has shared reviews on 5th Nov, 2020. It'll be worked upon. DM yet to share the reviews, the delay is attributed to the ongoing PPC. Hence DDPASS will be initiated post PPC implementation. [RAMACHA1, 5th Feb, 2021] 16 domains have been reviewed. 4 domains passed. 5 domains require PPC updates. 7 require resolution from TDM and SDTM team. Rest of the domains will be reviewed in the upcoming weeks. [RAMACHA1, 5th Feb, 2021] 8 domains passed review. 5 domains issue will be fixed after PPC. [RAMACHA1, 24th Feb, 2021] The team has requested to postpone the DDPASS by one week as steering committee meeting is on priority. It is agreed with the team to complete the primary review of all domains and close the issues by 31st March, 2021 [RAMACHA1, 14th Apr, 2021] 13 domains passed, 11 failed requiring PPC to fix issues, 3 domains do not have sufficient data. DDPASS document version 1.0 will be archived. DDPASS Success Rate = 59% | 59 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 6 | 65 | 101 | 0 | 786 | 1042 | 0 | 322 | 49 | 255 | 1346 | 4 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [10 empty] | 2020-07-10 05:30 | [5 empty] | None of the above | Yes
CINC280K1 | CINC280K12201 | C4007816 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-02-11 05:30 |  |  | DB On hold | [6 empty] | Stopped (with patients) |  |  |  |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase II, Open-Label, Multicenter Study in Adolescents and Adults Patients with advanced/metastatic solid tumors harboring MET Dysregulation, to investigate the clinical efficacy and safety of capmatinib | CINC280K12201 INC280 solid tumors (exc NSCLC) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Jayavaram, Pavan | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Carrie Ben Said | Carrie Ben Said | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini | Not Started |  |  |  | DRM | Shafiudeen, Rehana Banu | Shafiudeen, Rehana Banu | Not Started | 4Feb2021 : Requested for details on study go live and other documents and awaiting for reply. 4Jan2021 : As per the discussion with the DBD, the protocol is not yet finalized and the go-live date is not confirmed. 24Sep2020 : Study Golive postponed to 20Mar2021 14sep2020 : followup with DBD on study status and SS forms | [6 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Bile duct cancer; Colorectal cancer; Endometrial cancer; Gastric cancer; Gastroesophageal cancer; Glioblastoma multiforme; Glioma; Hepatocellular carcinoma metastatic; Neoadjuvant Melanoma; Non-small cell lung cancer; Renal cancer; Renal cell carcinoma | No | Global | Terminated | Yes | [16 empty] | None of the above
CINC280L1 | CINC280L12301 | C4009022 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-12-30 05:30 | 2021-06-24 05:30 | 2021-09-20 05:30 | DB Conduct | DB Snapshot | 2022-04-21 05:30 | 2021-09-22 05:30 | 2021-02-22 05:30 | 2021-03-02 05:30 | 2021-05-12 05:30 | Active | 2027-03-30 05:30 |  | 2027-05-10 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase III randomized, controlled, open-label, multicenter, global study of capmatinib in combination with osimertinib versus platinum - pemetrexed based doublet chemotherapy in patients with locally advanced or metastatic NSCLC harboring EGFR activating mutations who have progressed on prior EGFR-TKI therapy and whose tumors are T790M mutation negative and harbor MET amplification (GEOMETRY-E) | CINC280L12301 Ph3 study in post-EGFR TKI setting | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Dhamat, Rahul | Satoor, Deepti | Soni, Suchitra | Hiriyanna, Srinivas | Nathalie Smith | Nathalie Smith | Sinha, Deepakshi | Rachakonda, Hima Sailaja | Not Started |  | 04May2021 : Transitioned from Deepakshi to Hima as backup Lead. Deepakshi planned vacation 7 to 17th may. Hima to support until golive. Meda, Sreelakshmi & Katam, Veera Nagendra from ICON supporting programming. Pratik on adhoc basis. DB golive moved to 31May2021. TDM to update the activity planner. FPFV is 16Jul2021. Have asked her to check the rationale to have more than 4 weeks gap between FPFV and Golive. Edits approx .. 800 (including 269 CFs) - ICON programmers will support on Edit checks (Programmers assigned) - 292 global checks will release for peer review tomorrow. - 200 study specific checks will be developed by ICON Programmers. - CF request placed (269 CFs) DJ to assign the resource - Screens issues to be fixed (Dependency on CF Programmer) Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 30Dec2020 |  | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 30-Sep-2021: Rule file v2.0 is finalized in SUBWAY for the DTS (YRL, YDL, EG1L) addition. 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 25Jun2021 : Rule file is finalized in SUBWAY and the LSP is notified. 24Jun2021 : The study is Live. 28May2021 : Rule file peer review is completed. 21May2021 : The Rule file is completed and sent for peer review. 6May2021 : I have requested the DBD for the UAT completion date and the UAT ALS for review. 8Apr2021 : received ALS for review. 5Feb2021 : The go live is planned on the month of may and the date is not yet confirmed. 29-Jan-2021 : Requested the DBD for details on the study and the DBD mentioned that the study go live date is not confirmed yet. 03-Dec-2020 : Requested the DBD to update the FPFV date as per the DM BOW. | None | None | 2021-06-25 05:30 |  | Manoharan, Vivek |  | Sushant Sundar | Completed | 2021-08-12 | Completed | 2021-08-12 05:30 |  |  | 2021-08-12 05:30 | 2021-08-12 05:30 |  | 2021-08-27 05:30 |  |  |  | 0 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 1 | 47 | 94 | 0 | 587 | 1371 | 0 | 346 | 43 | 252 | 1666 | 5 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [10 empty] | 2021-08-11 05:30 | [5 empty] | None of the above | Yes
CINC280A0 | CINC280X2102 | C1001202 | Phase I | NOVDD | [7 empty] | 2012-02-29 05:30 |  | 2011-03-14 05:30 |  | Completed |  | 2017-07-04 05:30 |  | 2017-07-18 05:30 | FALSE |  |  |  | Outsourced |  | A Phase I open-label dose escalation study with expansion to assess the safety and tolerability of INC280 in patients with c-MET dependent advanced solid tumors | CINC280X2102 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Carrie Ben Said | Carrie Ben Said | [66 empty] | Metastatic neoplasm | Yes | Global | Completed | Yes | [16 empty] | None of the above
CINC280A0 | CINC280X2104 | C1202206 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-07-28 05:30 |  | 2014-03-20 05:30 |  | Completed | 2017-01-20 05:30 | 2017-01-20 05:30 |  | 2017-08-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase Ib, open-label, multicenter, dose escalation and expansion study, to evaluate the safety, pharmacokinetics and activity of INC280 in combination with cetuximab in c- MET+ positive CRC and HNSCC patients who have progressed after anti-EGFR monoclonal antibody therapyÂ¿ | CINC280X2104 | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Burjawale, Taj | YAMADA, KAYO | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Sergio Vicente Gabarda | [15 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Colorectal cancer; Squamous cell carcinoma of head and neck | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280C | CINC280X2105C | C1001207 | Phase I | NCDS | OC RDC - Inhouse |  | 2014-09-25 05:30 |  | DB Conduct | Final DBL | 2025-09-01 05:30 | 2015-01-13 05:30 |  | 2014-07-17 05:30 |  | Active | 2025-07-21 05:30 |  | 2025-09-01 05:30 |  | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase Ib/II, multicenter, open-label study of EGF816 in combination with INC280 in adult patients with EGFR mutated non-small cell lung cancer | CINC280X2105C INC280 and EGF816 in EGFR mut NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kundaram, Prasad | Jayavaram, Pavan | Soni, Suchitra | Hiriyanna, Srinivas | Aline Jary | Aline Jary | Meda, Sreelakshmi | Iliyas, Mohamed | [13 empty] | Challa, Nandini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2014-09-25 05:30 | Meda, Sreelakshmi | Shewane, Roshni | NA | [7 empty] | 205 | 0 |  |  | 0 |  |  |  | 669 | 8 | 0 |  | Non-small cell lung cancer | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CINC280H1 | CINC280X2108 | C1200387 | Phase I+II | NCDS | OC RDC - Inhouse |  | 2016-05-15 05:30 |  | DB Locked |  |  | 2016-06-15 05:30 |  | 2016-02-02 05:30 |  | Active | 2021-07-01 05:30 | 2021-06-24 05:30 | 2021-08-12 05:30 | 2021-08-06 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase Ib/II, open-label, multi-center study of INC280 in combination with PDR001 or PDR001 single agent in advanced hepatocellular carcinoma | CINC280X2108 Phase Ib/II in HCC | N7 Oncology - NIBR | Langlo, Francois | Vivier, Gregoire | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Brigitte Kuenzle | Brigitte K��nzle | Rana, Aamir | Gehlawat, Priya | Completed | [12 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [12 empty] | DDPASS session will be conducting soon | 0 | OCRDC - Inhouse | Yes | -NA- | 2021-08-19 05:30 | 2021-08-24 05:30 | Initial LSH Lock request #RITM2851770 raised on 6th Aug2021 (a partial LSH Lock) was cancelled due to an ad-hoc Randomization data ( Yx domains ) transfers request. Later a new LSH Full Lock request #RITM2893045 is raised on 19th Aug2021 |  | ONC | Novartis | InHouse | 2016-05-09 05:30 | 2016-05-09 05:30 | Kanchi, Pavan kumar | Gehlawat, Priya | IQVIA | [7 empty] | 153 | 0 |  |  | 0 |  |  |  | 778 | 9 | 0 |  | Hepatocellular carcinoma | No | Global | Open | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | Yes
CINC280E1 | CINC280X2201 | C1200251 | Phase II | NCDS | OC RDC - Inhouse | 2013-03-07 05:30 | 2013-03-07 05:30 |  | DB Conduct | Final DBL | 2024-04-22 05:30 | 2013-03-25 05:30 |  | 2012-10-26 05:30 |  | Active | 2022-12-26 05:30 |  | 2024-04-22 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase II, open label, single arm, multicenter study of INC280 administered orally in adult patients with advanced hepatocellular carcinoma | CINC280X2201 Phase II in HCC | N7 Oncology - NIBR | Langlo, Francois | Takano, Mamiko | Kansagara, Sachinkumar | Tanada, Miyako | Gupta Bhaya, Soumya Kanti | Tingting He | Tingting He | Ahuja, Mohit | Shewane, Roshni | In Progress |  | Study Transition is ongoing to DBD Roshni Shewane. | [10 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | Planned for Q3 | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse |  | 2013-03-08 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 118 | 0 |  |  | 0 |  |  |  | 518 | 6 | 0 |  | Hepatocellular carcinoma | No | Global | Open | Yes | [16 empty] | None of the above
CINC280B | CINC280X2202 | C1001205 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2012-04-05 05:30 |  | 2011-12-08 05:30 |  | Completed | 2020-05-27 05:30 | 2020-05-27 05:30 | 2020-06-29 05:30 | 2020-06-25 05:30 | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase IB/II, open label, multicenter study of INC280 administered orally in combination with gefitinib in adult patients with EGFR mutated, c-MET-amplified non-small cell lung cancer who have progressed after EGFR inhibitor treatment | CINC280X2202 INC280/gefinitib EGFR mut NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Nagargoje, Sudam | Majumder, Sabarni | Soni, Suchitra | Hiriyanna, Srinivas | Carrie Ben Said | Carrie Ben Said | Oguri, Praveen | Oguri, Praveen | [13 empty] | Kommu, Ranjith Kumar |  | Sushant Sundar | [12 empty] | Planned for Q3 | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse |  | 2012-03-16 05:30 | Gehlawat, Priya | Kanchi, Pavan kumar | NA | [7 empty] | 113 | 0 |  |  | 0 |  |  |  | 300 | 5 | 0 |  | Non-small cell lung cancer | Yes | Global | Completed | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | No
CINC280G1 | CINC280X2204 | C1202207 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-01-09 05:30 |  | 2013-07-08 05:30 |  | Completed |  | 2016-12-23 05:30 |  | 2017-03-02 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase Ib/II, open-label, multicenter study of INC280 in combination with buparlisib in adult patients with recurrent glioblastoma | CINC280X2204 | N7 Oncology - NIBR | Molander, Lei Ann | Burjawale, Taj | YAMADA, KAYO | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Sergio Vicente Gabarda | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [12 empty] | NA | [19 empty] | Glioblastoma multiforme | No | Global | Completed | Yes | [16 empty] | None of the above
CINC280F1 | CINC280X2205 | C1200608 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-01-20 05:30 |  | 2013-08-23 05:30 |  | Completed |  | 2019-10-15 05:30 | 2020-01-07 05:30 | 2019-11-27 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase II, open label, multiple arm study of single agent AUY922, BYL719, INC280, LDK378 and MEK162 in Chinese patients with advanced non-small cell lung cancer (NSCLC) | CINC280X2205 Phase II in NSCLC | N7 Oncology - NIBR | Molander, Lei Ann | Takano, Mamiko | N, Ram Kumar | Tanada, Miyako | Gupta Bhaya, Soumya Kanti | Hao Lu | Jue Wang | Tadiparthy, Ramakanth | Tadiparthy, Ramakanth | [13 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse |  | 2014-11-17 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 167 | 0 |  |  | 0 |  |  |  | 647 | 1 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CINC424A | CINC424A1401 | C1001625 | Phase IV | Other | CRO - EDC |  |  | 2019-06-24 05:30 | DB Conduct | Final DBL | 2024-04-30 05:30 | 2014-09-02 05:30 | 2020-02-13 05:30 | 2014-06-24 05:30 |  | Active | 2023-12-20 05:30 |  | 2024-04-30 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Special Drug use investigation (observational study) Myelofibrosis | CINC424A1401 JPN PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | MARUYAMA, KYOKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | YUKIE YOSHIZAWA | YUKIE YOSHIZAWA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Myelofibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CINC424A | CINC424A2104 | C1001210 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-12-18 05:30 |  | 2012-09-18 05:30 |  | Completed |  | 2017-09-28 05:30 | 2017-12-12 05:30 | 2017-11-15 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Hematology | A phase Ib, open-label, multi-center, two-arm, dose-finding study to assess the safety and efficacy of the oral combination of Ruxolitinib (INC424) and BKM120 in patients with primary myelofibrosis (PMF), postpolycythemia vera-myelofibrosis (PPV-MF), or postessential thrombocythemia-myelofibrosis (PET-MF) | CINC424A2104 (HARMONY) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Panda, Bidyuta Prabhat | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Savita Bharathy | Savita Bharathy |  | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Oncology | AP21 | Quintiles | Sandra.Lepart@quintiles.com | Earlier DBD: Shelly Antle /Jugnu; final DBL upcoming | [14 empty] | Myelofibrosis | No | Global | Completed | Yes | [16 empty] | None of the above
CINC424A | CINC424A2106 | C1001211 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-04-04 05:30 |  | 2017-02-08 05:30 |  | Completed |  | 2017-08-28 05:30 |  | 2017-10-18 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | An open-label, two-period, fixed-sequence, cross-over study to evaluate the effects of multiple doses of fluconazole, a dual CYP3A4 and CYP2C9 inhibitor, on the pharmacokinetics of ruxolitinib after a single oral dose in healthy subjects | CINC424A2106 PI Fluconazole DDI | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Magar, Abhijit | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Savita Bharathy | Savita Bharathy | Marx, Karl | [14 empty] | Mettugari, Sai Krishna |  | Amit Agavekar | [21 empty] | ONC | Novartis | InHouse | 2017-04-01 05:30 |  |  |  | NA | [19 empty] | Drug interaction NOS | No | Global | Completed | Yes | [16 empty] | None of the above
CINC424A | CINC424A2201 | C1001212 | Phase I | Other | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2011-03-03 05:30 |  | 2010-12-09 05:30 |  | Completed | 2019-12-31 05:30 | 2019-12-31 05:30 | 2020-02-11 05:30 | 2020-02-11 05:30 | FALSE | Submission | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A Phase Ib, open-label, dose-finding study of the JAK inhibitor INC424 tablets administered orally to patients with Primary Myelofibrosis (PMF), Post-Polycythemia Vera- Myelofibrosis (PPV-MF) or Post-Essential Thrombocythemia-Myelofibrosis (PET-MF) and baseline platelet counts ¿ 50 x109/L and <100 x109/L. | CINC424A2201 (EXPAND) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shenoy, Shweta Harimohan | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Bruyere Mahuzier | Bruyere Mahuzier | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Myelofibrosis | Yes | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CINC424A | CINC424A2202 | C1001213 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-10-14 05:30 |  | 2011-05-03 05:30 |  | Completed |  | 2017-10-31 05:30 | 2017-12-18 05:30 | 2017-12-18 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Hematology | A multi-national open-label phase II study of the JAK inhibitor INC424 in patients with primary myelofibrosis, post-polycythemia vera myelofibrosis or post-essential thrombocythemia myelofibrosis | CINC424A2202 (Pan Asia) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | YAMADA, KAYO | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | MASAYUKI ITO | MASAYUKI ITO |  | Rajan, Saranya | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Oncology |  | Quintiles | lionel.eck@quintiles.com | Earlier DBD: Jugnu Kumari | [14 empty] | Lymphoma malignant | Yes | Global | Completed | Yes | [16 empty] | None of the above
CINC424E | CINC424A2353 | C1003039 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-02-03 05:30 |  | 2015-10-01 05:30 |  | Completed |  | 2017-10-23 05:30 | 2018-01-23 05:30 | 2018-01-18 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A randomized, double blind, placebo-controlled, multicenter, Phase III study investigating the efficacy and safety of ruxolitinib in Early Myelofibrosis patients with high molecular risk mutations | CINC424A2353 (ReTHINK) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Soma, Shankar Reddy | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Robert Pack | Robert Pack | Malisetty, Sagarika | [14 empty] | Mettugari, Sai Krishna |  | Amit Agavekar | [21 empty] | ONC | Novartis | InHouse | 2016-01-20 05:30 | 2016-01-20 05:30 |  |  | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 419 | 9 | 0 |  | Myelofibrosis | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CINC424A | CINC424A2401 | C1001627 | Phase III | NOVDD | [7 empty] | 2011-01-25 05:30 |  | 2011-03-07 05:30 |  | Completed |  | 2017-01-26 05:30 |  | 2017-07-05 05:30 | FALSE |  |  |  | Outsourced |  | An open-label, multi-center, expanded access study of INC424 in patients with primary myelofibrosis (PMF), post-polycithemia with myelofibrosis (PV-MF) or post-essential thrombocythemia myelofibrosis (PET-MF) | CINC424A2401 MF/L1-M (JUMP) | PA Oncology (Hematology not for MA projects) | [5 empty] | Catherine Bouard; Fien Wai Han Tong | Catherine Bouard | [66 empty] | Myelofibrosis | No | Global | Completed | Yes | [16 empty] | None of the above
CINC424A_MA | CINC424A2411 | C1001626 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-03-31 05:30 |  | 2016-09-16 05:30 |  | Completed | 2019-04-30 05:30 | 2019-02-15 05:30 | 2019-04-26 05:30 | 2019-04-29 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A multicenter phase II, open label, single arm study to evaluate the efficacy and safety of ruxolitinib in the treatment of anemic myelofibrosis patients. | CINC424A2411 REALISE PIV-MF Anemia L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sadhu, Soumen Kumar | Bagayatkar, Rupali Sudesh | Gracey Sugunan, Unni Krishnan | Nair, Sreesha | Geralyn Gilotti | Geralyn Gilotti | Choppadandi, Kranthikumar | [14 empty] | Varate, Rohit |  | Amit Agavekar | [12 empty] | This is a OC study and 1st DDPASS meeting scheduled 14th Feb 2019. | 0 | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2017-02-06 05:30 | 2017-02-06 05:30 |  |  | NA | [7 empty] | 57 | 0 |  |  | 0 |  |  |  | 434 | 2 | 0 |  | Myelofibrosis | No | Global | Completed | Yes | [14 empty] | DBL | Tidke, Shyam | None of the above | Yes
CINC424A | CINC424A2412 | C4000122 | Phase IV | Other |  |  |  | 2020-11-11 05:30 |  |  |  | 2020-10-29 05:30 | 2020-06-04 05:30 | 2019-02-19 05:30 |  | Completed | 2021-05-31 05:30 |  | 2021-07-15 05:30 | 2021-09-06 05:30 | FALSE |  |  |  | Outsourced |  | A multi-center retrospective study in China of ruxolitinib treatment in patients with intermediate or high risk of primary myelofibrosis (PMF), post-polycythemia vera myelofibrosis (PPV-MF) or post-essential thrombocythemia myelofibrosis (PET-MF) | CINC424A2412 PASS Study China | PA Oncology (Hematology not for MA projects) | [5 empty] | Keira Ding | Liju Ding | [66 empty] | Myelofibrosis; Post polycythaemia vera myelofibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CINC424A | CINC424A2X01B | C1001628 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2025-11-10 05:30 | 2015-03-05 05:30 |  | 2014-11-20 05:30 |  | Active | 2025-09-30 05:30 |  | 2025-11-10 05:30 |  | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Hematology | An open label, multi-center, Phase IV rollover protocol for patients who have completed a prior global Novartis or Incyte sponsored ruxolitinib (INC424) study or ruxolitinib and panobinostat (LBH589) combination study, and are judged by the investigator to benefit from continued treatment | CINC424A2X01B PIV-MF/PV/L1,2-M (ROLLOVER) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Chalamalasetty, Kiran | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Jacqueline Ewan | Jacqueline Ewan |  | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | aleksei.volosenkov@ppdi.com | Earlier DBD: Shelly Antle /Jugnu |  |  | 12 | 0 |  |  | 0 |  |  |  | 77 | 1 | 0 |  | Myelofibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CINC424A_MA | CINC424AIC01T | C1001634 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-06-03 05:30 |  | 2012-10-03 05:30 |  | Completed |  | 2018-04-10 05:30 |  | 2018-07-05 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Hematology | A Non-Interventional Long-term Safety Study of Ruxolitinib in Myelofibrosis. JAKAVI PASS | PIV-MF/L-1-M CINC424AIC01T (PASS) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Marchand, Matthieu | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Robert Pack | Robert Pack | [17 empty] | Amit Agavekar | [28 empty] | PPD | [19 empty] | Myelofibrosis | Yes | Global | Completed | Yes | [16 empty] | None of the above
CINC424B | CINC424B1401 | C1001640 | Phase IV | Other | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2024-05-15 05:30 | 2016-01-21 05:30 |  | 2015-02-17 05:30 |  | Active | 2024-01-31 05:30 |  | 2024-05-15 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Drug use investigation of NIC424 in the patients with polycythemia vera | CINC424B1401 JPN PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | MARUYAMA, KYOKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | YUKIE YOSHIZAWA | YUKIE YOSHIZAWA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Polycythaemia vera | No | Global | Open | Yes | [16 empty] | None of the above
CINC424B_MA | CINC424B2001X | C1001641 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-11-21 05:30 |  | 2014-06-03 05:30 |  | Completed |  | 2017-12-29 05:30 | 2018-03-23 05:30 | 2018-03-29 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open-label, multicenter, expanded treatment protocol (ETP) of ruxolitinib for patients with polycythemia vera. | CINC424B2001X PIV-PV/L2-M (ETP) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Kumar HC, Vijay | Bagayatkar, Rupali Sudesh | Gracey Sugunan, Unni Krishnan | Nair, Sreesha | Linda Voice | Linda Voice |  | Gupta, Anshu | [15 empty] | Amit Agavekar | [28 empty] | IQVIA | Oncology | AP21 | Quintiles | Sandra Lepart (Sandra.Lepart@quintiles.com) | Earlier DBD: Chandrima /Asha | [14 empty] | Polycythaemia vera | No | Global | Completed | Yes | [16 empty] | None of the above
CINC424B | CINC424B2301 | C1001216 | Phase III | Other | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2010-02-01 05:30 |  | 2010-09-27 05:30 |  | Completed | 2018-02-09 05:30 | 2018-02-09 05:30 | 2018-04-26 05:30 | 2018-04-16 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | Randomized, open label, multicenter phase III study of efficacy and safety in polycythemia vera subjects who are resistant to or intolerant of hydroxyurea: JAK inhibitor INC424 tablets versus best available care (The RESPONSE Trial) | CINC424B2301 (RESPONSE) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Babu, Vikas | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Christine Rosko | Christine Rosko | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 7 | 0 |  | Polycythaemia vera | Yes | Global | Open | Yes | [16 empty] | None of the above
CINC424B_MA | CINC424B2401 | C1001642 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-03-25 05:30 |  | 2013-10-20 05:30 |  | Completed | 2020-04-08 05:30 | 2020-04-07 05:30 | 2020-07-02 05:30 | 2020-07-02 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Hematology | Randomized, open label, multicenter phase IIIb study evaluating the efficacy and safety of ruxolitinib versus best available therapy in patients with polycythemia vera who are hydroxyurea resistant or intolerant (Response 2) | CINC424B2401 (RESPONSE 2) PIIIb-PV/HU res/L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Kumar HC, Vijay | Bagayatkar, Rupali Sudesh | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Geralyn Gilotti | Geralyn Gilotti |  | Gandla, Prashanth | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | mailto:Vicky.Dils@ppdi.com%20,%20aditi%20shah | novartis.com; Earlier DBD: Chandrima /Asha |  |  | 36 | 0 |  |  | 0 |  |  |  | 495 | 3 | 0 |  | Polycythaemia vera | No | Global | Open | Yes | [16 empty] | None of the above
CINC424B_MA | CINC424B2403 | C4005005 | Phase IV | Other | CRO - EDC |  |  |  | DB Conduct | Final DBL Achieved |  |  | 2019-09-16 05:30 | 2019-09-11 05:30 |  | Active |  |  | 2021-12-31 05:30 | 2021-12-31 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | Impact of time to switch to second line therapy on important outcomes in Polycythemia Vera | CINC424B2403 (High Risk PV - Chart Review) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Bhataiya, Vishal | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Geralyn Gilotti | Geralyn Gilotti | [17 empty] | Sai Krishna Mettugari | [28 empty] | Analysis Group | [19 empty] | Polycythaemia vera | No | Global | Open | Yes | [16 empty] | None of the above
CINC424C | CINC424C1401 | C4009729 | Phase IV | Other | Other |  |  | 2023-03-31 05:30 | Study Planned | DB Go-live | 2022-03-31 05:30 |  | 2022-08-26 05:30 |  |  | Planned | 2027-01-14 05:30 |  | 2027-11-01 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology |  | CINC424C1401 INC424C_Japan PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | TAKAHASHI, CHIEKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | KEIKO FUJINO | KEIKO FUJINO | [17 empty] | Amit Agavekar | [28 empty] | Other | [7 empty] | 15 | 0 | [10 empty] | Acute graft versus host disease; Graft versus host disease | No | Global | Open | Yes | [16 empty] | None of the above
CINC424C | CINC424C2002 | C4009251 | Not Applicable | Other |  |  |  | 2022-09-22 05:30 |  | Final DBL | 2023-09-29 05:30 |  | 2021-07-30 05:30 | 2021-07-07 05:30 |  | Planned | 2023-08-18 05:30 |  | 2023-09-29 05:30 |  | FALSE |  |  |  | Outsourced |  | A multi-center, non-interventional, study with secondary use of data of JAKAVI (Ruxolitinib) in patients with corticosteroid-refractory acute graft versus host disease after allogeneic stem cell transplantation in China | CINC424C2002 China_RWE_Study | PA Oncology (Hematology not for MA projects) | [5 empty] | Robert Ma | Zheyong Ma | [66 empty] | Acute graft versus host disease | No | Global | Open | Yes | [16 empty] | None of the above
CINC424C | CINC424C2301 | C1001218 | Phase III | NCDS | OC RDC - Inhouse | 2016-12-09 05:30 | 2016-12-09 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-03-10 05:30 |  | 2016-09-06 05:30 |  | Completed | 2021-05-31 05:30 | 2021-04-23 05:30 | 2021-05-21 05:30 | 2021-05-28 05:30 | FALSE | Submission | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase III randomized open-label multi-center study of ruxolitinib versus best available therapy in patients with corticosteroid-refractory acute graft vs. host disease after allogeneic stem cell transplantation | CINC424C2301 (REACH 2) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Deshpandey, Vinayak | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Bruyere Mahuzier | Bruyere Mahuzier | Govula, Shashikanth | Gehlawat, Priya | [13 empty] | Agavekar, Amit |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | -NA- | 2021-05-28 05:30 | 2021-06-03 05:30 |  |  | ONC | Novartis | ICON | 2016-12-09 05:30 | 2016-12-09 05:30 | Gehlawat, Priya | Iliyas, Mohamed | NA | [7 empty] | 158 | 0 |  |  | 0 |  |  |  | 589 | 8 | 0 |  | Graft versus host disease | Yes | Global | Open | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CINC424D | CINC424D2301 | C1001219 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-06-09 05:30 |  | DB Conduct | Final DBL | 2023-01-25 05:30 | 2017-06-29 05:30 |  | 2017-03-21 05:30 |  | Active | 2022-12-14 05:30 |  | 2023-01-25 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase III randomized open-label multi-center study of ruxolitinib vs. best available therapy in patients with corticosteroid-refractory chronic graft vs host disease after allogeneic stem cell transplantation (REACH 3) | CINC424D2301 (REACH 3) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Deshpandey, Vinayak | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Maanasa Gowda | Maanasa Gowda | Vedula, Nagendra | Shewane, Roshni | Completed | 2020-02-12 05:30 | Study Transitioned to Roshni Shewane on 12-Feb-2020 | [10 empty] | Polagoni, Bharghavi |  | Amit Agavekar | [12 empty] | Previously DDPASS session was scheduled in month of august 2018 | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-06-09 05:30 | 2017-06-09 05:30 | Shewane, Roshni | Iliyas, Mohamed | NA | [7 empty] | 217 | 0 |  |  | 0 |  |  |  | 844 | 7 | 0 |  | Graft versus host disease | Yes | Global | Open | Yes | [16 empty] | None of the above
CINC424F1 | CINC424F12201 | C4000399 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-21 05:30 | 2019-04-30 05:30 | DB Conduct | Interim DBL | 2022-04-05 05:30 | 2019-02-21 05:30 | 2018-04-06 05:30 | 2018-03-12 05:30 |  | Active | 2023-02-13 05:30 |  | 2023-03-27 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A Phase I/II open-label, single-arm, multi-center study of ruxolitinib added to corticosteroids in pediatric patients with grade II-IV acute graft vs. host disease after allogeneic hematopoietic stem cell transplantation | CINC424F12201 Pediatric Study in aGvHD | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Babu, Vikas | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Christine Rosko | Christine Rosko | Kurella, Rakesh Reddy | Rana, Aamir |  |  | 15-Dec-2021 : Sandeep Bakka will be backup for Aamir till 15-Mar-2022 |  | DRM (DIAL) | Oguri, Praveen | Bai, Chandrakala | Completed | 23Aug2021:PPC#09 has no impact to RF hence only Snow#51 RITM2901935 Created. 31May2021: CB: Verified that 'LBG002_2_TR' was added in RF v9.0 and finalized hence the same is not reflecting in Missing forms report_25May2021. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 15Feb2021: Added in RF Version 9.0 and shared with team for peer review. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 LBG002_2_TR form listed. Please check 05Nov2020: No Activity. 11Sep2020: No Activity. 06Jul2020 : Rule file V8.0 is the latest one. Study will be transitioned from Ashok to Praveen 17Jun2020 : Rule file V8.0 is finalized in CREDI. 01Apr2020 : Reassigned RF from Roshan to Ashok 01Apr2020: LSH setup completed. No pending activities 26MAR2020: LSH setup completed for previous setup for missing form QSS001.But another DTS B11L is finalized to add in RF. RF file updated to include B11L and sent for peer review(Shashi) 10Mar2020 : RF sent for Peer review for QSS001 and B11L. 03MAR2020: Issue with QS domain. QSTSTLG values for 2 fields not present in metadata. Notified DBD to include in Metadata post which RF needs to be updated 09 Jan 20: Received notification about the PPC recently implemented. Need to update LB domain in rule file. | None | None | 2018-08-29 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2018-11-16 | Completed | 2019-06-28 05:30 |  |  | 2018-12-26 05:30 | 2018-12-26 05:30 |  | 2019-08-28 05:30 |  |  |  | 100 | RaveX - Inhouse |  | ZK | [11 empty] | NA | [5 empty] | 10 | 25 | 76 | 0 | 499 | 927 | 0 | 256 | 31 | 251 | 1209 | 4 | 0 |  | Acute graft versus host disease | No | Global | Open | Yes | [10 empty] | 2019-06-27 05:30 | [5 empty] | None of the above
CINC424G1 | CINC424G12201 | C4000680 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-09-13 05:30 | 2019-12-18 05:30 | 2020-05-29 05:30 | DB Conduct | Final DBL | 2024-11-14 05:30 | 2020-05-20 05:30 | 2019-04-12 05:30 | 2019-04-12 05:30 |  | Active | 2024-10-17 05:30 |  | 2024-11-14 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase II open-label multi-center study of ruxolitinib in pediatric patients with corticosteroid-refractory chronic graft vs. host disease after allogenic stem cell transplantation | CINC424G12201 Pediatric Study in cGvHD | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Chalamalasetty, Kiran | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Christine Rosko | Christine Rosko | Yadav, Priyanka | TEMBHARE, HITESH |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 13Sep2019 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 04-AUG-2021: PPC #3 form and difference report reviewed. No impact on RF, SMT / LSH. 08JUL2021: RF Version 6.0 finalized for updated Reference Metadata codes. SNOW#51 raised for SMT and LSH updates. 17-MAY-2021: RF Version 6.0 finalized for Donor 1 & 2 - Background Information updates as per SDTM request. SNOW#51 raised for SMT and LSH updates. 17-FEB-2021: RF V 5.0 finalized for B2L and B3L DTS table addition on 1-FEB-2021. LSH set-up on hold as we have not received test transfers. 01FEB2021: RF V 5.0 finalized for B2L and B3L DTS table addition. SNOW#51 raised for SMT and LSH updates. 17NOV2020: RF 4.0 finalized for FATST code updates. SNOW#51 raised for SMT and LSH updates. 12NOV2020: RF V3.0 finalized in CREDI for FACE updates as per updated SDTM annotations. SNOW#51 raised for SMT/LSH updates. 05OCT2020: RF V2.0 final for DTS table addition - B1L, B4L. SNOW#51 raised for SMT and LSH updates. 23SPE2020: B1L DTS table missing as per tracker. Request TDM confirmation to initiate RF updates. 11FEB2020: Rule file finalized in CREDI. SNOW#5 raised for LSH set-up. 07Feb2020: Released for Peer review 02Feb2020(Kranthi) 30JAN2020: All clarifications for SDTM annotations confirmed. 28JAN2020: SDTM annotations received. Rule file creation is in progress for pending forms. 7-JAN-2020: SDTM inputs not received. 31-DEC-2019: Rule file built for standard forms completed. SDTM and DM inputs requested (23 forms pending input). 17DEC2019: Shared first round of comments to Programmer for DB updates. Waiting for Updated ALS to further process the Rule file. 10DEC2019: Have received the input documents from DBD. But not started development of Rule file. | None | None | 2020-02-11 05:30 |  | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2020-03-16 | Completed | 2020-03-16 05:30 | GPS was down. Due to other issues SMT creation too time hence LSH setup took longer. However domains were made available to JReview/GPS before FPFV. |  | 2020-03-16 05:30 | 2020-03-16 05:30 |  | 2020-06-28 05:30 |  |  | FPFV was delayed due to COVID. No data entered in Rave for few months after Go-Live. DDPASS meeting is scheduled for Oct-2020 | 0 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 5 | 30 | 75 | 0 | 537 | 830 | 0 | 246 | 37 | 212 | 1079 | 1 | 0 |  | Graft versus host disease | No | Global | Open | Yes | [10 empty] | 2020-03-13 05:30 | [5 empty] | None of the above
CINC424H1 | CINC424H12201 | C4001944 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-09-09 05:30 | 2019-09-19 05:30 | DB Conduct | DB Snapshot | 2022-03-28 05:30 | 2019-09-26 05:30 | 2019-04-17 05:30 | 2019-04-30 05:30 |  | Active | 2026-01-23 05:30 |  | 2026-03-06 05:30 |  | FALSE | Not a part of GDD Objective as per HORIZON | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A randomized, open-label, phase I/II open platform study evaluating safety and efficacy of novel ruxolitinib combinations in myelofibrosis patients | CINC424H12201 MFCombo Ph1/2 (ADORE) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Pal, Arvind Kumar | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Bruyere Mahuzier | Bruyere Mahuzier | Vedula, Nagendra | Prasanna Kumar, VTSSR |  |  |  |  | DRM | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 20JAN22: RF V17.0 is final on 21JAN22 and SNOW 51 RITM3405928 request has been created, request you to rebuild LB domain for the addition of new DTS LB1L and LB2L 11OCT2021: RF V15.0 final and SNOW 51 request RITM3068489 has been created. B19L DTS added. 01OCT2021: RF V14.0 final and SNOW 51 request RITM3039954 has been created, request you to add XI and rebuild EC, EG, DV, ODM, M and AE domains Note: Due to milestone MO CRF updates will fixed in next PPC. 04AUG2021: PPC4 has been initiated for to fix MO pages and today change request form has been shared. Review is ongoing. 21JUL2021: B16L DTS added. RF V13.0 and SNOW 51 request RITM2841229 has been created 21Jul2021 : MOS001, MOS001_1, MOS001_2 and MOS001_3froms still reflecting in missing form/DTS report. PPC is ongoing 06Jul2021 : MOS001, MOS001_1, MOS001_2 and MOS001_3froms still reflecting in missing form/DTS report. 23JUN2021: As per Lead DBD confirmation, PPC will be intiated from 23JUN2021 for MOS001, MOS001_1, MOS001_2 and MOS001_3 16APR2021: DTS for NGS Navigate has come for review. Waiting for cleaned draft DTS for review. 16APR2021: Change request form has been reviewed and provided comments. PPC is ongoing 12FEB2021: B12L DTS has been added. RF finalized and SNOW 51 request RITM2263300 has been created. 04Feb2021 : Sent a follow-up email to DBD for PPC status.. 19JAN2021: As per lead confirmation, PPC is not yet planned and didn't received any communication from TDM. Lead DBD will once confirm with TDM and update us. 23DEC2020: MO form design issues will be fixed on PPC3 and PPC3 will be initiated on 4th of January 2021 as per study DM confirmation. 26NOV2020: Rule file V10.0 has been finalized and SNOW 51 Request RITM2030812 as per PPC2 and FACM updated SDTM annotations. 20NOV2020: Following pages are added as part of PPC2 and SNOW 51 RITM2010072 request has been created 1. SV domain: UPVG001_2 form has been added 2. EG domain: EGG001_1, EGG001_2 and EGG001_3 forms have been added 3. ZJ domain: ZJG002_10, ZJG002_11, ZJG002_12, ZJG002_13, ZJG002_14, ZJG006_10, ZJG006_11, ZJG006_12, ZJG006_13, ZJG006_14, ZJO011, ZJO012, ZJO013, ZJO014, ZJO015 and ZJO016 forms have been added 4. CV domain: CVG001 form has been added 5. EC domain: ECG002_8,ECG002_9,ECG003_10,ECG003_11,ECG003_13,ECG003_12,ECG002_7 and ECG002_10 forms have been added 6. DS domain: DSG005 Form has been added 7. ZX domain: ZXS002_8, ZXS002_7, ZXS002_1, ZXS002, ZXS002_6, ZXS002_12, ZXS002_11, ZXS002_5 and ZXS002_4 forms have been added 8. B1 domain: Logic has been updated from Direct to Union 13Nov2020 : MO domain updated as per DDPASS comments and final. Snow 51 raised Note: Newly added pages MOS001, MOS001_1, MOS001_2 and MOS001_3 have design issues and it will be fixed in upcoming PPC. 24SEP20: RF finalized with two new DTS B13L and B17L and SNOW 51 request RITM1830663 has been created. 22SEP20: RF updated with new DTS B13L and B17L. Peer review is ongoing and expected date of completion is 24SEP20 16SEP20: It seems B13L and B17L DTS are final. and come to know through LSP. Requested DBD for to share final DTS in excel format. 07JUL20: As of today, no pending forms and no pending DTS. 10-JUN-2020: No pending forms and pending DTS. RF has been finalized SNOW 51 request has been created. 13-MAY-2020: Received peer review comments, required clarification from SDTM programmer. Added three new DTS QS1L, QS2L and QS3L and sent for peer review. Meanwhile will work on peer review comments. 05-MAY-2020: Rule file has been updated. Change: ZT domain has been removed and remapped ZT forms to CM and PR domains. Peer review is ongoing (Angella). 30Apr2020 : Need to work on RF for ZT 15Apr2020 : RF to be completed for pending ZT domian by 21st and sent for peer review. 08Apr2020 : pending with Sujan 27-MAR-2020: ZT needs to be included in RF pending for awhile. TV was missing and LSP reachout , helped her by following up with TP/TDM. 02-MAR-2020: ZT Custom domain is created. It should be mapped to standard CM domain at Rule file level. If any SDTM annotations required need to contact SDTM programmer (Dara Tejaswini). 12-FEB-20: ZXS001 form has been added and SV domain has been corrected. MHCAT setdatapoint edit check is missing and it has to fix via PPC and same has been informed to study DBP and DM. Renderer has been executed and fixed all the issues. 11-FEB-20: ZXS001 form is incorrectly designed and SDTM annotations is missing. Once we've updates from study team, Rule file will be updated 20-JAN-20: No pending DTS NVE: 29 Nov 19: Peer review completed. Released the Rule File for SMT creation. | MOS001, MOS001_1, MOS001_2 and MOS001_3 | None | 2019-11-26 05:30 | Transition Study and Legacy process | Polagoni, Bharghavi | Agavekar, Amit | Amit Agavekar | Completed | 2019-12-09 | Completed | 2019-12-24 05:30 | Recieved SMT files on 24th DEC | Pre-requisites not met | 2019-12-26 05:30 | 2019-12-26 05:30 | Pre-requisites not met | 2020-05-28 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 6 | 101 | 152 | 0 | 1675 | 1355 | 0 | 283 | 37 | 671 | 2063 | 8 | 0 |  | Myelofibrosis; Post polycythaemia vera myelofibrosis | No | Global | Open | Yes | [10 empty] | 2019-12-24 05:30 | [5 empty] | None of the above
CINC424J1 | CINC424J12301 | C4009066 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-04-15 05:30 | 2020-04-21 05:30 | 2020-04-30 05:30 | DB Locked | Final DBL Achieved |  | 2020-05-02 05:30 | 2020-04-14 05:30 | 2020-04-13 05:30 |  | Completed | 2020-10-19 05:30 | 2020-10-17 05:30 | 2020-12-02 05:30 | 2020-12-03 05:30 | TRUE | no priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | Phase 3 randomised, double-blind, placebo-controlled, multi-center study to assess the efficacy and safety of ruxolitinib in patients with COVID-19 associated cytokine storm (RUXCOVID) | CINC424J12301 | P8 Respiratory | Mahajan, Vinay | Gijo, Ani | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Diane Bonagura | Diane Bonagura | Bora, Deepthi Reddy | Bora, Deepthi Reddy | Not Started |  |  |  | DRM |  | Choppadandi, Kranthikumar | Completed | 17-Aug-2020: RF_Version 4.0 fialized for PPC#03 07-Jul-2020(Kranthi): No pending issues 21Apr2020 : RF final and Snow ticket raised 08Apr2020 : Supporting DBD for SS forms review and inputs Total 6 SRFs in the study Two are Approved 4 are still not Approved | None | None | 2020-04-21 05:30 | RF finalized within Go-live + 5 days | Sundar, N Sushant | Kadam, Sandeep | Sushant Sundar | Completed | 2020-04-25 | Completed | 2020-04-25 05:30 |  |  | 2020-04-25 05:30 | 2020-04-25 05:30 |  | 2020-04-20 05:30 |  |  |  | 60 | RaveX - Inhouse |  | -NA- | 2020-12-03 05:30 | 2020-12-04 05:30 | [9 empty] | NA | [5 empty] | 5 | 30 | 45 | 0 | 272 | 461 | 0 | 166 | 40 | 126 | 627 | 2 | 0 |  | Acute respiratory distress syndrome; Corona virus infection | Yes | Global | Open | Yes | [10 empty] | 2020-04-24 05:30 | [5 empty] | COVID19
CINE963A0 | CINE963A02101 | C4007617 | Phase I | Other | CRO - EDC | 2021-03-15 05:30 |  | 2021-05-13 05:30 | DB Conduct | Final DBL | 2022-08-11 05:30 | 2021-05-13 05:30 | 2021-02-08 05:30 | 2021-02-08 05:30 |  | Active | 2022-06-28 05:30 |  | 2022-08-11 05:30 |  | FALSE | PoC | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CINE963A02101 FIH SAD/MAD for Malaria | R4 NITD - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Morgan Harris; Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CIWY357A0 | CIWY357A02101 | C4012530 | Phase I |  |  |  |  | 2023-03-13 05:30 |  | Final DBL | 2024-01-15 05:30 |  | 2022-11-19 05:30 |  |  | Planned | 2023-12-13 05:30 |  | 2024-01-15 05:30 | [5 empty] | Outsourced |  |  | CIWY357A02101 CSI_FIH SAD/MAD | R4 NITD - NIBR | [6 empty] | Megan Osborn | [66 empty] | Malaria | No | Global | Open | Yes
CJBH492A1 | CJBH492A12101 | C4006156 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-12-12 05:30 | 2020-04-03 05:30 | 2020-09-30 05:30 | DB Conduct | Final DBL | 2023-08-24 05:30 | 2020-09-07 05:30 | 2019-12-24 05:30 | 2019-11-05 05:30 |  | Active | 2023-06-15 05:30 |  | 2023-08-24 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I/Ib open-label, multi-center dose escalation study of JBH492 in patients with relapsed/refractory chronic lymphocytic leukemia (CLL) and Non-Hodgkinâs Lymphoma (NHL) | CJBH492A12101 JBH492 Mono FIH in CLL and NHL | N7 Oncology - NIBR | Langlo, Francois | Parmentier, Delphine | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Ashley Wagner; Jessica O'Keeffe; Jose Carlos Torres Cottes | Ashley Wagner | Gupta, Anshu | TEMBHARE, HITESH |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 12Dec19 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 11Jan2022: RF v9.0 finalized for B16L dts and RITM3368564 Created. 03Jan2022: RF v8.0 finalized for PPC#3 updates and RITM3341829 Created. 19Jul2021: RFv7.0 finalized for CVTEST,FATST_6 DDPASS issues. 07Jul2021: Re-confirmation mail sent to DBD, TDM and LSP for 'B12L' prod transfer. LSp confirmed-test transfer/production transfer is not completed yet. 17June2021: RF v6.0 finalized for 'B12L' dts table addition. 27May2021:Follow-up mail sent to DBD for confirmation on PPC3. ‘VE’ domain 3 fields VEPRESP, VEDECOD, VETERM need to be added in next PPC#3 post which VE will be included in the RF. 10May2021: CVS001 added in RF v5.0 and finalized. VE- Domain is on-hold for this version of Rule fie, as mandatory variables are missing in database. These will added in next PPC3 confirmed by TDM, DBD. 30Apr2021: PPC2 was implemented to include CVS001 and SVG001 updates. However, due to incorrect SV updates the RF is under discussion to be updated or kept on-hold for next PPC3 . 06Apr2021 : CVS001 Flagged in missing form and DTS report. 15Mar2021:Confirmed to be added in upcoming PPC02. 09Feb2021: Discussion ongoing w.r.t CVS001 crf. 25Jan2021: SG : Briefed Chandrakala on the status of this issue and informed the team to work with Chandrakala to resolve the Page setup issue. 7JAN2021: No upcoming task. 9Dec2020: DM discussed with Clinical to confirm if both Results are expected for this page. Awaiting clinical input on this. 5Nov2020: RF finalized and SNOW ticket raised on 29Oct. CMO001, OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, OPG003_5, OPG003_6, OPG003_7, OPG003_8, OPG003_9, OPG003_10. CVS001 : DB has to be upadted to fix log line issue and not included in RF. 05Oct2020 : Praveen worked on this update : CMO001, CVS001, OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, OPG003_5, OPG003_6, OPG003_7, OPG003_8, OPG003_9, OPG003_10 included and sent for Review (Angella). 25Sep2020: Received pending SDTM annotation on 22Sep. Praveen working on Rule file update. 8Sep2020: Rule file finalized and shared with LSP with the DTS (LBL, EG1L, B11L, B13L) update. PPC changes to be handled in the next version. 02Sep2020 : As per 02Sep2020 missing forms DTS report "CMO001, CVS001, OPG003, OPG003_1, OPG003_2, OPG003_3, OPG003_4, OPG003_5, OPG003_6, OPG003_7, OPG003_8, OPG003_9, OPG003_10" forms pending & LBL, EG1L, B11L, B13L DTS pending. PPC implemented and received on 27Aug2020. DBD to be consulted as DTS in RF is complete and received PPC form. whether 1 version can be used for both form and DTS. 11AUG2020: PPC01 implemented, RF being updated. Pending DTS's will be included along with PPC changes. Planned for implementation by 21AUG2020. 27Jul2020 : in 20thJul report CMO001, CVS001 forms & LBL, EG1L, B11L, B13L DTS are flagged in missing forms/DTS report. 06Jul2020: Followup email sent to DBD for missing forms and DTSs. 22Jun2020 : CMO001, CVS001 forms & LBL DTS are flagged in missing forms/DTS report. requested Praveen to look into in Shashi's Absence. Sent an email to DBD on the same. 18May2020: Rule file finalized. Snow ticket raised. 5May2020: CVS001, CMO001 not included in Rule file because of DB setup issue. All other pages released for Peer review. Received Peer review comments on 29Apr2020 for final batch. Planned date for finalization 7May2020. 13Apr2020 : released for Peer review excluding B2,CE,CM,FACE,FACM,FAMH,MH,TR,TU will be included by 16th. CV: CVS001 has build issue and needs to be fixed via PPC. 08Apr2020 : Released for Peer review (Kranthi) 03Apr2020 : Tentatively to be completed by 07Apr and sent for Review. 19-Mar-2020: Final SDTM annotations received on 18-Mar-2020. Rule file development started. 10-Mar-2020: Awaiting SDTM annotations from DBP for study specific pages. requested documents to start Rule file development. 09Mar2020 : Plan to start RF activity from 10th. 10Feb2020 :Requested DBD to provide Study specific forms for review. Approx 88 + study specific forms. | None | None | 2020-05-18 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-05-19 | Completed | 2020-06-04 05:30 | ​19th May 2020 : LSH setup completed till PREDRM stage. Awaiting SMT files for DRM setup. 4th June 2020 : LSH setup completed.​ |  | 2020-06-04 05:30 | 2020-06-04 05:30 |  | 2020-08-24 05:30 |  |  | DDPASS 1 was conducted on 19th Oct, 2020. DDPASS 2 was conducted on 28th Oct, 2020. All the issues are being worked upon by the team. [RAMACHA1, 5th Feb, 2021] 21 domains out of 32 have been reviewed. Only 3 domains have passed DDPASS. Rest of the domains are pending resolution. Team is working to resolve these and continuing to meet weekly to update. [RAMACHA1, 18th Feb, 2021] 5 domains passed DDPASS, 17 failed, 10 pending review. [RAMACHA1, 10 JUN 2021] DDPASS first round was completed with success rate 67% Second round of DDPASS is ongoing post PPC2 [RAMACHA1, 04 AUG 2021] DDPASS second round was completed with success rate of 79%. Third round of DDPASS will be initiated after PPC3 | 79 | RaveX - Inhouse | Yes | -NA- |  |  |  | [RAMACHA1, 20th May 2021] RITM2552217 was raised on 10th May, 2021. PPC2 implementation in LSH was completed on 20th May, 2021. | [7 empty] | IQVIA | [5 empty] | 4 | 77 | 172 | 0 | 2035 | 1240 | 0 | 281 | 45 | 577 | 1862 | 10 | 0 |  | Chronic lymphocytic leukaemia; Non-Hodgkin's lymphoma | No | Global | Open | Yes | [10 empty] | 2020-06-04 05:30 |  |  |  |  | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CJDQ443A1 | CJDQ443A12101 | C4008570 | Phase I+II | NCDS_2 | Rave EDC - Inhouse | 2021-02-01 05:30 | 2021-01-21 05:30 | 2021-02-17 05:30 | DB Conduct | Final DBL | 2024-10-01 05:30 | 2021-02-24 05:30 | 2020-10-01 05:30 | 2020-09-24 05:30 |  | Active | 2024-08-21 05:30 |  | 2024-10-01 05:30 |  | FALSE | Pioneer | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase Ib/II open-label, multi-center dose escalation study of JDQ443 in patients with advanced solid tumors harboring the KRAS G12C mutation | CJDQ443A12101 Trial | N7 Oncology - NIBR | Langlo, Francois | Amrutkar, Ashish | Thorat, Swapnil | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Ashley Jaeger; Helen Oakman; Kimberly Assmann | Ashley Jaeger | Moses, Leah | Thomas, Ankit | Completed | 2021-12-08 05:30 | 8-Dec-2021 - Study transitioned from Leah to Ankit Thomas | Study complexity/delay in finalizing specs. | DRM |  | Choppadandi, Kranthikumar | Completed | 04-Feb-2022: RF_V5.0 has been finalized for PPC03 and SNOW ticket(RITM3096850) on 19-10-2021. 28-Jul-2021: RF(B11L, B12L) finalized and Raised SNOW ticket for LSH update 21Jul2021 : DTSs B11L, B12L reflecting in 21Jul report. 26-Mar-2021: RF updated to include EG1L, B13L and B14L and released for peer review. 17-Feb-2021: RF_V2.0 is finalized and SNOW ticket has been raised to address the issues in MHO001_TR form RF logic 21Jan2021: RF finalize and SNOW ticket(RITM2189871) raised for LSH set-up. 21Jan2021: RF has been peer reviewed and ready to be finalized. Once the study is pushed to Prod, RF will be finalized. 03-Dec-2020: ALS and SRFs are received from Lead DBP. Review in progress from RF development perspective | None | None | 2021-01-21 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2021-02-01 | Completed | 2021-02-09 05:30 |  |  | 2021-02-09 05:30 | 2021-02-09 05:30 |  | 2021-02-15 05:30 |  |  |  | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 4 | 66 | 176 | 0 | 1042 | 1810 | 0 | 347 | 49 | 480 | 2339 | 7 | 0 |  | Non-small cell lung cancer metastatic | No | Global | Open | Yes | [10 empty] | 2021-02-09 05:30 | [5 empty] | None of the above
CJDQ443B1 | CJDQ443B12001 | C4015441 | Not Applicable | NCDS_2 | [8 empty] | 2022-04-29 05:30 |  |  | Planned | [8 empty] | Outsourced |  |  | CJDQ443B12001 China Natural History KRASmut NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Zheyong Ma | [63 empty] | 1 |  |  | Non-small cell lung cancer stage III | Yes | Global | Open | Yes
CJDQ443B1 | CJDQ443B12101 | C4008961 | Phase I | Other | CRO - EDC |  |  | 2022-01-03 05:30 | DB Set-Up | Final DBL | 2022-06-01 05:30 |  | 2021-11-03 05:30 | 2021-11-23 05:30 |  | Planned | 2022-03-30 05:30 |  | 2022-06-01 05:30 |  | FALSE | Pioneer | Indu Bala | Cluster A (SolidT,IO,Resp) | FULL Outsourced | GMA - Oncology | A single-center, open-label study to evaluate the absorption, distribution, metabolism and excretion (ADME) and pharmacokinetics of JDQ443 following a single oral dose of [14C]JDQ443 in healthy male subjects | CJDQ443B12101 hADME | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Melissa Hackling | Melissa Hackling | [17 empty] | Sai Krishna Mettugari | [28 empty] | PRA Health | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CJDQ443B1 | CJDQ443B12102 | C4008962 | Phase I | Other | CRO - EDC |  |  | 2022-06-14 05:30 | DB Set-Up | Final DBL | 2022-10-31 05:30 |  | 2022-04-14 05:30 |  |  | Planned | 2022-09-16 05:30 |  | 2022-10-31 05:30 |  | FALSE | Pioneer | Indu Bala | Cluster A (SolidT,IO,Resp) | FULL Outsourced | GMA - Oncology |  | CJDQ443B12102 Victim DDI | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Nikki Collar | Nicola Collar | [17 empty] | Sai Krishna Mettugari | [28 empty] | PRA Health | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CJDQ443B1 | CJDQ443B12103 | C4008963 | Phase I | Other | CRO - EDC |  |  | 2022-02-28 05:30 | DB Set-Up | Final DBL | 2023-08-28 05:30 |  | 2021-12-31 05:30 | 2021-12-10 05:30 |  | Planned | 2023-07-17 05:30 |  | 2023-08-28 05:30 |  | FALSE | Pioneer | Indu Bala | Cluster A (SolidT,IO,Resp) | FULL Outsourced | GMA - Oncology |  | CJDQ443B12103 Hepatic Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Nikki Collar | Nicola Collar | [17 empty] | Sai Krishna Mettugari | [28 empty] | PRA Health | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CJDQ443B1 | CJDQ443B12104 | C4008964 | Phase I | Other | CRO - EDC |  |  | 2022-04-07 05:30 | DB Set-Up | Final DBL | 2022-07-27 05:30 |  | 2022-02-11 05:30 |  |  | Planned | 2022-06-15 05:30 |  | 2022-07-27 05:30 |  |  | Pioneer | Indu Bala | Cluster A (SolidT,IO,Resp) | FULL Outsourced | GMA - Oncology |  | CJDQ443B12104 Food Effect | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Nikki Collar | Nicola Collar | [17 empty] | Sai Krishna Mettugari | [28 empty] | PRA Health | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CJDQ443B1 | CJDQ443B12201 | C4015363 | Phase II |  |  |  |  | 2022-10-31 05:30 |  | Final DBL | 2028-01-10 05:30 |  | 2022-05-06 05:30 |  |  | Planned | 2027-11-30 05:30 |  | 2028-01-10 05:30 | [5 empty] | InHouse |  |  | CJDQ443B12201 NSCLC 1L G12Cm, PD-L1 low, STK11m | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Shweta Malhotra | Funmi Abiola | [66 empty] | Non-small cell lung cancer metastatic | Yes | Global | Open | Yes
CJDQ443B1 | CJDQ443B12301 | C4008960 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-06-15 05:30 |  | 2022-05-10 05:30 | DB Set-Up | DB Go-live | 2022-04-01 05:30 |  | 2022-01-03 05:30 | 2021-10-18 05:30 |  | Planned | 2025-11-10 05:30 |  | 2025-12-08 05:30 |  | FALSE | Pioneer | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized, open label, phase III study evaluating the efficacy and safety of JDQ443 versus docetaxel in previously treated subjects with locally advanced or metastatic KRAS G12C mutant non-small cell lung cancer | CJDQ443B12301 single agent Ph3 study | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Yamjala, Karthik | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Anne-Sophie Longin | Anne-Sophie Longin | Shanmugam BALASUBRAMANIAN, Narendra | Shanmugam BALASUBRAMANIAN, Narendra | Not Started |  | 21May2021 : Shared folder OID for this study. 29Apr2021: DO Accelerate. Not yet started from DBD perspective. Initial golive 15Jun2021 planned when DBD assigned. |  | DRM | Mopuru, Satwik | Mopuru, Satwik | Completed | 24Jan2022: Rule file Version 1.0 has been finalized and the SNOW05# Test request has been raised. 13Jan2022: Rule file development has been completed and shared to the peer review. 10Jan2022: Rule file development has been started. 07Jan2022: Initial review of ALS, SRF, SDTM Annotations have been completed and the comments shared to Lead DBD. 03Jan2022: Rule file pre-requisites have been shared by lead DBD for initiating the Rule file activities. 06Jul2021 : RF developer assigned with DB go live as 07Sep2021. | None | None |  |  |  |  | Sushant Sundar | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | 2022-01-24 05:30 | [15 empty] | None of the above
CJDQ443C1 | CJDQ443C12301 | C4013984 | Phase III |  |  |  |  | 2023-02-27 05:30 |  | Final DBL | 2030-02-06 05:30 |  | 2022-11-17 05:30 |  |  | Planned | 2029-12-26 05:30 |  | 2030-02-06 05:30 | [5 empty] | InHouse |  |  | CJDQ443C12301 Ph3 Study JDQ + TNO Combination | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Denis Weber | [66 empty] | Non-small cell lung cancer metastatic | No | Global | Open | Yes
CJDQ443D1 | CJDQ443D12301 | C4014498 | Phase III |  |  |  |  | 2023-03-31 05:30 |  | Final DBL | 2030-02-08 05:30 |  | 2022-11-17 05:30 |  |  | Planned | 2029-12-28 05:30 |  | 2030-02-08 05:30 | [5 empty] | InHouse |  |  | CJDQ443D12301 Ph3 JDQ+Tisle in 1L NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Denis Weber | [66 empty] | Non-small cell lung cancer metastatic | No | Global | Open | Yes
CJDQ443E1 | CJDQ443E12101 | C4014842 | Phase I+II |  | Rave EDC - Inhouse |  |  | 2022-06-14 05:30 | DB Set-Up | DB Go-live | 2022-05-31 05:30 |  | 2022-02-22 05:30 |  |  | Planned | 2024-01-08 05:30 |  | 2024-02-05 05:30 |  |  | Platform | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | KontRASt-03: A Phase Ib/II, multicenter, open-label platform study of JDQ443 with select combinations in patients with advanced solid tumors harboring the KRAS G12C mutation | CJDQ443E12101 | N7 Oncology - NIBR | Langlo, Francois | Thomas, Ashtami Rohan | Thorat, Swapnil | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Florian Villegas; Maria Amparo Buigues Vila; Maria Cintrao Dos Santos Rosa | Maria Joao Cintrao Dos Santos Rosa | Chiranjeevi, Priyanka Boya | Chiranjeevi, Priyanka Boya | [15 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CJGY925A0 | CJGY925A02101 | C4012424 | Phase I |  | Rave EDC - Inhouse |  |  | 2023-06-06 05:30 | Study Planned | DB Go-live | 2022-08-01 05:30 |  | 2023-03-07 05:30 |  |  | Planned | 2024-02-20 05:30 |  | 2024-04-09 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - ATI |  | CJGY925A02101 FIH SAD/MAD in HV | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Izabela Rozenberg | [17 empty] | Rohit Varate | [36 empty] | 50 | [7 empty] | 700 | 2 |  |  | Acne | No | Global | Open | Yes
CJWT629A1 | CJWT629A12301 | C4009055 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-04-24 05:30 | 2020-04-24 05:30 | 2020-05-01 05:30 | DB Locked | Final DBL Achieved |  | 2020-05-01 05:30 | 2020-03-27 05:30 | 2020-04-09 05:30 |  | Completed | 2020-12-01 05:30 | 2020-07-27 05:30 | 2020-08-31 05:30 | 2020-08-13 05:30 | TRUE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, randomized, double-blinded, placebo-controlled study to evaluate the safety and efficacy of hydroxychloroquine monotherapy and in combination with azithromycin in patients with moderate and severe COVID-19 disease | CJWT629A12301 HCQ in COVID 19 patients | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Chaudhari, Vishal | Kumar, Amresh | Vasi, Munir | Ninan, Esther | Kathryn Cooke | Kathryn Cooke | Maricherla, Vijayroshan | Maricherla, Vijayroshan | Not Started |  |  |  | DRM | Pilli, Bhaskar | Pilli, Bhaskar | Completed | 15Jun2020: Rulefile v2.0 is finalized with EG DTS on 06May2020. 24Apr2020: RF final and sent for LSH setup. Post RF finalization got a request to Add EG DTS in RF which got finalized today. EG will be included on Monday | Study Locked |  | 2020-04-24 05:30 | RF finalized within Go-live + 5 days | Kommu, Ranjith Kumar | Agavekar, Amit | Sandeep Kadam | Completed | 2020-04-25 | Completed | 2020-04-26 05:30 | Locked​ |  | 2020-04-26 05:30 | 2020-04-26 05:30 |  | 2020-04-29 05:30 |  |  | Study locked on 14th Aug 2020 | 100 | RaveX - Inhouse | Yes | Y5 | 2020-08-13 05:30 | 2020-08-14 05:30 | [9 empty] | NA | [5 empty] | 2 | 10 | 52 | 0 | 122 | 514 | 0 | 165 | 39 | 154 | 707 | 1 | 0 |  | Corona virus infection; Pneumonia | No | Global | Open | Yes | [10 empty] | 2020-04-26 05:30 |  |  |  | DBL | Agavekar, Amit | COVID19 | Yes
CKAE609A0 | CKAE609A2103 | C1200491 | Phase I | Other |  |  |  | 2024-10-31 05:30 |  | Final DBL | 2025-06-13 05:30 |  | 2024-06-19 05:30 |  |  | Planned | 2025-05-16 05:30 |  | 2025-06-13 05:30 | [5 empty] | FULL Outsourced |  | Placeholder drug interaction | CKAE609A2103 DDI with ritonavir | P6 Global Health | [6 empty] | Megan Osborn | [66 empty] | Drug interaction; Malaria | No | Global | Open | Yes
CKAE609A0 | CKAE609A2105 | C1200489 | Phase I | Other |  |  |  | 2024-09-02 05:30 |  | Final DBL | 2025-05-12 05:30 |  | 2024-04-19 05:30 |  |  | Planned | 2025-03-24 05:30 |  | 2025-05-12 05:30 | [5 empty] | FULL Outsourced |  | place holder | CKAE609A2105 DDI with mefloquine | P6 Global Health | [6 empty] | Megan Osborn | [66 empty] | Malaria | No | Global | Open | Yes
CKAE609A0 | CKAE609A2107 | C1200637 | Phase I | Other |  |  |  | 2024-10-30 05:30 |  | Final DBL | 2026-08-12 05:30 |  | 2023-06-12 05:30 |  |  | Planned | 2026-02-17 05:30 |  | 2026-08-12 05:30 | [5 empty] | FULL Outsourced |  | place holder | CKAE609A2107 CSF vs Adult FMI Rel BA & food effect | P6 Global Health | [6 empty] | Megan Osborn | [66 empty] | Malaria | No | Global | Open | Yes
CKAE609A | CKAE609A2202 | C1001221 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-10-05 05:30 | 2017-11-08 05:30 | DB Locked | Final DBL Achieved |  | 2017-11-16 05:30 |  | 2017-04-07 05:30 |  | Completed | 2020-04-30 05:30 | 2019-11-23 05:30 | 2020-06-09 05:30 | 2020-01-22 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A Phase 2, multi-center, randomized, open-label, doseescalationstudy to determine safety of single (QD) andmultiple (3 QD) doses of KAE609, given to adults withuncomplicated Plasmodium falciparum malaria | Phase2A Safety study_KAE609A2202 | P6 Global Health | Vithala, Srinivas | Shedge, Vijay | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Sarita Barsainya | Sarita Gajendrapratap Barsainya | TEMBHARE, HITESH | TEMBHARE, HITESH | [13 empty] | Polagoni, Bharghavi |  | Sai Krishna Mettugari | [13 empty] | 100 | OCRDC - Inhouse |  | Y1;#Y5;#ZK |  |  |  |  | Pharma | Novartis | InHouse | 2017-10-05 05:30 | 2017-10-05 05:30 | Shewane, Roshni | Mareedu, Vasu | NA | [7 empty] | 115 | 0 |  |  | 0 |  |  |  | 636 | 3 | 0 |  | Malaria | Yes | Global | Open: Reapproval | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | Yes
CKAE609A | CKAE609A2203 | C1202081 | Phase II | NCDS_2 |  |  |  | 2022-02-11 05:30 |  | Final DBL | 2024-06-21 05:30 |  | 2021-10-01 05:30 |  |  | Planned | 2024-05-17 05:30 |  | 2024-06-21 05:30 |  | FALSE |  |  |  | InHouse |  |  | CKAE609A2203 | P6 Global Health | [6 empty] | Val��rie Klein | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 50 | 8 | 0 |  | Malaria | No | Global | [18 empty] | None of the above
CKAE609B1 | CKAE609B12101 | C4006929 | Phase I | Other |  |  |  | 2024-10-02 05:30 |  | Final DBL | 2026-02-24 05:30 |  | 2024-04-23 05:30 |  |  | Planned | 2026-01-20 05:30 |  | 2026-02-24 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CKAE609B12101 DDI with strong 3A4 inhibitor | P6 Global Health | [6 empty] | Megan Osborn | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CKAE609B1 | CKAE609B12102 | C4006928 | Phase I | Other |  |  |  | 2024-10-02 05:30 |  | Final DBL | 2025-11-28 05:30 |  | 2024-04-23 05:30 |  |  | Planned | 2023-10-25 05:30 |  | 2025-11-28 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CKAE609B12102 DDI with strong 3A4 inducer | P6 Global Health | [6 empty] | Megan Osborn | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CKAE609B1 | CKAE609B12103 | C4006930 | Phase I | Other |  |  |  | 2024-07-31 05:30 |  | Final DBL | 2024-01-01 05:30 |  | 2024-04-23 05:30 |  |  | Planned | 2023-12-31 05:30 |  | 2024-01-01 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CKAE609B12103 IV IM bridging study | P6 Global Health | [6 empty] | Megan Osborn | [66 empty] | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CKAE609B1 | CKAE609B12201 | C4004189 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-02-26 05:30 | 2021-06-18 05:30 | 2022-03-14 05:30 | DB Conduct | Final DBL | 2024-04-19 05:30 |  | 2020-10-16 05:30 | 2020-10-19 05:30 |  | Planned | 2024-02-26 05:30 |  | 2024-04-19 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | An adaptive, randomized, active-controlled, open-label, sequential cohort, multicenter study to evaluate the efficacy, safety, tolerability, and PK of i.v. KAE609 (Cipargamin) in adult and paediatric Patients with Severe P. falciparum malaria | CKAE609B12201 phase 2 severe malaria | P6 Global Health | Vithala, Srinivas | Bommareddy, Satya Sai Reddy | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Marc Cousin | Marc Cousin | Moses, Leah | Das, Devashish | Not Started |  | 07-May-2021: Reviewed the screens and provided comments to Lead DBP to update the study specific screens and questionnaires 29Apr2021 : Screens UAT is ongoing. Edit Check programming initiated. FPFV has been preponed to June, but an official date has not been finalized. I have requested the TDM to request for the official date from the CTT. Initial go live as 26Feb2021 when RF developer was assigned on 28Oct2020. DB Go live was revised from 26FEB2021 to 17MAY2021 owing to initial delays in finalization of protocol and specs. | 34.6 - Database amendments requested and immense programming rework | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 18-Jun-2021: Rule File Version 1.0 is now final in CREDI. Raised SNOW05 ticket for LSH set-up. 20-Apr-2021: Reviewed study specific SRFs and ALS. Provided comments to Lead DBP 17-Feb-2021: Reviewed study specific SRFs and ALS. Provided comments to Lead DBP | None | None | 2021-06-18 05:30 | RF finalized within Go-live + 5 days | Praveen kumar, Chakka Giri | Praveen kumar, Chakka Giri | Sai Krishna Mettugari | Completed | 2021-06-24 | Completed | 2021-07-08 05:30 |  |  | 2021-07-09 05:30 | 2021-07-09 05:30 |  | 2021-07-12 05:30 |  |  | FPFV not yet achieved | 0 | RaveX - Inhouse |  | ZJ,EC,DS,DV | [11 empty] | NA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Complicated malaria | Yes | Global | Open | Yes | [10 empty] | 2021-07-07 05:30 | [5 empty] | None of the above
CKAE609B1 | CKAE609X2111 | C1200302 | Phase I | Other | CRO - EDC |  |  | 2020-07-22 05:30 | DB Locked |  |  | 2020-07-22 05:30 | 2019-05-21 05:30 | 2020-02-19 05:30 |  | Completed | 2020-11-10 05:30 | 2020-11-10 05:30 | 2021-05-21 05:30 | 2021-05-12 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, subject and investigator-blinded, placebo controlled, single and multiple ascending dose study to assess the safety, tolerability, and pharmacokinetics of KAE609 administered intravenously in healthy subjects | CKAE609X2111 FIH SAD/MAD IV Formulation | P6 Global Health | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Amanda Nguyen | Amanda Nguyen | [13 empty] | 2020-08-24 05:30 |  | R, Harini |  | Rohit Varate |  |  | Not Applicable |  |  |  | 2020-08-24 05:30 | 2020-08-26 05:30 | [6 empty] | FSOM - Outsourced | No | ZK;#ZK02 | 2021-05-26 05:30 | 2021-05-27 05:30 | No comments. LSH lock completed on 27th May, 2021. | [8 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Malaria | No | Global | Completed | Yes | [14 empty] | DBL | Adi, Vishnupriya | None of the above | Yes
CKAF156A | CKAF156A2104 | C4011518 | Phase I | Other |  |  |  | 2022-03-08 05:30 |  | Final DBL | 2022-07-01 05:30 |  | 2021-11-02 05:30 | 2021-11-03 05:30 |  | Planned | 2022-06-03 05:30 |  | 2022-07-01 05:30 | [5 empty] | FULL Outsourced |  |  | CKAF156A2104 - PK DDI cocktail inhibition study | P6 Global Health | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Malaria | No | Global | Open | Yes
CKAF156A | CKAF156A2105 | C1200408 | Phase I | Other |  |  |  | 2021-11-18 05:30 |  | Final DBL | 2022-04-18 05:30 | 2021-11-18 05:30 | 2021-07-06 05:30 | 2021-06-30 05:30 |  | Active | 2022-04-18 05:30 |  | 2022-04-18 05:30 |  | FALSE |  |  |  | FULL Outsourced |  | A Phase I, open-label, fixed single sequence, two period crossover drug-drug interaction study to investigate the interaction potential of itraconazole on KAF156 /Lumefantrine combination in healthy participants. | CKAF156A2105 DDIA with Potent CYP 3A4 inhibitors | P6 Global Health | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Malaria | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CKAF156A0 | CKAF156A2106 | C1001222 | Phase I | Other |  |  |  | 2023-01-06 05:30 |  | Final DBL | 2023-04-18 05:30 |  | 2022-09-15 05:30 |  |  | Planned | 2024-05-21 05:30 |  | 2023-04-18 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CKAF156A2106 Rel BA & FE study | P6 Global Health | [6 empty] | Wendy Weis | [66 empty] | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CKAF156A | CKAF156A2107 | C4011534 | Phase I | Other |  |  |  | 2022-04-18 05:30 |  | Final DBL | 2022-07-25 05:30 |  | 2022-02-26 05:30 |  |  | Planned | 2022-05-23 05:30 |  | 2022-07-25 05:30 | [5 empty] | FULL Outsourced |  | PK DDI induction | CKAF156A2107 - PK DDI induction | P6 Global Health | [6 empty] | Wendy Weis | [66 empty] | Malaria | No | Global | Open: Reapproval | Yes
CKAF156A | CKAF156A2108 | C4008127 | Phase I | Other |  |  |  | 2022-08-12 05:30 |  | Final DBL | 2023-02-09 05:30 |  | 2022-04-26 05:30 |  |  | Planned | 2023-01-12 05:30 |  | 2023-02-09 05:30 | [5 empty] | FULL Outsourced |  | A single-center, open-label study to evaluate the absorption, distribution, metabolism and excretion and pharmacokinetics of KAF156 following a single oral dose of [14C]KAF156 in healthy subjects | CKAF156A2108 hADME Study | P6 Global Health | [6 empty] | Melissa Hackling | [66 empty] | Malaria | No | Global | Open | Yes
CKAF156A | CKAF156A2202 | C1001224 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-06-19 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-08-02 05:30 |  | 2016-11-21 05:30 |  | Completed | 2021-08-02 05:30 | 2021-06-28 05:30 | 2021-09-10 05:30 | 2021-09-10 05:30 | FALSE | DCN Priority | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A Phase 2 interventional, multi-center, randomized open-label study to determine the effective and tolerable dose of KAF156 with Lumefantrine Solid Dispersion Formulation, given once daily for 1, 2 and 3-days to adults and children with uncomplicated Plasmodium falciparum malaria | CKAF156A2202_Phase 2B | P6 Global Health | Vithala, Srinivas | Mayakrishnan, Amritaraj | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Havana Chikoto | Havanakwavo Chikoto | TEMBHARE, HITESH | Mareedu, Vasu | Completed | 2021-02-11 05:30 | [11 empty] | Tidke, Shyam |  | Sai Krishna Mettugari | [6 empty] | 2017-07-21 05:30 | 2017-08-03 05:30 |  | 2017-07-24 05:30 |  |  |  | 100 | OCRDC - Inhouse | Yes | DS;#EG;#ZJ | 2021-09-13 05:30 | 2021-09-16 05:30 |  |  | Pharma | Novartis | InHouse | 2017-06-19 05:30 | 2017-06-19 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 165 | 0 |  |  | 0 |  |  |  | 520 | 4 | 0 |  | Malaria | Yes | Global | Open | Yes | [15 empty] | Sundar, N Sushant | None of the above | Yes
CKAF156A | CKAF156A2203 | C1200416 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-09-10 05:30 | 2020-09-09 05:30 | 2021-02-19 05:30 | DB Conduct | Final DBL | 2023-05-12 05:30 | 2021-02-16 05:30 | 2020-05-28 05:30 | 2020-05-20 05:30 |  | Active | 2023-03-31 05:30 |  | 2023-05-12 05:30 |  | FALSE | Not yet confirmed by GTD | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A Phase 2 interventional, multicenter, randomized, open-label study in three age-descending cohorts to evaluate efficacy, safety and tolerability of KAF156 and Lumefantrine-SDF combination, under fasted or fed conditions, in the treatment of acute uncomplicated Plasmodium falciparum Malaria in a pediatric population | CKAF156A2203 - KALUMI | P6 Global Health | Vithala, Srinivas | Khatua, Sandeep | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Havana Chikoto | Havanakwavo Chikoto | R, Ankit | Kala, Arpit | In Progress | 2020-12-15 05:30 | 09-Sep-2020: Initial Go-live (Rave X) 15-Dec-2020 : Study Transitioned from R, Ankit to Jyoti Kumari 06-Jan-2022 : Study Transitioned in Progress form Jyoti Kumari to Arpit Kala |  | DRM |  | Patnaik, Angella | Completed | 2-AUG-2021: RF Version 4.0 finalized for Subject Status mapping to SS domain as per SDTM requirement. SNOW#51 raised for SMT/LSH updates. 23-JUN-2021: RF Version 3.0 finalzied for EG1L DTS table addition. SNOW#51 raised for SMT/LSH updates. 09SEP2020: RF V1.0 finalized. SNOW#05 raised for SMT creation and new study set-up in LSH. 04SEP2020: RF Peer Review comments fixed and updates documents release for second round of review on 02-SEP-2020. 19AUG2020: RF sent for peer review (Except SSS001) 13AUG2020: Awaiting SDTM annotations for SSS001 (Subject Status - Cohort Assignment) form. Rest all domains are ready for Peer Review. 07-JUL-2020: RF not initiated. SRF discussions ongoing. 24JUN2020: SRF discussions. Inputs provided for study specific CRF design. | None | None | 2020-09-09 05:30 |  | Praveen kumar, Chakka Giri | Praveen kumar, Chakka Giri | Sai Krishna Mettugari | Completed | 2020-10-27 | Completed | 2020-11-17 05:30 |  |  | 2020-11-11 05:30 | 2020-11-11 05:30 |  | 2021-02-10 05:30 |  |  | DDPASS INITIATED ON 4-JUNE-21 AND PLANNED DATE TO COMPLETE 30-JUNE-21 | 63 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 11 | 67 | 0 | 139 | 759 | 0 | 227 | 35 | 154 | 948 | 3 | 0 |  | Malaria | No | Global | Open | Yes | [10 empty] | 2020-11-12 05:30 | [5 empty] | None of the above | Yes
CKAF156A | CKAF156A2302 | C1200407 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-07-01 05:30 | Study Planned | DB Go-live | 2023-05-01 05:30 |  | 2022-09-01 05:30 |  |  | Planned | 2025-04-29 05:30 |  | 2025-06-10 05:30 |  | FALSE | None | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health |  | CKAF156A2302 - KALUMA | P6 Global Health | Vithala, Srinivas | Chandrakant, Khilari | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Havana Chikoto | Havanakwavo Chikoto | [17 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CKAF156B | CKAF156X2202 | C1200703 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-09-15 05:30 |  | 2013-11-15 05:30 |  | Completed |  | 2017-11-29 05:30 | 2018-02-12 05:30 | 2018-02-13 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | A randomized, double-blind, placebo-controlled, single-center, 5-week study to evaluate the safety and causal prophylactic efficacy of KAF156 in a controlled human malaria challenge (CHMI). | CKAF156X2202 | R4 NITD - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Danielle Spera | Danielle Spera | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [28 empty] | CMED | [19 empty] | Malaria | No | Global | Completed | Yes | [16 empty] | None of the above
CKAZ954A1 | CKAZ954A12101 | C4005548 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-11-22 05:30 | 2020-01-14 05:30 | 2020-02-28 05:30 | DB Conduct | Final DBL | 2024-10-18 05:30 | 2020-02-20 05:30 | 2019-11-15 05:30 | 2019-08-19 05:30 |  | Active | 2024-08-12 05:30 |  | 2024-10-18 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I/Ib, open-label, multi-center, study of KAZ954 as a single agent and in combination with Spartalizumab, NZV930 and NIR178 in patients with advanced solid tumors | CKAZ954A12101 TCO Phase I FIH Study | N7 Oncology - NIBR | Langlo, Francois | Sotelo, Yadira | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Lisa Nardi | Lisa Nardi | Lingampalli, Rohit | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Lingampalli Rohit transitioned the study to Chandana Sarasani on 18-Aug-2020. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 22Nov2019. |  | DRM | Maricherla, Vijayroshan | Shrivastava, Nikhil | Completed | 29-Sep-2021: Updated and finalized the RF V7.0 WRT PPC#07 updates. Raised SNOW-51 ad notified the LSP. 05-May-2021: LB2L DTS got finalized today. So, the RF V6.0 is also finalized WRT PPC#04 updates and LB2L DTS. SNOW-51 is raised and LSP is notified. 15-Apr-2021: PPC#04 is implemented and stated working on RF updates. 12-Apr-2021: PPC#04 CRF updates leading to RF impact (CMO005, CMO006, PRO003, TUO001, TUO002, TUO003, TUO004, TRO001 and TRO002). PPC ongoing. 12-Jan-2021: Angella provided IA on PPC#04 on 10th Dec 2020. PPC is currently ongoing. 26Nov2020: Backup: Angella Whats planned: Nothing planned as of now. 08-Jun-2020 (SHRIVNI5): Sequence order corrected for LB domain in RF V4.0 due to LHS failure. RF is finalized and LSH setup completed. 20-May-2020 (SHRIVNI5): LB and ECG DTS included in the rule file V3.0 and finalized. SNOW-51 ticket raised for LSH setup. 01Apr2020 : Reassigned RF from Roshan to Nikhil 01Apr2020: LSH setup completed. No pending activity 26MAR2020: LSH setup and SMT ongoing. Included "B1O004, LBG002_TR, ZJS001, ZJS001_1" pending forms and RF final. 06Mar2020 : Included pending forms and Sent for Peer review 03MAR2020: Awaiting SDTM annotations for ZJS001,ZJS001_1 20Feb2020: Raised Snow ticket for LSH setup and SMT development . As there are build issues excluded forms B1O004 (B1TEST values are greater than 8. Hence excluded. To be included post PPC), LBG002_TR (Wrong analytes are mapped. To be fixed post PPC), ZJS001 & ZJS001_1 SDTM annotations pending 23Jan20: Will be released for Peer review (Chandra) 20 Jan 20: requested Lead DBD for updated ALS 09 Jan 20: Raised issues to DBD to fix in database. Awaiting new ALS. | None | None | 2020-03-06 05:30 | Transition Study | R, Harini | Kadam, Sandeep | Rohit Varate | Completed | 2020-02-27 | Completed | 2020-03-09 05:30 | SMT Creation request was raised on 20th Feb 2020. PREDRM Setup completed by 27th Feb 2020. Awaiting SMT for DRM setup. SMT files attached on 6th March,2020 (Friday). TPT,epoch attached on 9th March, 2020. ​Issues with Epoch file being addressed currently. | Pre-requisites not met | 2020-03-09 05:30 | 2020-03-09 05:30 | Pre-requisites not met | 2020-05-01 05:30 |  |  | 3 domain issues are pending update. 2 domain do not have sufficient data for review. [RAMACHA1, 3rd Feb, 2021] Awaiting confirmation from SDTM and TDM to close QS domain. Once completed DDPASS will be completed to 100% [RAMACHA1, 16th Feb, 2021] DDPASS tracker version 1.0 uploaded to subway. DDPASS Success Rate = 100% [RAMACHA1, 10JUN2021] Second round of DDPASS was initiated on 20th May, 2021 following PPC4. DDPASS Success Rate = 52%. Next DDPASS follow up meeting is scheduled on 16 JUN 2021 [RAMACHA1, 2021JUL29] DDPASS version 2.0 document was archived. Status : 80%. Pending issues are with vendor, lab ranges and PPC dependent (TR) | 52 | RaveX - Inhouse | Yes | -NA- |  |  |  | [RAMACHA1, 6th May, 2021] PPC4 SNOW51 was raised on 5th May, SMT update and LSH rebuild is in progress. [RAMACHA1, 11th May, 2021] PPC4 implementation in LSH is completed. DDPASS for PPC will be initiated. | [7 empty] | IQVIA | [5 empty] | 8 | 59 | 116 | 0 | 729 | 1142 | 0 | 258 | 45 | 325 | 1512 | 7 | 0 |  | Colorectal cancer metastatic | No | Global | Open | Yes | [10 empty] | 2020-03-06 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Adi, Vishnupriya | None of the above | Yes
CKFA115A1 | CKFA115A12101 | C4014379 | Phase I |  |  |  |  | 2022-09-21 05:30 |  | Final DBL | 2025-12-01 05:30 |  | 2022-04-04 05:30 |  |  | Planned | 2025-09-15 05:30 |  | 2025-12-01 05:30 | [5 empty] | InHouse |  |  | CKFA115A12101 TCO Trial | N7 Oncology - NIBR | [6 empty] | Joanne Randolph | [66 empty] | Anal cancer; Colorectal cancer; Esophageal cancer; Melanoma; Mesothelioma; Nasopharyngeal cancer; Non-small cell lung cancer; Ovarian cancer; Renal cell carcinoma; Squamous cell carcinoma of head and neck; Thymic cancer metastatic | No | Global | Open | Yes
CKJX839A1 | CKJX839A11201 | C4008348 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-12-17 05:30 | 2020-12-24 05:30 | 2021-01-29 05:30 | DB Conduct | DB Snapshot | 2022-03-08 05:30 | 2021-01-29 05:30 | 2020-07-07 05:30 | 2020-07-07 05:30 |  | Active | 2022-10-16 05:30 |  | 2022-11-25 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CKJX839A11201 ORION-15_Japan | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Ohtaka, Masahiro | Bagayatkar, Rupali Sudesh | Kansagara, Sachinkumar | Nair, Sreesha | NAOKO YAMADA | NAOKO YAMADA | Gupta, Anshu | TEMBHARE, HITESH | Not Started |  |  |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 08-Jul-2021: RF_V5.0 is finalized for LB2 DTS and SNOW ticket raised. PPC03 is on hold due to some technical issue in dry-run migration 07-Jul-2021: PPC 03 in progress and DTS table will be added to RF along with PPC updates 06Jul2021 : LB2L reflecting in missing form DTS report 21-Apr-2021: LB1L DTS table included in RF_V3.0 and raised SNOW ticket for the same. 14-Apr-2021: RF updated to include LB dts table. 20-Feb-2021: RF_V2.0 finalized to include FAMHS002 form 17-Feb-2021: RF_V2.0 is released for peer review to include PPC01-new form(FAMHS001) 02-Dec-2020: Requested Lead DBP to share the UAT status and updated ALS 25-Nov-2020: Reviewed the ALS and provided comments to Lead DBP. | None | None | 2020-12-24 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2021-01-08 | Completed | 2021-01-28 05:30 |  |  | 2021-01-28 05:30 | 2021-01-28 05:30 |  | 2021-01-28 05:30 |  |  | There are few issues that are pending and are marked to different line functions. The issues will be fixed in the upcoming DDPASS. | 69 | RaveX - Inhouse | Yes | LB | [11 empty] | NA | [5 empty] | 6 | 19 | 52 | 0 | 157 | 700 | 0 | 187 | 38 | 118 | 856 | 3 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [10 empty] | 2021-01-27 05:30 | [5 empty] | None of the above | Yes
CKJX839A1 | CKJX839A12105 | C4008344 | Phase I | Other | Other |  |  | 2021-02-26 05:30 | DB Locked |  |  | 2021-02-26 05:30 | 2020-07-11 05:30 | 2020-07-10 05:30 |  | Active |  | 2021-10-18 05:30 | 2021-12-17 05:30 | 2021-12-03 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM |  | CKJX839A12105 (ORION-14) China PK/PD | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Sheena Kao | Lihuei Kao | [17 empty] | Rohit Varate | [36 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839A1 | CKJX839A12201E1 | C4008488 | Phase II | Other | Other |  |  | 2022-10-11 05:30 | DB Locked |  |  | 2017-04-27 05:30 | 2022-05-03 05:30 | 2021-04-04 05:30 |  | Active | 2021-12-31 05:30 |  | 2022-01-31 05:30 | 2022-02-10 05:30 | FALSE | Non Critical | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CKJX839A12201E1 (ORION-3) Extension to ORION-1 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Siddavaram, Dheeraj | Sharma, Prateek | Kansagara, Sachinkumar | Nair, Sreesha | James Teague | James Teague | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839A1 | CKJX839A12302 | C4008490 | Phase III | Other | Other |  |  | 2022-10-11 05:30 | DB Locked | Final DBL Achieved |  | 2019-02-06 05:30 | 2018-06-18 05:30 | 2021-04-04 05:30 |  | Active | 2021-09-14 05:30 | 2021-09-09 05:30 | 2021-10-22 05:30 | 2021-10-22 05:30 | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A TWO-PART (DOUBLE-BLIND PLACEBOCONTROLLED/ OPEN-LABEL) MULTICENTER STUDY TO EVALUATE SAFETY, TOLERABILITY, AND EFFICACY OF INCLISIRAN IN SUBJECTS WITH HOMOZYGOUS FAMILIAL HYPERCHOLESTEROLEMIA (HoFH) | CKJX839A12302 (ORION-5) HoFH Ph3 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sridhar, Shashikala | Sharma, Prateek | Kansagara, Sachinkumar | Nair, Sreesha | Ursula Loechner | Ursula Loechner | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839A1 | CKJX839A12306B | C4008495 | Phase III | Other | Other |  |  | 2022-10-11 05:30 | DB Conduct | Final DBL | 2023-03-28 05:30 | 2019-04-16 05:30 | 2022-05-03 05:30 | 2018-10-01 05:30 |  | Active | 2023-02-14 05:30 |  | 2023-03-28 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CKJX839A12306B (ORION-8) (Ph3 bucket for 9,10,11) | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Thokala, Silpa | Sharma, Prateek | Kansagara, Sachinkumar | Nair, Sreesha | Edna Cahill | Edna Cahill | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839A1 | CKJX839A12307 | C4008345 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-15 05:30 | 2021-01-29 05:30 | 2021-03-15 05:30 | DB Conduct | Final DBL | 2022-08-04 05:30 | 2021-03-01 05:30 | 2020-06-30 05:30 | 2020-07-02 05:30 |  | Active | 2022-07-14 05:30 |  | 2022-08-04 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter, randomized, double-blind, parallel group, placebo-controlled study to evaluate the efficacy and safety of inclisiran in Asian patients with ASCVD or ASCVD high risk and elevated low-density lipoprotein cholesterol as an adjunct to diet and maximally tolerated statins with or without additional lipid-lowering therapy (ORION-18) | CKJX839A12307 (ORION-18) Ph3_China | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | PENG, Tian | Bagayatkar, Rupali Sudesh | Kansagara, Sachinkumar | Nair, Sreesha | Dora Weng | Chiaching Weng | Moses, Leah | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Moses Leah transitioned the study to Chandana Sarasani on 13-Dec-2021. | 30.1 - Protocol Amendment and global library new version release | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 27-dEC-2021: Rule file Version 6.0 has been finalized in SubWay. LSP and TDM has been notified. 08-Dec-2021: Rule file Version 5.0 has been finalized in SubWay. LSP and TDM has been notified. 06-Dec-2021: Rule file development has been completed, and has been shared for peer review. 01-Dec-2021: PPC#3 Database go-live completed. Rule file pre-requisites has been received from lead DBD. 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 13Jul2021 : LB1L and LB2L DTS are included and the RF is finalized in SUBWAY 06Jul2021 : LB1L reflecting in missing form DTS report 1Jul2021 : Will check with Praveen on the status of the Rule file and take necessary action on this. 26May2021 : Reassigned the study from Praveen Oguri to Rehana Banu. 25-May-2021: Pratheeksha is working on RF to include LB1L and will be finalized by 25-May-2021. 26-Apr-2021: Working on RF update to include LB1L DTS, will be finalized by 28-Apr-2021 01-Feb-2021: RF Version Finalized and raised SNOW05 ticket on 29-Jan-2021. 02-Dec-2020: Received all the documents, I will assign this study to Prateeksha by 04-Dec-2020 and I will perform review. | None | None | 2021-01-29 05:30 |  | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2021-02-23 | Completed | 2021-02-23 05:30 |  |  | 2021-02-23 05:30 | 2021-02-23 05:30 |  | 2021-02-23 05:30 | [18 empty] | NA | [5 empty] | 4 | 23 | 66 | 0 | 200 | 1123 | 0 | 302 | 38 | 187 | 1348 | 2 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [10 empty] | 2021-02-16 05:30 | [5 empty] | None of the above
CKJX839A1_MA | CKJX839A12401 | C4010963 | Phase IV | Other | CRO - EDC |  |  | 2022-06-01 05:30 | Study Planned | DB Go-live | 2022-03-02 05:30 |  | 2021-11-30 05:30 | 2021-12-15 05:30 |  | Planned | 2027-04-01 05:30 |  | 2027-06-01 05:30 |  | FALSE | Awaiting info | Indu Bala | Cluster B (Haem,CRM,NS) | FULL Outsourced | GMA - Pharma | VICTORION REAL: A prospective multi-country Real world study to evaluate Effectiveness and Adherence of incLisiran vs standard of care in patients with familial and non-familial hyperlipidemia | CKJX839A12401 MA_VICTORION REAL | P9 Cardiovascular Renal and Metabolism (CRM) | Vithala, Srinivas | ASWALE, SWAPNIL | ASWALE, SWAPNIL | Kansagara, Sachinkumar | Nair, Sreesha | Lucile Penaud | Swetha Kappera | [17 empty] | Sai Krishna Mettugari | [28 empty] | Parexel | [7 empty] | 25 | 0 |  |  | 0 |  |  |  | 200 | 5 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839A1_MA | CKJX839A12402 | C4013655 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2022-01-20 05:30 |  | 2022-04-11 05:30 | DB Set-Up | DB Go-live | 2022-03-11 05:30 |  | 2021-10-05 05:30 | 2021-10-06 05:30 |  | Planned | 2025-01-30 05:30 |  | 2025-03-18 05:30 |  |  | No DCN Priority | Indu Bala | Cluster B (Haem,CRM,NS) | InHouse | GMA - Pharma | Efficacy, safety, tolerability and quality of life of participant-individually optimizedâ¯ lipid-lowering therapy with or without inclisiran (KJX839) â a randomized, placebo-controlled, double-blind multicenter phase IV study in participant with hypercholesterolemia | CKJX839A12402 Victorion Difference | P9 Cardiovascular Renal and Metabolism (CRM) | Vithala, Srinivas | ASWALE, SWAPNIL | ASWALE, SWAPNIL | Kansagara, Sachinkumar | Nair, Sreesha | Nathalie Force-Lambert | Nathalie Force-Lambert | Musku, Srikanth Reddy | Maricherla, Vijayroshan | Completed | 2022-01-31 05:30 |  |  |  | PRAKASH PATIL, PRATIKSHA | PRAKASH PATIL, PRATIKSHA | Not Started | 12 Dec 2021: RF programmer assigned. 8 Feb 2022: Screen Review is still ongoing. 15 Feb 2022: Screen UAT completed. 17 Feb 2022: Received ALS, provided comments from RF perspective to DBD. | [6 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes
CKJX839B1 | CKJX839B12302 | C4012240 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-12-01 05:30 | 2021-10-25 05:30 | 2021-11-30 05:30 | DB Conduct | Final DBL | 2027-05-10 05:30 | 2021-11-23 05:30 | 2021-07-14 05:30 | 2021-07-16 05:30 |  | Active | 2027-03-15 05:30 |  | 2027-05-10 05:30 |  |  | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized double-blind, placebo controlled, multicenter trial, assessing the impact of inclisiran on major adverse cardiovascular events in participants with established cardiovascular disease | CKJX839B12302 (VICTORION-2-PREVENT) | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Joshi, Shrinivas | Bagayatkar, Rupali Sudesh | Kansagara, Sachinkumar | Nair, Sreesha | Mayur Kherdikar; Ying Chen | Mayur Kherdikar | Shanmugam BALASUBRAMANIAN, Narendra | Shanmugam BALASUBRAMANIAN, Narendra |  |  | Dec-2021 : Deepthi supported 1st PPC for incorrect role restrictions 06May2021 : As per Lateef the Golive advanced to 15Oct2021 and will be in DO accelerate. 24mar2021 : DBD Madhu assigned to the study with planned golive as Dec2021. |  | DRM | Mopuru, Satwik | Mopuru, Satwik | Completed | 01Dec2021: Rule file 3.0 is finalized in SubWay. LSP and TDM are notified. 11Nov2021: Rule file 2.0 is finalized in SubWay. LSP and TDM are notified. 27Oct2021: Rule file Version 1.0 is finalized in SubWay. LSP and TDM are notified. 06Oct2021: Rule file has been shared to the peer review. Go-live date is pushed to 25th OCT. 04Oct2021: Rule file development has been completed. 22Sept2021: ALS, SDTM Annotations, SRFs review is completed and comments shared with DBD and SDTM Programmer 20Sep2021: Received ALS, SDTM Annotations, SRFs from DBD. 06Jull2021: RF developer assigned with golive as 01Dec2021. | None | None | 2021-10-27 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2021-11-03 | Completed | 2021-11-25 05:30 |  |  | 2021-11-25 05:30 | 2021-11-25 05:30 |  | 2021-12-03 05:30 |  |  |  |  | RaveX - Inhouse | No | [18 empty] | 2 | 20 | 56 | 0 | 142 | 683 | 0 | 200 | 38 | 188 | 909 | 3 | 0 |  | Cardiovascular event prophylaxis | No | Global | Open | Yes | [10 empty] | 2021-11-23 05:30 | [6 empty] | No
CKJX839B1_MA | CKJX839B12401 | C4012458 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-01 05:30 | Study Planned | DB Go-live | 2022-08-02 05:30 |  | 2022-05-16 05:30 |  |  | Planned | 2024-11-01 05:30 |  | 2025-02-03 05:30 |  | FALSE | Awaiting info | Indu Bala | Cluster B (Haem,CRM,NS) | InHouse | GMA - Pharma | A randomized, placebo controlled, multicenter, double blind trial comparing an early in hospital pre-discharge treatment with inclisiran on top of usual care versus usual care alone in patients with a recent acute coronary syndrome | CKJX839B12401 Post ACS RCT | P9 Cardiovascular Renal and Metabolism (CRM) | Vithala, Srinivas | ASWALE, SWAPNIL | ASWALE, SWAPNIL | Kansagara, Sachinkumar | Nair, Sreesha |  | Lucile Penaud | [17 empty] | Sai Krishna Mettugari | [36 empty] | 40 | 0 |  |  | 0 |  |  |  | 500 | 3 | 0 |  | Cardiovascular event prophylaxis | No | Global | Open | Yes | [16 empty] | None of the above
CKJX839C1 | CKJX839C12301 | C4008337 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-04 05:30 | 2021-01-06 05:30 | 2021-01-29 05:30 | DB Conduct | Final DBL | 2025-01-15 05:30 | 2021-01-27 05:30 | 2020-06-30 05:30 | 2020-07-01 05:30 |  | Active | 2024-12-09 05:30 |  | 2025-01-15 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Two part (double-blind inclisiran versus placebo [Year 1] followed by open-label inclisiran [Year 2]) randomized multicenter study to evaluate safety, tolerability, and efficacy of inclisiran in adolescents (12 to less than 18 years) with heterozygous familial hypercholesterolemia and elevated LDL-cholesterol (ORION-16) | CKJX839C12301 ORION-16 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Wakekar, Sucheta Amit | Bagayatkar, Rupali Sudesh | Kansagara, Sachinkumar | Nair, Sreesha | Akiko Inubushi-Molessa | Akiko Inubushi-Molessa | Rao, S Shashikanth | Rao, S Shashikanth | Not Started |  |  |  | DRM | Shafiudeen, Rehana Banu | Mopuru, Satwik | Completed | 04-Oct-2021: Rule File 9.0 is finalized in SUBWAY and the LSP is notified. 27-Sept-2021: MHS003 form is updated in the Rule file. As the SDTM Annotations got updated. 31-Aug-2021 : The study is transitioned to Mopuru, Satwik. 31-Aug-2021 : No Pending tasks. 17Aug2021 : Rule File 8.0 is finalized in SUBWAY and the LSP is notified. 13Jul2021 :The RF including LB2L DTS is already final. Will check with the LSP and update the status in here. 06Jul2021 : LB2L reflecting in missing form DTS report 26May2021 : Reassigned the study from Praveen Oguri to Rehana Banu. 25-May-2021: Included in RF Version 4.0 and raised SNOW ticket on 21-May-2021. 26-Apr-2021: Working in RF update, planning to finalize by 28-Apr-2021 19Apr2021 : CMG001_3 in report 13-Jan-2021: RF Final . RF finalization is delayed by couple of days as there was an issue with UAT SOD Generation. RF finalization was delayed by 2 working days as UAT SOD's were not available for RF validation. IT ticket was raised to Medidata to provide a resolution. 02-Dec-2020: SRF's and SDTM annotations shared by DBD. I have provided my comments. RF development activity is not yet started. 11Aug2020 : SS forms shared by DBD for review. provided feedback. | None | None | 2021-01-11 05:30 | RF finalized within golive + 5 days | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2021-01-26 | Completed | 2021-02-02 05:30 |  | Pre-requisites not met | 2021-02-02 05:30 | 2021-02-02 05:30 | 02-Feb-2021 : All domains (AE,APMH,CM,DD,DM,DV,EC,FAAE,FAMH,IE,LB,MH,MO,ODM,PR,RP,SV,SU,VE,VS,ZJ) except DS published to Jreview and GPS DS domain has an RF issue - CNST_DSCAT1_STD#CNST_DSCAT1 these variables were not transposed to core variables. | 2021-02-02 05:30 |  |  |  |  | RaveX - Inhouse | No | LB and YR - Masked, Y1 and Y5 - Blinded | [11 empty] | NA | [5 empty] | 6 | 13 | 62 | 0 | 142 | 1226 | 0 | 305 | 38 | 213 | 1477 | 3 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [10 empty] | 2021-02-02 05:30 | [5 empty] | None of the above
CKJX839C1 | CKJX839C12302 | C4008335 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-02-11 05:30 | 2021-02-09 05:30 | 2021-03-15 05:30 | DB Conduct | Final DBL | 2025-01-15 05:30 | 2021-02-16 05:30 | 2020-06-30 05:30 | 2020-07-01 05:30 |  | Active | 2024-12-09 05:30 |  | 2025-01-15 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Two part (double-blind inclisiran versus placebo [Year 1] followed by open-label inclisiran [Year 2]) randomized multicenter study to evaluate safety, tolerability, and efficacy of inclisiran in adolescents (12 to less than 18 years) with homozygous familial hypercholesterolemia and elevated LDL-cholesterol (ORION-13) | CKJX839C12302 ORION-13 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Wakekar, Sucheta Amit | Bagayatkar, Rupali Sudesh | Kansagara, Sachinkumar | Nair, Sreesha | Akiko Inubushi-Molessa | Akiko Inubushi-Molessa | Kancharla, Susmita | Palande, Sujit | Completed |  | Nov 2021 : Giftson transitioned to Sujit Susmita lead DBD transitioned study to Giftson DTS finalization is in progress. Once DTS get finalized study transition will be completed. |  | DRM | Shafiudeen, Rehana Banu | Saha, Saikat | Completed | 21Feb2022: Received the updated ALS, IA, SOD and SDTM annotation for the RF updates. RF is updated and sent for peer review. Peer review is completed and will be finalized once the PPC is implemented. 6Jan2022: Reviewed the IA and provided my inputs to the DBD. 5Jan2022: Received the PPC#3 IA for review. 31-Aug-2021 : The study is transitioned to Saha, Saikat. 31-Aug-2021 : No Pending tasks. 18Aug2021 : Rule file 3.0 is finalized in SUBWAY and the LSP is notified. 9Aug2021 : Recent updates on "Familial Hypercholestemia" , "Medical History Statin Intolerance", "Protocol Solicited Medical History" and "Carotid Intima media Thickness Assessment" form are being included in the study. Once these are completed the RF will be finalized. 9Aug2021 : The LB1L DTS is included in the Rule file and was finalized on 21-May-2021. 21May2021 : The DTS is included in the Rule file. The review is completed and will be soon finalized once YRL,YDL DTS is also finalized. 11May2021 : SDTM annotations for 3 forms - MHS001, MHS002 and MOS001 are updated and have included in RF. LB1L DTS is also included in the RF. 10Feb2021: RF final and snow05 raised 3Feb2021 : Rule file developed and sent for peer review 27Jan2021 : Shared the review comments with the DBD. 22Jan2021 : Received necessary documents for review 27JAN2021: Rulefile to be created. Planned golive is 13Jan2021. 18Jan2021 : (RB) Golive date postponed to 11Feb2021, awaiting for details and documents from the DBD. | PPC#3 is on hold | None | 2021-02-10 05:30 | Transition study | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2021-02-22 | Completed | 2021-02-24 05:30 |  | Pre-requisites not met | 2021-02-24 05:30 | 2021-02-24 05:30 | Pre-requisites not met | 2021-03-03 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB and YR - Masked, Y1 and Y5 - Blinded | [11 empty] | NA | [5 empty] | 3 | 13 | 62 | 0 | 143 | 1210 | 0 | 298 | 41 | 177 | 1428 | 3 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [10 empty] | 2021-02-24 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Ramayanam, Vinay | None of the above | Yes
CKJX839D1_MA | CKJX839D12303 | C4010177 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-05-27 05:30 | DB Set-Up | DB Go-live | 2022-04-22 05:30 |  | 2021-12-15 05:30 | 2022-01-18 05:30 |  | Planned | 2025-06-05 05:30 |  | 2025-07-18 05:30 |  |  | No DCN Priority | Indu Bala | Cluster B (Haem,CRM,NS) | InHouse | GMA - Pharma |  | CKJX839D12303 V-Plaque Imaging Primary Prevention | P9 Cardiovascular Renal and Metabolism (CRM) | Vithala, Srinivas | Bhandari, Aditi | ASWALE, SWAPNIL | Kansagara, Sachinkumar | Nair, Sreesha | Abdelkader Si Bouazza | Abdelkader Si Bouazza | Sinha, Deepakshi | Sinha, Deepakshi | [5 empty] | Mopuru, Satwik | Mopuru, Satwik | Not Started | [7 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 53 | 0 |  |  | 0 |  |  |  | 900 | 4 | 0 |  | Cardiovascular event prophylaxis | No | Global | Open | Yes
CKRP203A0 | CKRP203A2105 | C1001226 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-06-28 05:30 |  | 2012-12-05 05:30 |  | Completed | 2018-08-13 05:30 | 2018-08-21 05:30 | 2018-11-15 05:30 | 2018-11-29 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A two-part, single- and two arm randomized, open-label study to evaluate the safety, tolerability, pharmacokinetics and efficacy (in Part 2 only) of KRP203 in patients undergoing allogeneic hematopoietic stem cell transplant for hematological malignancies | CKRP203A2105 P1b for safety and efficacy | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Soni, Kushal | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | David Sanchez Ramos | David Sanchez Ramos | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED |  | AP21 | CMED Clinical services | elazarescu@cmedresearch.com | [15 empty] | Graft versus host disease | No | Global | Completed | Yes | [16 empty] | None of the above
CLA-EP2006 | CLA-EP06-104 | C1050254 | Phase I | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2017-04-14 05:30 | 2018-08-29 05:30 | 2017-01-26 05:30 |  | Completed | 2018-09-03 05:30 | 2018-08-01 05:30 | 2018-11-30 05:30 | 2018-10-26 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | Outsourced | Biosimilars/ Sandoz | A randomized, double-blind, three-way crossover study to\ncompare the pharmacokinetics, pharmacodynamics and\nsafety of a single 6 mg subcutaneous administration of the\nproposed biosimilar product LA-EP2006, NeulastaÂ® US and\nNeulastaÂ® EU in healthy subjects | CLA-EP06-104 Phase I Study | P2 SZ Biopharma | Marshall, Lee | Gandepalli, Sangeetha | Machado, Sundeep | Machado, Sundeep | Ninan, Esther | Steven Schussler | Steven Schussler | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Pharmacokinetic study | No | Global | Completed | No | [16 empty] | None of the above
CLAF237A | CLAF237A1401 | C1001230 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2010-04-28 05:30 | 2010-02-04 05:30 | 2010-02-04 05:30 |  | Completed | 2015-05-01 05:30 | 2015-04-28 05:30 | 2023-04-10 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational Study of Equa in Diabetes Melltus Type2 | JPN PMS_CLAF237A1401 | P6 Global Health | [5 empty] | YOHEI SHINFUKU | [67 empty] | Diabetes mellitus non-insulin-dependent | No | Global | Open | Yes | [16 empty] | None of the above
CLAF237A | CLAF237A1402 | C1001231 | Phase IV | Other | [7 empty] | 2010-10-05 05:30 | 2019-04-29 05:30 | 2010-02-04 05:30 |  | Completed | 2018-01-01 05:30 | 2017-12-22 05:30 | 2018-01-01 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational stuy of Equa in Diabetes Melltus Type 2 for renal impairment patients | JPN PMS_CLAF237A1402 | P6 Global Health | [73 empty] | Diabetes | No | Global | Open | Yes | [16 empty] | None of the above
CLAF237A | CLAF237A1403 | C1001232 | Phase IV | Other | [7 empty] | 2010-10-19 05:30 | 2017-12-08 05:30 | 2010-02-04 05:30 |  | Completed | 2018-01-01 05:30 | 2017-12-22 05:30 | 2018-01-01 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational stuy of Equa in Diabetes Melltus Type 2 for hepatic impairment patients | JPN PMS_CLAF237A1403 | P6 Global Health | [73 empty] | Diabetes | No | Global | Open | Yes | [16 empty] | None of the above
CLAF237A | CLAF237A1404 | C1001229 | Phase IV | Other | [7 empty] | 2013-04-01 05:30 | 2018-01-19 05:30 | 2013-01-25 05:30 |  | Completed | 2018-01-01 05:30 | 2017-12-22 05:30 | 2018-01-01 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of LAF237A for combination therapy in T2DM | JPN_PMS_Combi_CLAF237A1404 | P6 Global Health | [5 empty] | YOHEI SHINFUKU | [67 empty] | Diabetes mellitus non-insulin-dependent | No | Global | Open | Yes | [16 empty] | None of the above
CLAF237A_MA | CLAF237A23156 | C1001647 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-03-30 05:30 |  | 2011-10-17 05:30 |  | Completed | 2019-05-01 05:30 | 2019-04-04 05:30 | 2019-05-17 05:30 | 2019-05-10 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A 5-year study to compare the durability of glycemic control of a combination regimen with vildagliptin & metformin versus standard-of-care monotherapy with metformin, initiated in treatment-naÃ¯ve patients with type 2 diabetes mellitus | CLAF237A23156 VERIFY | P6 Global Health | Vithala, Srinivas | Vithanala, Kiran Kumar | Varshney, Kapil | Fazili, Subeh Mohsin | Krishnan, Kripesh | Abhishek Sople | Abhishek Sople | Tripathi, Shakuntala | R, Ankit | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Pharma | AP21 | [17 empty] | Diabetes mellitus non-insulin-dependent | No | Global | Open | Yes | [16 empty] | None of the above
CLAF237A_MA | CLAF237AJP01 | C1200824 | Phase IV Local | Other | [7 empty] | 2011-02-18 05:30 |  |  |  | Completed | 2018-01-01 05:30 | 2017-12-22 05:30 | 2018-01-01 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Evaluation of Safety of Equa in early stages of use, and the relationship between changes in HbA1c and patient characteristics | CLAF237AJP01 | P6 Global Health | [73 empty] | Diabetes mellitus non-insulin-dependent; Diabetes mellitus, non-insulin dependent | No | Local | Terminated | Yes | [16 empty] | None of the above
CLAF237A_MA | CLAF237AJP04 | C1200838 | Phase IV Local | Other | [7 empty] | 2013-03-04 05:30 |  |  |  | Completed | 2018-01-01 05:30 | 2017-12-22 05:30 | 2018-01-01 05:30 | 2017-12-22 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of LAF237A in T2DM | CLAF237AJP04 | P6 Global Health | [73 empty] | Diabetes Type 2 Mellitus; Type 2 diabetes mellitus | No | Local | Terminated | Yes | [16 empty] | None of the above
CLAG525B | CLAG525B2101 | C3003634 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-14 05:30 | 2018-06-21 05:30 | DB Conduct |  |  | 2018-07-02 05:30 | 2018-03-07 05:30 | 2018-03-09 05:30 |  | Active | 2021-08-02 05:30 | 2021-11-24 05:30 | 2022-01-28 05:30 | 2022-01-06 05:30 | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | A phase II open label, randomized, three-arm, multicenter study of LAG525 given in combination with spartalizumab (PDR001), or with spartalizumab and carboplatin, or with carboplatin, as first or second line therapy in patients with advanced triple-negative breast cancer | CLAG525B2101 Ph II in TNBC-1L & 2L (+PDR001) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Darapureddy, Dilip Kumar | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Sarah Rawlings | Sarah Rawlings | Munukutla, Valli | Bora, Deepthi Reddy | Completed | 2021-06-22 05:30 | 22Jun2021 : Transition from Valli Munukutla to Deepthi Bora PPC-11 Development Ongoing Transition from Bhaskar Pilli to Valli Munukutla |  | DRM (DIAL) | Pilli, Bhaskar | Shrivastava, Nikhil | Completed | 01-Apr-2021: B14L DTS included in the Rule File and finalized in CREDI. SNOW-51 is raised. LSP and SMT developers have been notified. 25-Mar-2021: B14L DTS (Flagged in the missing form and DTS report) but TDM/DBD did not inform about the DTS finalization. Reviewing the DTS 12-Jan-2021: SNOW-51 was raised on 14th Sep 2020 to rebuild DV and ZB domains as per PPC#09. LSP and SMT developers were notified. No impact to Rule File. 26Nov2020: Backup: Chandrakala Whats planned: Nothing planned as of now. 01Apr2020 : Reassigned RF from Bhaskar to Nikhil 03Mar2020 : All forms and DTSs included | None | None | 2018-08-16 05:30 | Transition Study and Legacy process | Polavarapu, Vanaja | Varate, Rohit | Sushant Sundar | Completed | 2018-08-17 | Completed | 2019-06-07 05:30 |  |  | 2018-08-17 05:30 | 2018-08-17 05:30 | Pre-requisites not met | 2019-07-09 05:30 |  |  | DDPASS is ongoing as we have final DBL | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 15 | 115 | 96 | 0 | 526 | 1303 | 0 | 289 | 39 | 304 | 1646 | 6 | 0 |  | Breast cancer | No | Global | Wind Down | Yes | [10 empty] | 2019-07-04 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Sahu, Ahallad | None of the above | Yes
CLAG525D1 | CLAG525X2101C | C1001650 | Phase I+II | NCDS | OC RDC - Inhouse | 2015-05-15 05:30 | 2015-05-15 05:30 |  | DB Locked |  |  | 2015-06-17 05:30 |  | 2015-03-11 05:30 |  | Completed | 2020-11-23 05:30 | 2020-12-31 05:30 | 2021-04-08 05:30 | 2021-03-23 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/II, open label, multicenter study of the safety and efficacy of LAG525 single agent and in combination with PDR001 administered to patients with advanced malignancies | CLAG525X2101C TCO-PhI/II-LAG3-Immunother-solid-tum | N7 Oncology - NIBR | Langlo, Francois | Vivier, Gregoire | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon | Gabriela Mere Villanueva | Sama, Ashok | Shewane, Roshni | Completed | 2020-08-05 05:30 | Study Transitioned to Roshni Shewane on 05Aug2020. | [10 empty] | Mettugari, Sai Krishna |  | Rohit Varate |  |  | Not Applicable | [9 empty] | Old OC Study. Will conduct DDPASS before any milestone All the domains were reviewed and no issues were identified by the team. |  | OCRDC - Inhouse | No | -NA- | 2021-03-30 05:30 | 2021-04-01 05:30 |  |  | ONC | Novartis | ICON | 2015-05-15 05:30 | 2015-05-15 05:30 | Shewane, Roshni | Meda, Sreelakshmi | IQVIA | [7 empty] | 193 | 0 |  |  | 0 |  |  |  | 539 | 7 | 0 |  | Cervical cancer; Colorectal cancer; Gastric cancer; Melanoma; Mesothelioma; Non-small cell lung cancer; Renal cell carcinoma; Triple negative breast cancer | No | Global | Open | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CLAP016A | CLAP016A1401 | C1001651 | Phase IV | Other |  |  |  | 2009-06-25 05:30 |  |  |  | 2009-06-25 05:30 | 2009-04-24 05:30 | 2009-04-24 05:30 |  | Completed | 2017-03-13 05:30 | 2017-04-13 05:30 | 2017-03-13 05:30 | 2017-04-17 05:30 | FALSE |  |  |  | Outsourced |  |  | Japan PMS_LAP016A1401_smTKIs_(EGF113092) | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | HARUKA NISHIOKA | NAOKO USHIDA | [66 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2101 | C1001236 | Phase I | GSK | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2023-02-10 05:30 | 2005-09-26 05:30 |  | 2005-02-22 05:30 |  | Active | 2022-12-30 05:30 |  | 2023-02-10 05:30 |  | FALSE | fgsk long term follow up study | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2101_(EGF100161) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Das, Mayuree | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2102 | C1001237 | Phase I | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2006-12-07 05:30 |  | 2006-01-31 05:30 |  | Completed | 2019-09-30 05:30 | 2019-09-12 05:30 | 2019-11-11 05:30 | 2019-10-11 05:30 | FALSE | non priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2102_(EGF103892) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Parmar, Dhirendra | Kumar, Amresh | Sonmale, Pravin | Ninan, Esther |  | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2201 | C1001238 | Phase II | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2007-02-27 05:30 |  | 2006-06-19 05:30 |  | Completed | 2021-06-30 05:30 | 2020-06-19 05:30 | 2020-09-02 05:30 | 2020-09-02 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2201_(EGF103890) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Parmar, Dhirendra | Basani, Sravan | Sonmale, Pravin | Ninan, Esther |  | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2202 | C1001239 | Phase II | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2005-12-02 05:30 |  | 2005-09-01 05:30 |  | Completed | 2018-03-15 05:30 | 2018-03-15 05:30 | 2018-04-26 05:30 | 2018-04-13 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2202 (EGF105084) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Parmar, Dhirendra | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2204 | C1001240 | Phase II | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2008-07-02 05:30 |  |  |  | Completed | 2018-01-03 05:30 | 2018-01-03 05:30 | 2018-01-31 05:30 | 2018-01-31 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2204_(LPT111111) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Parmar, Dhirendra | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2205 | C1001241 | Phase II | GSK | Other |  |  |  | DB Locked |  |  | 2009-11-25 05:30 |  |  |  | Completed |  | 2015-11-24 05:30 |  | 2016-06-17 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CLAP016A2205_(EGF112620) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Kumar, Amresh | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2206 | C1001242 | Phase II | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2014-10-24 05:30 |  | 2014-03-14 05:30 |  | Completed | 2020-04-30 05:30 |  | 2020-10-23 05:30 | 2020-11-27 05:30 | FALSE | low priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | An Open-Label, Phase II, Study to Evaluate Biomarkers Associated with Response to Subsequent Therapies in Subjects with HER2-Positive Metastatic Breast Cancer Receiving Treatment with Trastuzumab in Combination with Lapatinib or Chemotherapy | CLAP016A2206_(EGF117165) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Juneja, Twinkle | Basani, Sravan | Sonmale, Pravin | Ninan, Esther | Janet Lasher | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2301 | C1001243 | Phase III | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2005-12-13 05:30 |  | 2005-12-02 05:30 |  | Completed | 2019-12-31 05:30 | 2019-10-21 05:30 | 2019-12-02 05:30 | 2019-11-13 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2301 (EGF104383) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sinkar, Abhijeet | Basani, Sravan | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  | Breast cancer | No | Global | Draft | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2302 | C1001244 | Phase III | GSK | CRO - EDC |  |  |  | DB Locked |  |  | 2006-01-02 05:30 |  | 2005-09-29 05:30 |  | Active | 2021-12-31 05:30 |  | 2022-02-11 05:30 | 2022-01-04 05:30 | FALSE | fGSK trial long term follow up study. | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2302_(EGF104535) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Sinkar, Abhijeet | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2303 | C1001245 | Phase III | GSK | Paper |  |  |  | DB Conduct | Final DBL | 2022-05-16 05:30 | 2008-10-07 05:30 |  | 2008-02-14 05:30 |  | Active | 2022-03-31 05:30 |  | 2022-05-16 05:30 |  | FALSE | Long term Follow up study transitioned from GSK | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | FULL Outsourced | fGSK |  | CLAP016A2303_(EGF108919-COMPLETE) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Gorla, Krishna Sagar Reddy | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2304 | C1001246 | Phase III | Other | Paper |  |  |  | DB Locked |  |  | 2007-07-18 05:30 |  | 2007-02-22 05:30 |  | Completed | 2020-03-31 05:30 | 2020-07-01 05:30 | 2020-09-17 05:30 | 2021-01-20 05:30 | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CLAP016A2304_(EGF109491) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Qian, Celia | Basani, Sravan | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2305 | C1001247 | Phase III | GSK | Other |  |  | 2009-04-14 05:30 | DB Locked | Final DBL Achieved |  | 2009-04-14 05:30 |  |  |  | Completed | 2019-03-22 05:30 | 2018-03-22 05:30 | 2018-05-03 05:30 | 2018-04-19 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2305 (EGF111438) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Sinkar, Abhijeet | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2306 | C1001248 | Phase III | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2010-01-20 05:30 |  | 2009-07-21 05:30 |  | Completed | 2018-12-31 05:30 | 2018-03-30 05:30 | 2019-03-25 05:30 | 2018-03-27 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2306_(LPT112515) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Sinkar, Abhijeet | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2307 | C1001653 | Phase III | GSK | CRO - EDC |  |  | 2019-01-04 05:30 | DB Conduct | Final DBL | 2023-07-27 05:30 | 2011-05-05 05:30 | 2018-08-17 05:30 | 2010-05-19 05:30 |  | Active | 2023-07-27 05:30 |  | 2023-07-27 05:30 |  | FALSE | 9 | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2307 MBC fGSK EGF114299 (ALTERNATIVE) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | CHRIS PRANUSHA, GODUGU ANNIE | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther | Ivanka Zic | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAP016A | CLAP016A2308 | C1001249 | Phase III | GSK | Paper |  |  |  | DB Locked | Final DBL Achieved |  | 2003-12-09 05:30 |  | 2003-07-17 05:30 |  | Completed | 2018-03-15 05:30 | 2008-06-03 05:30 | 2018-04-30 05:30 | 2018-04-24 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | CLAP016A2308_(EGF30008) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Gorla, Krishna Sagar Reddy | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther |  | Karen McBride | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 |  |  |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLAP016A_MA | CLAP016A2410 | C1001654 | Phase II | GSK | Other |  |  |  | DB Locked |  |  | 2014-12-17 05:30 |  | 2014-02-17 05:30 |  | Completed |  | 2017-10-19 05:30 |  | 2018-02-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CLAP016A2410 EGF117314-RELATED | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Suryawanshi, Sandip | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | LaTonya Smith | LaTonya Smith | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Breast cancer metastatic | No | Global | Completed | No | [16 empty] | None of the above
CLAP016A | CLAP016A2412B | C4013693 | Phase IV | NCDS_2 |  |  |  | 2022-06-14 05:30 |  | Final DBL | 2033-04-26 05:30 |  |  |  |  | Planned | 2033-03-15 05:30 |  | 2033-04-26 05:30 | [5 empty] | InHouse |  | A rollover trial of Tykerb single agent or in combination with other products | CLAP016A2412B LAP016A Roll Over | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Ivanka Zic | Ivanka Zic | [54 empty] | 60 | [7 empty] | 900 | 8 |  |  | Breast cancer; Gastric cancer | No | Global | Wind Down | No
CLAP016B | CLAP016B2301 | C1001655 | Phase III | GSK | Paper |  |  |  | DB Locked | Final DBL | 2022-01-03 05:30 | 2007-05-16 05:30 |  | 2007-02-05 05:30 |  | Active | 2021-07-01 05:30 |  | 2022-01-03 05:30 |  | FALSE | 9 | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | FULL Outsourced | fGSK |  | CLAP016B2301 LTFU ABC fGSK EGF106708 (ALTTO) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Gorla, Krishna Sagar Reddy | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther | Nayia Gkolfi | Panagiota Gkolfi | [17 empty] | Sandeep Kadam | [28 empty] | BrEAST group | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 |  |  |  | Locally advanced breast cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CLAP016B | CLAP016B2302 | C1001656 | Phase III | GSK | Paper |  |  |  | DB Locked |  |  | 2008-01-05 05:30 |  | 2007-02-09 05:30 |  | Completed | 2019-12-23 05:30 |  | 2020-04-30 05:30 | 2020-04-24 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | FULL Outsourced | fGSK |  | CLAP016B2302 LTFU nABC fGSK EGF106903 (NeoALTTO) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Gorla, Krishna Sagar Reddy | Basani, Sravan | Sonmale, Pravin | Ninan, Esther | Nayia Gkolfi | Panagiota Gkolfi | [17 empty] | Sandeep Kadam | [28 empty] | BrEAST group | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 |  |  |  | Locally advanced breast cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CLAP016C | CLAP016C2301 | C1001251 | Phase III | GSK | Paper |  |  |  | DB Conduct | Final DBL | 2023-02-13 05:30 | 2008-06-04 05:30 |  | 2017-12-17 05:30 |  | Active | 2022-12-31 05:30 |  | 2023-02-13 05:30 |  | FALSE | fGSK outsourced LTFU study | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | CLAP016C2301_(EGF110656-LOGIC) | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Gorla, Krishna Sagar Reddy | Gorla, Krishna Sagar Reddy | Sonmale, Pravin | Ninan, Esther |  | Ivanka Zic | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Gastric cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLAZ696B1 | CLAZ696B11101 | C4009582 | Phase I |  |  |  |  | 2024-08-05 05:30 |  | Final DBL | 2024-12-13 05:30 |  | 2024-04-07 05:30 |  |  | Planned | 2024-10-25 05:30 |  | 2024-12-13 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CLAZ696B11101 Japan BE 200mg_2.5mg | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | SATORU SHINMYO | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Heart failure | No | Global | Open | Yes | [16 empty] | None of the above
CLAZ696B1 | CLAZ696B11102 | C4009584 | Phase I |  |  |  |  | 2024-12-02 05:30 |  | Final DBL | 2025-05-02 05:30 |  | 2024-08-04 05:30 |  |  | Planned | 2025-03-14 05:30 |  | 2025-05-02 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CLAZ696B11102 Japan BE 200mg_10mg and Food effect | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | SATORU SHINMYO | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Heart failure | No | Global | Open | Yes | [16 empty] | None of the above
CLAZ696B1 | CLAZ696B11301 | C4009597 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2024-07-02 05:30 | Study Planned | DB Go-live | 2022-05-27 05:30 |  | 2023-05-31 05:30 |  |  | Planned | 2026-01-16 05:30 |  | 2025-02-25 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLAZ696B11301 LAZ696B1 JPN Multifactorial study | P9 Cardiovascular Renal and Metabolism (CRM) | Okuzono, Seigou | Nishi, Nahoko | Okuzono, Seigou | Okuzono, Seigou | Okuzono, Seigou | YUJI HACHIYA | YUJI HACHIYA | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CLAZ696B1 | CLAZ696B11302 | C4009598 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2024-06-02 05:30 | Study Planned | DB Go-live | 2022-04-28 05:30 |  | 2023-05-31 05:30 |  |  | Planned | 2024-06-21 05:30 |  | 2026-06-29 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLAZ696B11302 LAZ696B1 JPN Non-responder study | P9 Cardiovascular Renal and Metabolism (CRM) | Okuzono, Seigou | SAKAKI, SAYAKA | Okuzono, Seigou | Okuzono, Seigou | Okuzono, Seigou | YUJI HACHIYA | YUJI HACHIYA | [17 empty] | Amit Agavekar | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CLBH589B | CLBH589B2206 | C1001252 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2008-04-22 05:30 |  | 2007-04-25 05:30 |  | Completed | 2017-11-13 05:30 | 2017-11-08 05:30 | 2018-03-07 05:30 | 2018-02-16 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A phase Ib, multi-center, open-label, dose-escalation study of oral LBH589 when administered in combination with oral lenalidomide & dexamethasone in adult patients with multiple myeloma | MM LBH REV DEX 2nd L CLBH589B2206 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bhattad, Poonam | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Ursula Loechner | Ursula Loechner |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | CMED | Oncology | BP21 | CMED Clinical services | sduff@cmedresearch.com | Earlier DBD: Jugnu Kumari | [14 empty] | Multiple myeloma | No | Global | Completed | Yes | [16 empty] | None of the above
CLBH589B_MA | CLBH589B2402B | C1001657 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-06-24 05:30 |  | 2013-02-14 05:30 |  | Completed | 2018-11-19 05:30 | 2018-11-19 05:30 | 2019-04-09 05:30 | 2019-04-17 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open-label multi-center single agent panobinostat rollover protocol for patients who have completed a previous Novartis-sponsored panobinostat study and are judged by the investigator to benefit from continued single agent panobinostat treatment | CLBH589B2402B All indications roll-over | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Vaibhav, Soni | Sardesai, Pallavi Sharad | Gracey Sugunan, Unni Krishnan | Nair, Sreesha | Anne Ruault | Anne Ruault |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | mailto:Tatiana.Khibina@ppdi.com | Earlier DBD: Jugnu Kumari | [14 empty] | Haematological malignancy | No | Global | Completed | Yes | [16 empty] | None of the above
CLBH589D | CLBH589D1201 | C1001253 | Phase II | NCDS | [7 empty] | 2014-12-16 05:30 |  | 2014-08-06 05:30 |  | Completed | 2018-12-25 05:30 | 2018-12-25 05:30 | 2019-02-04 05:30 | 2019-01-31 05:30 | FALSE |  |  |  | InHouse |  | A phase II, multi-center, single arm, open label study to evaluate the efficacy and safety of panobinostat in combination with bortezomib and dexamethasone in Japanese patients with relapsed/refractory multiple myeloma | CLBH589D1201 Japan PhII MM Post Marketing | PA Oncology (Hematology not for MA projects) | [6 empty] | ERI TANABE | Ambati, Purnachander | [14 empty] | Tidke, Shyam | [16 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | InHouse |  | 2014-11-12 05:30 | [22 empty] | Multiple myeloma | No | Local | Open | Yes | [16 empty] | None of the above
CLBH589D | CLBH589D1401 | C1001661 | Phase IV | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2015-10-28 05:30 | 2019-05-02 05:30 | 2015-06-25 05:30 |  | Completed | 2022-07-30 05:30 | 2020-08-28 05:30 | 2021-09-10 05:30 | 2021-09-10 05:30 | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Special Drug use investigation (observational study) Multiple myeloma | CLBH589D1401 Japan PMS | PA Oncology (Hematology not for MA projects) | YAMADA, KAYO | MURAKAMI, TAKUMI | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | HARUKA NISHIOKA | HARUKA NISHIOKA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Multiple myeloma | No | Global | Open | Yes | [16 empty] | None of the above
CLBH589D_MA | CLBH589D2001X | C1001662 | Phase III | NOVDD | CRO - EDC |  |  | 2015-02-24 05:30 | DB Locked | Final DBL Achieved |  | 2015-01-07 05:30 | 2014-01-14 05:30 | 2014-01-14 05:30 |  | Completed | 2017-05-22 05:30 | 2017-05-15 05:30 | 2017-08-01 05:30 | 2017-08-01 05:30 | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | An open label, multi-center, expanded access study of oral Panobinostat in combination with bortezomib and dexamethasone in adult patients with relapsed multiple myeloma. | CLBH589D2001x ETP PH IV MM L2C | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sadhu, Soumen Kumar | Sardesai, Pallavi Sharad | Kachchhava, Avinash Balasaheb | Nair, Sreesha | Anne Ruault | Anne Ruault | [17 empty] | Amit Agavekar | [28 empty] | PPD | [19 empty] | Multiple myeloma | No | Global | Completed | Yes | [16 empty] | None of the above
CLBH589D | CLBH589D2222 | C1001254 | Phase II | NCDS | OC RDC - Inhouse | 2016-04-06 05:30 | 2016-04-06 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-04-27 05:30 |  | 2015-11-24 05:30 |  | Active | 2024-05-02 05:30 | 2020-03-20 05:30 | 2024-08-09 05:30 | 2020-03-20 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A multicenter, randomized, open-label Phase 2 study evaluating the safety and efficacy of three different regimens of oral panobinostat in combination with subcutaneous bortezomib and oral dexamethasone in patients with relapsed or relapsed/refractory multiple myeloma who have been previously exposed to immunomodulatory agents | MM Rel L2C, CLBH589D2222 PANO3, US PMR1 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Pal, Arvind Kumar | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Jenna Garner | Ursula Loechner | Tadiparthy, Ramakanth | Shewane, Roshni | Not Started |  | Study not transitioned to Roshni Shewane. It was decided not to start transition for this study. | [10 empty] | Agavekar, Amit |  | Amit Agavekar | [12 empty] | Old OC study. Will conduct DDPASS before milestone activity |  | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2016-04-06 05:30 | 2016-04-06 05:30 | Shewane, Roshni | Mulla, Afreen | NA | [7 empty] | 210 | 0 |  |  | 0 |  |  |  | 901 | 2 | 0 |  | Multiple myeloma | No | Global | Open | Yes | [16 empty] | None of the above
CLBH589D_MA | CLBH589D2408 | C1001663 | Phase IV | NCDS | OC RDC - Inhouse |  | 2016-12-01 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-05-05 05:30 |  | 2016-10-07 05:30 |  | Completed | 2019-04-12 05:30 | 2019-03-31 05:30 |  | 2019-06-04 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Non-interventional study of panobinostat in combination with bortezomid and dexamethasone in patients with Relapsed or Relapsed and Refractory Multiple Myeloma (RRMM) | CLBH589D2408 EU PASS PH IV MM L2C | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Kumar HC, Vijay | Sardesai, Pallavi Sharad | Gracey Sugunan, Unni Krishnan | Nair, Sreesha | Anne Ruault | Anne Ruault | Maricherla, Vijayroshan | Mareedu, Vasu | [13 empty] | Challa, Nandini |  | Amit Agavekar | [12 empty] | flowed down all the variables of AE to GPS on request from TDM, Performed fix for FAZQ and ZQ by changing the rule file logic. | 100 | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | ICON | 2017-02-10 05:30 | 2017-02-10 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 33 | 0 |  |  | 0 |  |  |  | 397 | 1 | 0 |  | Multiple myeloma | No | Global | Completed | Yes | [14 empty] | DBL | Kadam, Sandeep | None of the above | Yes
CLBH589H | CLBH589H2101 | C1001256 | Phase II | NOVDD | Paper |  |  |  | DB Locked |  |  | 2009-12-02 05:30 |  | 2009-06-12 05:30 |  | Completed | 2019-05-06 05:30 | 2019-04-29 05:30 | 2019-12-02 05:30 | 2019-07-03 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A phase I/b, open-label, multi-center, dose-escalation study of oral Panobinostat (LBH589) administered with 5-Azacitidine (Vidaza®) in adult patients with myelodysplastic syndromes (MDS), chronic myelomonocytic leukemia (CMML) or acute myeloid leukemia (AML) | CLBH589H2101 PIb/IIb in MDS, CMML and AML | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Subramanian, Mahaveeran | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laura Abbott | Jacqueline Ewan |  | Gupta, Anshu | [15 empty] | Amit Agavekar | [28 empty] | CMED | Oncology | BP21 |  | Francesca Stone (fstone@cmedresearch.com) | Earlier DBD: Asha Rajanna | [14 empty] | Myelodysplastic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CLBH589H | CLBH589H2101A1 | C1200087 | Phase I |  |  |  |  | 2018-02-28 05:30 |  |  |  | 2011-07-18 05:30 | 2018-02-28 05:30 | 2009-06-12 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE |  |  |  | FULL Outsourced |  | Addendum study to core study LBH589H2101 (due to limitation of 99 visits per trial in the visit design) | CLBH589H2101A1 | PA Oncology (Hematology not for MA projects) | [6 empty] | Ursula Loechner | [66 empty] | Myelodysplastic syndrome | No | Global | Terminated | Yes | [16 empty] | None of the above
CLBH589A0 | CLBH589X2106 | C1001670 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2011-11-01 05:30 |  | 2011-05-24 05:30 |  | Completed | 2020-06-22 05:30 | 2020-06-22 05:30 | 2020-08-03 05:30 | 2020-07-31 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A Phase 1b, open-label, multi-center, single arm, dose finding study to assess safety and pharmacokinetics of the oral combination of panobinostat and ruxolitinib in patients with primary myelofibrosis (PMF), post-polycythemia veramyelofibrosis (PP-MF) or post-essential thrombocythemiamyelofibrosis (PET-MF) | CLBH589X2106 PI-Safety and PK in MF | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bhattad, Poonam | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Flavia Kiertsman | Flavia Kiertsman |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | BP21 | PPD | mailto:Dennis.Wang@ppdi.com | Earlier DBD: Jugnu Kumari | [14 empty] | Myelofibrosis | No | Global | Completed | Yes | [16 empty] | None of the above
CLCI699C | CLCI699C1201 | C3003251 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-09-24 05:30 |  | 2015-05-13 05:30 |  | Completed | 2019-03-29 05:30 | 2018-10-29 05:30 | 2018-12-06 05:30 | 2018-12-03 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase II, open-label, dose titration, multi-center study to assess the safety/tolerability and efficacy of osilodrostat in patients with all types of endogenous CushingÂ¿s syndrome except Cushing's disease. | Japan_LCI699C1201 Cushing's syndrome | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Ushijiama, Sachiko | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | RIE NAGAHARI | MARI UMEZU | Oguri, Praveen | [14 empty] | Kommu, Ranjith Kumar |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2015-08-06 05:30 | 2015-08-06 05:30 |  |  | NA | [7 empty] | 122 | 0 |  |  | 0 |  |  |  | 491 | 4 | 0 |  | Cushing's syndrome | Yes | Local | Completed | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CLCI699A0 | CLCI699C2108 | C1001258 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-08-16 05:30 |  | 2017-02-21 05:30 |  | Completed | 2017-12-20 05:30 | 2017-12-07 05:30 | 2018-03-29 05:30 | 2018-04-30 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | An open-label, two period fixed sequence study to evaluate the effects of osilodrostat (LCI699) on the pharmacokinetics of a monophasic oral contraceptive in healthy female subjects. | LCI699C2108 DDI Oral Contraceptive | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Venkataswamy, Pavana | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Lisa Burgmeyer | Lisa Burgmeyer | Bai, Chandrakala | [14 empty] | Varate, Rohit |  | Sai Krishna Mettugari | [14 empty] | CRO | [6 empty] | ONC | Parexel | Outsourced | 2017-08-04 05:30 |  |  |  | Parexel | [7 empty] | 15 | 0 | [7 empty] | 1 | 0 |  | Drug interaction NOS | No | Global | Completed | Yes | [16 empty] | None of the above
CLCI699C | CLCI699C2201 | C1001260 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2011-03-23 05:30 |  | 2010-09-27 05:30 |  | Completed | 2019-11-18 05:30 | 2019-10-22 05:30 | 2019-11-26 05:30 | 2019-11-26 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A proof-of concept, open-label, forced titration, multi-center study to assess the safety/tolerability and efficacy of 10-weeks treatment of LCI699 followed by a 12 - week treatment period in patients with Cushing's disease | LCI699C2201 Cushing's disease PIE LINC-2 | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Dsouza, Carlton | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh |  | David Craig | [17 empty] | Sai Krishna Mettugari | [28 empty] | PPD | [7 empty] | 27 | 0 |  |  | 0 |  |  |  | 470 | 7 | 0 |  | Cushing's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLCI699C | CLCI699C2301 | C1001261 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-10-06 05:30 |  | 2014-01-28 05:30 |  | Completed | 2019-12-09 05:30 | 2019-12-04 05:30 | 2020-01-29 05:30 | 2020-02-05 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A Phase III, multi-center, double-blind, randomized withdrawal study of LCI699 following a 24 week, single-arm, open-label dose titration and treatment period to evaluate the safety and efficacy of LCI699 for the treatment of patients with Cushingâs disease | CLCI699C2301 (LINC-3) Cushing's Disease | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Dsouza, Carlton | Sharma, Harish | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Janet Lasher | Janet Lasher |  | Gandla, Prashanth | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | Dennis Wang <Dennis.Wang@ppdi.com> | novartis.com; Earlier DBD: Asha Rajanna |  |  | 94 | 0 |  |  | 0 |  |  |  | 689 | 7 | 0 |  | Cushing's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLCI699C | CLCI699C2302 | C1001262 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-04-29 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-10-03 05:30 |  | 2016-01-27 05:30 |  | Completed | 2021-01-01 05:30 | 2020-12-31 05:30 | 2021-03-10 05:30 | 2021-03-10 05:30 | FALSE | Not applicable | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A Phase III, multi-center, randomized, double-blind, 48 week study with an initial 12 week placebo-controlled period to evaluate the safety and efficacy of osilodrostat in patients with Cushing's disease | CLCI699C2302 Cushing's disease LINC-4 | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Poggi, Marie-Line | Sharma, Harish | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Anne Zuse | Anne Zuse | Iliyas, Mohamed | Mokhamatam, Madhu Purnachandra Rao |  | 2020-04-17 05:30 | [11 empty] | Sundar, N Sushant |  | Sai Krishna Mettugari | [12 empty] | Old OC Study. Will conduct meeting before study milestone | 100 | OCRDC - Inhouse | Yes | LB | 2021-03-10 05:30 | 2021-03-11 05:30 |  |  | ONC | Novartis | ICON | 2016-04-28 05:30 | 2016-04-28 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 116 | 0 |  |  | 0 |  |  |  | 746 | 6 | 0 |  | Cushing's disease | No | Global | Open | Yes | [14 empty] | DBL | Agavekar, Amit | None of the above | Yes
CLCI699C | CLCI699C2X01B | C3000205 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-05 05:30 | 2018-10-05 05:30 | DB Locked | Final DBL | 2023-11-16 05:30 | 2018-10-05 05:30 | 2018-08-30 05:30 | 2018-02-22 05:30 |  | Active |  | 2021-12-08 05:30 | 2023-11-16 05:30 |  | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | An open-label, multi-center, roll-over study to assess long\nterm safety in patients with endogenous Cushingâs\nsyndrome who have completed a prior Novartis-sponsored\nosilodrostat (LCI699) study and are judged by the\ninvestigator to benefit from continued treatment with\nosilodrostat | LCI699C2X01B long-term safety roll-over | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Rane Kulkarni, Vaidehi Sujay | Sharma, Harish | Chouhan, Mithun Mahesh | Krishnan, Kripesh | David Craig | David Craig | Tadiparthy, Ramakanth | Tadiparthy, Ramakanth |  |  |  |  | DRM (DIAL) | Tadiparthy, Ramakanth | Choppadandi, Kranthikumar | Completed | 18-Aug-2020: Reviewed PPC08 and raised SNOW ticekt for LSH as RF update is not required PPC changes. 06-Jul-2020: Not received any updates. Data exposed to J-review & GPS II except Biomarker DTSs which is pending Finalization | None | None | 2018-11-09 05:30 | Legacy Process | Gandikota, Sree Lakshmi | Purohit, Hemanshu | Sai Krishna Mettugari | Completed | 2018-12-24 | Completed | 2019-05-20 05:30 |  |  | 2018-11-12 05:30 | 2018-11-13 05:30 |  | 2020-01-29 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 23 | 34 | 0 | 152 | 375 | 0 | 134 | 35 | 124 | 534 | 1 | 0 |  | Cushing's disease; Cushing's syndrome | No | Global | Open | Yes | [10 empty] | 2019-05-20 05:30 | [5 empty] | None of the above
CLCZ696A | CLCZ696A1402 | C4007789 | Phase IV | Other |  |  |  | 2024-01-31 05:30 |  | Final DBL | 2026-03-31 05:30 |  | 2023-12-29 05:30 |  |  | Planned | 2025-11-28 05:30 |  | 2026-03-31 05:30 |  | FALSE |  |  |  | Outsourced |  |  | CLCZ696A1402 Japan PMS_HTN | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | NOBUTAKA NAKAGAWA | [66 empty] | Hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CLCZ696A | CLCZ696A2216 | C1200216 | Phase II | NCDS |  |  |  | 2012-12-05 05:30 |  |  |  | 2012-12-05 05:30 | 2012-07-09 05:30 | 2012-07-09 05:30 |  | Completed | 2015-04-08 05:30 | 2015-04-08 05:30 | 2015-05-13 05:30 | 2015-05-13 05:30 | FALSE |  |  |  | IDMA Shared |  | A randomized, double-blind, active-controlled, multicenter, 52-week study to evaluate the safety and efficacy of an LCZ696 regimen on arterial stiffness through assessment of central blood pressure in elderly patients with essential hypertension. | CLCZ696A2216 | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Michele Sauer | Michele Sauer | [66 empty] | Hypertension | No | Global | [18 empty] | None of the above
CLCZ696B | CLCZ696B1101 | C4007334 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-03-06 05:30 | 2020-03-06 05:30 | 2020-03-09 05:30 | DB Locked | Final DBL Achieved |  | 2020-03-09 05:30 | 2019-12-27 05:30 | 2019-12-26 05:30 |  | Completed | 2020-04-17 05:30 | 2020-04-17 05:30 | 2020-07-01 05:30 | 2020-06-25 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM |  | CLCZ696B1101 Japan BE 50mg_100mg | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Takano, Mamiko | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | YASUYUKI TABEI | YASUYUKI TABEI | Suzuki, Hiroko | Rapaka, Sindhuja |  | 2020-03-17 05:30 | DB golive 06Mar2020 as of 07Jan2020. |  | DRM | Govula, Shashikanth | Govula, Shashikanth | Completed | 7JAN2021: No upcoming tasks. 21Apr2020 : LBG003_TR included in V2.0 14Apr2020 : included penidng LBG003_TR and sent for peer review (Nikhil) 08APr2020: PPC pushed in prod on 06thApr. Working on RF updates. 03Apr2020 : Awaiting PPC implementation for LBG003_TR 19-Mar-2020: SNOW05 raised on 16-Mar-2020. 10Mar2020: released for peer review . Excluded LBG003_TR form as it has screen design issue and need a fix via PPC notifed DBD. 02Mar2020 : Received docs from DBD on 14Feb2020. WIll be sent for peer review by 06th mar 2020. 10Feb2020 : Awaiting response from DBD. Followed up to share the Study specific forms for review along with ALS and Unique CRFs. No study specific forms. Screen UAT is ongoing and would be tentatively completed by 14Feb2020. | None | None | 2020-03-16 05:30 | Legacy Process | Gouni, Harita | Kadam, Sandeep | Rohit Varate | Completed | 2020-03-17 | Completed | 2020-03-24 05:30 | Completed.. Study got locked on 29-Jul-2020. | Rule file issues | 2020-03-26 05:30 | 2020-03-26 05:30 | Pre-requisites not met | 2020-05-01 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-06-26 05:30 | 2020-06-29 05:30 | [9 empty] | NA | [5 empty] | 4 | 13 | 47 | -1 | 106 | 363 | -138 | 138 | 35 | 149 | 547 | 0 | 0 |  | Heart failure | No | Global | Completed | Yes | [10 empty] | 2020-03-23 05:30 |  |  |  | DBL | R, Harini | None of the above | Yes
CLCZ696B | CLCZ696B1301 | C1001269 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-06-15 05:30 |  | 2015-01-22 05:30 |  | Completed | 2021-01-30 05:30 | 2021-02-18 05:30 | 2021-03-12 05:30 | 2021-03-09 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter, randomized, double-blind, parallel group, active-controlled study to evaluate the efficacy and safety of LCZ696 compared to enalapril on morbidity and mortality in Japanese patients with chronic heart failure and reduced ejection fraction | CLCZ696B1301 JPN_RARALLEL | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Takano, Mamiko | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha | YOSHIUMI OKUBO | YOSHIUMI OKUBO | Meda, Sreelakshmi | Mokhamatam, Madhu Purnachandra Rao | [13 empty] | Darisi, Pallavi |  | Amit Agavekar | [21 empty] | Pharma | Novartis | ICON | 2015-05-28 05:30 | 2015-05-28 05:30 | Meda, Sreelakshmi | Rajhans, Khushbu Kumari | NA | [7 empty] | 98 | 0 |  |  | 0 |  |  |  | 695 | 9 | 0 |  | Heart failure | Yes | Local | Open | Yes | [14 empty] | DBL | Shah, Manasi | None of the above | No
CLCZ696B | CLCZ696B1401 | C4003063 | Phase IV | Other | CRO - EDC | 2021-03-31 05:30 |  | 2021-03-31 05:30 | DB Conduct | Final DBL | 2024-02-29 05:30 | 2021-03-04 05:30 | 2021-02-08 05:30 | 2021-01-18 05:30 |  | Active |  |  | 2024-02-29 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | DF CRM |  | CLCZ696B1401 Japan PMS_HF | P9 Cardiovascular Renal and Metabolism (CRM) | YAMADA, KAYO | MATSUNAKA, REIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | NOBUTAKA NAKAGAWA | NOBUTAKA NAKAGAWA | [17 empty] | Amit Agavekar | [28 empty] | Other | [7 empty] | 15 | 0 | [10 empty] | Heart failure | No | Global | Open | Yes | [16 empty] | None of the above
CLCZ696A0 | CLCZ696B2233 | C3002539 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2021-08-04 05:30 | DB On hold |  |  |  | 2021-02-24 05:30 | 2017-09-05 05:30 |  | Stopped (with patients) | 2023-01-31 05:30 |  | 2023-03-07 05:30 | 2019-05-14 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED InHouse | NIBR - CVM | Effects of LCZ696 (Sacubitril/ Valsartan, EntrestoÂ®) or Valsartan alone on cardiac hemodynamics in patients with chronic heart failure with reduced ejection fraction (HFrEF) | CLCZ696B2233 Cardiac hemodynamics in HFrEF | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Diego Albrecht | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Cardiac failure congestive | No | Global | Terminated | No | [16 empty] | None of the above
CLCZ696B | CLCZ696B2317 | C1001266 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-10-16 05:30 |  | 2014-07-10 05:30 |  | Completed | 2018-05-01 05:30 | 2017-12-28 05:30 | 2018-04-23 05:30 | 2018-03-15 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter study to evaluate safety and tolerability in patients with chronic heart failure and reduced ejection fraction from PARADIGM-HF receiving open label LCZ696 | OpenLabel_CLCZ696B2317 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Kumar, Nitin | Sengupta, Arijit | Tummalapenta, Venkateswarlu | Nair, Sreesha | Maryam Aalamian-Mattheis | Richard Gerber | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Bhosale, Pritam |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse |  | 2014-10-22 05:30 |  |  | NA | [7 empty] | 40 | 0 |  |  | 0 |  |  |  | 434 | 1 | 0 |  | Heart failure | No | Global | Completed | Yes | [16 empty] | None of the above
CLCZ696F | CLCZ696B2319 | C1001273 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-10-24 05:30 |  | DB Conduct |  |  | 2016-11-03 05:30 |  | 2015-11-19 05:30 |  | Active | 2021-12-31 05:30 | 2022-01-03 05:30 | 2022-01-27 05:30 | 2022-01-27 05:30 | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Multicenter, open-label, study to evaluate safety, tolerability, pharmacokinetics and, pharmacodynamics ofLCZ696 followed by a 52-week randomized, double-blind, parallel group, active-controlled study to evaluate the efficacy and safety of LCZ696 compared with enalapril in pediatric patients from1 month to &lt; 18 years of age with heart failure due to systemic left ventricle systolic dysfunction | PANORAMA_CLCZ696B2319 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Ramachandran, Smita | Ramachandran, Smita | Tummalapenta, Venkateswarlu | Nair, Sreesha | Michele Kocun | Michele Kocun | Rana, Aamir | Shewane, Roshni | Completed | 2020-03-26 05:30 | Study transitioned to Roshni Shewane on 26 Mar 2020. | [10 empty] | Kadam, Sandeep |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse |  | SLLB;#Y1;#Y5;#YR;#ZK |  |  |  |  | Pharma | Novartis | ICON | 2016-10-24 05:30 | 2016-10-24 05:30 | Shewane, Roshni | Iliyas, Mohamed | NA | [7 empty] | 235 | 0 |  |  | 0 |  |  |  | 1260 | 4 | 0 |  | Heart failure | Yes | Global | Open | Yes | [15 empty] | Sundar, N Sushant | None of the above | Yes
CLCZ696F | CLCZ696B2319E1 | C4000507 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-03-15 05:30 | 2019-04-16 05:30 | 2019-04-15 05:30 | DB Conduct | Final DBL | 2029-02-12 05:30 | 2019-05-02 05:30 | 2018-10-31 05:30 | 2018-11-30 05:30 |  | Active | 2023-12-31 05:30 |  | 2029-02-12 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter study to evaluate safety and tolerability of open label LCZ696 in pediatric heart failure patients who have successfully completed the PANORAMA-HF study.Â | CLCZ696B2319E1 PANORAMA OLE | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Jodve, Monika | Ramachandran, Smita | Tummalapenta, Venkateswarlu | Nair, Sreesha | Michele Kocun | Michele Kocun | Bakka, Sandeep | Bakka, Sandeep |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 15Mar2019 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 07Sep2021: No RF impacted due to PPC#03 updates I have raised the snow#51 - RITM2951222 directly for SMT/LSH updates. 7JAN2021: SG: No upcoming tasks. 14Apr2020 : LB pending DTS included in RF and sent for LSH setup on 08Apr2020. 08Apr2020: There are some issues faced by DBD in migrations for the PPC. Will go ahead and finalize the RF for pending LB. 30Mar2020 : Pending DTS LB included and RF ready for finalization . Send mail to Sandeep to confirm PPC changes to include in this version of RF or next version of RF. 27Mar2020 : received LB DTS (PPC) to inclde in RF. 13Jun19 : 3rd party domains pending to be included in rule file | None | None | 2019-05-22 05:30 | Transition Study | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2019-05-28 | Completed | 2019-05-28 05:30 |  | Pre-requisites not met | 2019-05-28 05:30 | 2019-05-28 05:30 | Pre-requisites not met | 2019-08-19 05:30 |  |  |  | 71 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 6 | 19 | 45 | 0 | 104 | 524 | 0 | 156 | 36 | 130 | 690 | 2 | 0 |  | Chronic heart failure | No | Global | Open | Yes | [10 empty] | 2019-05-27 05:30 | [5 empty] | None of the above | Yes
CLCZ696B | CLCZ696B2320 | C1001267 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-11-04 05:30 |  | DB Conduct | Final DBL | 2022-06-24 05:30 | 2016-11-23 05:30 |  | 2016-05-20 05:30 |  | Active | 2022-05-13 05:30 |  | 2022-06-24 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter, randomized, double-blind, active-controlled study to evaluate the effects of LCZ696 compared to valsartan on cognitive functionin patients with chronic heart failure with preserved ejection fraction | CLCZ696B2320 PERSPECTIVE | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | P, Roja Rani | Ramachandran, Smita | Tummalapenta, Venkateswarlu | Nair, Sreesha | Eddie Marriere | Eddie Marriere | Rana, Aamir | Shewane, Roshni | Completed | 2020-05-24 05:30 | Transition completed to Roshni Shewane on 24-May-2020. | [10 empty] | Agavekar, Amit |  | Amit Agavekar | [13 empty] | 0 | OCRDC - Inhouse | No | SLLB |  |  |  |  | Pharma | Novartis | ICON | 2016-11-05 05:30 | 2016-11-05 05:30 | Shewane, Roshni | Iliyas, Mohamed | NA | [7 empty] | 95 | 0 |  |  | 0 |  |  |  | 955 | 12 | 0 |  | Heart failure | Yes | Global | Open | Yes | [16 empty] | None of the above
CLCZ696B_MA | CLCZ696B2401 | C1001671 | Phase IV | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-02-12 05:30 |  | 2015-10-16 05:30 |  | Completed | 2018-06-15 05:30 | 2018-06-20 05:30 | 2018-10-29 05:30 | 2018-10-25 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | ICON | DF CRM | A multicenter, randomized, open label, parallel group study comparing pre-discharge and posT-discharge tReatment initiation with LCZ696 in heArt failure patieNtS with reduced ejectIon-fracTion hospItalized for an acute decOmpensation eveNt (ADHF) (the TRANSITION study) | TRANSITION_CLCZ696B2401 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Muniyappa, Poornima | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha | Satya Konkesa | Mohammed Ali | [15 empty] | Shanmugam, Sharmila |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2016-01-13 05:30 | 2016-01-13 05:30 |  |  | ICON | [7 empty] | 87 | 0 |  |  | 0 |  |  |  | 861 | 1 | 0 |  | Congestive heart failure | No | Global | Completed | Yes | [16 empty] | None of the above
CLCZ696B | CLCZ696B2406 | C3004047 | Phase IV | NCDS_2 |  |  |  | 2019-02-28 05:30 |  | Final DBL | 2022-03-04 05:30 | 2019-07-02 05:30 | 2018-08-30 05:30 | 2018-08-30 05:30 |  | Active | 2022-08-31 05:30 |  | 2022-03-04 05:30 |  | FALSE |  |  |  | Outsourced |  |  | CLCZ696B2406 China Safety Study | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Chiaching Weng | [54 empty] | 40 | 0 |  |  | 0 |  |  |  | 450 | 5 | 0 |  | Heart failure | No | Global | Open | Yes | [16 empty] | None of the above
CLCZ696D | CLCZ696D1301E1 | C4003929 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-03-25 05:30 | 2019-04-15 05:30 | DB Locked | Final DBL Achieved |  | 2019-05-07 05:30 | 2018-12-28 05:30 | 2018-12-24 05:30 |  | Completed | 2019-11-19 05:30 | 2019-11-19 05:30 | 2019-12-20 05:30 | 2019-12-17 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLCZ696D1301E1 JAPAN OLE | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Tsukazaki, Mayuka | Sengupta, Arijit | Tummalapenta, Venkateswarlu | Nair, Sreesha | YUJI HACHIYA | YUJI HACHIYA | Yadav, Priyanka | Sama, Ashok |  |  |  |  | DRM | Yadav, Priyanka | Maricherla, Vijayroshan | Completed | 14 Jan 20: Study DB Lock achieved | Study Locked | Study Locked | 2019-04-15 05:30 |  | Polagoni, Bharghavi | Garje, Sagar | Amit Agavekar | Completed | 2019-04-16 | Completed | 2019-04-18 05:30 |  |  | 2019-04-18 05:30 | 2019-04-18 05:30 |  | 2019-07-19 05:30 |  |  |  |  | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 1 | 10 | 37 | 0 | 63 | 410 | 0 | 129 | 32 | 114 | 556 | 1 | 0 |  | Chronic heart failure | No | Global | Wind Down | Yes | [10 empty] | 2019-04-18 05:30 |  |  |  | DBL | Sundar, N Sushant | None of the above | Yes
CLCZ696D | CLCZ696D2301 | C1001270 | Phase III | NCDS | OC RDC - Inhouse |  | 2014-06-23 05:30 |  | DB Locked | Final DBL Achieved |  | 2014-07-18 05:30 |  | 2013-06-07 05:30 |  | Completed | 2019-05-31 05:30 | 2019-06-07 05:30 | 2019-07-15 05:30 | 2019-07-13 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter, randomized, double-blind, parallel group, active-controlled study to evaluate the efficacy and safety of LCZ696 compared to valsartan, on morbidity and mortality in heart failure patients (NYHA Class II-IV) with preserved ejection fraction | PARAGON_CLCZ696D2301 | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Sengupta, Arijit | Srinivasan, Subramani | Lateefuddin, Shariff Mohd | Nair, Sreesha | Akiko Inubushi-Molessa | Akiko Inubushi-Molessa | Rana, Aamir | [14 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [12 empty] | Planned for Q3 | 100 | OCRDC - Inhouse | Yes | SLLB;#ZK;#Y1;#Y5 |  |  |  |  | Pharma | Novartis | InHouse |  | 2014-06-23 05:30 |  |  | NA | [7 empty] | 161 | 0 |  |  | 0 |  |  |  | 1356 | 7 | 0 |  | Heart failure | Yes | Global | Open | Yes | [15 empty] | Kadam, Sandeep | None of the above | Yes
CLCZ696D | CLCZ696D2302 | C1001271 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-05-26 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-08-22 05:30 |  | 2017-01-26 05:30 |  | Completed | 2019-10-28 05:30 | 2019-10-28 05:30 | 2019-11-25 05:30 | 2019-11-24 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A 24-week, randomized, double-blind, multi-center, parallel group, active controlled study to evaluate the effect of LCZ696 on NT-proBNP, symptoms, exercise function and safety compared to individualized medical management of comorbidities in patients with heart failure and preserved ejection fraction | PARALLAX_CLCZ696D2302 | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Chatterji, Riteeka | Sengupta, Arijit | Tummalapenta, Venkateswarlu | Nair, Sreesha | Ronda Tawfik | Akiko Inubushi-Molessa | TEMBHARE, HITESH | TEMBHARE, HITESH | [13 empty] | Girvasiya, Shaili |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | Yes | DV;#SV |  |  |  |  | Pharma | Novartis | InHouse | 2017-05-26 05:30 | 2017-05-26 05:30 | Shewane, Roshni | Gehlawat, Priya | NA | [7 empty] | 73 | 0 |  |  | 0 |  |  |  | 1032 | 5 | 0 |  | Heart failure | Yes | Global | Open | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | No
CLCZ696G | CLCZ696G2301 | C1001274 | Phase III | NCDS | OC RDC - Inhouse | 2016-10-24 05:30 | 2016-10-24 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-12-09 05:30 |  | 2016-05-23 05:30 |  | Completed | 2021-04-01 05:30 | 2021-02-26 05:30 | 2021-04-10 05:30 | 2021-04-09 05:30 | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Prospective comparison of Angiotensin Receptor neprilysin inhibitor (ARNI) versus ACE inhibitor trial to Determine Impact on Serious Events after Myocardial Infarction (PARADISE-MI) | CLCZ696G2301 PARADISE-MI post MI | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Kulkarni, Abhijeet | Ramachandran, Smita | Tummalapenta, Venkateswarlu | Nair, Sreesha | Wojciech Smoron | Wojciech Smoron | Killamsetty, Nanari Ram | Meda, Sreelakshmi | [13 empty] | Kommu, Ranjith Kumar |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | Y1;#Y5 | 2021-04-09 05:30 | 2021-04-10 05:30 |  |  | Pharma | ICON | ICON | 2016-10-21 05:30 | 2016-10-21 05:30 | Meda, Sreelakshmi |  | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1362 | 5 | 0 |  | Acute myocardial infarction | Yes | Global | Open | Yes | [14 empty] | DBL |  | None of the above | Yes
CLCZ696I1 | CLCZ696I12201 | C4004932 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-12-01 05:30 | 2019-12-19 05:30 | 2020-01-08 05:30 | DB Conduct | Final DBL | 2023-06-15 05:30 | 2020-01-08 05:30 | 2019-08-01 05:30 | 2019-08-08 05:30 |  | Active | 2023-05-04 05:30 |  | 2023-06-15 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM | A multi-center, randomized, placebo-controlled patient and investigator-blinded study to explore the efficacy of oral sacubitril/valsartan in adult patients with non-obstructive hypertrophic cardiomyopathy (nHCM) | CLCZ696I12201 PIE PoC in HCM | N1 CVM - NIBR | Langlo, Francois | Kumar, Samoj | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Sabine Bregenhorn | Sabine Bregenhorn | Rana, Aamir | Rana, Aamir |  |  | 15-Dec-2021 : Rajshekhar Siripuram will be backup for Aamir till 15-Mar-2022 Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 01Dec19 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 13-Oct-2020: RF_V6.0 is finlized for VS DTS update 25-Sep-2020: LBL DTS included in RF V4.0 and raised SNOW ticket for LSH update in Aug 2020 13-Aug-2020: RF_V3.0 finalized and raised SNOW ticket for LSH update 11-Aug-2020: Added in RF V2.1 and released for peer review on 29-Jul-2020. Waiting for review comments. 06-Jul-2020(Kranthi): No pending issues 28-May-2020: CV1L, VS1L DTSs are added to RF V3.0 18May2020 : Included pending DTS CV1L, VS1L and sent for review 14May2020 : As per the missing form and DTS CV1L, VS1L DTS weer flagged. DBD didnt share the same to incldue in RF. Followed up with DBD. 26-Dec-2019: SNOW05 ticket raised for LSH set up 23-Dec-2019: RF finalized and requested SMT team to initiate DRM SMT files 19Dec19: recieved peer review comments 18Dec19 : Released for peer review (Chandrakala) 06Dec19 : DBD shared unique CRF for Rule file development (3 forms pending inputs from SDTM team) 27-Nov-2019: Study DBP details not found to request the status of the study | None | None | 2019-12-26 05:30 | SDTM annotations delayed | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2019-12-27 | Completed | 2020-01-06 05:30 |  |  | 2020-01-07 05:30 | 2020-01-07 05:30 |  | 2020-08-25 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 9 | 46 | 0 | 106 | 487 | 0 | 176 | 37 | 132 | 656 | 4 | 0 |  | Cardiomyopathy | Yes | Global | Open | Yes | [10 empty] | 2020-01-06 05:30 |  |  |  |  | R, Harini | None of the above | Yes
CLDE225A | CLDE225A2201 | C1001275 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2011-06-29 05:30 |  | 2011-03-03 05:30 |  | Completed | 2018-10-01 05:30 | 2018-06-29 05:30 | 2018-08-16 05:30 | 2018-08-20 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | A phase II, randomized double-blind study of efficacy and safety of two dose levels of LDE225 in patients with locally advanced or metastatic basal cell carcinoma Amendment 7- Editorial corrected version | CLDE225A2201/PII/BCC/BOLT | P0 Oncology (Solid Tumors all MA Onc projects) |  | Maji, Dipankar | Purra, Shashikanth | Soni, Suchitra | Hiriyanna, Srinivas |  | Yan Zhou | Oguri, Praveen | [14 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse |  | 2011-06-07 05:30 |  |  | NA | [7 empty] | 121 | 0 |  |  | 0 |  |  |  | 413 | 15 | 0 |  | Basal cell carcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CLDE225C | CLDE225C2301 | C1001277 | Phase II | NCDS | [7 empty] | 2013-05-06 05:30 |  | 2012-08-17 05:30 |  | Completed |  | 2016-10-05 05:30 |  | 2016-11-15 05:30 | FALSE |  |  |  | InHouse |  | A Phase II, multi-center, open-label, single-arm study of the efficacy and safety of oral LDE225 in patients with Hhpathway activated relapsed medulloblastoma | CLDE225C2301 (CLIMB)/PIII/MB/L1-C (Temodar) | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Yan Zhou | [15 empty] | Agavekar, Amit | [16 empty] | OCRDC - Inhouse | No | -NA- | [31 empty] | Medulloblastoma | No | Global | Completed | Yes | [16 empty] | None of the above
CLDE225A0 | CLDE225X2116 | C1001682 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2013-05-08 05:30 |  | 2013-02-05 05:30 |  | Completed | 2018-04-10 05:30 | 2018-04-10 05:30 | 2018-06-04 05:30 | 2018-06-05 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A Phase Ib/II, open-label, multi-center, dose-finding study to assess the safety and efficacy of the oral combination of LDE225 and INC424 (Ruxolitinib) in patients with myelofibrosis | CLDE225X2116/PI/MF/L1-C (Ruxolitinib) | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Panda, Bidyuta Prabhat | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh | Janet Taylor; Savita Bharathy | Savita Bharathy | Choppadandi, Kranthikumar | [14 empty] | Agavekar, Amit |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | InHouse |  | 2013-04-29 05:30 |  |  | NA | [7 empty] | 197 | 0 |  |  | 0 |  |  |  | 389 | 6 | 0 |  | Myelofibrosis | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A1201 | C3003060 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-08-21 05:30 |  | 2015-01-20 05:30 |  | Completed | 2018-06-28 05:30 | 2018-05-24 05:30 | 2018-07-18 05:30 | 2018-07-17 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II, Multi-center, Open-label, Single-Arm Study to Evaluate the Efficacy and Safety of Oral LDK378 Treatment for Patients with ALK-Positive Non-Small Cell Lung Cancer previously treated with alectinib | Japan_CLDK378A1201-NSCLC-ALK-post_Alectinib-L2-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Kikawa, Mirai | Satoor, Deepti | Regula, Ramakrishna | Hiriyanna, Srinivas | MASAYUKI ITO | MASAE KAI | Bakka, Sandeep | [14 empty] | Mettugari, Sai Krishna |  | Sushant Sundar | [21 empty] | ONC | Novartis | InHouse | 2015-04-24 05:30 | 2015-04-24 05:30 |  |  | NA | [7 empty] | 89 | 0 |  |  | 0 |  |  |  | 592 | 2 | 0 |  | Non-small cell lung cancer | No | Local | Completed | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A1401 | C1001687 | Phase IV | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2016-06-27 05:30 | 2019-11-13 05:30 | 2016-03-29 05:30 |  | Active | 2021-11-10 05:30 | 2021-11-10 05:30 | 2021-12-09 05:30 | 2021-12-09 05:30 | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | TBD | CLDK378A1401 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | IROKAWA, TAKURO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | TETSUYA KANAYAMA | HARUKA NISHIOKA | [17 empty] | Sushant Sundar | [28 empty] | Other | [19 empty] | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLDK378A0 | CLDK378A2103 | C1001284 | Phase I | NCDS | OC RDC - Inhouse |  | 2015-05-20 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-10-23 05:30 |  | 2014-09-11 05:30 |  | Completed |  | 2017-12-12 05:30 | 2018-02-20 05:30 | 2018-01-11 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase I, multi-center, open label, drug-drug interaction study to assess the effect of ceritinib on the pharmacokinetics of warfarin and midazolam administered as a two-drug cocktail in patients with ALK-positive advanced tumors including non-small cell lung cancer (NSCLC) | CLDK378A2103-NSCLC-ALKpos-3A4_2C9_DDI-L0-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Kunte, Nahush | Satoor, Deepti | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Tracey McCulloch | Mario Stegert | Subbiah, Bala Azhagan | [14 empty] | Kommu, Ranjith Kumar |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2015-04-29 05:30 | 2015-04-29 05:30 |  |  | NA | [7 empty] | 116 | 0 |  |  | 0 |  |  |  | 652 | 3 | 0 |  | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A2109 | C1001688 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2014-03-07 05:30 |  | 2013-09-30 05:30 |  | Completed |  | 2017-07-27 05:30 | 2017-11-09 05:30 | 2017-11-10 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase I/II, multicenter, open-label, single-arm study of LDK378, administered orally in adult Chinese patients with ALK-rearranged (ALK-positive) advanced non-small cell lung cancer (NSCLC) previously treated with Crizotinib | CLDK378A2109-NSCLC-ALKpos-post_Criz-China-L2-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Patel, MilanKumar | Satoor, Deepti | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Karen Greenshields | Mario Stegert | Yadav, Santosh | [14 empty] | Mettugari, Sai Krishna |  | Sushant Sundar | [21 empty] | ONC | Novartis | InHouse |  | 2014-01-15 05:30 |  |  | NA | [19 empty] | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378B | CLDK378A2112 | C1001287 | Phase I | NCDS | OC RDC - Inhouse |  | 2014-12-08 05:30 |  | DB Locked |  |  | 2015-04-09 05:30 |  | 2014-09-25 05:30 |  | Completed | 2020-03-07 05:30 | 2020-03-06 05:30 | 2020-04-13 05:30 | 2020-04-13 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A Phase I, multi-center, randomized open label study to&#xD; assess the systemic exposure and safety of 450 mg&#xD; ceritinib taken with a low-fat meal and 600 mg ceritinib&#xD; taken with a low-fat meal as compared with that of 750 mg&#xD; ceritinib taken in the fasted state in adult patients with ALK&#xD; rearranged (ALK-positive) metastatic non-small cell lung&#xD; cancer (NSCLC) | CLDK378A2112-NSCLC-ALKpos-capsule_food-L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Yamjala, Karthik | Satoor, Deepti | Soni, Suchitra | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Joshi, Alekhya | Joshi, Alekhya | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | ZK;#ZK02;#ZK03 |  |  |  |  | ONC | Novartis | InHouse |  | 2014-12-08 05:30 | Kanchi, Pavan kumar | Shewane, Roshni | ICON | [7 empty] | 108 | 0 |  |  | 0 |  |  |  | 735 | 10 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A2120C | C1001278 | Phase I | NCDS | OC RDC - Inhouse | 2015-04-01 05:30 | 2015-04-01 05:30 |  | DB Conduct | Final DBL | 2023-02-10 05:30 | 2015-05-27 05:30 |  | 2014-12-18 05:30 |  | Active | 2022-12-30 05:30 |  | 2023-02-10 05:30 |  | FALSE | None | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A multi-center, open-label study to assess the safety and efficacy of combination ceritinib (LDK378) and nivolumab in adult patients with anaplastic lymphoma kinase (ALK)- positive non-small cell lung cancer (NSCLC) | CLDK378A2120C NSCLC ALKpos in combo with Nivo | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Mothali, Hameed Sadiq | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Oguri, Praveen | Shewane, Roshni | Not Started |  | Transition checklist not shared to Transition DBD Roshni Shewane. | [10 empty] | Manoharan, Vivek |  | Sushant Sundar | [13 empty] | 0 | OCRDC - Inhouse | No | ZK;#ZK02;#ZK03 |  |  |  |  | ONC | Novartis | InHouse | 2015-04-02 05:30 | 2015-04-02 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 190 | 0 |  |  | 0 |  |  |  | 711 | 6 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CLDK378D | CLDK378A2121 | C1001690 | Phase I | NCDS | [7 empty] | 2017-01-03 05:30 |  | 2016-04-08 05:30 |  | Completed |  | 2017-03-16 05:30 |  | 2017-06-07 05:30 | FALSE |  |  |  | Outsourced |  | A randomized, open-label, three-period, six-sequence crossover study to assess the relative bioavailability of 750 mg ceritinib tablets (2 x 375 mg tablets) administered with either a low-fat low-calorie or high-fat high-calorie meal compared to under fasting condition in healthy subjects. | CLDK378A2121-HV-tablet_rel_BA_food-L0-M | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Flavia Kiertsman; Janet Lasher | Flavia Kiertsman | [15 empty] | Agavekar, Amit | [50 empty] | Lung cancer metastatic | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378D | CLDK378A2122 | C1001691 | Phase I | NCDS | [7 empty] | 2017-01-04 05:30 |  | 2016-01-27 05:30 |  | Completed |  | 2017-04-03 05:30 |  | 2017-05-24 05:30 | FALSE |  |  |  | Outsourced |  | A randomized, open-label, two-cohort, two-period crossover study to assess the bioequivalence between ceritinib FMI tablets and ceritinib FMI capsules at 450 mg (3 x 150 mg tablets vs. 3 x 150 mg capsules) and 600 mg (2 x 300 mg tablets vs. 4 x 150 mg capsules) in healthy subjects under fed state | CLDK378A2122-HV-tablet_fed_BE-L0-M | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Flavia Kiertsman; Janet Lasher | Flavia Kiertsman | [15 empty] | Varate, Rohit | [50 empty] | Lung cancer metastatic | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A2201 | C1001280 | Phase II | NCDS | [7 empty] | 2012-11-26 05:30 |  | 2012-08-10 05:30 |  | Completed |  | 2016-03-29 05:30 |  | 2016-04-11 05:30 | FALSE |  |  |  | InHouse |  | A phase II, multicenter, single-arm study of oral LDK378 in adult patients with ALK-activated non-small cell lung cancer | CLDK378A2201-NSCLC-ALKpos-post_Criz_chemo-L3-M | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Massimiliano Quadrigli | Massimiliano Quadrigli | [15 empty] | Chakravarthy, Praveen J | [50 empty] | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378B | CLDK378A2203 | C1001288 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2012-12-20 05:30 |  | 2012-08-10 05:30 |  | Completed | 2018-01-29 05:30 | 2018-01-22 05:30 | 2018-05-02 05:30 | 2018-04-27 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase II, multicenter, single-arm study of oral LDK378 in crizotinib naive adult patients with ALK-activated non-small cell lung cancer | CLDK378A2203-NSCLC-ALKpos-Criz_naive_post_CT-L2-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Jayavaram, Pavan | Satoor, Deepti | Biswas, Koushik | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Malisetty, Sagarika | [14 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse |  | 2012-11-27 05:30 |  |  | NA | [7 empty] | 113 | 0 |  |  | 0 |  |  |  | 479 | 7 | 0 |  | Non-small cell lung cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLDK378C | CLDK378A2205 | C1001692 | Phase II | NCDS | OC RDC - Inhouse |  | 2015-01-04 05:30 |  | DB Locked |  |  | 2015-04-01 05:30 |  | 2014-08-04 05:30 |  | Completed | 2019-02-14 05:30 | 2019-02-06 05:30 | 2019-03-08 05:30 | 2019-03-18 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | Solid Tumor | A phase II, Multi-center, Open-label, five-arm study to evaluate the efficacy and safety of oral ceritinib treatment for patients with ALK-positive non-small cell lung cancer (NSCLC) metastatic to the brain and/or to leptomeninges | CLDK378A2205 NSCLC ALKpos brain mets | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Patel, MilanKumar | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Narasetty, Indumathi | [14 empty] | Genga, Vardhini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2015-01-28 05:30 | 2015-01-28 05:30 |  |  | NA | [7 empty] | 134 | 0 |  |  | 0 |  |  |  | 759 | 8 | 0 |  | Non-small cell lung cancer | Yes | Global | Completed | Yes | [14 empty] | DBL | Shah, Manasi | None of the above | Yes
CLDK378B | CLDK378A2301 | C1001286 | Phase III | NCDS | OC RDC - Inhouse | 2013-06-20 05:30 | 2013-06-24 05:30 |  | DB Conduct | Final DBL | 2024-05-16 05:30 | 2013-07-09 05:30 |  | 2013-03-25 05:30 |  | Active | 2023-12-14 05:30 |  | 2024-05-16 05:30 |  | FALSE | Not Specified | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase III multicenter, randomized study of oral LDK378 versus standard chemotherapy in previously untreated adult patients with ALK rearranged (ALK-positive), stage IIIB or IV, non-squamous non-small cell lung cancer | CLDK378A2301 NSCLC ALKpos vs chemo 1L | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Darapureddy, Dilip Kumar | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Govula, Shashikanth | Gehlawat, Priya | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [12 empty] | Planned for Q3 | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2013-06-24 05:30 | Gehlawat, Priya | Mareedu, Vasu | NA | [7 empty] | 146 | 0 |  |  | 0 |  |  |  | 809 | 9 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A2303 | C1001279 | Phase III | NCDS | OC RDC - Inhouse | 2013-12-12 05:30 | 2013-12-12 05:30 |  | DB Conduct | Final DBL | 2024-02-14 05:30 | 2013-06-28 05:30 |  | 2013-03-23 05:30 |  | Active | 2023-12-15 05:30 |  | 2024-02-14 05:30 |  | FALSE | Not Specified | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase III, multicenter, randomized, open-label study of oral LDK378 versus standard chemotherapy in adult patients with ALK-rearranged (ALK-positive) advanced non-small cell lung cancer who have been treated previously with chemotherapy (platinum doublet) and crizotinib | CLDK378A2303 NSCLC ALKpos vs chemo 2L criz | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Angom, Promila | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Bakka, Sandeep | Shewane, Roshni | Completed | 2020-07-13 05:30 | Study Transitioned to Roshni Shewane on 13-Jul-2020. | [10 empty] | Manoharan, Vivek |  | Sushant Sundar | [12 empty] | Planned for Q3 | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2013-06-20 05:30 | Shewane, Roshni |  | NA | [7 empty] | 140 | 0 |  |  | 0 |  |  |  | 853 | 7 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLDK378A_MA | CLDK378A2402 | C1001683 | Phase III | NCDS | OC RDC - Inhouse |  | 2013-10-18 05:30 | 2019-03-07 05:30 | DB Locked | Final DBL Achieved |  | 2013-10-18 05:30 | 2018-10-18 05:30 | 2013-05-29 05:30 |  | Completed | 2018-08-31 05:30 | 2018-08-29 05:30 | 2018-12-24 05:30 | 2018-11-09 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | An open-label, multi-center, Expanded Treatment Protocol (ETP) of oral LDK378 in adult patients with non-small cell lung cancer (NSCLC) characterized by ALK positivity | CLDK378A2402 NSCLC ALKpos | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Vaibhav, Soni | Bagayatkar, Rupali Sudesh | Gracey Sugunan, Unni Krishnan | Hiriyanna, Srinivas | Yulia Hirschberg | Yulia Hirschberg | Choppadandi, Kranthikumar | [14 empty] | Kommu, Ranjith Kumar |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse |  | 2013-08-13 05:30 |  |  | NA | [7 empty] | 42 | 0 |  |  | 0 |  |  |  | 487 | 1 | 0 |  | Non-small cell lung cancer | No | Global | Completed | No | [16 empty] | None of the above
CLDK378A_MA | CLDK378A2407 | C1001684 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-05-06 05:30 |  | 2015-04-28 05:30 |  | Completed | 2018-08-23 05:30 | 2018-08-20 05:30 | 2018-10-03 05:30 | 2018-10-12 05:30 | FALSE | no | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | A Phase II, Open Label, Multi-Center, Multi-Arm Study of Ceritinib in Patients with Advanced Solid Tumors and Hematological Malignancies Characterized by Genetic Abnormalities of Anaplastic Lymphoma Kinase (ALK) | CLDK378A2407 Rare indications ALKpos | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Marchand, Matthieu | Bagayatkar, Rupali Sudesh | Gracey Sugunan, Unni Krishnan | Hiriyanna, Srinivas | Yulia Hirschberg | Yulia Hirschberg | Bakka, Sandeep | [14 empty] | Kommu, Ranjith Kumar |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2016-03-21 05:30 | 2016-03-21 05:30 |  |  | NA | [7 empty] | 96 | 0 |  |  | 0 |  |  |  | 652 | 2 | 0 |  | Anaplastic large-cell lymphoma; Breast cancer; Glioblastoma multiforme; Inflammatory myofibroblastic tumour | No | Global | Terminated | Yes | [16 empty] | None of the above
CLDK378A | CLDK378A2X01B | C1001685 | Phase IV | NCDS | OC RDC - Inhouse | 2012-04-27 05:30 | 2012-04-27 05:30 |  | DB Conduct | Final DBL | 2025-07-21 05:30 | 2015-12-11 05:30 |  | 2015-06-24 05:30 |  | Active | 2025-06-09 05:30 |  | 2025-07-21 05:30 |  | FALSE | Rollover study | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | An open label, multi-center LDK378 roll-over protocol for patients who have completed a previous Novartis sponsored LDK378 study and are judged by the investigator to benefit from continued LDK378 treatment. | CLDK378A2X01B-RollOver | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Jagani, Dhara Bhupendra | Satoor, Deepti | Sharma, Atul | Hiriyanna, Srinivas | Vanessa Giannone | Vanessa Giannone | Katam, Veera Nagendra | Yadav, Santosh |  | 2020-04-08 05:30 | [11 empty] | Sundar, N Sushant |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | ICON | 2015-09-16 05:30 | 2015-09-16 05:30 | Mareedu, Vasu | Shewane, Roshni | NA | [7 empty] | 24 | 0 |  |  | 0 |  |  |  | 282 | 1 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLDK378A0 | CLDK378X2103 | C1001283 | Phase I | NOVDD | Other |  |  |  | DB Locked |  |  | 2013-08-28 05:30 |  | 2012-11-27 05:30 |  | Completed | 2019-04-29 05:30 | 2019-04-26 05:30 | 2019-06-11 05:30 | 2019-06-07 05:30 | FALSE | Non priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase I, open label, dose escalation study of LDK378 in pediatric patients with malignancies that have a genetic alteration in anaplastic lymphoma kinase (ALK) | CLDK378X2103-ALKpos-pediatric-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Satoor, Deepti | Satoor, Deepti | Soni, Suchitra | Hiriyanna, Srinivas | Nathalie Guichard | Kevin Dec |  | Gandla, Prashanth | [15 empty] | Sushant Sundar | [28 empty] | Syneos Health | Oncology | AP21 | INC | Donna.Cockram@INCResearch.com | novartis.com>; Earlier DBD: Brinda Shree | [14 empty] | Neuroblastoma recurrent | No | Global | Open | Yes | [16 empty] | None of the above
CLDT600A | CLDT600A2306 | C1001289 | Phase III | NCDS | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2014-10-31 05:30 |  | 2018-04-11 05:30 |  | Completed | 2019-01-31 05:30 | 2019-01-09 05:30 | 2019-02-27 05:30 | 2019-02-15 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A randomized, double-blind, 104-weeks treatment study to evaluate the efficacy, safety, tolerability and pharmacokinetics of telbivudine oral solution and tablets in children and adolescents with compensated HBeAg-positive and negative chronic hepatitis B virus infection, | Eff - Saf Study in Hep B Child-Adol_CLDT600A2306 | P6 Global Health | Vithala, Srinivas | Varshney, Kapil | Bhabhe, Nikhil | Tummalapenta, Venkateswarlu | Krishnan, Kripesh |  | Abhishek Sople | Bonam, Rajesh Babu | [16 empty] | Sai Krishna Mettugari | [21 empty] | Pharma | Novartis | InHouse |  |  |  |  | NA | [7 empty] | 49 | 0 |  |  | 0 |  |  |  | 665 | 4 | 0 |  | Hepatitis B | No | Global | Open | Yes | [16 empty] | None of the above
CLDT600A | CLDT600A2409 | C3001249 | Phase IV | NOVDD | [7 empty] | 2011-03-21 05:30 |  | 2010-08-31 05:30 |  | Completed |  | 2015-12-10 05:30 |  | 2016-05-20 05:30 | FALSE |  |  |  | Outsourced |  | A Randomized, Open-label, 156-week Treatment Study to Evaluate the efficacy and safety of Telbivudine or Tenofovir Treatment in HBeAg-negative Chronic Hepatitis B patients Based on the Roadmap Concept. Short description: Core + Extension Study (2+1yr) LdT vs TDF in HBeAg negative pats with roadmap strategy | Efficacy and Safety of Telbivudine_CLDT600A2409 | P6 Global Health | [73 empty] | Hepatitis B | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2109 | C1001294 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-03-25 05:30 |  | 2014-11-14 05:30 |  | Completed |  | 2017-01-09 05:30 |  | 2017-03-17 05:30 | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | : A phase I, open label, multi-center, parallel cohort, single dose study to evaluate the pharmacokinetics of LEE011 in healthy subjects with normal hepatic function and subjects with impaired hepatic function | CLEE011A2109 PK/HV-Hepatic Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vavasseur, Celine | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Karen Greenshields | Mihaela Gazdoiu | [17 empty] | Sushant Sundar | [28 empty] | PPD | [19 empty] | Hepatic impairment | No | Local | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2112C | C1001290 | Phase I | NCDS | [7 empty] | 2014-06-27 05:30 |  | 2014-03-14 05:30 |  | Completed |  | 2016-10-26 05:30 |  | 2016-12-16 05:30 | FALSE |  |  |  | InHouse |  | A Phase I dose escalation study of LEE011 in combination with buparlisib and letrozole for the treatment of HR+, HER2-negative post-menopausal women with locally advanced or metastatic breast cancer | CLEE011A2112C mBC/HRpos/HER2neg/L2 | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Mihaela Gazdoiu | [15 empty] | Varate, Rohit | [16 empty] | OCRDC - Inhouse | [33 empty] | Breast cancer metastatic | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2115C | C1001291 | Phase I | NCDS | OC RDC - Inhouse |  | 2014-10-15 05:30 |  | DB Conduct | Final DBL | 2022-09-23 05:30 | 2015-02-04 05:30 |  | 2014-09-10 05:30 |  | Active | 2022-08-12 05:30 |  | 2022-09-23 05:30 |  | FALSE | ASMO publication | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase Ib dose escalation study of the combination of LEE011 with letrozole and dose expansion of LEE011 with hormonal therapy for the treatment of pre-(with goserelin) and postmenopausal women with hormone receptor positive, HER2-negative, advanced breast cancer | CLEE011A2115C mBC/HRpos/HER2neg | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Gwendolyn Gobbo | Gwendolyn Gobbo | Iliyas, Mohamed | Maricherla, Vijayroshan | [13 empty] | Challa, Nandini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2014-12-19 05:30 | Gehlawat, Priya | Gehlawat, Priya | NA | [7 empty] | 168 | 0 |  |  | 0 |  |  |  | 533 | 6 | 0 |  | Breast cancer | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2116 | C1001295 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-10-23 05:30 |  | 2015-01-28 05:30 |  | Completed | 2018-05-31 05:30 | 2018-05-11 05:30 | 2018-08-10 05:30 | 2018-08-10 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase I, open label, multicenter, parallel-group, single dose two-staged study to evaluate the pharmacokinetics and safety of a single 400 mg oral dose of LEE011 in subjects with varying degrees of impaired renal function compared to matched healthy volunteers with normal renal function | CLEE011A2116 PK/HV-Renal Impairment | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vaishnav, Deepti | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas |  | Mihaela Gazdoiu |  | Sinha, Deepakshi | [15 empty] | Sushant Sundar | [28 empty] | PPD | Oncology | AP21 | PPD | prince.kelly@ppdi.com | Earlier DBD: Shelly Antle /Jugnu; interim database lock for part 1 of CLEE011A2116 has occurred. No update on Final DBL date | [14 empty] | Renal impairment | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2117 | C1001296 | Phase I | NCDS | CRO - EDC |  |  | 2018-05-29 05:30 | DB Locked |  |  | 2018-05-31 05:30 |  | 2017-05-11 05:30 |  | Completed | 2018-10-01 05:30 | 2018-09-10 05:30 | 2018-10-22 05:30 | 2018-10-15 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase I, single center, two-period, two-treatment, open-label, randomized cross-over study to investigate the absolute bioavailability of a single oral dose of 600 mg of ribociclib (LEE011) compared with an intravenous (i.v.) infusion of 150 mg ribociclib in healthy subjects | CLEE011A2117 + PK/HV-AbsBA | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vaishnav, Deepti | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Priya Deshpande | Priya Deshpande | Marx, Karl | [14 empty] | Agavekar, Amit |  | Sushant Sundar | [14 empty] | CRO | No | -NA- |  |  |  |  | ONC | Novartis | InHouse |  |  |  |  | Parexel | [7 empty] | 94 | 0 |  |  | 0 |  |  |  | 339 | 2 | 0 |  | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2206 | C3000314 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-17 05:30 | 2018-08-31 05:30 | DB Conduct | Final DBL | 2024-01-05 05:30 | 2018-08-29 05:30 |  | 2017-04-24 05:30 |  | Active | 2023-12-13 05:30 |  | 2024-01-05 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase II randomized, double blind, placebo-controlled study of LEE011 (ribociclib) or placebo in combination with endocrine therapy for the treatment of premenopausal and postmenopausal Chinese women with hormone receptor positive, HER2-negative advanced breast cancer, including a subset with pharmacokinetic analysis. | CLEE011A2206 + mBC/HRpos/HER2-/China | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Lokhande, Deepak Sharadkumar | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Priya Deshpande | Priya Deshpande | Oguri, Praveen | TEMBHARE, HITESH |  |  |  |  | DRM (DIAL) | Oguri, Praveen | Bai, Chandrakala | Completed | 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 24-Feb-2021: Rule File Version 10.0 is finalized and raised SNOW Ticket (RITM2298907). TU1L, RS1L, TR1L were added in Rule File. 15-Feb-2021: Received finalized TU1L, RS1L, TR1L DTS's, Pratheeksha is working on RF update. 21Jan2021: Finalized DTS's not shared yet, requested DBD to share the DTS's. TU1L, TR1L and RS1L DTS's will be included in RF by 22-Jan-2021. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 TU1L, RS1L, TR1L DTSs listed. Please check 05Nov2020: No Activity. 11Sep2020: No Activity. 29Jul2020: IEG001 CRF along with FAMHO001 is added in Version 8.0 Final. 27Jul2020 : IEG001 is flagged in 20thjul report 20Apr2020: OPS002 form included in ODM doamin as per teams request. 17Feb2020 : All forms and Finalized DTS in Rule file. Imaging DTS but currently in development (Not final yet). | None | None | 2018-09-27 05:30 | Legacy Process | Challa, Nandini | Varate, Rohit | Sushant Sundar | Completed | 2018-10-09 | Completed | 2019-06-18 05:30 |  | Study Transition | 2018-10-10 05:30 | 2018-10-10 05:30 | Study Transition | 2019-09-10 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5;#YR;#YD;#ZK | [11 empty] | NA | [5 empty] | 16 | 123 | 85 | 0 | 884 | 1005 | 0 | 348 | 41 | 324 | 1370 | 6 | 0 |  | Breast Cancer | No | Global | Open | Yes | [10 empty] | 2019-06-18 05:30 |  |  |  | Interim-Analysis | Tidke, Shyam | None of the above | Yes
CLEE011A | CLEE011A2207 | C3001294 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-05-21 05:30 | 2019-06-03 05:30 | DB Conduct | Final DBL | 2026-02-10 05:30 | 2019-06-11 05:30 | 2019-02-08 05:30 | 2018-12-12 05:30 |  | Active | 2025-12-30 05:30 |  | 2026-02-10 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Clinical trial to assess the efficacy and safety of an alternative dosing regimen of ribociclib in breast cancer | CLEE011A2207 mBC/HRpos/HER2neg | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Dhamat, Rahul | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Gwendolyn Gobbo | Gwendolyn Gobbo | Oguri, Praveen | TEMBHARE, HITESH |  |  |  |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 27-JUL-2021: RF Version 10.0 finalized for ZL domain as per SDTM requirements. SNOW #51 raised for SMT/LSH updates. 22-JUL-2021: PPC #8 updates are for CF only. No impact of RF, SMT or LSH. 1-JUL-2021: RF Version 9.0 is final in CREDI for PPC#7 updates. SNOW#51 (RITM2702365) raised for SMT and LSH updates. 28-MAY-2021: RF Version 8.0 is final in CREDI for PPC#6 updates. SNOW#51 (RITM2617824) raised for SMT and LSH updates. 23-APR-2021: RF Version 7.0 finalized for FAMH SDTM annotations updated. SNOW#51 (RITM2499863) raised for SMT and LSH updates. 14-APR-2021: RF released for Peer Review. 4-MAR-2021: PPC6 form IA reviewed and comments provided. 3-DEC-2020: RF finalized in CREDI. SNOW#51 raised for SMT and LSH updates. 3-DEC-2020: RF updated for RS1L, TR1L, TU1L and released for Peer Review. 07-JUL-2020: RF Finalized and SNOW# 51 raised for SMT and LSH updates. 06-JUL-2020: RF Peer Review ongoing for PPC3 updates. 06Jul2020: DSG005 flagged in missing report 1JUL2020: RF updated for PPC2 and released for Peer Review. UAT SOD extraction issue, hence unable to validate the RF updates. Waiting till Medidata resolves this issue. 11Jul19: Rule file completed on 20th Jun with pending comments (DDTEST will be fixed via PPC) 06JUN19: Sent for peer review 10JUN2019: Rule file final in CREDI. SNOW#05 raised for LSH set-up. 3-DEC-2019: Rule file final for all DTS and till PPC2. | None | None | 2019-06-10 05:30 |  | Challa, Nandini | Varate, Rohit | Sushant Sundar | Completed | 2019-06-14 | Completed | 2019-06-14 05:30 |  | KPI met - incorrect source date entry (example FPFV) | 2019-06-14 05:30 | 2019-06-14 05:30 | KPI met - incorrect source date entry (example FPFV) | 2019-08-29 05:30 |  |  | 1) Visit and Subject Status table: We don’t have SS domain can we use ODM on behalf-need confirmation from DBP i) Name of assessment variable is missing in aCRF and Jreview NC:Need variable name and form ii) OPSTAT variable is missing in Jreview NC:This not present in the source for LSH, @Catherine,@Angella kindly confirm if this is expected to flow downstream AP: The variable OPSTAT was operational and was approved not to flow downstream. Hence it was dropped at Rule file level. Attached SRF for your reference. 2) Diagnosis and extent of cancer of table Part 1 i) DGCAN, INISTG, CUSTG, FRTPGDAT, HISGR and HISCYT variable is missing in Jreview Could you please let me know the Form name /Domain name[Kobagapu, Shalini] -FAMHO001-Diagnosis and Extent of Cancer These are expected values to be collected in the FATEST_STD column @Catherine: Kindly confirm AP: The variables are renamed to follow the FA domain structure as per the reference SDTM annotations attached. Rule file mapping of variables for “Diagnosis and Extent of Cancer” form as per the SDTM standards. 3) Diagnosis and extent of cancer of table Part 2 i) MTSIYN variable is missing in Jreview Could you please let me know the Form name /Domain name[Kobagapu, Shalini] -FAMHO001-Diagnosis and Extent of Cancer NC: MTSISY is present in the SMT files but MTSIYN is not available. @Angella, Could you please let me know if this is expected to be present.If its present in the ALS , i Will ask the SMT developer to Add this element. AP: Renamed in Rule file as a FA Domain structure. Refer the above screenshot for Rule file mapping of variables for “Diagnosis and Extent of Cancer” form. 4) Prior Antineoplastic Therapy – Medications i) ZT domain is missing – So it’s tough to check the complete table ZTCATL variable length is not defined in SMT,i have asked for The SMT update and In progress, Once fixed , you will have ZT available. NC:ZT is available, no pending action from LSH 5) Prior Antineoplastic Therapy – Radiotherapy i) RDLOCOS variable is missing in Jreview NC: RDLOCOS is not present in the SMT files. @Angella, Could you please let me know if this is expected to be present,If its present in the ALS , i Will ask the SMT developer to Add this Element AP: We do not have any such variable collected in the study. Please re-confirm on the variable name. 6) Concomitant Medications i) CMINDSP variable is missing in Jreview CMINDSP is collected at EDC but at DRM it is not flowing downstream to JReview and GPS. NC:@Catherine: CMINDSP is collected in EDC but as per standards it is not flowing Downstream. 7) Prior or Concomitant non-drug therapies/procedures: i) PRINDSP variable is missing in Jreview NC:@Catherine: Same is scenario like the CMINDSP, PRINDSP is as per standard not flowing downstream. 8) OPPKAG variable is missing in DS domain: NC:@Angella, Could you please let me know if this is OPPKAG expected to be present as element/Column. If its present in the ALS , i Will ask the SMT developer to Add this element AP: OPKKAG is again an operational variable for branching purpose and not flowing downstream. 9) In Post Antineoplastic Therapy – Radiotherapy table:] i) Other Specify variable is missing in Jreview NC: Need more information on the same, Please let me know what is the variable. AP: This is STT variable and should be present in J-review as per Rule file logic. Please re-verify and confirm. 10) Body Fluid/Tissue collection: i) Concern datapage name is missing in JReview NC: Need more information on the same, Please let me know what is the variable. AP: This should be under ZL domain (ZLO001) Study_Name Target_Domain FormOID Logic Target Contributing_Form_Element Seq Target_Element Comment1 Comment2 CLEE011A2207 ZL ZLO001 DIRECT ZL 1 | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 10 | 78 | 78 | 0 | 542 | 1344 | 0 | 371 | 41 | 241 | 1626 | 6 | 0 |  | Breast cancer | No | Global | Open | Yes | [10 empty] | 2019-06-14 05:30 | [5 empty] | HA Commitment | Yes
CLEE011A | CLEE011A2301 | C1001292 | Phase III | NCDS | OC RDC - Inhouse |  | 2013-12-15 05:30 |  | DB Conduct | Final DBL | 2022-10-10 05:30 | 2013-12-17 05:30 |  | 2013-09-23 05:30 |  | Active | 2022-08-31 05:30 |  | 2022-10-10 05:30 |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized double blind, placebo-controlled study of LEE011 in combination with letrozole for the treatment of postmenopausal women with hormone receptor positive, HER2 negative, advanced breast cancer who received no prior hormonal therapy for advanced disease | CLEE011A2301 - mBC/HRpos/HER2neg/L1-C | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Lokhande, Deepak Sharadkumar | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Eva Vagnon | Eva Marie Vagnon | Gehlawat, Priya | Ramaraju, Bhargav | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2013-11-19 05:30 | Gehlawat, Priya | Iliyas, Mohamed | NA | [7 empty] | 91 | 0 |  |  | 0 |  |  |  | 493 | 9 | 0 |  | Breast cancer metastatic | Yes | Global | Open | Yes | [16 empty] | None of the above
CLEE011A_MA | CLEE011A2404 | C1001695 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-10-21 05:30 |  | DB Conduct | Final DBL | 2022-10-17 05:30 | 2016-11-30 05:30 |  | 2016-08-19 05:30 |  | Active | 2022-09-05 05:30 |  | 2022-10-17 05:30 |  | FALSE | Not Applicable | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | An open-label, multicenter, Phase IIIb study of ribociclib (LEE011) in combination with letrozole for the treatment of postmenopausal women with hormone receptor-positive (HR+) HER2-negative (HER2-) advanced breast cancer (ABC) who received no prior hormonal therapy for advanced disease | CLEE011A2404 mBC/HRpos/HER2neg | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Chiluveru, Nagender Reddy | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Yulia Hirschberg | Yulia Hirschberg | Oguri, Praveen | Maricherla, Vijayroshan | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2016-11-10 05:30 | 2016-11-10 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 72 | 0 |  |  | 0 |  |  |  | 758 | 2 | 0 |  | Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CLEE011A | CLEE011A2412B | C4007148 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2022-02-16 05:30 | 2022-02-16 05:30 | 2022-05-24 05:30 | DB Set-Up | Final DBL | 2028-02-14 05:30 |  | 2021-11-30 05:30 | 2021-11-28 05:30 |  | Planned | 2028-01-03 05:30 |  | 2028-02-14 05:30 |  |  | None | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A post-trial access roll-over study to allow access to ribociclib (LEE011) for patients who are on ribociclib treatment in Novartis-sponsored study | CLEE011A2412B Roll-Over Study | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kundaram, Prasad | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Ivanka Zic | Ivanka Zic | Maricherla, Vijayroshan | Maricherla, Vijayroshan | [6 empty] | R, Pratheeksha K | Completed | 17Feb2022: Raised LSH Prod set-up request on 17Feb2022 (SNOW05 Ticket number - RITM3505563) 10Feb2022: Finalized RF in subway and raised LSH test set-up on 9feb2022 (SNOW05 Ticket number - RITM3476870) ALS review comments have been provided and RF development started. | None | None | 2022-02-17 05:30 |  | JAGIRDHAR, NAVYA | Sundar, N Sushant | Sushant Sundar | [13 empty] | 0 | [14 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Advanced breast cancer | No | Global | Open | Yes | 2022-02-09 05:30
CLEE011E | CLEE011E2301 | C1001302 | Phase III | NCDS | OC RDC - Inhouse | 2014-11-11 05:30 | 2014-11-11 05:30 |  | DB Conduct | Final DBL | 2022-08-10 05:30 | 2014-11-20 05:30 |  | 2014-08-05 05:30 |  | Active | 2022-06-30 05:30 |  | 2022-08-10 05:30 |  | FALSE | None | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A Phase III randomized, double blind, placebo-controlled study of LEE011 or placebo in combination with tamoxifen and goserelin or a non-steroidal aromatase inhbitor (NSAI) and goserelin for the treatment of premenopausal women with hormone receptor positive, HER2-negative, advanced breast cancer. | CLEE011E2301 [MONALEESA-7]_mBC/HRpos/HER2-/L1-C | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Marchand, Matthieu | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Melissa Tripodi | Samantha Campbell | Tadiparthy, Ramakanth | Katam, Veera Nagendra |  |  | Ramakanth transitioned to Nagendra | [10 empty] | Agavekar, Amit |  | Sushant Sundar | [12 empty] | DDPASS will be conducted before next Milestone. |  | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | InHouse |  | 2014-11-11 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 178 | 0 |  |  | 0 |  |  |  | 1462 | 14 | 0 |  | Breast cancer | Yes | Global | Open | Yes | [14 empty] | DBL | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CLEE011F | CLEE011F2301 | C1001303 | Phase III | NCDS | OC RDC - Inhouse | 2015-06-04 05:30 | 2015-06-04 05:30 |  | DB Conduct | Interim DBL | 2022-02-23 05:30 | 2015-06-09 05:30 |  | 2015-03-11 05:30 |  | Active | 2022-09-30 05:30 |  | 2022-11-11 05:30 |  | FALSE | IDBL | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | MONALEESA-3: A randomized double-blind, placebocontrolled study of ribociclib in combination with fulvestrant for the treatment of postmenopausal women with hormone receptor positive, HER2-negative, advanced breast cancer who have received no or only one line of prior endocrine treatment | CLEE011F2301 [MONALEESA-3] - mBC/HRpos/HER2-/L1/2- | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Eva Vagnon | Eva Marie Vagnon | Ambati, Purnachander | Mareedu, Vasu |  | 2020-04-08 05:30 | [11 empty] | Challa, Nandini |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | ICON | 2015-06-04 05:30 | 2015-06-04 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 639 | 12 | 0 |  | Breast cancer metastatic | Yes | Global | Open | Yes | [16 empty] | None of the above
CLEE011G | CLEE011G2301 | C1001304 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-06-20 05:30 |  | 2017-02-14 05:30 |  | Completed | 2020-03-05 05:30 | 2020-03-09 05:30 | 2020-04-21 05:30 | 2020-04-21 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Ribociclib + Standard Endocrine therapy in patients with HR+HER2-Early BC at High Risk for Recurrence | CLEE011G2301 BC/HRpos/HER2-/Adjuvant-C [High Risk] | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Poggi, Marie-Line | Vavasseur, Celine | Gupta Bhaya, Soumya Kanti | Hiriyanna, Srinivas | Melissa Tripodi | Susan Poggio | Bakka, Sandeep | Rana, Aamir | [13 empty] | Agavekar, Amit |  | Sushant Sundar | [14 empty] | CRO | No | -NA- |  |  |  |  | ONC | Novartis | Outsourced | 2017-06-13 05:30 |  | Mareedu, Vasu | Gehlawat, Priya | IQVIA | [7 empty] | 87 | 0 |  |  | 0 |  |  |  | 1027 |  |  |  | Breast cancer | Yes | Global | Completed | Yes | [15 empty] | Mettugari, Sai Krishna | None of the above | No
CLEE011H | CLEE011H2301 | C1001305 | Phase III | NCDS_2 | Other |  |  |  |  | Final DBL | 2023-08-02 05:30 |  |  | 2017-02-14 05:30 |  | Stopped (with patients) | 2023-05-25 05:30 |  | 2023-08-02 05:30 |  | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Phase III, multicenter, randomized, double-blind, placebo-controlled study to evaluate efficacy and safety of ribociclib with endocrine therapy as an adjuvant treatment in patients with hormone receptor-positive, HER-2 negative, early breast cancer with intermediate risk of relapse | BC/HRpos/HER2-/Adj-C_CLEE011H2301 Intermed Risk | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Maji, Dipankar | Vavasseur, Celine | Sharma, Atul | Hiriyanna, Srinivas | Sabine Turri | Sabine Turri | [15 empty] | Tidke, Shyam |  | Sushant Sundar | [21 empty] | ONC | Novartis | InHouse | 2017-06-28 05:30 |  |  |  | IQVIA | [19 empty] | Breast cancer | Yes | Global | Completed | Yes | [16 empty] | None of the above
CLEE011O1 | CLEE011O12301C | C4001228 | Phase III | Other | Other |  |  | 2018-12-28 05:30 | DB Conduct | DB Snapshot | 2022-05-03 05:30 | 2018-12-07 05:30 | 2018-10-09 05:30 | 2018-08-27 05:30 |  | Active | 2026-05-29 05:30 |  | 2026-07-31 05:30 |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | FULL Outsourced | Solid Tumor | Ribociclib + Standard Endocrine therapy in patients with HR+HER2-Early BC at High & Intermediate Risk for Recurrence | CLEE011O12301C BC/HRpos/HER-2/Adjuvant-C | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sawant, Sayli Sunil | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Diana Pelov | Diana Pelov | [17 empty] | Sushant Sundar | [28 empty] | TRIO | [7 empty] | 71 | 0 |  |  | 0 |  |  |  | 943 | 4 | 0 |  | Breast cancer | Yes | Global | Open | Yes | [16 empty] | None of the above
CLEE011Q1 | CLEE011Q12101 | C4009485 | Phase I+II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-08-10 05:30 | Study Planned | DB Go-live | 2022-06-10 05:30 |  | 2022-05-02 05:30 |  |  | Planned | 2028-01-28 05:30 |  | 2028-03-09 05:30 |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Phase I/II multicenter study to assess efficacy and safety of ribociclib (LEE011) in combination with topotecan and temozolomide (TOTEM) in pediatric patients with relapsed or refractory neuroblastoma and other solid tumors | CLEE011Q12101 ped neuroblastoma | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Laugel, Catherine | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Samantha Campbell | Samantha Campbell | Chiranjeevi, Priyanka Boya | Chiranjeevi, Priyanka Boya | [6 empty] | R, Pratheeksha K | Not Started | [7 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Medulloblastoma; Neuroblastoma | No | Global | Open | Yes | [16 empty] | None of the above
CLEE011A | CLEE011X2101 | C1200270 | Phase I | NOVDD | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2010-12-21 05:30 |  | 2010-07-23 05:30 |  | Completed |  | 2017-03-09 05:30 |  | 2017-04-27 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase 1 multicenter, open label, dose-escalation study of oral LEE011 in patients with advanced solid tumors or lymphomas | CLEE011X2101 | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Rowshan Chowdhury | Rowshan Chowdhury | [17 empty] | Rohit Varate | [28 empty] | ICON | [19 empty] | Metastatic neoplasm | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011A | CLEE011X2102 | C1001297 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-05-28 05:30 |  | 2012-11-15 05:30 |  | Completed |  | 2017-06-29 05:30 |  | 2017-08-07 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | TCO | A phase I, multi-center, open-label study of LEE011 in patients with malignant rhabdoid tumors and neuroblastoma | CLEE011X2102 pediatric study | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Rowshan Chowdhury | Rowshan Chowdhury | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Malignant tumour; Neuroblastoma | No | Global | Terminated | Yes | [16 empty] | None of the above
CLEE011A0 | CLEE011X2106 | C1001298 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-09-06 05:30 |  | 2013-05-10 05:30 |  | Completed | 2020-09-11 05:30 | 2020-04-16 05:30 | 2019-01-16 05:30 | 2020-06-29 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase Ib/II of LEE011 in combination with everolimus (RAD001) and exemestane in the treatment of postmenopausal women with estrogen receptor positive Her2 negative locally advanced or metastatic breast cancer. | CLEE011X2106 + mBC/HRpos/HER2- | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Marchand, Matthieu | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas |  | Priya Deshpande |  | Sinha, Deepakshi | [15 empty] | Sushant Sundar | [28 empty] | ICON | Oncology | AP21 | ICON | Lee Ann Shuman (LeeAnn.Shuman@iconplc.com) | Earlier DBD: Brinda Shree | [14 empty] | Breast cancer metastatic | No | Global | Open | Yes | [16 empty] | None of the above
CLEE011A0 | CLEE011X2107 | C1001299 | Phase I | NCDS | OC RDC - Inhouse |  | 2013-09-20 05:30 |  | DB Conduct | Final DBL | 2023-02-15 05:30 | 2013-10-22 05:30 |  | 2013-05-10 05:30 |  | Active | 2022-12-31 05:30 |  | 2023-02-15 05:30 |  | FALSE | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A phase Ib/II, multicenter, study of the combination of LEE011 and BYL719 with letrozole in adult patients with advanced ER+ breast cancer | CLEE011X2107 mBC/HRpos/HER2-/L1 | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Patil, Omprakash | Maradani, Satish | Sharma, Atul | Hiriyanna, Srinivas | Alexandre Weimann | Alexandre Weimann | Meda, Sreelakshmi | Katam, Veera Nagendra | [13 empty] | Challa, Nandini |  | Sushant Sundar | [12 empty] | Planned DDPASS in Q2 | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON |  | 2013-09-20 05:30 |  | Meda, Sreelakshmi | NA | [7 empty] | 244 | 0 |  |  | 0 |  |  |  | 877 | 8 | 0 |  | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLEE011A | CLEE011X2108 | C1001300 | Phase I | NCDS | OC RDC - Inhouse |  | 2014-03-14 05:30 |  | DB Locked | Final DBL Achieved |  | 2014-05-19 05:30 |  | 2013-12-20 05:30 |  | Completed | 2018-04-23 05:30 | 2018-04-17 05:30 | 2018-07-12 05:30 | 2018-07-16 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase Ib/II study of LEE011 in combination with fulvestrant and BYL719 or BKM120 in the treatment of postmenopausal women with hormone receptor positive, HER2 negative locally recurrent or advanced metastatic breast cancer | CLEE011X2108 TCO Breast cancer metastatic study | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Amole, Alexander | N, Ram Kumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Lisa Nardi | Subbiah, Bala Azhagan | [14 empty] | Gandikota, Sree Lakshmi |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse |  | 2014-03-14 05:30 |  |  | ICON | [7 empty] | 215 | 0 |  |  | 0 |  |  |  | 515 | 5 | 0 |  | Breast cancer metastatic | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011K1 | CLEE011X2110C | C1200749 | Phase I+II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-05-14 05:30 |  | 2014-09-01 05:30 |  | Completed | 2018-08-31 05:30 | 2018-09-26 05:30 | 2018-11-30 05:30 | 2018-11-30 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase 1b/II study of the ALK inhibitor ceritinib in combination with the CDK4/6 inhibitor LEE011 in patients with ALK-positive Non Small Cell Lung Cancer | CLEE011X2110C | N7 Oncology - NIBR | Molander, Lei Ann | Parveen, Yasmin | N, Ram Kumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sarah DiDominick | Sarah DiDominick | Tadiparthy, Ramakanth | [14 empty] | Mulla, Afreen |  | Rohit Varate | [21 empty] | ONC | Novartis | InHouse | 2015-01-19 05:30 | 2015-01-19 05:30 |  |  | ICON | [7 empty] | 287 | 0 |  |  | 0 |  |  |  | 566 | 2 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLEE011L1 | CLEE011X2201 | C3000364 | Phase II | NCDS | OC RDC - Inhouse |  |  | 2018-06-08 05:30 | DB Locked | Final DBL Achieved |  | 2015-02-26 05:30 | 2018-10-19 05:30 | 2014-05-09 05:30 |  | Completed | 2019-12-20 05:30 | 2018-02-21 05:30 | 2018-05-02 05:30 | 2018-05-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A randomized, blinded, placebo-controlled, phase II trial of&#xD; LEE011 in patients with relapsed, refractory, incurable&#xD; teratoma with recent progression | CLEE011X_2201 Phase II Germ cell neoplasm study | N7 Oncology - NIBR | Molander, Lei Ann | Amole, Alexander | N, Ram Kumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Mary Ising | Ambati, Purnachander | [14 empty] | Gandikota, Sree Lakshmi |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse |  | 2014-12-19 05:30 |  |  | ICON | [7 empty] | 92 | 0 |  |  | 0 |  |  |  | 497 | 5 | 0 |  | Germ cell neoplasm | No | Global | Completed | Yes | [16 empty] | None of the above
CLEE011N1 | CLEE011X2X01B | C1200472 | Phase II | NCDS | OC RDC - Inhouse | 2016-12-15 05:30 | 2016-12-15 05:30 |  | DB Conduct | Final DBL | 2024-11-12 05:30 | 2016-12-15 05:30 |  | 2016-02-08 05:30 |  | Active | 2024-09-03 05:30 |  | 2024-11-12 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | An open-label, multi-center rollover protocol for patients who have participated in a Novartis-sponsored ribociclib (LEE011) study and are continuing to benefit from ribociclib as single agent or in combination with other investigational treatments | CLEE011X2X01B Rollover Study | N7 Oncology - NIBR | Langlo, Francois | Sotelo, Yadira | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Renee Pashos | Ourania Pashos | Iliyas, Mohamed | Yadav, Santosh | [13 empty] | Rajhans, Khushbu Kumari |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2016-03-29 05:30 | 2016-03-29 05:30 | Iliyas, Mohamed | Gehlawat, Priya | IQVIA | [7 empty] | 27 | 0 |  |  | 0 |  |  |  | 162 | 1 | 0 |  | Breast cancer; Liposarcoma; Melanoma; Neuroblastoma; Non-small cell lung cancer; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CLEX123J | CLEX123J1401 | C1001307 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2009-08-06 05:30 | 2019-04-29 05:30 | 2009-02-12 05:30 |  | Completed | 2023-04-10 05:30 | 2017-05-11 05:30 | 2023-04-10 05:30 | 2017-05-11 05:30 | FALSE |  |  |  | Outsourced |  |  | CLEX123J1401 Japan PMS | P6 Global Health | [6 empty] | YOSHIHISA SATOU | [66 empty] | Treatment-resistant schizophrenia | No | Global | Completed | Yes | [16 empty] | None of the above
CLFG316A0 | CLFG316A2204 | C1200227 | Phase II | NOVDD | [7 empty] | 2012-12-20 05:30 |  | 2011-10-14 05:30 |  | Completed |  | 2017-08-24 05:30 | 2017-11-17 05:30 | 2017-11-21 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A randomized, active-controlled, open-label, multiple-dose, proof-of concept study of intravitreal LFG316 in patients with active non-infectious intermediate-, posterior-, or panuveitis requiring systemic immunosuppressive therapy | CLFG316A2204 | P7 Immunology Hepatology and Dermatology | [5 empty] | Jen Watts | Jen Watts | [66 empty] | Uveitis | No | Global | Completed | No | [16 empty] | None of the above
CLFG316A0 | CLFG316B2101 | C1001308 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-08-26 05:30 |  | 2016-02-19 05:30 |  | Completed |  | 2017-07-19 05:30 | 2017-11-07 05:30 | 2017-11-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | Open-label, parallel-group, drug-drug interaction study in end-stage renal disease patients awaiting kidney transplant to investigate the potential effect of IVIG treatment on the pharmacokinetics and pharmacodynamics of LFG316. | CLFG316B2101 DDI study in patients CLFG316B2101 | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Srinivasan, Subramani | Temgire, Ganesh | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Kristina Wagner | Kristina Wagner | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | [12 empty] | NA | [19 empty] | End stage renal disease | No | Global | Completed | Yes | [16 empty] | None of the above
CLFG316A0 | CLFG316B2102 | C1001309 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-08-10 05:30 |  | 2016-05-12 05:30 |  | Completed |  | 2016-12-27 05:30 |  | 2017-06-09 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA Shared | NIBR - ATI | A randomized, double-blind, placebo-controlled, single ascending dose study to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of intravenously administered LFG316 in healthy subjects. | CLFG316B2102 SAD invest doses >20 mg/kg | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Noemi Giglioli | Noemi Giglioli | [15 empty] | Rathinasabapathy, Mehala |  | Rohit Varate | [28 empty] | NA | [19 empty] | Antibody-mediated rejection | No | Global | Completed | Yes | [16 empty] | None of the above
CLFG316C | CLFG316X2201 | C1001314 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2022-07-08 05:30 | 2015-09-09 05:30 |  | 2015-03-20 05:30 |  | Active | 2022-05-14 05:30 |  | 2022-07-08 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | An open-label proof of concept study to assess the efficacy, safety and harmacokinetics of LFG316, an anti-C5 monoclonal antibody in patients with paroxysmal nocturnal hemoglobinuria (PNH) | CLFG316X2201 PoC in PNH | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Izabela Rozenberg | Izabela Rozenberg | Tripathi, Shakuntala | Bora, Deepthi Reddy | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:abirdeanu@cmedresearch.com | [15 empty] | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes | [16 empty] | None of the above
CLFG316A0 | CLFG316X2202 | C4000733 | Phase II | NOVDD | [7 empty] | 2016-04-22 05:30 | 2018-01-19 05:30 | 2015-05-08 05:30 |  | Stopped (with patients) | 2019-10-18 05:30 | 2017-06-30 05:30 | 2019-11-22 05:30 | 2017-09-29 05:30 | FALSE |  |  |  | FULL Outsourced |  | A randomized, open label, controlled, multiple dose study to evaluate the clinical efficacy, safety, tolerability, pharmacokinetics and pharmacodynamics of LFG316 in\npatients with transplant associated microangiopathy after\nhematopoietic precursor cell transplantation | CLFG316X2202 POC transplant assoc. microangiopathy | P7 Immunology Hepatology and Dermatology | [5 empty] | Nasri Abdallah | Nasri Abdallah | [66 empty] | Bone marrow transplant | No | Global | Completed | No | [16 empty] | None of the above
CPIM447A1 | CLGH447X2101 | C1200141 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-04-25 05:30 |  | 2011-09-28 05:30 |  | Completed | 2019-06-05 05:30 | 2019-06-05 05:30 | 2019-09-30 05:30 | 2019-09-30 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Multi-Center, Open-Label, Dose Escalation, Phase 1 Study of Oral LGH447 in Patients with Relapsed and/or Refractory Multiple Myeloma | CLGH447X2101 TCO Phase 1 Multiple Myeloma study | N7 Oncology - NIBR | Langlo, Francois | Maritz, Henri | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Rebecca Gusek | [17 empty] | Rohit Varate | [28 empty] | IQVIA | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Multiple myeloma | No | Global | Completed | Yes | [16 empty] | None of the above
CPIM447B1 | CLGH447X2102 | C1001698 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-03-20 05:30 |  | 2013-10-09 05:30 |  | Completed | 2019-07-18 05:30 | 2019-04-18 05:30 | 2019-07-18 05:30 | 2019-07-03 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I, multicenter, open-label study of oral LGH447 in patients with acute myeloid leukemia or high risk myelodysplastic syndrome | CLGH447X2102 OTM-PhIb-Dose-Escalation-in-AML-pts | N7 Oncology - NIBR | Langlo, Francois | Maritz, Henri | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Rowshan Chowdhury | Rowshan Chowdhury | [17 empty] | Rohit Varate | [28 empty] | ICON | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Acute myeloid leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CWNT974A1 | CLGK974X2101 | C1200255 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2024-02-20 05:30 | 2011-12-01 05:30 |  | 2011-04-26 05:30 |  | Active | 2023-11-23 05:30 |  | 2024-02-20 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | TCO | A Phase I, open-label, dose escalation study of oral LGK974 in patients with malignancies dependent on Wnt ligand | CLGK974X2101 TCO Ph I Dose Escalation Study | N7 Oncology - NIBR | Langlo, Francois | John, Christina | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Rebecca Gusek | Rebecca Gusek |  | Gupta, Anshu | [15 empty] | Rohit Varate | [28 empty] | PPD | Oncology | BP21 | PPD | Suzanne.Mills@ppdi.com/Marco.Cramarossa@ppdi.com / Susan.McGurn@ppdi.com | Earlier DBD: Asha Rajanna |  |  | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Breast cancer metastatic; Cervical cancer; Colorectal cancer; Melanoma; Pancreatic carcinoma; Solid tumour; Squamous cell carcinoma of head and neck | No | Global | Open | Yes | [16 empty] | None of the above
CLHA510A0 | CLHA510X2201A | C1200658 | Phase I | RAVE_RAW | [7 empty] | 2015-03-03 05:30 |  | 2014-11-03 05:30 |  | Completed |  | 2016-10-18 05:30 |  | 2016-11-16 05:30 | FALSE |  |  |  | Alcon InHouse |  | A randomized, double-masked, vehicle-controlled, proofÂ¿ofÂ¿concept study for topically delivered LHA510 as a maintenance therapy in patients with wet age related macular degeneration | CLHA510X2201A | N8 Ophthalmology - NIBR | [6 empty] | Michael Ferriere | [66 empty] | Age-related macular degeneration | No | Global | Completed | Yes | [16 empty] | None of the above
CLHC165A1 | CLHC165X2101 | C1200282 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2017-12-05 05:30 | 2019-02-27 05:30 | DB Conduct | Final DBL | 2022-05-30 05:30 | 2018-01-31 05:30 |  | 2017-08-03 05:30 |  | Active | 2022-03-21 05:30 |  | 2022-05-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/Ib, open-label, multi-center dose-escalation and dose-expansion study of the safety and tolerability of intratumorally administered LHC165 single agent and in combination with PDR001 in patients with advanced malignancies | CLHC165X2101 Ph I/Ib Advanced Malignancies Study | N7 Oncology - NIBR | Langlo, Francois | Pelloni, Luca | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Carolyn McGarry | Carolyn McGarry | Patnaik, Angella | Rao, S Shashikanth |  |  |  | DB Go-live planned with respect to FPFV Date. | DRM (DIAL) | Patnaik, Angella | Patnaik, Angella | Completed | 8JUL2021: PPC #14 does not have any impact on RF, SMT and LSH. 23SEP2020: IA for PPC12 reviewed and updates highlighted to DBD. There are no RF, SMT , RF updates pertaining to this PPC12 changes requests. 09SEP2020: RF V9.0 finalized for PPC11 updates. SNOW#51 raised for SMT and LSH updates. 02Sep2020 : SDTM confirmation pending for B1O004 form. 19AUG2020: RF V9.0 for PPC11 updates released for Peer Review. 28JUL2020: RF finalized and SNOW#51 raised for SMT And LSH updates. 27JUL2020 : B13L is listed in 20jul report. 23JUL2020: RF updated and released for Peer Review. 07-JUL-2020: RF up to date for all final DTS and PPCs implemented in the study. 06MAY2020: RF updated for adding SSG004 form, peer reviewed, finalized and SNOW#51 raised for SMT and LSH updates. 3-DEC-2019: Rule file final for all final DTS and till PPC7. NGDX DTS not initiated yet. | None | None | 2018-03-15 05:30 |  | Gouni, Harita | Kadam, Sandeep | Rohit Varate | Completed | 2018-03-28 | Completed | 2020-05-07 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-03-29 05:30 | 2018-03-29 05:30 | Pre-requisites not met | 2019-08-28 05:30 |  |  | B1 third party data yet to receive, QC data received and loaded in LSH on 8 March 2019 | 97 | RaveX - Inhouse | Yes | [12 empty] | IQVIA | [5 empty] | 15 | 75 | 137 | 0 | 335 | 1118 | 0 | 278 | 35 | 442 | 1595 | 6 | 0 |  | Colorectal cancer; Malignant melanoma; Pancreatic cancer; Prostatic cancer; Squamous cell carcinoma of head and neck | No | Global | Open | Yes | [10 empty] | 2020-05-07 05:30 | [5 empty] | None of the above
CLHW090A | CLHW090X2102 | C1001315 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-03-21 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-03-10 05:30 |  | 2015-11-30 05:30 |  | Completed | 2018-10-09 05:30 | 2018-10-11 05:30 | 2018-11-20 05:30 | 2018-11-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM | A two part randomized, double-blind, parallel-group, placebo-controlled study to evaluate the renal safety, tolerability and pharmacokinetics of LHW090 in patients with moderately impaired renal function on angiotensin receptor blockers | CLHW090X2102 TM_Renal Impairment | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Bhoite, Raviraj Vijay | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Natalia Baginski | Natalia Baginski | Samuel, Giftson | [14 empty] | Bothe, Dnyanesh |  | Rohit Varate | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2017-03-21 05:30 | 2017-03-21 05:30 |  |  | NA | [7 empty] | 144 | 0 |  |  | 0 |  |  |  | 308 | 5 | 0 |  | Renal impairment | No | Global | Completed | Yes | [16 empty] | None of the above
CLHW090A | CLHW090X2202 | C1200452 | Phase IIA | NOVDD | [7 empty] | 2015-11-04 05:30 |  | 2015-07-29 05:30 |  | Completed |  | 2017-08-17 05:30 |  | 2017-10-06 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A randomized, sponsor open, site and subject double blind, parallel group, placebo-controlled study to evaluate the safety and efficacy of LHW090 after 4 weeks treatment in patients with resistant hypertension | CLHW090X2202 | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Neda Huseinovic | [66 empty] | Uncontrolled hypertension | No | Global | Completed | Yes | [16 empty] | None of the above
CLIF606A1 | CLIF606A12203 | C4008400 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-06-01 05:30 |  | 2022-08-15 05:30 | Study Planned | DB Go-live | 2022-06-01 05:30 |  | 2021-09-24 05:30 | 2021-10-08 05:30 |  | Planned | 2023-08-04 05:30 |  | 2023-09-01 05:30 |  |  | NA | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CLIF606A12203 China bridging study | P5 Ophthalmology | Navarro, Christelle | Pandranki, Ajesh Babu |  | Datta, Debtanu | Krishnan, Kripesh | Angela Xiao | Yi Ni Xiao | Kabra, Pratik Govind | Kabra, Pratik Govind | [5 empty] | Bairagi, Arpita | Bairagi, Arpita | Not Started | [7 empty] | Sai Krishna Mettugari | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 8 | 0 |  | Dry eye | No | Global | Open | Yes
CLIF606A1 | CLIF606A12305 | C4008400 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-06-17 05:30 | Study Planned | DB Go-live | 2022-06-01 05:30 |  | 2021-09-24 05:30 |  |  | Planned | 2023-06-14 05:30 |  | 2023-07-26 05:30 |  |  | NA | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CLIF606A12305 China bridging study | P5 Ophthalmology | Navarro, Christelle |  |  | Datta, Debtanu | Krishnan, Kripesh |  | RYOHEI IWASAKI | [17 empty] | Sai Krishna Mettugari | [36 empty] | 60 | [7 empty] | 700 | 8 |  |  | Dry eye | No
CLIK066B | CLIK066B1201 | C1001322 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-11-09 05:30 | 2017-12-08 05:30 | DB Locked | Final DBL Achieved |  | 2017-12-07 05:30 |  | 2017-05-31 05:30 |  | Completed | 2018-07-25 05:30 | 2018-07-25 05:30 | 2018-10-03 05:30 | 2018-10-03 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized, double-blind, dose-finding study to evaluate the change in weight after 12 weeks treatment with 4 doses of LIK066 compared to placebo in Japanese patients with obesity disease | CLIK066B1201 JPN_DF Ph2b study | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Ohtaka, Masahiro | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha | REIKO TAKAHASHI | RYOHEI IWASAKI | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Mitra, Architakamal |  | Amit Agavekar | [21 empty] | Pharma | Novartis | InHouse | 2017-11-08 05:30 | 2017-11-08 05:30 |  |  | NA | [7 empty] | 76 | 0 |  |  | 0 |  |  |  | 839 | 6 | 0 |  | Obesity | Yes | Local | Completed | Yes | [16 empty] | None of the above
CLIK066A0 | CLIK066B2101 | C1001316 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-06-21 05:30 |  | 2017-03-13 05:30 |  | Completed |  | 2017-07-22 05:30 |  | 2017-08-17 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA | NIBR - CVM | An open-label, single center, single dose study in\nhealthy adult male volunteers to assess the absorption,\nmetabolism, and excretion of a single oral dose of 100 mg\n[14C]LIK066 | CLIK066B2101 hADME in healthy male volunteers | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Mareedu, Vasu | Sneha, Kumari | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Roland Huber | Roland Martin Huber | [15 empty] | Shah, Manasi |  | Rohit Varate | [28 empty] | Cognizant | [19 empty] | Obesity | No | Global | Completed | Yes | [16 empty] | None of the above
CLIK066B | CLIK066B2201 | C1001320 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-04-21 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-05-06 05:30 |  | 2016-08-31 05:30 |  | Completed | 2018-08-13 05:30 | 2018-08-02 05:30 | 2018-09-26 05:30 | 2018-09-20 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized, double-blind, dose-finding study to evaluate the change in weight after 24 weeks of treatment with 8 doses of LIK066 compared to placebo in obese or overweight adults, followed by 24 weeks treatment with 2 doses of LIK066 and placebo | CLIK066B2201_Weight_Loss_DRF | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Varada, Kumar | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha | Maryam Aalamian-Mattheis | Maryam Aalamian-Mattheis | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Genga, Vardhini |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | LB |  |  |  |  | Pharma | Novartis | InHouse | 2017-04-21 05:30 | 2017-04-21 05:30 |  |  | NA | [7 empty] | 85 | 0 |  |  | 0 |  |  |  | 793 | 3 | 0 |  | Obesity | Yes | Global | Completed | Yes | [16 empty] | None of the above
CLIK066A0 | CLIK066B2202 | C1001317 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-04-28 05:30 |  | 2017-01-17 05:30 |  | Completed | 2017-12-18 05:30 | 2018-01-16 05:30 | 2018-02-19 05:30 | 2018-02-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ICON | NIBR - CVM | An open-label, parallel-group study to assess the effect of LIK066 on urinary glucose excretion, pharmacokinetics, safety and tolerability following multiple dose administration in patients with decreased renal function compared to subjects with normal renal function | CLIK066B2202 TM Renal Mechanistic | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois |  | Sneha, Kumari | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Alok Pachori | [15 empty] | Rathinasabapathy, Mehala |  | Rohit Varate | [21 empty] | Pharma | ICON | External Full | 2017-04-28 05:30 | 2017-04-28 05:30 |  |  | ICON | [7 empty] | 69 | 0 |  |  | 0 |  |  |  | 464 | 3 | 0 |  |  |  | Global | Completed | Yes | [16 empty] | None of the above
CLIK066A0 | CLIK066B2203 | C1001318 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-06-21 05:30 |  | 2017-02-03 05:30 |  | Completed |  | 2017-09-04 05:30 | 2017-12-19 05:30 | 2017-12-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA | NIBR - CVM | A randomized, open label, two-part, three-period, cross over study to investigate the effects of carbohydrate in diet and to evaluate supplements on the gastrointestinal tolerability of LIK066 in overweight or obese subjects | CLIK066B2203 TM Diarrhoea Mechanistic | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Jul Schofield | Jul Schofield | [15 empty] | Kommu, Ranjith Kumar |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | Cognizant | [19 empty] | Obesity | No | Global | Completed | Yes | [16 empty] | None of the above
CLIK066B | CLIK066B2204 | C1001321 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-06-23 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-07-25 05:30 |  | 2016-11-23 05:30 |  | Completed | 2018-06-06 05:30 | 2018-06-06 05:30 | 2018-08-08 05:30 | 2018-08-09 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multi-center, randomized, double-blind, parallel-group dose-finding study to assess the effect of 3 doses of LIK066 compared to placebo or empagliflozin in type 2 diabetes meliltus patients with heart failure | CLIK066B2204_Heart_Failure_DRF | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | S, Vijaya Kumar | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Shakil Riaz | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Kadam, Sandeep |  | Amit Agavekar | [14 empty] | OCRDC - Inhouse | [6 empty] | Pharma | Novartis | InHouse | 2017-06-23 05:30 | 2017-06-23 05:30 |  |  | NA | [7 empty] | 78 | 0 |  |  | 0 |  |  |  | 896 | 11 | 0 |  | Heart failure | No | Global | Terminated | Yes | [16 empty] | None of the above
CLIK066B | CLIK066B2205 | C3000334 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  |  | DB On hold |  |  |  |  | 2017-10-12 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLIK066B2205 China Ph2 DRF | P9 Cardiovascular Renal and Metabolism (CRM) | Iyer, Srinarayani | Nadimpalli, Swarna Kumari | Srinivasan, Subramani | Tummalapenta, Venkateswarlu | Nair, Sreesha | RYOHEI IWASAKI | RYOHEI IWASAKI | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Obesity | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CLIK066A0 | CLIK066X2201 | C1001319 | Phase II | NCDS | [7 empty] | 2015-06-05 05:30 |  | 2015-03-09 05:30 |  | Completed |  | 2016-03-25 05:30 |  | 2016-05-20 05:30 | FALSE |  |  |  | ED Outsourced |  |  | CLIK066X2201 PIE PoC 12-week effect on body weight | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Ahmed Amer | [69 empty] | Completed | Yes | [16 empty] | None of the above
CLIK066C1 | CLIK066X2204 | C1200331 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-10-04 05:30 |  | 2017-06-07 05:30 |  | Completed | 2019-11-11 05:30 | 2019-11-14 05:30 | 2020-03-19 05:30 | 2020-03-09 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CLIK066X2204 PIE PoC in phenotypic NASH patients | N1 CVM - NIBR | Langlo, Francois | Bhatkar, Priyanka | Bhatkar, Priyanka | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Martha Watkins | [15 empty] | Sultana, Salma |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | CMED | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Draft | Yes | [16 empty] | None of the above
CLIK066D1 | CLIK066X2205 | C1200308 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-07-24 05:30 |  | 2017-04-12 05:30 |  | Completed | 2018-06-25 05:30 | 2018-06-25 05:30 | 2018-10-05 05:30 | 2018-10-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM |  | CLIK066X2205 PoC in Poly-Cystic Ovary Syndrome | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Neda Huseinovic | [15 empty] | Pagolu, Sahithi Venkata |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [7 empty] | 10 | 0 | [10 empty] | Polycystic Ovarian Syndrome | No | Global | Terminated | Yes | [16 empty] | None of the above
CLJC242A0 | CLJC242A2101 | C3003057 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-11-07 05:30 |  | 2017-09-25 05:30 |  | Completed |  | 2018-01-03 05:30 | 2018-02-21 05:30 | 2018-02-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | A randomized, parallel group, three arm, double-blind, double dummy study to investigate the drug-drug interaction potential between tropifexor (LJN452) and cenicriviroc (CVC) in healthy and healthy but overweight to obese subjects | CLJC242A2101 FIH study CVC + LJN452 | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [15 empty] | Shah, Manasi |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | IQVIA | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLJC242A | CLJC242A2102 | C4007864 | Phase I | NCDS |  |  |  | 2022-08-02 05:30 |  | Final DBL | 2022-11-16 05:30 |  | 2022-06-25 05:30 |  |  | Planned | 2022-10-12 05:30 |  | 2022-11-16 05:30 |  | FALSE |  |  |  | FULL Outsourced |  | Open-label, randomized study of single oral doses of LJC242 in healthy but overweight-to-obese subjects using a 3-treatment, 3-period, 6-sequence, crossover design | CLJC242A2102 - RelBA | P7 Immunology Hepatology and Dermatology | [73 empty] | Non-alcoholic steatohepatitis | No | [19 empty] | None of the above
CLJC242A | CLJC242A2201J | C3002805 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-20 05:30 | 2018-09-06 05:30 | DB Locked | Final DBL Achieved |  | 2018-09-11 05:30 | 2017-11-15 05:30 | 2018-04-11 05:30 |  | Completed | 2020-10-15 05:30 | 2020-10-15 05:30 | 2020-11-23 05:30 | 2020-11-20 05:30 | FALSE | Not DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | Ph 2_CLJC242A2201J | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | Ajit Kore | Ajit Kore | Vedula, Nagendra | Munukutla, Valli |  |  |  |  | DRM (DIAL) | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 10NOV20: RF has been finalized and snow 51 request RITM1976113 has been created Change: FAOBJ = "Preferred Term for Adjudication" for FATESTCD = PRTERM has been added as per SDTM team request. 13OCT20: RF has been finalized and SNOW 51 request RITM1889617 has been created. Change: FAAA domain has been rebuild and AA domain has been removed as per latest SDTM annoations and SRF. 10OCT20: PPC has been completed and RF development is ongoing. 16SEP20: RF developement kept on hold due to some more update needed on Adjudication CRF which requires a PPC. Hence to avaoid duplicate work, DM requested to put RF devlopment on hold. 11SEP20: RF development is ongoing as per PPC7 07JUL20: No pending forms and no pending DTS. RF V9.0 is final, SNOW 51 request RITM1576581 has been creted. 3JUL20: PPC completed on 30JUN20 for LBG001_TR. RF development is ongoing 22MAY2020: Rule file has been finalized and SNOW 51 request has been raised, Included FAAAG001_TR_1. 18MAY2020: Rule file updated and released for peer review (Shashi) 06May2020 : PPC 3 was implemented and released on 03Apr2020 , DBD didn't notified RF developer to include in RF. FAAAG001_TR_1 was identified in missing forms report on 06may2020 and notified DBD.. SDTM annotations pending for this new form to include in RF. Following up with DBD NVE:29 Nov 19: No Pending domains/updates expected. All domains(including 3rd party domains) are final. | None | None | 2018-07-25 05:30 |  | Praveen kumar, Chakka Giri | Sahu, Ahallad | Sandeep Kadam | Completed | 2018-09-14 | Completed | 2019-07-03 05:30 |  |  | 2018-09-14 05:30 | 2018-09-14 05:30 | Study Transition | 2019-08-20 05:30 |  |  | All data ready for DMC | 100 | RaveX - Inhouse | Yes | ZK;#ZK02;#Y1;#Y5 | 2020-11-20 05:30 | 2020-11-24 05:30 | [9 empty] | NA | [5 empty] | 10 | 14 | 51 | 0 | 124 | 577 | 0 | 185 | 32 | 171 | 780 | 11 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [10 empty] | 2019-07-03 05:30 |  |  |  |  | Tidke, Shyam | None of the above | Yes
CLJM716C1 | CLJM716X2102 | C1200241 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2012-09-21 05:30 |  | 2012-02-07 05:30 |  | Completed |  | 2017-08-02 05:30 |  | 2017-09-26 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A multicenter, open-label, dose escalation, Phase I study of LJM716 administered intravenously in combination with trastuzumab in patients with HER2 overexpressing metastatic breast cancer or gastric cancer | CLJM716X2102 | N7 Oncology - NIBR | Molander, Lei Ann | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Mary Ising | Mary Ising | [15 empty] | Sundar, N Sushant |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Breast cancer metastatic | No | Global | Completed | Yes | [16 empty] | None of the above
CLJM716B1 | CLJM716X2103 | C1200515 | Phase I | NCDS | [7 empty] | 2013-07-26 05:30 |  | 2013-03-21 05:30 |  | Completed |  | 2016-06-03 05:30 |  | 2016-09-09 05:30 | FALSE |  |  |  | InHouse |  | A phase Ib/II, open-label study of LJM716 in combination with BYL719 compared to taxane or irinotecan in patients with previously treated esopheageal squamous cell carcinoma | CLJM716X2103 | N7 Oncology - NIBR | [5 empty] | Mary Ising | Mary Ising | [15 empty] | Mettugari, Sai Krishna | [50 empty] | Esophageal cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452A | CLJN452A1301 | C4008906 | Phase III | NCDS_2 |  |  |  | 2021-12-29 05:30 |  | Final DBL | 2024-03-08 05:30 |  | 2021-07-09 05:30 |  |  | Planned | 2024-01-26 05:30 |  | 2024-03-08 05:30 |  | FALSE |  |  |  | InHouse |  |  | CLJN452A1301 Japanese Safety Study | P7 Immunology Hepatology and Dermatology | [6 empty] | RYOHEI IWASAKI | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Non-alcoholic steatohepatitis | No | Global | [18 empty] | None of the above
CLJN452A0 | CLJN452A2101 | C1001328 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-05-02 05:30 | 2018-04-20 05:30 | DB Locked |  |  | 2018-04-20 05:30 |  | 2017-10-19 05:30 |  | Completed | 2018-05-24 05:30 | 2018-05-24 05:30 | 2018-07-11 05:30 | 2018-07-16 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED InHouse | NIBR - ID | An open-label, single center, single dose study in healthy adult male volunteers to assess the absorption, distribution, metabolism, and excretion of a single oral dose of 1 mg [14C]LJN452 | CLJN452A2101 hADME | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palav, Mahesh | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Elizabeth McNamara | Elizabeth McNamara | Kurella, Rakesh Reddy | Kurella, Rakesh Reddy |  |  |  |  | Pre-DRM | Kurella, Rakesh Reddy | Kurella, Rakesh Reddy | Completed | Study Locked | Study Locked | Study Locked | 2018-05-31 05:30 | Legacy Process | Kommu, Ranjith Kumar |  | Rohit Varate | Completed | 2018-06-04 | Not Applicable |  | ​Locked |  | 2018-06-04 05:30 | 2018-06-05 05:30 | Rule file issue or delay | [5 empty] | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 10 | 62 | 62 | 158 | 353 | 616 | 140 | 39 | 224 | 616 | 0 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2103 | C1001329 | Phase I | NCDS |  |  |  | 2019-10-01 05:30 |  |  |  | 2019-10-02 05:30 | 2019-08-16 05:30 | 2019-09-03 05:30 |  | Completed | 2020-01-07 05:30 | 2019-12-16 05:30 | 2020-02-11 05:30 | 2020-02-11 05:30 | FALSE |  |  |  | FULL Outsourced |  |  | CLJN452A2103 DDI CYP3A4 | P7 Immunology Hepatology and Dermatology | [5 empty] | Mollie Watkins | Paola Paganoni | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2104 | C1001330 | Phase I | NCDS | CRO - EDC |  |  | 2018-02-28 05:30 | DB Locked |  |  | 2018-02-28 05:30 |  | 2017-02-15 05:30 |  | Completed | 2018-06-05 05:30 | 2018-05-10 05:30 | 2018-11-05 05:30 | 2018-07-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | A randomized, open-label, single-dose, 3-treatment, 3-period, 6-period, crossover study in healthy subjects to assess the relative bioavailability of the prototype final market image formulation as compared to the clinical service formulation under fasted conditions and to evaluate the effect of food on the pharmacokinetics of LJN452 prototype final market image formulation | CLJN452A2104 2nd relative BA | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Catherine Gray | [15 empty] | Sultana, Salma |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | PPD | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2107 | C1001333 | Phase I | Other | [11 empty] | Planned |  |  |  |  | FALSE |  |  |  | FULL Outsourced |  |  | CLJN452A2107 Renal impairment | P7 Immunology Hepatology and Dermatology | [5 empty] | Mollie Watkins | Martha Watkins | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Terminated | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2108 | C1001334 | Phase I | [12 empty] | Planned |  |  |  |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CLJN452A2108 pH dependent DDI | P7 Immunology Hepatology and Dermatology | [5 empty] | Mollie Watkins | Martha Watkins | [68 empty] | Global | Terminated | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2109 | C1001335 | Phase I | NCDS | CRO - EDC |  |  | 2018-09-25 05:30 | DB Locked |  |  | 2018-09-24 05:30 | 2018-04-23 05:30 | 2018-04-23 05:30 |  | Completed | 2019-09-30 05:30 | 2019-09-25 05:30 | 2019-12-04 05:30 | 2019-12-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A phase 1, open-label, single-dose, multi-center, parallel group study to evaluate the pharmacokinetics of tropifexor (LJN452) in subjects with mild, moderate or severe hepatic impairment compared to healthy control subjects | CLJN452A2109 Hepatic impairment | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | IQVIA | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2110 | C1001336 | Phase I | NCDS | CRO - EDC |  |  | 2018-06-26 05:30 | DB Locked |  |  | 2018-06-26 05:30 | 2018-05-28 05:30 | 2018-05-25 05:30 |  | Completed | 2018-08-20 05:30 | 2018-08-05 05:30 | 2018-10-05 05:30 | 2018-10-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | An open-label, single sequence, two-period cross-over study to assess the pharmacokinetic drug-drug interaction between tropifexor (LJN452) and atazanavir (ATZ) in healthy subjects | CLJN452A2110 DDI UGT inhibitors | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [15 empty] | Praveen kumar, Chakka Giri |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | IQVIA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 450 | 2 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452A2111 | C1001337 | Phase I | Other | [11 empty] | Planned |  |  |  |  | FALSE |  |  |  | FULL Outsourced |  |  | CLJN452A2111 Absolute BA | P7 Immunology Hepatology and Dermatology | [5 empty] | Mollie Watkins | Martha Watkins | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Terminated | Yes | [16 empty] | None of the above
CLJN452A | CLJN452A2113 | C4007493 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-05-08 05:30 | 2020-04-11 05:30 | 2020-07-13 05:30 | DB Locked | Final DBL Achieved |  | 2020-05-29 05:30 | 2020-03-04 05:30 | 2020-03-09 05:30 |  | Completed | 2020-11-06 05:30 | 2020-11-04 05:30 | 2020-12-21 05:30 | 2020-12-22 05:30 | FALSE | Submission | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ID | A randomized, investigator and subject blinded, multi-center, parallel-arm study to determine the safety and tolerability of tropifexor administered in the morning or in the evening to patients with non-alcoholic steatohepatitis (NASH) | CLJN452A2113 - Evening Dose Study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Prasanna, Snehalata | Bhatkar, Priyanka | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Phil Koo | Phillip Koo | Chitransh, Arpit | Sarasani, Chandana | Completed | 2020-05-07 05:30 |  |  | DRM |  | Oguri, Praveen | Completed | 05Nov2020: No Activity. 11Sep2020: No Activity. 11Aug2020 : LBL DTS received on 29Jul2020 and included in RF on same day and finalized. 16Apr2020: RF Finalized and SNOW ticket raised. 14Apr2020 : Released for Peer review (Ashok) 06Apr2020 : RF development planned to complete by this week 19Mar2020 : Received docs for RF development 19Mar2020 : followed up with DBD, Screen UAT completed today and docs will be shared for RF today. 17Feb2020 : Followed up with DBD and yet to receive study specific forms for review. No RF activity started | None | None | 2020-04-16 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-04-21 | Completed | 2020-04-29 05:30 |  |  | 2020-04-30 05:30 | 2020-04-30 05:30 |  | 2020-08-25 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-12-23 05:30 | 2020-12-24 05:30 | [9 empty] | NA | [5 empty] | 3 | 10 | 43 | 0 | 100 | 455 | 0 | 160 | 31 | 147 | 633 | 2 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [10 empty] | 2020-04-28 05:30 |  |  |  | DBL | Adi, Vishnupriya | None of the above | Yes
CLJN452A | CLJN452A2202 | C1001323 | Phase II | NCDS | OC RDC - Inhouse | 2016-07-14 05:30 | 2016-07-14 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-08-01 05:30 |  | 2015-12-17 05:30 |  | Completed | 2020-04-06 05:30 | 2020-04-06 05:30 | 2020-05-06 05:30 | 2020-05-06 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo controlled, 3- part, adaptive design, multicenter study to assess safety, tolerability and efficacy of tropifexor (LJN452) in patients with non-alcoholic steatohepatitis (NASH) | Ph2 DRF_CLJN452A2202 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Jain, Snehil Rajmal | Kadam, Abhishek Vilas | Ninan, Esther | Marilyn Cines | Marilyn Cines | Meda, Sreelakshmi | Meda, Sreelakshmi | [13 empty] | Garje, Sagar |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | ICON | ICON | 2016-07-14 05:30 | 2016-07-14 05:30 | Meda, Sreelakshmi | Rajhans, Khushbu Kumari | NA | [7 empty] | 214 | 0 |  |  | 0 |  |  |  | 851 | 13 | 0 |  | Non-alcoholic steatohepatitis | Yes | Global | Wind Down | Yes | [14 empty] | Interim-Analysis | Shanmugam, Sharmila | None of the above | Yes
CLJN452D1 | CLJN452D12201C | C4002627 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-10-16 05:30 | 2019-11-01 05:30 | 2021-12-15 05:30 | DB Conduct | Final DBL | 2023-06-15 05:30 | 2019-12-11 05:30 | 2019-09-17 05:30 | 2019-09-12 05:30 |  | Active | 2023-05-04 05:30 |  | 2023-06-15 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, parallel-group, multicenter study to assess efficacy, safety, and tolerability of oral tropifexor (LJN452) & licogliflozin (LIK066) combination therapy and to each monotherapy, compared with placebo for treatment of adult patients with nonalcoholic steatohepatitis (NASH) and liver fibrosis | CLJN452D12201C NASH Ph2b platform study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kulkarni, Manish | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | Linda Wraith | Pranjali Gaunker | Vedula, Nagendra | Thomas, Ankit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 16Oct2019 |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 23-Dec-2021: RF v11.0 for LSH issue fix is finalized and SNOW#51- RITM3113933 mended as discussed with LSP. 22-OCt-2021: RF v10.0 for PPC#07 updates finalized. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. DSG005 form now not reflecting in report. issue resolved 26-Apr-2021: Sent email to LSP to confirm on LSH setup for DSG005 form. 22-Feb-2021: RF Version 8.0 finalized and raised SNOW ticket(RITM2289916). 15-Feb-2021: DSG005 CRF added in RF Version 8.0 and shared with team for peer review 21-Jan-2021: MI1L and PR1L DTS's included in RF Version 7.0 and raised SNOW ticket(RITM2179626) on 19-Jan-2021. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 MI1L, PR1L DTSs listed. Please check 05Nov2020: PPC03 Updates received on 05Nov2020, working on RF updates. 11Sep2020: Included MO1L in RF and raised SNOW ticket on 08Sep2020. 02Sep2020 : As per 02Sep2020 missing forms DTS report "MO1L" pending 16Jun2020: Included DTSs QS1L to QS4L & EG1L completed and raised SNow ticket. 27May2020 : Below DTSs are flagged again in the 22may report QS1L to QS4L & EG1L 11May2020 : Received 4 DTSs QS1L to QS4L which are final for RF update. 30Apr2020 : ECG005 form included in v2.0 and snow ticket raised. 01Apr2020 : Reassigned RF from Roshan to Praveen 01Apr2020: No pending activity 03MAR2020: LSH setup completed 09Jan20: SMT development ongoing 17Dec19 : Rule file sent for SMT development 10 Dec 2019: Rule file issues fixed. Awaiting inputs from DBD and TDM on the peer review comments to finalize rule file. 06Dec19 : Released for Peer review (Chandra) 26Nov2019: Pending SDTM annotations for 2 SRFs from lead DBD. | None | None | 2020-01-10 05:30 | DB Set-up Issues | Majumdar, Shreya | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-01-29 | Completed | 2020-01-31 05:30 | All the prerequisites were provided on 28/1/2020. | Study Transition | 2020-01-31 05:30 | 2020-01-31 05:30 | Study Transition | 2020-04-21 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA-;#Y1;#Y5;#ZK;#ZK02;#ZK03 | [11 empty] | NA | [5 empty] | 7 | 14 | 53 | 0 | 134 | 514 | 0 | 179 | 35 | 150 | 699 | 10 | 0 |  | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [10 empty] | 2020-01-30 05:30 | [5 empty] | None of the above
CLJN452E1 | CLJN452E12101 | C4003966 | Phase I | NCDS | CRO - EDC |  |  | 2019-07-08 05:30 | DB Locked |  |  | 2019-06-28 05:30 | 2019-06-04 05:30 | 2019-06-05 05:30 |  | Completed | 2019-11-05 05:30 | 2019-11-05 05:30 | 2019-12-31 05:30 | 2020-01-07 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CLJN452E12101 DDI tropifexor/ 3 external compounds | P7 Immunology Hepatology and Dermatology |  | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Open | Yes | [16 empty] | None of the above
CLJN452A0 | CLJN452X1101 | C1001338 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-03-02 05:30 |  | 2016-12-01 05:30 |  | Completed | 2017-09-15 05:30 | 2017-09-14 05:30 |  | 2017-12-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA Shared JP | NIBR - ID | A randomized, placebo-controlled two-part study to assess safety, tolerability, pharmacokinetics and pharmacodynamics of single ascending and multiple doses of LJN452 in Japanese healthy male subjects | CLJN452X1101 Japan Phase I | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Ohtaka, Masahiro | Khanke, Sanjay | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | YASUYUKI TABEI | YASUYUKI TABEI | [17 empty] | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452B | CLJN452X2201 | C1200741 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-09-09 05:30 |  | 2015-05-13 05:30 |  | Completed | 2018-08-02 05:30 | 2018-08-02 05:30 | 2018-10-23 05:30 | 2018-10-24 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A multi-part, randomized, double-blind, placebo-controlled study to assess the safety, tolerability and efficacy of tropifexor (LJN452) in patients with Primary Biliary Cholangitis. | CLJN452X2201 PoC in PBC | N5 DAx - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Phil Koo | Phillip Koo | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:amotrea@cmedresearch.com | [15 empty] | Biliary cirrhosis primary | No | Global | Completed | Yes | [16 empty] | None of the above
CLJN452C1 | CLJN452X2202 | C1200602 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2016-01-16 05:30 |  | 2015-09-11 05:30 |  | Completed | 2018-03-12 05:30 | 2018-01-25 05:30 | 2018-05-18 05:30 | 2018-05-17 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A double blind, randomized placebo controlled crossover multiple dose study of LJN452 to assess safety, tolerability and efficacy in patients with primary bile acid diarrhea (pBAD). | CLJN452X2202 | N5 DAx - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Prafulla Bhad | Prafulla Bhad | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | mailto:elazarescu@cmedresearch.com |  |  |  | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Bile acid malabsorption | No | Global | Terminated | Yes | [16 empty] | None of the above
CLKA651A1 | CLKA651X2104 | C1200342 | Phase I | RAVE_SDTM |  |  |  |  | DB Locked |  |  | 2016-09-21 05:30 |  | 2016-04-21 05:30 |  | Completed | 2018-02-19 05:30 | 2018-02-15 05:30 | 2018-08-14 05:30 | 2018-03-09 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Alcon InHouse | NIBR - OPHTHA |  | CLKA651X2104 | N8 Ophthalmology - NIBR | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Valerie Brooks | Valerie Brooks | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [28 empty] | NA | [19 empty] | Age-related macular degeneration; Diabetic macular oedema; Retinal vein occlusion | No | Global | Completed | Yes | [16 empty] | None of the above
CLKA651A1 | CLKA651X2202 | C1200306 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-04-29 05:30 | 2019-05-14 05:30 | 2019-05-24 05:30 | DB Conduct | Final DBL | 2022-10-14 05:30 | 2019-01-23 05:30 | 2018-07-19 05:30 | 2018-06-28 05:30 |  | Active | 2022-08-19 05:30 |  | 2022-10-14 05:30 |  | FALSE | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A randomized, active-controlled, subject and investigator-masked, multiple dose proof-of-concept study of intravitreal LKA651 in patients with diabetic macular edema | CLKA651X2202 Macular Edema PoC | N8 Ophthalmology - NIBR | Langlo, Francois | Kulkarni, Aravind Rao | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Neha Thakur; Valerie Brooks | Valerie Brooks | Bonam, Rajesh Babu | TEMBHARE, HITESH |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 29Apr2019 |  | DRM | Sama, Ashok | Kuttoboina, Sujan Kumar | Completed | 25AUG2020: RF finalized and SNOW 51 request has been created. No pending forms and no pending DTS as of today. 14AUG2020: RF development is ongoing. As part of PPC three new forms ZXS007_2,, DSG005 and ZJG002_4 have been added 06Jul2020: RF will be transitioned from Ashok to Sujan 21Apr2020: RF v4.0 is finalized Included all ZX pages in this RF v4.0 and EGG001,EGG001_1 kept as excluded since this pages are removed from DB as part of PPC1. 08Apr2020 : Received all docs from DBD on 06th Apr for RF updates for Pending forms post PPC implementation. one field is designed as non-log for 2 pages which we are facing issues to map in RF, consultaing SDTM programmer. 17Mar2020: RF v3.0 latest is CREDI. Transition completed. SNOW 51 Ticket: RITM1185464 for SMT. 04Mar2020: RF v2.0 updated with only the dts tables. ZX & EG will be updated post PPC completion as confirmed by the study DBD.17Feb2020: The finalized dts(LBL,EG1L,MO1L,MO2L,MO3L) were included in RFv2.0 however, it is not yet finalized in CREDI as we had to include the changes related to ‘EG’, ‘ZX’ crfs as per another mail communication to be completed via PPC. 'EG' forms are being removed from the study DB and also inactivated at sites. hence, will be removed in the upcoming RF v2.0 once PPC completed and ZX included. March2020 : RF transitioned from Chandrakala to Ashok. 13Feb2020 : Sent followup email to DBD including RF developer on PPC status. As per Missing forms and DTSs report below forms and LBL, MO1L, MO2L, MO3L, EG1L DTSs are pending to be included in RF. 17Jan2020: RF v2.0 were removed from CREDI . To update the same after the PPC completion for inclusion on ZX and EG. 26Dec2019: Pending confirmation on ‘EG’ crfs collected in ALS v1.0 from CREDI which is excluded from RFv2.0 as per mail shared to Hitesh and Rajesh. | None | None | 2019-07-09 05:30 | Transition Study and Legacy process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Rohit Varate | Completed | 2019-07-12 | Completed | 2019-07-17 05:30 | Rajesh(28Nov2019): ZX domain is excluded from current rule file version 1.0 and same will be added once after PPC1 implementation. All the Lab DTSs need to be included in upcomming rule file as recently these DTSs got finalized by TDM. 10Dec2019: RF v2.0 to be finalized with updates related to MO, EG and LB as per dts finalized. | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-07-20 05:30 | 2019-07-20 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2020-05-06 05:30 |  |  | 04-Sep-2020: All domains are reviewed and issues must be checked and closed by all line functions | 56 | RaveX - Inhouse | Yes | DV | [11 empty] | NA | [5 empty] | 7 | 13 | 54 | 0 | 136 | 644 | 0 | 197 | 31 | 144 | 819 | 5 | 0 |  | Diabetic macular oedema | No | Global | Open | Yes | [10 empty] | 2019-07-17 05:30 | [5 empty] | None of the above
CLLF580A1 | CLLF580X2102 | C1200750 | Phase I | NCDS | CRO - EDC |  |  | 2018-03-01 05:30 | DB Locked |  |  | 2018-02-26 05:30 | 2018-03-21 05:30 | 2017-11-12 05:30 |  | Completed | 2019-11-13 05:30 | 2019-11-13 05:30 | 2020-04-14 05:30 | 2020-04-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A 12 week Phase Ib Randomized Investigator and Subject Blinded Placebo Controlled Repeat-dose Study of LLF580 | CLLF580X2102 Safety Study in Obese Volunteers | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Amanda Nguyen | Amanda Nguyen | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [19 empty] | Hypertriglyceridaemia; Liver disorder; Obesity | No | Global | Completed | Yes | [16 empty] | None of the above
CLLG783A0 | CLLG783X2101 | C1200664 | Phase I | NOVDD | [7 empty] | 2014-12-19 05:30 |  | 2014-08-25 05:30 |  | Completed |  | 2017-06-09 05:30 |  | 2017-08-08 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A first-in-human randomized, double-blind, placebo-controlled, study to assess the safety, tolerability, pharmacokinetics, and pharmacodynamics of single-ascending doses of LLG783 in healthy subjects | CLLG783X2101 | N1 CVM - NIBR | [5 empty] | Brian Flannery | Brian Flannery | [66 empty] | Peripheral vascular disease | No | Global | Completed | Yes | [16 empty] | None of the above
CLLG783B1 | CLLG783X2201 | C1200656 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-09-20 05:30 |  | 2017-05-15 05:30 |  | Completed | 2018-12-27 05:30 | 2018-12-27 05:30 | 2019-03-22 05:30 | 2019-03-25 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A Patient and Investigator-blinded, randomized, placebo-controlled study of LLG783 in patients with peripheral artery disease (PAD) and intermittent claudication | CLLG783X2201 PAD PoC | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Koeun Im | [15 empty] | Kadam, Sandeep |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [19 empty] | Peripheral vascular disease | Yes | Global | Completed | Yes | [16 empty] | None of the above
CLMB763A0 | CLMB763X2101 | C1200733 | Phase I | NOVDD | [7 empty] | 2015-07-27 05:30 |  | 2015-05-20 05:30 |  | Completed |  | 2016-03-29 05:30 |  | 2016-04-26 05:30 | FALSE |  |  |  | ED Outsourced |  | A first-in-human, randomized, double-blind, placebo controlled, interwoven, two-part study to assess safety, tolerability, pharmacokinetics, and pharmacodynamics of single- and multiple-ascending doses of LMB763 in healthy subjects | CLMB763X2101 FIH SAD/MAD in HV | N5 DAx - NIBR | [5 empty] | Sachin Desai | Sachin Desai | [66 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLMB763A1 | CLMB763X2201 | C1200732 | Phase II | RAVE_SDTM | Rave EDC - Inhouse |  |  |  | DB Locked |  |  | 2016-10-24 05:30 |  | 2016-07-22 05:30 |  | Completed |  | 2018-09-19 05:30 | 2019-04-16 05:30 | 2019-04-16 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Alcon InHouse | NIBR - ID | A randomized, patient and investigator blinded, placebo-controlled, multicenter study to assess the safety, tolerability, pharmacokinetics and efficacy of LMB763 in patients with non-alcoholic steatohepatitis (NASH) | CLMB763X2201 PoC in NASH | N5 DAx - NIBR | Langlo, Francois |  | Young, Pamela | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Lihuei Kao | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK03 | [11 empty] | ICON | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLMB763B1 | CLMB763X2202 | C1202129 | Phase II | NCDS | CRO - EDC |  |  | 2018-12-14 05:30 | DB Conduct |  |  | 2018-12-17 05:30 | 2018-07-13 05:30 | 2018-07-16 05:30 |  | Active | 2021-04-20 05:30 | 2021-05-03 05:30 | 2021-07-08 05:30 | 2021-08-17 05:30 | FALSE | NIBR-GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, patient- and physician-blinded, placebo-controlled, 24-week study to assess the safety, tolerability and efficacy of LMB763 in patients with diabetic nephropathy | CLMB763X2202 PiE PoC in Diabetic Nephropathy | N5 DAx - NIBR | Langlo, Francois | Bhatkar, Priyanka | Bhatkar, Priyanka | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Danielle Spera | Danielle Spera | [15 empty] | Girvasiya, Shaili |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | Y1;#Y5;#ZK;#ZK02;#YD | [11 empty] | CMED | [19 empty] | Diabetic nephropathy | No | Global | Open | Yes | [16 empty] | None of the above
CLME636A | CLME636X2201A | C1200690 | Phase I | RAVE_RAW | [7 empty] | 2015-07-17 05:30 |  | 2015-04-09 05:30 |  | Completed |  | 2016-03-21 05:30 |  | 2016-04-13 05:30 | FALSE |  |  |  | Alcon InHouse |  | A Multicenter, Randomized, Double-Masked, Active-Controlled Study to Evaluate the Safety and Efficacy of A Multicenter, Randomized, Double-Masked, Active-Controlled Study to Evaluate the Safety and Efficacy of LME636 in Patients with Acute Anterior Uveitis | CLME636X2201A | N8 Ophthalmology - NIBR | [5 empty] | Valerie Brooks | Valerie Brooks | [66 empty] | Uveitis | No | Global | Completed | Yes | [16 empty] | None of the above
CLMF237A | CLMF237A1401 | C1001339 | Phase IV | Other | [7 empty] | 2016-01-08 05:30 | 2018-01-19 05:30 | 2015-10-02 05:30 |  | Completed | 2019-02-28 05:30 | 2018-01-16 05:30 | 2019-02-28 05:30 | 2019-02-28 05:30 | FALSE |  |  |  | Outsourced |  | PMS-Special Investigation of vildagliptin/Metformin in Type 2 DM | CLMF237A1401 JPN PMS | P6 Global Health | [5 empty] | MINE KIMURA | MINE KIMURA | [66 empty] | Diabetes mellitus non-insulin-dependent | No | Global | Open | Yes | [16 empty] | None of the above
CLMG324A1 | CLMG324X2201A | C1200657 | Phase I | RAVE_SDTM | [7 empty] | 2015-07-22 05:30 |  | 2014-12-17 05:30 |  | Completed | 2017-09-15 05:30 | 2016-05-20 05:30 | 2017-11-10 05:30 | 2017-12-18 05:30 | FALSE |  |  |  | Alcon InHouse |  | An open-label single ascending dose and randomized double-masked, ranibizumab controlled, safety, tolerability, and efficacy study of intravitreal LMG324 in subjects with neovascular age-related macular degeneration | CLMG324X2201A FIM and PoC study in patients with w | N8 Ophthalmology - NIBR | [5 empty] | Valerie Brooks | Valerie Brooks | [15 empty] | Garje, Sagar | [16 empty] | FSOM - Outsourced | No | ZK03;#ZK | [31 empty] | Macular degeneration | No | Global | Completed | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070A02101 | C4006344 | Phase I | Other | CRO - EDC |  |  | 2021-05-03 05:30 | DB Conduct |  |  | 2021-02-10 05:30 | 2020-11-11 05:30 | 2020-11-24 05:30 |  | Active | 2021-05-25 05:30 | 2021-05-14 05:30 | 2021-06-24 05:30 | 2021-11-18 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A single-center, open-label study to evaluate the absorption, distribution, metabolism, and excretion (ADME) and pharmacokinetics of LMI070 (branaplam) following a single oral dose of 140 mg [14C]branaplam in healthy male participants | CLMI070A02101 hADME | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Huntington's disease | Yes | Global | Open | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070A02102 | C4006826 | Phase I | NCDS | CRO - EDC |  |  | 2020-08-03 05:30 | DB Locked |  |  | 2020-08-06 05:30 | 2019-12-16 05:30 | 2019-12-13 05:30 |  | Completed | 2020-12-18 05:30 | 2020-12-07 05:30 | 2021-02-19 05:30 | 2021-02-12 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CLMI070A02102 HV Clin Pharm SAD | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Patricia Wagner | Patricia Wagner | [15 empty] | Adi, Vishnupriya |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK02 | 2021-06-17 05:30 | 2021-06-18 05:30 | [9 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Huntington's disease | No | Global | Open | Yes | [14 empty] | DBL | Gouni, Harita | None of the above | Yes
CLMI070A0 | CLMI070A02103 | C4007258 | Phase I | Other | CRO - EDC | 2021-04-07 05:30 |  | 2022-05-02 05:30 | Study Planned | Final DBL | 2022-08-30 05:30 |  | 2022-03-02 05:30 |  |  | Planned | 2022-07-12 05:30 |  | 2022-08-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CLMI070A02103 DDI CYP3A4 inducer/inhibitor | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Huntington's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070A02104 | C4007257 | Phase I | Other | CRO - EDC | 2021-06-30 05:30 |  | 2022-04-22 05:30 | Study Planned | Final DBL | 2022-10-20 05:30 |  | 2022-01-14 05:30 | 2022-01-13 05:30 |  | Planned | 2022-08-25 05:30 |  | 2022-10-20 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CLMI070A02104 PK bridging study ped formulation | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Huntington's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070A02105 | C4007671 | Phase I | Other | CRO - EDC | 2021-04-09 05:30 |  | 2023-02-02 05:30 | Study Planned | Final DBL | 2023-09-22 05:30 |  | 2022-10-04 05:30 |  |  | Planned | 2023-07-21 05:30 |  | 2023-09-22 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS |  | CLMI070A02105 DDI study CYP3A4 perpetrator | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Denise Serra | [17 empty] | Rohit Varate | [28 empty] | Other | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Huntington's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070A02106 | C4007252 | Phase I | Other | CRO - EDC | 2021-02-18 05:30 |  | 2023-01-23 05:30 | Study Planned | Final DBL | 2023-07-18 05:30 |  | 2022-10-07 05:30 |  |  | Planned | 2023-05-16 05:30 |  | 2023-07-18 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CLMI070A02106 DDI -UGT | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti |  | Christine Reynolds | [17 empty] | Rohit Varate | [28 empty] | Other | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 700 | 0 | 0 |  | Huntington's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLMI070A | CLMI070A2304 | C4010358 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-11 05:30 | Study Planned | Final DBL | 2023-05-08 05:30 |  | 2022-05-27 05:30 |  |  | Planned | 2023-03-27 05:30 |  | 2023-05-08 05:30 |  | FALSE | Unknown at this stage | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | CLMI070A2304 LMI070A_Umbrella extension study | P4 Neuroscience | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha |  | Tiffany Kunz | [17 empty] | Amit Agavekar | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Spinal muscular atrophy | No | Global | Wind Down | Yes | [16 empty] | None of the above
CLMI070A0 | CLMI070C11101 | C4007450 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-01-09 05:30 | Study Planned | DB Go-live | 2022-10-17 05:30 |  | 2022-07-29 05:30 |  |  | Planned | 2023-06-14 05:30 |  | 2023-08-08 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS |  | CLMI070C11101 ESS JPN | P4 Neuroscience | Langlo, Francois | Oda, Azusa | Mane, Kunal Yashavant | Tanada, Miyako | Gupta Bhaya, Soumya Kanti | TAKAHIRO MURAMOTO | TAKAHIRO MURAMOTO | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Huntington's disease | No | Global | Open | Yes | [16 empty] | None of the above
CLMI070C1 | CLMI070C12203 | C4007229 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-05-10 05:30 | 2021-10-19 05:30 | 2021-12-01 05:30 | DB Conduct | Final DBL | 2025-03-31 05:30 | 2021-12-08 05:30 | 2021-04-09 05:30 | 2021-07-08 05:30 |  | Active | 2025-02-17 05:30 |  | 2025-03-31 05:30 |  | FALSE | Mission Possible | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A Randomized, Double-Blind, Placebo-Controlled Dose Range Finding Study with Open-Label Extension to Evaluate the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of LMI070/branaplam when Administered as Weekly Oral Doses in Participants with Early Manifest Huntingtonâs Disease | CLMI070C12203 PhIIb in Huntington's Disease | P4 Neuroscience | Chaghasbanian, Harut | Narisepalli, Satishkumar | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Pilar Cazorla Arratia | Pilar Cazorla Arratia | Musku, Srikanth Reddy | SIRIPURAM, RAJSHEKHAR TIRUPATI | Completed | 2022-01-27 05:30 | 12MAY2021 : Go-Live Date has been moved from 18JUN2021 to 04AUG2021, Based on Study Complexity and FPFV Date. 29Apr2021 : Go-Live Date: GTD says it is not possible to have RIS with in 15 days.. and there on to FPFV as there are many vendors in this study and vendor set up also need to be completed with all the required trainings etc to recruit patients. RIS is expected probably in mid week of Jul or early Aug. Study Status: Unique Form Built is Completed [Waiting for 1 more SRF], OSRM #1 Conducted on 28APR But Could not able to complete, Need to conduct for Remaining Forms. OSRM #2 is Planned on 05MAY2021. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 10May2021 |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 7Feb2022: The Rule File version 2.0 has been finalized in the subway and SNOW51 ticket has been raised (Ticket number - RITM3465152) on 7Feb2022. 21OCT2021: RF finalized on 20Oct2021, SNOW05 ticket raised (RITM3103797), RF checklist finalized on 21Oct2021. 20Sept2021: The RF has been developed and shared for the review. The RF is under peer review. 10Aug2021: SRF review is completed and shared the comments with the DBD. ALS review has begun. Screen UAT will be completed next week. 12-Jul-2021: The SRFs and ALS are under review. 10May2021: The team is planning to complete Screen UAT by 26MAY2021. 06May2021 : Follow up with DBD 21Apr2021 : LC : RF developer assigned. | None | None | 2021-10-20 05:30 |  | Polavarapu, Vanaja | Polavarapu, Vanaja | Amit Agavekar | [28 empty] | NA | [5 empty] | 1 | 157 | 76 | 0 | 998 | 936 | 0 | 244 | 37 | 238 | 1211 | 21 | 0 |  | Huntington's disease | Yes | Global | Open | Yes | [10 empty] | 2021-11-05 05:30 | [5 empty] | GDD annual target
CLMI070C1 | CLMI070C12204 | C4010214 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-11 05:30 | Study Planned | Final DBL | 2023-05-08 05:30 |  | 2021-12-10 05:30 |  |  | Planned | 2023-03-27 05:30 |  | 2023-05-08 05:30 |  | FALSE | Unknown at this stage | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | CLMI070C12204 Juvenile HD study_childhood onset | P4 Neuroscience | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha |  | Matthew Quinn | [17 empty] | Amit Agavekar | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Huntington's disease | Yes | Global | Open | Yes | [16 empty] | None of the above
CLMI070C1 | CLMI070C12301 | C4009628 | Phase III | NCDS_2 |  |  |  | 2024-06-03 05:30 |  | Final DBL | 2026-07-14 05:30 |  | 2023-10-31 05:30 |  |  | Planned | 2026-06-03 05:30 |  | 2026-07-14 05:30 | [5 empty] | InHouse |  |  | CLMI070C12301 Juvenile HD study_adolescent onset | P4 Neuroscience | [6 empty] | Matthew Quinn | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Huntington's disease | Yes | Global | Open | Yes
CLMI070A | CLMI070X2201 | C3001621 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2023-01-30 05:30 | 2015-04-02 05:30 |  | 2014-08-27 05:30 |  | Active | 2022-12-30 05:30 |  | 2023-01-30 05:30 |  | FALSE | Other | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | FULL Outsourced | DF NS | An open-label multi-part first-in-human study of oral LMI070 in infants with Type 1 spinal muscular atrophy. | CLMI070X2201 study (ph1/2 incl PoC and OLE) | P4 Neuroscience | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Christie Doerr | Christie Doerr | Bora, Deepthi Reddy | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | CMED | Pharma | AP21 | CMED Clinical services | [16 empty] | Central nervous system disorder; Muscle atrophy | Yes | Global | Open | Yes | [16 empty] | None of the above
CLML134B1 | CLML134X2201 | C1200739 | Phase II | NCDS | Rave EDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-07-26 05:30 |  | 2017-03-03 05:30 |  | Completed |  | 2018-09-12 05:30 | 2019-02-14 05:30 | 2019-02-14 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A randomized, subject and investigator-blinded, placebo\ncontrolled, cross-over, multi-center Proof of Concept (PoC)\nstudy to assess the wakefulness promoting effect, safety,\ntolerability, and pharmacokinetics of LML134 in shift work\ndisorder (SWD) patients | CLML134X2201 Shift work disorder PoC study | N6 Neuroscience - NIBR | Langlo, Francois |  | Young, Pamela | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Samantha Mauro | [15 empty] | Polagoni, Bharghavi |  | Rohit Varate | [13 empty] | 100 | FSOM - Outsourced | Yes | [12 empty] | ICON | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Shift work disorder | No | Global | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CLNA043A1 | CLNA043A11101 | C4008243 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-09-07 05:30 | 2020-09-15 05:30 | 2020-10-01 05:30 | DB Locked | Final DBL Achieved |  | 2020-09-23 05:30 | 2020-06-03 05:30 | 2020-06-19 05:30 |  | Completed | 2021-01-20 05:30 | 2020-12-10 05:30 | 2021-02-25 05:30 | 2021-01-19 05:30 | FALSE | Submission | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A randomized, participant and investigator blinded, placebo-controlled, single ascending dose study investigating the safety, tolerability and pharmacokinetics of LNA043 in Japanese participants with osteoarthritis of the knee | CLNA043A11101 Japan ES | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Hagiwara, Yayoi | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | SATORU SHINMYO | SATORU SHINMYO | Mokhamatam, Madhu Purnachandra Rao | Suzuki, Hiroko |  | 2020-07-06 05:30 | Madhu to Hiroko from startup. Initial go live as 07Sep2020 when RF developer assigned on 01Jun2020. |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 30NOV20: RF has been finalized and SNOW 51 RITM2041836 request has been created for QS domain update. 15SEP20: RF has been finalized and SNOW 05 Request RITM1797165 has been created. No pending forms and No pendind DTS as of today. DB golive on 15Sep2020. DB notification sent on 16Sep2020. 11SEP20: RF is ready with all forms once database is released into Production, we can finalize RF and SNOW 05 request will be created. 09SEP20: RF updated with two new ZJ pages. Peer review is ongoing. 01SEP20: Added two more new forms and expected DB golive is 15SEP20 21AUG20: RF is completed. Once database is pushed into production, we can finalize RF. 07AUG20: RF developed and released for peer review testing 03AUG20: Screen UAT testing is completed, We've to received ALS and RF development is ongoing. 24JUL20: Screen UAT is ongoing 07-JUL-20: Once UAT screens are finalized, RF development will be started. 30-JUN-20: Study specific page QS has been reviewed and provided comments to DBD. 25-Jun-2020: Draft Study specific pages has been shared for review by DBD. Review is ongoing. | None | None | 2020-09-15 05:30 | RF finalized within golive + 5 days | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-10-05 | Completed | 2020-10-05 05:30 | LSH setup is in progress. | Pre-requisites not met | 2020-10-05 05:30 | 2020-10-05 05:30 | Pre-requisites not met | 2020-11-25 05:30 |  |  |  |  | RaveX - Inhouse | Yes | -NA- | 2021-01-19 05:30 | 2021-01-21 05:30 | [9 empty] | NA | [5 empty] | 1 | 9 | 50 | 0 | 83 | 411 | 0 | 156 | 35 | 218 | 664 | 1 | 0 |  | Osteoarthritis knee | No | Global | Open | Yes | [10 empty] | 2020-10-01 05:30 |  |  |  | DBL | Adi, Vishnupriya | None of the above | Yes
CLNA043A1 | CLNA043A12202 | C4006226 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-01-10 05:30 | 2021-05-06 05:30 | 2021-06-30 05:30 | DB Conduct | Final DBL | 2028-02-25 05:30 | 2021-05-31 05:30 | 2021-03-08 05:30 | 2021-02-24 05:30 |  | Active | 2027-10-25 05:30 |  | 2028-02-25 05:30 |  | FALSE | None as on 10-May-2021 | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A 5-year, randomized, double-blind, placebo-controlled, multi-center study assessing the efficacy, safety, and tolerability of intra-articular regimens of LNA043 versus placebo in patients with symptomatic knee osteoarthritis (ONWARDS) | CLNA043A12202 Ph2 DRF study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Panyam, Pradeep Kumar | Chaudhari, Vishal | Vasi, Munir | Ninan, Esther | Hiroshi Sawata | Hiroshi Sawata | Sarasani, Chandana | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | 06May2021 : DB golive 06may2021. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 10Jan2021 |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 09-Nov-2021: RF v5.0 is finalized for QS4L, QS5L and CM1L, PR1L dts 11-Aug-2021: RF v4.0 finalized for QS1L,QS2L,QS3L,QS6L,QS7L,QS8L,QS9L DTSs. 21Jul2021:CB-LB1L was part of RF v2.0 and MO1L,ZW1L part of RFv3.0, prod transfer not received yet. 21Jul2021 : DTSs LB1L, MO1L, ZW1L reflecting in 21Jul report. 08Jul2021: RFv3.0 finalized for MO1L, ZW1L dts. 08Jun2021: RF v2.0 finalized for Yx, LB dts addition 10May2021 : CLNA043A12202 Rule File_Version 1.0 is finalized in Subway and SNOW-05 ticket has been raised (Ticket number- RITM2550939) for LSH Setup. Pratheeksha supported in RF development 1.0. 06May2021 : Pratheeksha supported in RF development 1.0 for this study on behalf of Chandrakala. 3May2021: Rule File v1.0 is in process. | None | None | 2021-05-10 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2021-06-02 | Completed | 2021-06-03 05:30 |  | Study Transition | 2021-06-03 05:30 | 2021-06-03 05:30 | Study Transition | 2021-06-03 05:30 | 2021-06-05 05:30 |  |  |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 1 | 42 | 47 | 0 | 262 | 595 | 0 | 208 | 38 | 123 | 756 | 16 | 0 |  | Osteoarthritis knees | Yes | Global | Open | Yes | [10 empty] | 2021-06-02 05:30 | [5 empty] | None of the above | Yes
CLNA043B1 | CLNA043A12203 | C4007219 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-02-16 05:30 | 2021-07-02 05:30 | 2021-07-27 05:30 | DB Conduct | Final DBL | 2024-05-20 05:30 | 2021-08-27 05:30 | 2021-01-27 05:30 | 2021-02-01 05:30 |  | Active | 2024-04-15 05:30 |  | 2024-05-20 05:30 |  | FALSE | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A randomized, four-arm, placebo-controlled, participant, investigator and sponsor-blinded study investigating the safety, tolerability and efficacy of intra-articular canakinumab followed by intra-articular LNA043 in patients with knee osteoarthritis | CLNA043A12203 ACZ885 and LNA043 in knee OA | N4 MSD - NIBR | Langlo, Francois | Chavan, Shweta S | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Ola Bunte | Bror G��ran Ola Bunte | Gupta, Anshu | Bora, Deepthi Reddy | Not Started |  | 12May2021 : DB Golive moved to 02Jul2021 due to pending deliverables. 07May2021: OSRM 2 on 07May2021. CRFs to be finalized along with SSD as per OSRM 2 feedback. ECS to be finalized. Abhinash esae, Lakshmi - CF, Iliyas, Mohamed, Priya Gehlawat, Mareedu, Vasu, Meda, Sreelakshmi, Shewane, Roshni supporting the study along with Jesica. 28 Apr2021 : Study Status 1) This is actually Anshu’s study and Jesica taking care of study tasks in her absence. 2) Screen updates are going on based on CTT comments. 3) As we have very less time for all the for study activities. Sumith and me have started with the dynamics and planning to have OSRM2 on 30APR2021 if all goes well.(Golive as per today planned on 17MAY2021). 4) already assigned Iliyas from ICON for edit check support. 5) DJ will assign CF programmer for checks. 6) eSAE request has been raised for setup. 13 Nov 2020 : CDD assignment request from Kunal Mane based on 16Feb2021 DB golive. 17th Nov 2020 DBD assigned. The Tentative date for Protocol finalization is by End of Next week and Go-live date is 16Feb2021. NOTE: - The Clinical team need a Draft CRF for submission by 15-Dec-2020. |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 02-Jul-2021: RF is final in Subway and raised SNOW05 ticket(RITM2736370) for LSH set-up 07-May-2021: Requested Lead DBP to update few screens and will initiate the RF development post UAT. RF developer assigned on 12Dec2020. with initial golive as 16feb2021 and FPFV as 01Apr2021. | None | None | 2021-07-02 05:30 |  | Adi, Vishnupriya | Adi, Vishnupriya | Rohit Varate | Completed | 2021-07-07 | Completed | 2021-07-20 05:30 |  |  | 2021-07-20 05:30 | 2021-07-20 05:30 |  | 2021-07-22 05:30 |  |  | DDPASS is yet to be initiated. Will be done once more data is available for review. |  | RaveX - Inhouse | No | EC#Y1,Y5,YR,YD#ZK | [11 empty] | NA | [5 empty] | 1 | 11 | 66 | 0 | 150 | 878 | 0 | 204 | 39 | 224 | 1141 | 2 | 0 |  | Osteoarthritis; Osteoarthritis knee | No | Global | Open | Yes | [10 empty] | 2021-07-19 05:30 | [5 empty] | None of the above
CLNA043A1 | CLNA043X2101 | C1200692 | Phase I | NOVDD | CRO - EDC |  |  | 2017-06-08 05:30 | DB Locked |  |  | 2015-11-16 05:30 |  | 2015-05-26 05:30 |  | Completed | 2018-03-12 05:30 | 2018-03-06 05:30 | 2018-05-11 05:30 | 2018-05-11 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A randomized, placebo controlled, double-blind first-in-human single ascending dose study of LNA043 in primary osteoarthritis patients scheduled for total knee replacement | CLNA043X2101 | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Florine Polus | Florine Polus | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Osteoarthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CLNA043A1 | CLNA043X2201 | C1200317 | Phase II | NCDS | CRO - EDC |  |  | 2017-11-14 05:30 | DB Locked |  |  | 2017-10-18 05:30 |  | 2016-11-30 05:30 |  | Completed | 2019-04-15 05:30 | 2019-04-05 05:30 | 2019-08-14 05:30 | 2019-08-14 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD |  | CLNA043X2201 PoM in ACI | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Andrea Biondani | Noemi K��tterer | [15 empty] | Sundar, N Sushant |  | Rohit Varate | [12 empty] | FSOM study. Only PK. Will conduct DDPASS before milestone | 0 | FSOM - Outsourced | No | [12 empty] | CMED | [19 empty] | Aching in knees | No | Global | Completed | Yes | [16 empty] | None of the above
CLNA043A1 | CLNA043X2202 | C1200422 | Phase II | NCDS | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2022-11-17 05:30 | 2017-09-12 05:30 |  | 2017-01-20 05:30 |  | Active | 2022-09-02 05:30 |  | 2022-11-17 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A two-part randomized, placebo-controlled, patient and investigator blinded, Proof of Concept study investigating the safety, tolerability and preliminary efficacy of multiple intra-articular LNA043 injections in regenerating the articular cartilage of the knee in patients with articular cartilage lesions (Part A) and in patients with knee osteoarthritis (Part B) | CLNA043X2202 PoC in knee OA | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Julie Mabille | Julie Mabille | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [19 empty] | Cartilage damage; Cartilage injury; Cartilage repair; Cartilage tear in knee; Osteoarthritis knee | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023A | CLNP023A2002B | C4008363 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-15 05:30 | 2021-08-09 05:30 | 2021-08-27 05:30 | DB Conduct | Final DBL | 2029-02-08 05:30 | 2021-09-20 05:30 | 2020-08-19 05:30 | 2021-05-12 05:30 |  | Active | 2028-12-03 05:30 |  | 2029-02-08 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter rollover extension program (REP) to evaluate the long-term safety and tolerability of open label iptacopan in adult participants with primary IgA nephropathy who have completed study CLNP023X2203 or CLNP023A2301 | CLNP023A2002B Umbrella Ext study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Subramanian, Mahaveeran | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha | Shannon O'Connell-Jones | Shannon O'Connell-Jones | Porandla, Swapna | Porandla, Swapna | Not Started |  | 29Apr2021 : Swapna P supporting the study as backup for Anshu. supporting form updates. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 15Jan2021 |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 8Feb2022: RF Version 3.0 Finalized in subway after adding LB1L and YDL DTS. SNOW51 ticket raised (RITM3471392) and LSP notified of the same. 09Aug2021 : CLNP023A2002B Rule File Version 1.0 is finalized in CREDI and SNOW-05 ticket has been raised (Ticket number- RITM2856698) for LSH Setup and LSP notified. Checklist not finalized yet since CREDI is not working since 2 days. 14-Jul-2021: Received the updated ALS. RF under development. 20May2021: SRF review has been completed 7May2021: DBD has shared the latest PDR to TDM. Status will be updated post the meeting to be held on 7May2021 26Apr2021 : Reassigned study from Praveen to Pratheeksha. 02-Dec-2020: Sent email to Anshu to provide study setup status and to share study specific forms for review. 06Oct2020 : RF Developer assigned (Praveen Oguri) with DB golive planned as 15Jan2021. | None | None | 2021-08-09 05:30 |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | Completed | 2021-08-23 | Completed | 2021-08-26 05:30 |  |  | 2021-08-27 05:30 | 2021-08-27 05:30 |  | 2021-10-29 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 34 | 56 | 0 | 426 | 577 | 0 | 193 | 47 | 142 | 766 | 2 | 0 |  | IgA nephropathy | Yes | Global | Open | Yes | [10 empty] | 2021-08-25 05:30 | [5 empty] | None of the above
CLNP023A | CLNP023A2101 | C4002066 | Phase I | NCDS | CRO - EDC |  |  | 2019-06-20 05:30 | DB Locked |  |  | 2019-06-24 05:30 | 2019-04-19 05:30 | 2019-05-02 05:30 |  | Completed | 2019-08-06 05:30 | 2019-07-26 05:30 | 2019-09-19 05:30 | 2019-09-23 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A single-center, open-label study to evaluate the absorption, distribution, metabolism and excretion (ADME) and pharmacokinetics of LNP023 following a single oral dose of [14C]LNP023 in healthy male subjects | CLNP023A2101 (hADME) | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | PRA Health | [19 empty] | IgA nephropathy | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023A | CLNP023A2103 | C4005305 | Phase I | NCDS |  |  |  | 2021-02-18 05:30 |  | Final DBL | 2021-12-07 05:30 |  | 2020-11-25 05:30 |  |  | Planned | 2021-09-28 05:30 |  | 2021-12-07 05:30 | [5 empty] | FULL Outsourced |  |  | CLNP023A2103 DDI perpetrator | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Louise Mooney | [66 empty] | IgA nephropathy | No | Global | Terminated | Yes
CLNP023A | CLNP023A2104 | C4005306 | Phase I | Other |  |  |  | 2021-05-21 05:30 |  | Final DBL | 2022-02-11 05:30 | 2021-05-12 05:30 | 2021-02-11 05:30 | 2021-02-11 05:30 |  | Active | 2022-01-28 05:30 | 2021-12-30 05:30 | 2022-02-11 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLNP023A2104 DDI victim | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Paola Paganoni | Paola Paganoni | [66 empty] | IgA nephropathy | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023A | CLNP023A2105 | C4005727 | Phase I | Other |  |  |  | 2021-10-29 05:30 |  | Final DBL | 2022-07-20 05:30 | 2021-11-10 05:30 |  | 2021-09-23 05:30 |  | Active | 2022-06-01 05:30 |  | 2022-07-20 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLNP023A2105 Organ Impairment Study (Hepatic) | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Paola Paganoni | Paola Paganoni | [66 empty] | IgA nephropathy; Membranous nephropathy; Paroxysmal nocturnal haemoglobinuria | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CLNP023A | CLNP023A2106 | C3004060 | Phase I | Other |  |  |  | 2023-04-21 05:30 |  | Final DBL | 2023-06-15 05:30 |  | 2020-10-21 05:30 | 2020-10-19 05:30 |  | Planned | 2023-05-11 05:30 |  | 2023-06-15 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLNP023A2106 China PK Study | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Romain Barnouin | Huei Ping Lee | [54 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | IgA nephropathy | No | Local | Open | Yes | [16 empty] | None of the above
CLNP023A | CLNP023A2107 | C4012714 | Phase I |  | CRO - EDC |  |  | 2022-03-23 05:30 | DB Conduct | Final DBL | 2022-05-12 05:30 | 2022-01-15 05:30 | 2021-09-21 05:30 | 2021-09-30 05:30 |  | Active | 2022-03-11 05:30 |  | 2022-05-12 05:30 |  |  | TBD | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - ATI | A randomized, participant-blinded, placebo-controlled, single ascending dose study to measure the effects of supra-therapeutic doses of oral iptacopan (LNP023) on QTcF in healthy participants | CLNP023A2107 QT | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Noemi Kaetterer | Noemi K��tterer | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | IgA nephropathy | No | Global | Open | Yes
CLNP023A | CLNP023A2108 | C4014871 | Phase I |  |  |  |  | 2022-08-12 05:30 |  | Final DBL | 2023-05-02 05:30 |  | 2022-04-03 05:30 |  |  | Planned | 2023-02-28 05:30 |  | 2023-05-02 05:30 | [5 empty] | FULL Outsourced |  |  | CLNP023A2108 QD formulation | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Louise Mooney | [66 empty] | IgA nephropathy | No | Global | Open | Yes
CLNP023A | CLNP023A2301 | C4001965 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-12-30 05:30 | 2021-01-04 05:30 | 2021-01-27 05:30 | DB Conduct | Interim DBL | 2023-04-06 05:30 | 2021-01-25 05:30 | 2020-08-28 05:30 | 2020-08-29 05:30 | 2020-12-04 05:30 | Active | 2025-01-14 05:30 |  | 2025-02-25 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023A2301 Phase III IGAN Pivotal APPLAUSE-IgAN | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Bulusu, Sravani | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha | Leena Bhundia | Leena Bhundia | Bora, Deepthi Reddy | Rana, Aamir | Not Started |  | 15-Dec-2021 : Sandeep Bakka will be backup for Aamir till 15-Mar-2022 |  | DRM | Shrivastava, Nikhil | Shrivastava, Nikhil | Completed | 14-Feb-2022: Updated and finalized the RF V7.0 to update the Rule File issue for MI domain. Raised SNOW-51 (RITM3490741) ad notified the LSP. 02-Feb-2022: Updated and finalized the RF V6.0 as per the SDTM requirement for MI and FACM domains. Raised SNOW-51 ad notified the LSP. 17-Sep-2021: Updated and finalized the RF V5.0 WRT PPC#02 and PPC#03 updates. Raised SNOW-51 ad notified the LSP. 23-Aug-2021: As per PPC#02 implementation, SNOW-51 raised for the domains (DV, EC, HO, LB, ODM and SS) where Rule File is not impacted. For the rest of the domains (CM, DD, FACM, PR, MI and SU), Rule File update has not been started as there are some issues in the database and the annotations which requires PPC to further update. Once those issues are corrected in the database, I will update the Rule File and will raise another SNOW ticket. 06-Aug-2021: PPC#02 got implemented on 03rd Aug but input documents related Rule File have not been shared with RF programmer. Did not even receive the response yet on the previously given comments. Following up with DBD on providing the input documents. RF updates required (New fields addition or DDG002, SUG001 and PRC001_TR forms; 3 News CRFs (Dialysis, Booster Vaccination, ACEi_ARB Treatment) will be added) 26-Jul-2021: The Rule File V4.0 has been updated and finalized in CREDI WRT IRT DTS V2.0 SNOW-51 raised and LSP has been notified. 13-Jul-2021: Sent reminder to TDM and DBD to provide the requested documents related to PPC#2. Waiting for the reply. 23-Jun-2021: PPC#02 is ongoing and RF will be impacted. Reviewed the PPC form and shared comments with TDM and DBD. 18-May-2021: Sent mail to TDM to update the table name of IRT DTS for YR and YD domains. Post DTS updated, RF will be updated. 15-Apr-2021: PPC#01 is implemented. SNOW-51 is raised and LSP is notified for LSH rebuild. There is no impact to RF. 14-Apr-2021: PPC#01 is currently ongoing. There is no impact to RF but LSH and SMT will be impacted. 03-Mar-2021: All 6 DTS (LB1L, Yx, QS1L, QS2, QS3L and QS4L) included in the RF V3.0 and finalized in CREDI. SNOW-51 is raised and LSP is notified. 11-Feb-2021: 6 DTS in draft state and near finalization (LB1L, Yx, QS1L, QS2, QS3L and QS4L). Reviewed the DTS and provided the comments to TDM. Included the DTS in Rule File and released for peer review. 20-Jan-2021: Rule File V2.0 updated and finalized in CREDI for the adhoc issue reported by SMT programmer. Attached the Rule File in same SNOW-05 request and informed LSP-SMT programmers. 04-Jan-2021: Rule File V1.0 WRT study Go-Live is finalized in CREDI. SNOW-05 request is raised and LSP is notified for LSH setup. 22-Dec-2020: Created the Rule File V0.1 and shared with team for peer review. 26Nov2020: Backup: Rehana Whats planned: Reviewed the SRF, SDTM annotations and provided comments to DBD. Will create the Rule File after resuming the office. 25-Nov-2020: Reviewed shared SRFs, SDTM annotation and DB design from RF perspective and provided the comments. Waiting for DBD response. 10-Nov-2020: Started the review of study documents. 28-Oct-2020 (SHRIVNI5): Followed up with DBD to share the document. DBD confirmed she will share document by 29th Oct. 17-Sep-2020 (SHRIVNI5): Sent mail to study DBD to provide study status and study related documents. Waiting the reply. | None | B1 DTS (upcoming) | 2021-01-04 05:30 |  | Polagoni, Bharghavi | Polagoni, Bharghavi | Amit Agavekar | Completed | 2021-01-20 | Completed | 2021-01-28 05:30 |  | Study Transition | 2021-02-01 05:30 | 2021-02-01 05:30 | Study Transition | 2021-02-08 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 5 | 13 | 66 | 0 | 219 | 711 | 0 | 210 | 39 | 168 | 918 | 9 | 0 |  | Nephropathy | No | Global | Open | Yes | [10 empty] | 2021-01-20 05:30 | [5 empty] | Pioneer
CLNP023B1 | CLNP023B12001B | C4001973 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-06-17 05:30 | 2019-09-04 05:30 | 2019-10-03 05:30 | DB Conduct | Final DBL | 2025-01-24 05:30 | 2019-10-03 05:30 | 2019-04-02 05:30 | 2019-04-02 05:30 |  | Active | 2024-12-02 05:30 |  | 2025-01-24 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | An open-label, non-randomized extension study to evaluate the long-term efficacy, safety and tolerability of LNP023 in subjects with C3 glomerulopathy | CLNP023B12001B OL Extension Study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Joglekar, Prajakta | Prajapati, Vaishali | Tummalapenta, Venkateswarlu | Nair, Sreesha | Ronda Tawfik | Ronda Tawfik | Rana, Aamir | Rana, Aamir |  |  | 15-Dec-2021 : Rajshekhar Siripuram will be backup for Aamir till 15-Mar-2022 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 17Jun2019 |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 09Aug2021: There is some update to be made in the LBL5 DTS as per the TDM. Once it is updated, It will add it in the RF. 26-Jul-2021: Will be adding the DTS and sending the RF for review. 26-Jul-2021: DTS will be added along with the PPC changes and will be sent for review. 21Jul2021 : DTS LBL5 reflecting in 21Jul report as well. 09Jul2021: LB5L DTS has to be updated by the TDM. Once the update is completed, I will add it in the RF. 06Jul2021 : LBL5 reflecting in missing form DTS report 22Jun2021: Received LBL5 DTS for review. It is under review. It is not finalized yet. PPC 07 request form has been reviewed and comments have been shared with Aamir. (PPC 07 is in review state as confirmed by the DBD). 26May2021 : Reassigned the study from Praveen Oguri to Pratheeksha. 25-May-2021: Sent email to Aamir Rana to confirm on LBL5 DTS finalization status. 05Nov2020: RF Version 5.0 finalized and raised snow ticket on 15Oct2020. 11Sep2020: Included all missing forms in RF and raised SNOW ticket on 11Sep2020. LBG002_TR, LBG002_1_TR, LBG002_2_TR, LBG002_3_TR are in RF but flagging in Report as LSH setup not completed. Discussions ongoing between LSP and TDM 02Sep2020 : As per 02Sep2020 missing forms DTS report "LBG002_TR, LBG002_1_TR, LBG002_2_TR, LBG002_3_TR " forms pending. Praveen to update 11Dec19 : All forms and DTS included in Rule file. | None | None | 2019-10-11 05:30 | Transition Study and Legacy process | Kommu, Ranjith Kumar | Varate, Rohit | Amit Agavekar | Completed | 2019-10-12 | Completed | 2019-10-18 05:30 |  | Pre-requisites not met | 2019-10-18 05:30 | 2019-10-18 05:30 |  | 2019-10-18 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 9 | 15 | 68 | 0 | 216 | 532 | 0 | 194 | 36 | 252 | 820 | 2 | 0 |  | C3 glomerulopathy | No | Global | Open | Yes | [10 empty] | 2019-10-18 05:30 |  |  |  | Interim-Analysis | Sundar, N Sushant | Pioneer | Yes
CLNP023H1 | CLNP023B12201 | C4003781 | Phase II |  |  |  |  | 2023-09-04 05:30 |  | Final DBL | 2025-05-22 05:30 |  | 2024-01-19 05:30 |  |  | Planned | 2025-03-14 05:30 |  | 2025-05-22 05:30 |  | FALSE |  |  |  | InHouse |  |  | CLNP023H12201 C3G Pediatric Study | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Elizabeth Miles | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | C3 glomerulopathy; C3 glomerulopathy | No | [19 empty] | None of the above
CLNP023B1 | CLNP023B12301 | C4001972 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-04-30 05:30 | 2021-06-15 05:30 | 2021-07-28 05:30 | DB Conduct | DB Snapshot | 2022-07-26 05:30 | 2021-07-28 05:30 | 2021-06-02 05:30 | 2021-03-08 05:30 | 2021-05-24 05:30 | Active | 2023-08-24 05:30 |  | 2023-10-05 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023B12301 Phase III Study APPEAR-C3G | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sawant, Vishal Bhaskar | Prajapati, Vaishali | Tummalapenta, Venkateswarlu | Nair, Sreesha | Ronda Tawfik | Ronda Tawfik | Moses, Leah | Palande, Sujit | Not Started |  | 29Apr2021 : Screens build initiated. OSRM 2 to be conducted next week. Initial golive as of 30Apr2021 when RF developer was assigned on 01Feb2021. 15Jul2020 : PCDM Mahaveeran request for DBD assignment FPFV Feb2021. Planned FPFV was updated to 30JUN2021 and hence the milestones were accordingly adjusted. | 14.1 - Updates from CTT | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 11Feb2022: PPC 01 was implemented on 7Feb2022. RF Version 4.0 was finalized on 10Feb2022 and SNOW51 Ticket was raised (Ticket number - RITM3481582). CMC001 form was removed and CMC001_1 form was added in the RF as per the PPC changes. 12Aug2021: 2 DTS have been reviewed. The DTSs are not finalized yet. Once finalized it will added in RF. 16JUN2021: RF finalized in CREDI and SNOW-05 ticket has been raised (Ticket number- RITM2675882) for LSH Setup. Arpita developed the RF on Pratheeksha's behalf. 08JUN2021: There was delay from the SDTM programmer end in providing the annotation due to which the ALS review got delayed. Now, the ALS review has been completed and have sent the comments to the DBD on 04Jun2021. Waiting for the final ALS to be shared to start developing Rule File. 01Jun2021: ALS are under review 06May2021 : SRFs and draft ALS are under review. Screen UAT will be starting on 12-May-2021 as confirmed by the DBD. 01Feb2021: RF developer Assigned | None | None | 2021-06-16 05:30 |  | Polagoni, Bharghavi | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2021-06-22 | Completed | 2021-07-12 05:30 |  |  | 2021-07-13 05:30 | 2021-07-13 05:30 |  | 2021-07-13 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 12 | 70 | 0 | 173 | 698 | 0 | 189 | 39 | 213 | 950 | 9 | 0 |  | C3 glomerulopathy | No | Global | Open | Yes | [10 empty] | 2021-07-12 05:30 | [5 empty] | Pioneer
CLNP023C1 | CLNP023C12001B | C4007488 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-03 05:30 | 2021-07-08 05:30 | 2021-07-27 05:30 | DB Conduct | Final DBL | 2024-10-16 05:30 | 2021-07-27 05:30 | 2020-12-02 05:30 | 2021-04-06 05:30 | 2021-07-10 05:30 | Active | 2024-09-04 05:30 |  | 2024-10-16 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023C12001B Extension study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sharma, Prateek | Kulkarni, Abhijeet | Tummalapenta, Venkateswarlu | Nair, Sreesha | Maryam Aalamian-Mattheis | Maryam Aalamian-Mattheis | Ganesan, Dhanalakshmi | Kashyap, Sandeep |  |  | Nov-2021 : Dhanalakshmi transitioned study to Sandeep Kashyap 29Apr2021 : No support required currently. Go-live date updated from 03MAY2021 to 23JUN2021. TDM will update the activity planner and iBOW by this week. Screen build completed and UAT ongoing. Due to personal emergency TDM requested CTT to push the golive date in Jun as FPFV is in Jul2021. CTT agreed on the same. Initial go live as 03May2021 when RF developer assigned on 17Apr2021. |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 13-Jul-2021: Rule is finalized in Subway and SNOW05 Ticket has been raised (RITM2763818) and LSP is notified. RF Checklist is finalized in subway. 01-Jul-2021: RF is under peer review 23-Jun-2021: RF development has started. 08JUN2021: The SRFs and SDTM annotations will be taken from CLNP023C12302 study. Hence, SRFs have not been reviewed. Final ALS has been shared by the DBD. ALS is under review. 01Jun2021: For time being, Deepthi is handling the study. The screen UATs have been completed yesterday(31MAY2021). 07May2021: DBD confirmed that screens will be finalized by 10May2021(Monday) 06May2021 : Followup with DBD 17Feb2021 : RF Developer assigned. | None | None | 2021-07-12 05:30 | RF finalized within Go-live + 5 days | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2021-07-20 | Completed | 2021-07-27 05:30 |  |  | 2021-07-27 05:30 | 2021-07-27 05:30 |  | 2021-07-28 05:30 |  |  | Currently there is very minimal data, once the data flow is normal, DDPASS will be scheduled. | 0 | RaveX - Inhouse | No | No Blinding/masking | [11 empty] | NA | [5 empty] | 1 | 32 | 58 | 0 | 229 | 765 | 0 | 190 | 47 | 142 | 954 | 7 | 0 |  | Paroxysmal nocturnal haemoglobinuria | Yes | Global | Open | Yes | [10 empty] | 2021-07-26 05:30 | [5 empty] | None of the above | Yes
CLNP023C1 | CLNP023C12301 | C4005061 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-22 05:30 | 2021-06-01 05:30 | 2021-07-30 05:30 | DB Conduct | Final DBL | 2023-08-16 05:30 | 2021-07-19 05:30 | 2021-01-29 05:30 | 2021-03-16 05:30 |  | Active | 2023-07-10 05:30 |  | 2023-08-16 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023C12301 Ph3 PNH Naive APPOINT-PNH | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Zhou, Fan | Kulkarni, Abhijeet | Tummalapenta, Venkateswarlu | Nair, Sreesha | Zhixin Wang | Zhixin Wang | Katam, Veera Nagendra | Katam, Veera Nagendra | Completed | 2021-09-22 05:30 | 21MAY2021: Go-Live Postposed from 26MAY2021 to 02JUN2021 Due to the spec update. 29APr2021: Study Status: All Edit Checks are in UAT, Need to address UAT Finding. PD Spec Finalized, Need to Provide to UAT by 10MAY2021. tSDV Spec is in final Review. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 22Jan2021 The DB Go live date was postponed from 22JAN2021 to 26MAY202, Due to Delay in Protocol Finalization. |  | DRM | Shafiudeen, Rehana Banu | Saha, Saikat | Completed | 31-Aug-2021 : The study is transitioned to Saha, Saikat. 31-Aug-2021 : No Pending tasks. Upcoming tasks : Work on DDPASS comments if any. 20Aug2021 : Rule file 3.0 is finalized in SUBWAY and the LSP is notified. LB1L DTS is included in tis version. 28Jul2021 : Rule file 2.0 is finalized in SUBWAY. B11L, QS1L, QS2L, QS3L, QS4L DTS and SUG001, OPS001 forms were included in this version. 21Jul2021 : Forms SUG001, OPS001 along with B11L, QS1L, QS2L, QS3L, QS4L DTs reflecting in 21Jul report as well. 06Jul2021 : B11L, QS1L, QS2L, QS3L, QS4L reflecting in missing form DTS report 3June2021 : The Study is pushed to production on 02June2021 and the SNOW - 05 request is raised . 07May2021 : Please be informed that the Rule file V1.0 for the CLNP023C12301 trial is finalized in SUBWAY as per below comment. 6May2021 : The Rule file is completed and shared with the LSP. Since this trial is one of the J review/LST Test instance Pilot studies. Will be finalized in SUBWAY once it is up and running. 15Apr2021 : Started with the ALS review. 7Apr2021 : Received the ALS and other documents for review. Since this is a pilot study for Jreview setuo, the RF should be finalized by 22Apr2021. 7Jan2021 : The Go-live is postpone to May due to the protocol finalization delay. Will be requesting the date to be updated once it confirmed. | None | None | 2021-06-03 05:30 |  | Polagoni, Bharghavi | Agavekar, Amit | Amit Agavekar | Completed | 2021-06-18 | Completed | 2021-07-08 05:30 |  |  | 2021-07-13 05:30 | 2021-07-13 05:30 |  | 2021-07-13 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 19 | 72 | 0 | 265 | 1138 | 0 | 306 | 44 | 221 | 1403 | 7 | 0 |  | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes | [10 empty] | 2021-07-07 05:30 | [5 empty] | None of the above
CLNP023C1 | CLNP023C12302 | C4004999 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-09-01 05:30 | 2020-11-04 05:30 | 2020-11-30 05:30 | DB Conduct | DB Snapshot | 2022-06-20 05:30 | 2021-01-25 05:30 | 2020-05-27 05:30 | 2020-08-17 05:30 |  | Active | 2023-01-10 05:30 |  | 2023-02-21 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized, multicenter, active-comparator controlled, open-label trial to evaluate efficacy and safety of oral, twice daily LNP023 in adult patients with PNH and residual anemia, despite treatment with an intravenous anti-C5 antibody | CLNP023C12302 Ph3 PNH Partial Responders APPLY-PNH | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sridhar, Shashikala | Kulkarni, Abhijeet | Tummalapenta, Venkateswarlu | Nair, Sreesha | Rakesh Kumar | Rakesh Kumar | Bonam, Rajesh Babu | Katam, Veera Nagendra | Completed | 2021-06-23 05:30 | 23Jun2021 : Transition from Rajesh Bonam to Katam, Veera Nagendra OSRM#1 on 13Aug and new forms have ben added. DB GOlive moved from 01Sep20 to 18Oct2020 PPC-03 completed on 24-May-2021. No PPC ongoing |  | DRM | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 12AUG2021: RF V7.0 is final and SNOW 51 request RITM2867656 has been created. Request you to rebuild CM, AE and CE domains as per below changes. AE Domain: AES001 form has been removed. CE Domain: AES001 form: Domain name has been mapped from 'AE' to 'CE' as per updated SRF and SDTM annotations CM Domain: CMSCAT variable has been added for all pages as per SDTM team requirement 08JUL2021: RF V6.0 is final and SNOW 51 RITM2753740 requested for to rebuild EG domain. 05JUN2021; RF V5.0 and SNOW 51 RITM2644777 request has been created for to rebuild LB domain. 01JUN2021: RF 4.0 and SNOW 51 RITM2625423 request has been created. Request you to rebuild LB and FACE domains 28May2021 : Rule file for PPC03 completed. CM domain: CMS001 form: CMTRT1 has been renamed to CMTRT and CMTRT to CMTRTXX CMS003 form: TRFTPC3 has been renamed to CMTRTXX, CE domain has been updated as part of post production change FACE domain has been updated as part of post production change, LB domain has been updated as part of post production change, SS domain has been updated as per latest SDTM annotation 15APR21: PPC3 is ongoing. I've reviewed change request form and provided comments. Waiting for the draft ALS for further review and RF development 04FEB21: RF has been finalized and SNOW 51 request has been created by Chandra as part of PPC1 updates (HOG002_TR, LBG001_TR_4, LBG001_TR_5, LBG001_TR_6, LBG001_TR_7, LBG001_TR_8 & LB1L , B11L DTS included) 28JAN21: HOS001 and HOS002 have been removed in this PPC and replaced with HOG002. Note: B11L and LB1L DTS has been shared after request with DM. Chandrakala working on the RF development. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021HOS001, HOS002 forms & B11L, LB1L DTSs are listed. Please check 7JAN2021: SG: PPC1 review comments provided to DB lead. PPC is planned to be implemented by end of Jan. Subsequent Rulefile update will be required. 04Nov2020 : finalized the Rulefile and raised the SNOW05 ticket for the same. RITM1960629 05Oct2020 : Followup with DBB on the study. 8Sep2020: Screens Peer review ongoing. 04Sep2020 : Followup with DBD on study status 12AUG2020: RF activties not yet started. Awaiting DB lead inputs on status of DB Development activities. | None | None | 2020-11-04 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2020-11-13 | Completed | 2020-12-03 05:30 |  |  | 2020-12-03 05:30 | 2020-12-03 05:30 |  | 2020-12-08 05:30 |  |  | There are few issues that are pending and are marked to different line functions. The issues will be fixed in the upcoming DDPASS. | 75 | RaveX - Inhouse | Yes | Y1,Y5 | [11 empty] | NA | [5 empty] | 6 | 21 | 73 | 0 | 272 | 948 | 0 | 250 | 44 | 180 | 1172 | 7 | 0 |  | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes | [10 empty] | 2020-12-02 05:30 |  |  |  |  | R, Harini | Pioneer | Yes
CLNP023C1 | CLNP023C12303 | C4008272 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-02-14 05:30 | Study Planned | DB Go-live | 2023-02-25 05:30 |  | 2022-10-01 05:30 |  |  | Planned | 2023-07-31 05:30 |  | 2023-09-11 05:30 |  |  | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023C12303 PNH Switch Study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Kulkarni, Abhijeet | Kulkarni, Abhijeet | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Elizabeth Miles | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | [7 empty] | 800 | 8 |  |  | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes
CLNP023D1 | CLNP023D12201 | C4001562 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-10-15 05:30 | 2019-11-18 05:30 | 2019-11-29 05:30 | DB Conduct | Interim DBL | 2022-10-01 05:30 | 2019-11-23 05:30 | 2019-06-19 05:30 | 2019-06-21 05:30 |  | Active | 2023-11-24 05:30 |  | 2024-01-25 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A randomized, open-label, two arm, parallel group, proofâof-concept clinical trial to investigate the efficacy and safety of LNP023 compared with rituximab in the treatment of subjects with idiopathic membranous nephropathy | CLNP023D12201 PoC iMN | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Mane, Kunal Yashavant | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Andrea Biondani | Andrea Biondani | Kuttoboina, Sujan Kumar | Thomas, Ankit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Oct19 |  | DRM | Bai, Chandrakala | Kuttoboina, Sujan Kumar | Completed | 20DEC21: RF V4.0 is final and SNOW 51 request has been created as part of PPC5 and PPC6 changes. 03AUG21: SNOW 51 request RITM2835828 has been created as part of PPC4 changes and no impact on the Rule file 03JUN21: RF 3.0 has been finalized as part of PPC3 and SNOW 51 request RITM2633556 has been created. New forms ECG005, ECG006_1 and VSG001_3 have been added. 07JUL20: As of today, no pending forms and no pending DTS. 15APR2020: Rule file has been finalized and SNOW 51 request has been created. Included PRS001, FAMHS001,SSG002 pending forms in this version 14Apr2020 : Sent for 2nd round of peer review for pedning forms by addressing the fedback 03Apr2020 : received Peer review feedback. 02Apr2020 : Included pending forms (PRS001, FAMHS001,SSG002), DTS (LB) and sent for Peer review (Nikhil) 24MAR2020: PPC is ongoing, will update all changes at once. 09Mar2020 : received Peer review comments and working on the same. 02MAR2020: Peer review is ongoing. On 28FEB2020 confirmation received from SDTM programmer for FAMH domain. Expected date of completion is 05MAR2020 12Feb2020 : Reassigned to Sujan from Chandrakala. Pending forms PRS001, FAMHS001,SSG002 & LB DTS will be included in RF v2.0 by 13Feb2020. 15Oct2019: RF v1.0 finalized. Pending Form/DTS: PRS001, FAMHS001,SSG002. No DTS finalized yet. | None | None | 2019-11-19 05:30 | RF finalized within golive + 5 days | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2019-11-20 | Completed | 2019-11-22 05:30 | Rule file v1.0: PRS001, FAMHS001,SSG002 forms are exclu61ded due to unavailable SDTM annotations. |  | 2019-11-22 05:30 | 2019-11-22 05:30 |  | 2020-04-20 05:30 |  |  | [RAMACHA1, 5th Feb, 2021] Study setup DDPASS success rate = 70% PPC1,2 DDPASS success rate = 30%. Data issues are queried to sites and vendor data related issues are being handled currently. [RAMACHA1, 10JUN2021] PPC3 implementation was completed on 8th Jun, 2021. DDPASS is scheduled for 17th Jun, 2021. All pending issues will be followed upon along with review for PPC3. | 61 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK |  |  |  | [RAMACHA1, 10JUN2021] SNOW51 was raised on 3rd Jun, 2021. Completed on 8th Jun, 2021 [RAMACHA1, 21JUL2021] eSAE PPC4 completion was communicated on 21st Jul, 2021. Requested CV refresh status as the changes are not reflecting in SOD. [RAMACHA1, 27OCT2021] Last DDPASS was conducted after PPC4 in August, 2021. 61% success rate, will conduct the next DDPASS post PPC5 | [7 empty] | NA | [5 empty] | 6 | 14 | 69 | 0 | 196 | 605 | 0 | 177 | 36 | 195 | 836 | 2 | 0 |  | Membranous nephropathy | Yes | Global | Open | Yes | [10 empty] | 2019-11-21 05:30 | [5 empty] | Pioneer | Yes
CLNP023D1 | CLNP023D12301 | C4003584 | Phase III | NCDS_2 |  |  |  | 2022-09-06 05:30 |  | Final DBL | 2023-04-03 05:30 |  | 2022-05-20 05:30 |  |  | Planned | 2023-02-20 05:30 |  | 2023-04-03 05:30 |  | FALSE |  |  |  | InHouse |  |  | CLNP023D12301 iMN Ph3 Pivotal Study | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Elizabeth Miles | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Membranous nephropathy | No | Global | Draft | Yes | [16 empty] | None of the above
CLNP023E1 | CLNP023E12201 | C4006254 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-01-31 05:30 | 2022-02-07 05:30 | 2022-02-22 05:30 | DB Set-Up | Final DBL | 2026-12-29 05:30 |  |  | 2021-07-21 05:30 |  | Planned | 2026-11-10 05:30 |  | 2026-12-29 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A randomized, participant and investigator masked, placebo-controlled, multicenter, proof-of-concept study to assess the safety and efficacy of LNP023 (Iptacopan) in patients with early and intermediate age-related macular degeneration | CLNP023E12201 LNP iAMD PIE POC | N8 Ophthalmology - NIBR | Langlo, Francois | Tadakamalla, Pranitha | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Karen Holopigian | Karen Holopigian | Porandla, Swapna | Porandla, Swapna |  |  |  |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 08Feb2022: CLNP023E12201_Rule file_version 2.0 is finalized in Subway with updated QS domain and Yx DTS added. SNOW-05 New Study Setup (PROD) ticket is raised with ticket number- RITM3468576 for LSH update. 02Feb2022: Peer Review completed. 01Feb2022: Release CLNP023E12201_Rule File_version 1.1 with QS2S831_TR and Yx DTS added in this version for peer review. 31Jan2022: DBD shared updated ALS with new QS form added. Review completed and RF update started. 13Jan2022: Angella supported in review of Yx DTS in my absence. 10Jan2022: TDM shared the Yx DTS for review 24Dec2021: Study transitioned from Swapna (lead DBD) to Anshu (Lead DBD) 29Nov2021: Peer review completed. CLNP023E12201_Rule file_version 1.0 is finalized in Subway. SNOW-05 New study setup (TEST) ticket is also raised with ticket number-RITM3235858 for LSH TEST setup. 23Nov2021: Released CLNP023E12201_Rule file_version 0.1 for peer review. 17Nov2021: Rule file development is started 11Nov2021: Shared ALS review comments with DBD 02Nov2021: Received the Pre-requisite documents for initial review 10Aug2021: DBD confirmed that the golive date has been pushed to 19NOV2021 23Jul2021: No documents are shared for review yet. 23Jul2021: Requested DBD to share the study status, SRFs and activity Planner. DBD informed that they have not started with the activities yet as protocol finalization was pending from the CTT. They will start working on study activities from 25th July 2021. DBD mentioned the tentative Go-Live date: 1st Oct 2021 06Jul2021: RF developer assigned with DB golive as 24Sep2021. | None | None | 2022-02-08 05:30 |  | Saranji, Muthu |  | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Age-related macular degeneration | No | Global | Open: Reapproval | Yes | 2021-11-29 05:30 | [15 empty] | None of the above
CLNP023F1 | CLNP023F12301 | C4008291 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-02-08 05:30 | 2021-07-26 05:30 | 2021-08-31 05:30 | DB Conduct | Final DBL | 2025-02-11 05:30 | 2022-01-17 05:30 | 2021-03-09 05:30 | 2021-03-10 05:30 |  | Active | 2025-01-14 05:30 |  | 2025-02-11 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | An open-label, multi-center, single-arm clinical trial of LNP023 in adult patients with atypical Hemolytic Uremic Syndrome (aHUS) | CLNP023F12301 aHUS Ph3 Pivotal study APPELHUS | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Roongta, Surabhi Sushil Kumar | Prajapati, Vaishali | Tummalapenta, Venkateswarlu | Nair, Sreesha | Claire Garin-Coupillaud | Claire Marie Garin-Coupillaud | Katam, Veera Nagendra | Katam, Veera Nagendra | Completed | 2021-11-17 05:30 | 29Apr2021 : Go-Live Date: As per PDM RIS Date (12Jul2021) is considered for populating Go-Live date. Study Status: OSRM #2 Completed, But Based on few updates from CTT, The Dynamics and Forms need updates, Expecting to finish by Tomorrow first half. Support Required: Requesting to assign Screen Peer Reviewer [03MAY2021 to 05MAY2021]. Initial go live as 10Mar2021 when RF developer assigned on 23Dec2020. The Initial Go-Live date when study was assigned is 08FEB2021 But Moved to 22JUN2021 Due to the delay in the Protocol Finalization. |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 28-Jul-2021: The Rule File has been finalized, SNOW05 ticket raised (Ticket number - RITM2813283), LSP POC has been notified to assign the LSP and the RF checklist has also been finalized in subway. 14-Jul-2021: The RF development is completed and sent for review. Addressing the RF comments now. There were few database changes made after sending the RF for review. Due to the DB update the Go-Live is postponed to 20-Jul as informed by the DBD. I have asked the DBD to ask the TDM to update the iBoW. 18Jun2021: SRFs were shared on 11-Jun-2021 and are under review. 08JUN2021: The DBD has informed that the Go-live date will be postponed. As per his response the go-live date might get postponed to 05July2021. The DBD will be confirming soon on this. Forms are in UAT round 2 and the UAT is expected to be completed by 09JUN2021. 1Jun2021: Screens are in UAT Round 2 and the screen UAT are expected to be completed by 03JUN2021 7May2021: DBD has confirmed that the study screen UAT is expected to complete by 11MAY2021 EOD. 26-Apr-2021: Sent email to study DBD Srikanth to share the study build status. 26Apr2021 : Reassigned from Praveen to Pratheeksha. 23Dec2020 : RF Developer (Praveen O) assigned with planned DB golive as 10Mar2021. | None | None | 2021-07-27 05:30 |  | Polagoni, Bharghavi | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2021-08-03 | Completed | 2021-08-24 05:30 |  |  | 2021-08-25 05:30 | 2021-08-26 05:30 |  | 2021-09-21 05:30 |  |  | No data available in EDC forms. |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 24 | 72 | 0 | 280 | 851 | 0 | 234 | 42 | 175 | 1068 | 9 | 0 |  | Haemolytic uraemic syndrome; Haemolytic uraemic syndrome | Yes | Global | Open | Yes | [10 empty] | 2021-08-19 05:30 | [5 empty] | None of the above | Yes
CLNP023F1 | CLNP023F12302 | C4008341 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-06-01 05:30 |  | 2023-01-17 05:30 | Study Planned | DB Go-live | 2022-06-01 05:30 |  | 2022-09-05 05:30 |  |  | Planned | 2025-05-19 05:30 |  | 2025-06-30 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023F12302 Switch study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Prajapati, Vaishali | Prajapati, Vaishali | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Vipul Halbe | Govula, Shashikanth | Govula, Shashikanth | [5 empty] | Shrivastava, Nikhil | Shrivastava, Nikhil | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Haemolytic uraemic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023G1 | CLNP023G12201 | C4003777 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-01-02 05:30 | Study Planned | DB Go-live | 2022-12-02 05:30 |  | 2023-05-19 05:30 |  |  | Planned | 2025-06-30 05:30 |  | 2023-02-10 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023G12201 IgAN Pediatric Study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Subramanian, Mahaveeran | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Elizabeth Miles | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | IgA nephropathy | No | Global | Draft | Yes | [16 empty] | None of the above
CLNP023H1 | CLNP023H12101 | C4015397 | Phase I |  |  |  |  | 2022-11-24 05:30 |  | Final DBL | 2023-05-17 05:30 |  | 2022-07-13 05:30 |  |  | Planned | 2023-03-15 05:30 |  | 2023-05-17 05:30 | [5 empty] | FULL Outsourced |  |  | CLNP023H12101 Rel BA minitablets | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Louise Mooney | [66 empty] | C3 glomerulopathy | No | Global | Open | Yes
CLNP023H1 | CLNP023H12201 | C4003781 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-09-04 05:30 | Study Planned | DB Go-live | 2023-08-04 05:30 |  | 2024-01-19 05:30 |  |  | Planned | 2025-03-14 05:30 |  | 2025-05-22 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CLNP023H12201 C3G Pediatric Study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Subramanian, Mahaveeran | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Elizabeth Miles | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | C3 glomerulopathy | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023K1 | CLNP023K12201 | C4010755 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-09-29 05:30 |  | 2022-05-02 05:30 | DB Set-Up | DB Go-live | 2022-03-28 05:30 |  | 2021-09-29 05:30 | 2021-11-03 05:30 |  | Planned | 2028-03-13 05:30 |  | 2024-12-05 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | An adaptive, randomized, double-blind, parallel group, placebo-controlled, multicenter phase 2 trial to evaluate the efficacy, safety and tolerability of LNP023 in combination with standard-of-care with and without oral corticosteroids in patients with active lupus nephritis Class III-IV, +/- V | CLNP023K12201 Ph2 study in LN | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Kulkarni, Abhijeet | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha | Piyush Mahajan | Piyush Mahajan | Ganesan, Dhanalakshmi | Ganesan, Dhanalakshmi |  |  |  |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Not Started | 28Jul2021: No documents are shared for review yet. 28Jul2021: DBD informed that protocol design is getting changed for this trial. So Go-live and FPFV date will get pushed. Once DBD get the confirmation from TDM, she will update. 22Jul2021: Requested DBD to share the study status, SRFs and activity planner. 06Jul2021 : RF developer assigned with golive as 29Sep2021. |  |  |  |  | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Lupus nephritis | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023L1 | CLNP023L12201 | C4011072 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-09-27 05:30 | 2021-10-23 05:30 | 2021-12-22 05:30 | DB Conduct | Final DBL | 2025-12-04 05:30 | 2021-12-21 05:30 | 2021-07-14 05:30 | 2021-07-16 05:30 |  | Active | 2025-11-03 05:30 |  | 2025-12-04 05:30 |  |  | PoC | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | An open-label, multi-center, phase 2 basket study to assess efficacy, safety and pharmacokinetics of iptacopan (LNP023) in participants with autoimmune benign hematological disorders | CLNP023L12201 PoC basket study in ITP&CAD | N7 Oncology - NIBR | Langlo, Francois | Kumar, Samoj | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Claudia Simonett | Claudia Simonett | Das, Devashish | Das, Devashish |  |  |  | Change in personnel leading to delay in specification | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 23Oct2021:CLNP023L12201 Go-Live is achieved and CLNP023L12201_Rule File_version 1.0 is finalized in Subway and SNOW-05 New study setup (TEST) is raised with ticket number- RITM3115503 for LSH setup. 22Oct2021: Peer Review completed. Rule file is updated and ready for finalization. 19Oct2021: Released CLNP023L12201_Rule file version 0.1 for peer review. 18Oct2021: DBD shared the QS mapping file, updated ALS and UAT SODs 08Oct2021: Nikhil Shrivastava supported as a back up for this study during my absence. 07Oct2021: SDTM programmer provided the SDTM annotation and confirmation to use the reference study annotation for this study with few updates. 06Oct2021: TAPOD provided the approval to use the reference study SRFs for this study. 05Oct2021: DBD shared the updated ALS. QS mapping file and SDTM annotation is yet to be received from DBD. 30Sep2021: Requested DBD to provide the SDTM annotation for the study specific pages and approval from TAPOD for using reference study SRFs and annotation. 29Sep2021: DBD shared the few of the documents for initial review. Review completed and comments shared with DBD. 07Sep2021: Requested DBD to share the status of the study. 13Aug2021 : RF developer assigned with Golive as 27Sep2021 | None | None | 2021-10-23 05:30 |  | Nagalla, Lakshmi Naga Lavanya | Nagalla, Lakshmi Naga Lavanya | Rohit Varate | Completed | 2021-10-29 | Completed | 2021-11-02 05:30 |  |  | 2021-11-03 05:30 | 2021-11-03 05:30 |  | 2021-11-19 05:30 | 2021-11-19 05:30 |  |  |  | RaveX - Inhouse | [13 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Cold agglutinin disease; Immune thrombocytopenic purpura | No | Global | Open | Yes | [10 empty] | 2021-11-02 05:30
CLNP023O1 | CLNP023O12101 | C4015724 | Phase I | [6 empty] | Final DBL | 2024-05-16 05:30 |  | 2023-05-26 05:30 |  |  | Planned |  |  | 2024-05-16 05:30 | [5 empty] | FULL Outsourced |  |  | CLNP023O12101 FiH SAD/MAD IV Formulation | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Claudia Simonett | [66 empty] | Acute kidney injury | No | Global | Draft | Yes
CLNP023A0 | CLNP023X1102 | C3001660 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-03-30 05:30 | 2018-03-30 05:30 | DB Locked | Final DBL Achieved |  | 2018-03-30 05:30 | 2017-12-21 05:30 | 2017-12-21 05:30 |  | Completed | 2018-05-25 05:30 | 2018-05-18 05:30 | 2018-07-31 05:30 | 2018-07-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A randomized, subject-blind, placebo-controlled, and single ascending dose study to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of orally administered LNP023 in Japanese healthy male subjects | CLNP023X1102 Japan_ESS | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Ichinowatari, Mihoko | Sneha, Kumari | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | TOMOHIRO YONEDA | YUMIKO OTSUKA | Suzuki, Hiroko | Suzuki, Hiroko |  |  |  |  | Pre-DRM | Suzuki, Hiroko | Suzuki, Hiroko | Completed | Study Locked | Study Locked | Study Locked | 2018-05-14 05:30 | Legacy Process | Tidke, Shyam |  | Rohit Varate | Completed | 2019-05-17 | Not Applicable |  |  |  | 2018-05-17 05:30 | 2018-05-17 05:30 | Retrospective DRM studies | [5 empty] | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 2 | 7 | 67 | -1 | 120 | 444 | 0 | 134 | 40 | 263 | 747 | 0 | 0 |  | IgA nephropathy | Yes | Global | Completed | Yes | [16 empty] | Pioneer
CLNP023A0 | CLNP023X2101 | C1200474 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-07-25 05:30 |  | 2016-02-05 05:30 |  | Completed |  | 2017-06-20 05:30 |  | 2017-08-01 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, subject-blinded, placebo-controlled, ascending single and multiple dose study to explore the safety, tolerability, pharmacokinetics and pharmacodynamics of orally administered LNP023 in healthy subjects. | CLNP023X2101 First-in-human SAD/ MAD Study in HVs | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Louise Mooney | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | C3 glomerulopathy; Paroxysmal nocturnal haemoglobinuria | No | Global | Completed | Yes | [16 empty] | None of the above
CLNP023C1 | CLNP023X2201 | C1200364 | Phase II | NCDS | CRO - EDC |  |  | 2018-04-11 05:30 | DB Conduct | Final DBL | 2022-04-14 05:30 | 2018-04-09 05:30 |  | 2017-09-12 05:30 |  | Active | 2022-02-11 05:30 |  | 2022-04-14 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | An open label, single arm, multiple dose study to assess efficacy, safety, pharmacokinetics and pharmacodynamics of LNP023 when administered in addition to Standard of Care (SoC) in patients with paroxysmal nocturnal hemoglobinuria (PNH) with signs of active hemolysis | CLNP023X2201 PoC in PNH | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Niamh Fagan | Niamh Fagan | [15 empty] | Ramayanam, Vinay |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | CMED | [19 empty] | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes | [16 empty] | None of the above
CLNP023B1 | CLNP023X2202 | C1200363 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-03-25 05:30 | 2019-05-14 05:30 | 2019-02-25 05:30 | DB Locked | Final DBL Achieved |  | 2019-02-20 05:30 | 2018-09-07 05:30 | 2018-09-12 05:30 |  | Active | 2021-05-19 05:30 | 2021-04-23 05:30 | 2021-07-02 05:30 | 2021-07-05 05:30 | FALSE | DCN Priority | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | An open-label, non-randomized study on efficacy, pharmacokinetics, pharmacodynamics, safety and tolerability of LNP023 in two patient populations with C3 glomerulopathy | CLNP023X2202 PoC C3G | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Mane, Kunal Yashavant | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Andrea Biondani | Andrea Biondani | Kurella, Rakesh Reddy | Joshi, Alekhya |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 25mar2019 |  | DRM | Kurella, Rakesh Reddy | Kuttoboina, Sujan Kumar | Completed | 06JUL2021: Study has been locked. 31MAY2021: RF final and SNOW 51 request RITM2621806 has been created for the below change and no pending action items. 28May2021 : LB (PPC 06) ongoing updates to RF. 23FEB21: Rule file V10.0 finalized and SNOW 51 request RITM2275029 has been created on 17FEB21. Changes: MI domain: MIS002 form: Step 2: a. MITEST Typo error has been corrected from "Nomal" to "Normal" as per SDTM team confirmation. b. MITEST has been updated from "Per Interstitial Fibrosis Tubular Atropy" to "Interstitial Fibrosis/Tubular Atrophy %" as per SDTM team confirmation. 07JUL20: As of today, No pending forms and pending DTS. 19MAY2020: Rule file has been finalized and SNOW 51 request has been created. 19MAY2020: New DTS ZW1L has been added and LB domian updated due to update with central lab DTS LB1L. Peer review is ongoing (Ashok) 14MAY2020: Three new EGG001_5, EGG001_6, EGG001_7 and EGG001_8 forms have been added. And for forms MIS001, MIS002 and MIS003 Logic has been rebuilt due to incorrect SDTM annotations and CRF page update. Rule file has been finalized and SNOW 51 request has been created. 30Apr2020: PPC implemented to add 4 new forms. Need to include in RF and will be completed by 08th May2020. 13MAR2020: No pending issues as of today, LSH setup has been completed. 03Mar2020 : included pending forms FAMHS001, PRS001 AND CMS001 and sent for LSH setup 02MAR2020: Rule file update will sent for peer review on 03MAR2020 and expected date of completion is 06MAR2020. 13Feb2020 : Received SDTM annotations on 12Feb2020. Tentatively RF will be completed by 18Feb2020. 22-JAN-20: FAMHS001, PRS001 AND CMS001 forms are pending and lead DBP following up with SDTM programmer for SDTM annotations. 29-NOV-2019: Developer is not available, will update status after receiving updates. 23Jul2019,BAICH3: RF finalized with 4 forms excluded due pending for SDTM annotations. 18Jul2019,BAICH3: Round 1 RF review comments shared. 10Jul19: Pending with SDTM annotations of 3 forms, DBD will send a updated RF by excluded forms for now. 06Jun19: 3 forms pending | None | None | 2019-08-02 05:30 | Transition Study and Legacy process | Tidke, Shyam | Agavekar, Amit | Rohit Varate | Completed | 2019-07-29 | Completed | 2019-08-06 05:30 |  | Earlier this was retro trial but later we did DRM for this trial | 2019-07-10 05:30 | 2019-08-08 05:30 | Study Transition | 2019-08-08 05:30 |  |  |  | 0 | RaveX - Inhouse | Yes | -NA- | 2021-07-06 05:30 | 2021-07-08 05:30 | [9 empty] | NA | [5 empty] | 10 | 26 | 67 | 0 | 270 | 706 | 0 | 185 | 32 | 209 | 947 | 2 | 0 |  | C3 glomerulopathy | Yes | Global | Open | Yes | [10 empty] | 2019-08-06 05:30 | [5 empty] | Pioneer;#GDD annual target | Yes
CLNP023A | CLNP023X2203 | C1200319 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2017-12-08 05:30 | 2018-03-07 05:30 | DB Locked | Final DBL Achieved |  | 2018-02-07 05:30 |  | 2017-09-20 05:30 |  | Active | 2021-06-29 05:30 | 2021-06-22 05:30 | 2021-08-10 05:30 | 2021-08-03 05:30 | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | An adaptive seamless randomized, double-blind, placebo-controlled, dose ranging study to investigate the efficacy and safety of LNP023 in primary IgA nephropathy patients | CLNP023X2203 POC/Ph2b in IgA Nephropathy | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sridhar, Shashikala | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha | Vipul Halbe | Vipul Halbe | Kuttoboina, Sujan Kumar | Rao, S Shashikanth |  |  |  |  | DRM (DIAL) | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 02FEB21: RF has been finalized and SNOW 51 RITM2224159 has been created. Change: ZJG001_7, ZJG001_8, ZJG001_9 and ZJG001_10 forms: ZJCAT defaulted value has been updated from “PHARMACOKINETICS” to “BIOMARKER" as per study team confirmation 04SEP20: RF has been finalized and SNOW 51 request RITM1765680 has been created. Note: As of today, no pending forms and no pending DTS 02SEP20: RF updated with B1L DTS and peer review is ongoing. 29-JUL-20: RF finaliized and SNOW 51 request has been raised. ZJ domain has been updated, added categories and specimen blood collection type as per team requirement. 07-JUL-20: As of today, no pending forms and no pending DTS 04-JUN-20: Rule file has been finalized with newly added forms 24h urine collection_1 (ZJG008_3) 24h urine collection_1 (ZJG008_4) Exploratory Biomarkers in Serum_1 (ZJG001_13) PD and Exploratory Biomarkers in Plasma_1 (ZJG001_14). And SNOW 51 request has been created. Note: 1. For forms ‘ZJG008_3 and ‘ZJG008_4’ (24h urine collection_1), ZJCAT is coming as blank and same has been informed to Lead DBD for to fix the issue. 2. Since UAT data is not coming, PROD data has been taken for to validate Rule file logic. 27MAY20: It's a critical issue: For forms ZJG008_3, ZJG001_14 and ZJG001_13 SOD data is not coming either in DEV, UAT or PROD environment and Rule file development is kept on hold until issue is resolved. 04MAY20: As part of PPC 24h urine collection_1 (ZJG008_3) 24h urine collection_1 (ZJG008_4) Exploratory Biomarkers in Serum_1 (ZJG001_13) PD and Exploratory Biomarkers in Plasma_1 (ZJG001_14) Forms have been added but in the SOD data ZJG008_3, ZJG001_14 and ZJG001_13 forms are not coming. Shashi raised a request to Medidata. 21APR2020: No pending forms, included MIS001. Rule file has been finalized and snow 51 has been requested. 08Apr2020 : following up for pending form 09Mar2020: Awaiting response from SDTM programmer following up on the same. 02MAR202: SDTM annotations has bee requested and expected date of completion is 06MAR2020. No data available yet. 13Feb2020 : MIS001 This is a special form entered by Specialty data provider and no data available yet in this form. Form design update is expected. Awaiting confirmation from TDM 03Feb2020 : Rule file finalized for PPC on 27Jan2020, LSH setp for PPC completed on 28Jan2020. 09-JAN-20: Additional Part 2 forms are missing, By 09-JAN-20 will update rule file and send for peer review. ZJG004_1,DSG005_1,MIS001,PRS001,CMS001,ZJG008_1,ZJG008_2,ZJG004_2,ZJG004_3,ZJG001_5,ZJG001_6,ZJG001_7,ZJG001_8,ZJG001_9,ZJG001_10,ECG003_1,ZJG001_ 17-DEC-19: Part 2 PPC changes needs to be included in Rule file and tentative date of completion is 23-DEC-19. 29-NOV-2019: New CRF's has been added as part of part 2, Rule fie update is ongoing and it will completed by 04-DEC-19 | None | None | 2018-04-04 05:30 | Legacy Process | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2018-04-09 | Completed | 2020-05-26 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-04-06 05:30 | 2018-04-06 05:30 |  | 2020-03-06 05:30 |  |  | N/A | 100 | RaveX - Inhouse | Yes | ZK;#ZK02 | 2021-08-04 05:30 | 2021-08-06 05:30 | [9 empty] | NA | [5 empty] | 21 | 15 | 78 | 0 | 158 | 1183 | 0 | 242 | 33 | 314 | 1530 | 4 | 0 |  | IgA nephropathy | No | Global | Open | Yes | [10 empty] | 2020-05-26 05:30 |  |  |  | DBL | Sundar, N Sushant | Pioneer;#GDD annual target | Yes
CLNP023C1 | CLNP023X2204 | C1200305 | Phase II | NCDS | CRO - EDC |  |  | 2019-04-05 05:30 | DB Conduct | Final DBL | 2022-04-11 05:30 | 2019-04-05 05:30 | 2018-09-27 05:30 | 2018-10-05 05:30 |  | Active | 2022-02-28 05:30 |  | 2022-04-11 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A multi-center, randomized, open-label, efficacy, safety, pharmacokinetics and pharmacodynamics study, assessing multiple LNP023 doses in adult patients with paroxysmal nocturnal hemoglobinuria and active hemolysis | CLNP023X2204 PoM in PNH Naive | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Izabela Rozenberg; Louise Mooney | Yaliang Li | [15 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | CMED | [19 empty] | Paroxysmal nocturnal haemoglobinuria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064A02102 | C4010314 | Phase I | Other |  |  |  | 2023-01-23 05:30 |  | Final DBL | 2023-04-25 05:30 |  | 2022-10-22 05:30 |  |  | Planned | 2023-03-28 05:30 |  | 2023-04-25 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLOU064A02102 Human ADME | P7 Immunology Hepatology and Dermatology | [5 empty] | Melissa Hackling | Melissa Hackling | [66 empty] | Autoimmune disorder | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064A02103 | C4008063 | Phase I | Other |  |  |  | 2021-11-10 05:30 |  | Final DBL | 2022-05-27 05:30 | 2021-11-15 05:30 | 2021-10-03 05:30 | 2021-09-06 05:30 |  | Active | 2022-04-29 05:30 |  | 2022-05-27 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLOU064A02103 DDI Study-induction & intestinal PgP | P7 Immunology Hepatology and Dermatology | [5 empty] | Robert Beecham | Robert Beecham | [66 empty] | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064A02104 | C4008928 | Phase I |  |  |  |  | 2022-10-11 05:30 |  | Final DBL | 2023-05-08 05:30 |  | 2022-05-03 05:30 | 2021-10-29 05:30 |  | Planned | 2023-03-27 05:30 |  | 2023-05-08 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CLOU064A02104 Food Effect PK study in China | P7 Immunology Hepatology and Dermatology | [5 empty] | Lin Liu | Lin Liu | [66 empty] | Chronic spontaneous urticaria | No | Global | Open | Yes
CLOU064A | CLOU064A1301 | C4008915 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-11-26 05:30 | 2021-11-26 05:30 | 2022-05-13 05:30 | DB Conduct | DB Snapshot | 2022-05-31 05:30 | 2022-01-15 05:30 | 2021-06-07 05:30 | 2021-07-01 05:30 |  | Active | 2024-01-09 05:30 |  | 2024-02-20 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multicenter, randomized, double-blind, placebo- controlled Phase 3 study of remibrutinib (LOU064) to investigate the efficacy, safety and tolerability for 52 weeks in adult Japanese chronic urticaria patients inadequately controlled by H1-antihistamines. | CLOU064A1301 Japan Ph3 1 year | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Hagiwara, Yayoi | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | TOMOKO YUTORI | TOMOKO YUTORI | Suzuki, Hiroko | Gehlawat, Priya |  |  |  |  | DRM | Mopuru, Satwik | Mopuru, Satwik | Completed | 04Feb2022: Rule file version 2.0 has been finalized. DTS (QS1L,QS2L,QS3L,QS4L,QS5L,QS6L,QS7L,QS8L,EG1L,LB1L,APQS1L) are added in the Rule file. 26Nov2021: Database go-live has been completed and Rule file Version 1.0 has been finalized in CREDI. 24Nov2021: Rule file peer review has been completed. Go-live has been pushed to 26Nov2021. 08Nov2021: Rule file has been sent for the Peer review. 26Oct2021: Rule file development has been started. 25Oct2021: Review of ALS, SDTM Annotation, SRFs are completed. 21Oct2021: Received ALS, SDTM Annotation, SRFs. Go-live has been pushed to 10-Nov-2021. 06Jul2021 : RF developer assigned. | None | None | 2021-11-26 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2022-01-11 | Completed | 2022-02-15 05:30 |  |  | 2022-02-15 05:30 | 2022-02-15 05:30 |  | 2022-02-15 05:30 |  |  |  | 0 | [14 empty] | NA | [5 empty] | 1 | 14 | 60 | 0 | 134 | 670 | 0 | 196 | 39 | 153 | 862 | 12 | 0 |  | Chronic spontaneous urticaria | No | Local | Open | Yes |  | Ongoing |  | Ongoing | [6 empty] | 2022-01-12 05:30 | [5 empty] | None of the above
CLOU064A0 | CLOU064A2101 | C4000097 | Phase I | Other |  |  |  | 2022-06-16 05:30 |  | Final DBL | 2023-11-08 05:30 |  | 2022-03-25 05:30 |  |  | Planned | 2023-10-04 05:30 |  | 2023-11-08 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLOU064A2101 Organ Impairment Study (Hepatic) | P7 Immunology Hepatology and Dermatology | [5 empty] | Louise Mooney | Louise Mooney | [66 empty] | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A | CLOU064A2102 | C4000096 | Phase I | Other |  |  |  | 2021-08-06 05:30 |  | Final DBL | 2022-05-17 05:30 |  | 2021-05-06 05:30 |  |  | Planned | 2022-04-12 05:30 |  | 2022-05-17 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CLOU064A2102 TQT Study | P7 Immunology, Hepatology and Dermatology | [6 empty] | Louise Mooney | [66 empty] | Chronic spontaneous urticaria | No | Global | [18 empty] | None of the above
CLOU064A | CLOU064A2201 | C3003612 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-04-17 05:30 | 2019-05-20 05:30 | 2019-06-17 05:30 | DB Locked | Final DBL Achieved |  | 2019-06-06 05:30 | 2018-06-01 05:30 | 2019-01-09 05:30 |  | Completed | 2021-04-24 05:30 | 2021-04-15 05:30 | 2021-05-26 05:30 | 2021-05-28 05:30 | TRUE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multicenter, randomized, double-blind, placebo- controlled phase 2b dose-finding study to investigate the efficacy, safety and tolerability of LOU064 in adult chronic spontaneous urticaria patients who are inadequately controlled by second generation H1 receptor antagonists | CLOU064A2201 Phase IIB DRF | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kulkarni, Manish | Sharma, Harish | Bhabhe, Nikhil | Ninan, Esther | Sophie Hugot | Sophie Hugot | Kurella, Rakesh Reddy | Prasanna Kumar, VTSSR |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 17Apr2019 |  | DRM | Kurella, Rakesh Reddy | Kuttoboina, Sujan Kumar | Completed | 28May2021 : DB locked 29APR21: Rule file has been finalized and SNOW 51 RITM2519155 request has been created Change : MH domain: MHPRESP variable has been added in MHI002 and MHS001 forms 16APR21: PPC8 has been initiated, change request has been reviewed and provided comments 02DEC20: LSH setup was completed on 02DEC20 and this form will not come as missing in the next report execution. Note: As per PPC5, MH and LB domains are impacted in LSH. LB domain is rebuilt and data is available in LSH. 13Nov2020 : Local lab page qualitative LBG003_TR : UBLOSTH_LVALUE (Urine blood dipstick (hemolyzed)), LBCHARES_7 (Urine blood dipstick (non-hemolyzed)) page design issue needs to handeled in RF. 03NOV2020: RF has been finalized and SNOW 51 request created. No pending forms and No pending DTS as of today. 22Oct2020 : MHS001_1, LBG001_1_TR, LBG001_2_TR, LBG001_2_TR_1 and LBG001_2_TR_2 forms added and sent for peer review 9OCT20: All required documents have been recevied, RF development is ongoing. 22SEP20: PPC has been completed on 21SEP20. Requested for SOD, SRF adn SDTM annotations for to proceed RF development. 02SPE20: PPC has been initiated, waiting for updated ALS from Lead DBD for pending forms 07AUG20: PPC has been put on hold due to Interim analysis and expected date of PPC will be communicate by DBD until Rule file will be on hold. 29JUL20: Tentative date of PPC completion 31JUL20 until RF update will be on hold. 06JUL20: RF will be on hold until next PPC. During RF development noticed that Local lab pages are not inline with standard page modeling and same has been informed to Lead DBD. Study team is planning for another PPC. 3JUL20: After PPC, final ALS received on 24JUN20. RF development is ongoing for forms LBG001_1_TR, LBG001_2_TR, LBG001_2_TR_1, LBG001_2_TR_2 as per PPC. 23JUN20: PPC completed on 21JUN20. Change request form was not shared with RF developer. RF development is ongoing and tentative date of peer review is on 29JUN20. 31Mar2020 : Pending form DSG005 included in RF and sent for LSH Setup 27MAR20: Rule file update is ongoing for DSG005 form which is added in PPC, received the documents on 12March. Will release for peer review by 30MAR2020. 13MAR20: As part of PPC additional 2 forms have been added and I've received request on 12MAR2020 end of the day. Rule file needs to be developed 02Dec19 : No pending domins/DTS. No action 04Jul2019, BAICH3:RF final no further comments.Completed 06Jun19 : Peer review Pending 26Jun19 : Released for Peer review 03Jul2019,BAICH3: R1 RF review comments shared. | Study Locked | Study Locked | 2019-07-05 05:30 | Transition Study and Legacy process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2019-07-18 | Completed | 2019-07-23 05:30 |  | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-07-24 05:30 | 2019-07-24 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-09-23 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5;#YR;#ZK;#ZK02 | 2021-05-28 05:30 | 2021-06-02 05:30 | [9 empty] | NA | [5 empty] | 9 | 7 | 56 | 0 | 84 | 484 | 0 | 179 | 38 | 149 | 671 | 6 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [10 empty] | 2019-07-23 05:30 | [5 empty] | GDD annual target | Yes
CLOU064A | CLOU064A2201E1 | C3003624 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-09-04 05:30 | 2019-10-18 05:30 | DB Conduct | Final DBL | 2022-10-18 05:30 | 2019-10-24 05:30 | 2019-04-12 05:30 | 2019-04-23 05:30 |  | Active | 2022-09-06 05:30 |  | 2022-10-18 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | An open-label, multicenter, extension study to evaluate the long-term safety and tolerability of LOU064 in eligible subjects with CSU who have participated in preceding studies with LOU064 | CLOU064A2201E1 Phase IIB DRF OL Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kulkarni, Manish | Sharma, Harish | Bhabhe, Nikhil | Ninan, Esther | Sophie Hugot | Sophie Hugot | Shrivastava, Nikhil | Prasanna Kumar, VTSSR |  |  |  |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 11Aug2021 : Reassigned the study from Kranthi to Arpita. 21-Jan-2021: RF_V9.0 is finalized for EC1L DTS and PPC#3 updates on 09-Jan-2021 02-Sep-2020: Updated RF to included PPC02 changes and released for Peer review 01-Sep-2020: Received confirmation from DBP on UAT data on 31-Aug-2020, started Working on RF updated for PPC02. 07-Aug-2020: UAT data is missing in newly added CRFs via PPC02. Requested DBP/TDM to enter the data to proceed with RF updates 06-Jul-2020(Kranthi): No pending issues 07Feb2020: Finalized Rule File V4.0 including QS1L, QS2L and QS3L after DTS updates and SNOW ticket raised for LSH set up. 05Feb2020 : EG and LBL DTSs included in RF. QS1L, QS2L, QS3L will be included in version 4.0 . DTS Updates required for QS1L & QS3L 13Jan2020 (SHRIVNI5): Rule file transition ongoing. SHRIVNI5: 15th Oct: Rule file is finalized and SNOW-05 ticket has been raised for LSH setup. SHRIVNI5: 17th Sep; Rule file created and sent for peer review. | None | None | 2019-10-15 05:30 | Legacy Process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | Completed | 2019-10-23 | Completed | 2019-10-23 05:30 |  |  | 2019-10-23 05:30 | 2019-10-23 05:30 |  | 2019-10-23 05:30 | 2019-10-23 05:30 |  |  |  | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 8 | 17 | 58 | 0 | 102 | 559 | 0 | 176 | 36 | 129 | 724 | 6 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [10 empty] | 2019-10-22 05:30 | [5 empty] | None of the above
CLOU064A | CLOU064A2301 | C3004430 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-28 05:30 | 2021-09-09 05:30 | 2021-11-30 05:30 | DB Conduct | DB Snapshot | 2022-05-31 05:30 | 2021-11-30 05:30 | 2021-05-17 05:30 | 2021-05-21 05:30 | 2021-08-16 05:30 | Active | 2024-03-01 05:30 |  | 2024-04-12 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multicenter, randomized, double-blind, placebo- controlled Phase 3 study of remibrutinib (LOU064) to investigate the efficacy, safety and tolerability for 52 weeks in adult chronic spontaneous urticaria patients inadequately controlled by H1-antihistamines. | CLOU064A2301 CSU Ph 3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | Anne Barron; Kathryn Cooke | Kathryn Cooke | Supraja, Samala |  |  |  | 29Apr2021 :Protocol finalization on 14 May 2021, Go live- 28 July 2021 and FPFV on 26 Oct 2021. There is a gap of more than 30 days for FPFV as we have a sister study which is the exact match of this study which needs to be cloned (need to add 1 extra assessment form- 3rd party) and this study go live is planned in Sep 2021. Then both the studies FPFV is targeted on the same day. There are 2 studies and team wants to clone from study 1 so the Golive date is in Aug2021 which will allow us to have DB build for 2nd study. Both have FPFV as 26Oct2021 Initial DB golive planned 28May2021 when DBD assigned. | As there was a complete update to screen dynamics, we need to reprogram whole dynamics again. | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 16Oct2021: Peer review is completed and the Rule file version 3.0 is finalized in CREDI. 09Oct2021: LB1L,QS2L,QS5L,QS8L,QS3L,QS4L,QS7L,QS1L,QS6L,EG1L,YRL,YDL DTS tables are added in the Rule file and sent for peer review. 12Oct2021: QS and SV domain changes have been updated in Rule file 2.0. As LSP got an issue in the LSH setup. 10Sep2021: Rule File Version 1.0 finalized in CREDI. SNOW#05 (RITM2967554) Request raised for new study setup in LSH. 08Sep2021: Rule file peer review is completed. 07Sep2021: Sent for Rule file peer review. 31Aug2021: Rule file development has been started. Go-live is pushed to 09Sep2021 26Aug2021: Review of SRFs, ALS, SDTM Annotations are completed and comments are shared with DBD. 12Aug2021: As confirmed by the DBD. Go-live is pushed to 2nd week of September, iBOW to be updated by TDM. Study Specific SRFs received for review. 9Aug2021 : Reassigned from Angella to Satwik. Satwik developed RF and Review by Angella. 24Apr2021 : RF developer assigned as per the Go-live date as 28Jul2021. | None | None | 2021-09-10 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sandeep Kadam | [28 empty] | NA | [5 empty] | 2 | 14 | 65 | 0 | 147 | 761 | 0 | 198 | 39 | 180 | 980 | 12 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [10 empty] | 2021-12-04 05:30 | [5 empty] | None of the above
CLOU064A | CLOU064A2302 | C3004602 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-28 05:30 | 2021-10-12 05:30 | 2021-11-30 05:30 | DB Conduct | DB Snapshot | 2022-05-31 05:30 | 2021-12-01 05:30 | 2021-05-17 05:30 | 2021-05-20 05:30 | 2021-10-01 05:30 | Active | 2024-03-01 05:30 |  | 2024-04-12 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | . | CLOU064A2302 CSU Ph3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | Anne Barron | Anne Barron | Supraja, Samala | Meda, Sreelakshmi | Completed | 2022-01-31 05:30 | 03May2021: Clone study of CLOU064A2301 which is supported by Supraja as Lead DBD |  | DRM | R, Pratheeksha K | Mopuru, Satwik | Completed | 16Oct2021: Peer review is completed and the Rule file version 2.0 is finalized in CREDI. 09Oct2021: LB1L,QS2L,QS5L,QS8L,QS3L,QS4L,QS7L,QS1L,QS6L,EG1L,YRL,YDL DTS tables are added in the Rule file and sent for peer review. 12Oct2021: Rule File Version 1.0 finalized in CREDI. SNOW#05 (RITM3077326) Request raised for new study setup in LSH. 09Oct2021: Rule file peer review is completed. 05Oct2021: Rule file development has been started. Released for Peer Review. 04Oct2021: Review of SRFs, ALS, SDTM Annotations are completed 01Oct2021: Received ALS, SDTM Annotations, SRFs, SODs from DBD. 10Aug2021: The DBD has confirmed that the timelines are not yet finalized. This is clone study of CLOU064A2301 study and since the study go-live for this study is pushed to end of August the timeline for CLOU064A2302 study also will be updated accordingly. 14-Jul-2021: The forms of CLOU064A2301 study are used in this study. I have asked the DBD Supraja to share the activity tracker. 06Jul2021 : RF developer assigned with Golive as 20Sep2021. | None | None | 2021-10-12 05:30 |  | Polavarapu, Vanaja | Polavarapu, Vanaja | Sandeep Kadam | [28 empty] | NA | [5 empty] | 1 | 14 | 65 | 0 | 147 | 755 | 0 | 198 | 39 | 178 | 972 | 12 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [10 empty] | 2021-12-01 05:30 | [5 empty] | None of the above
CLOU064A | CLOU064A2303B | C4008910 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-03 05:30 | Study Planned | DB Go-live | 2022-09-23 05:30 |  | 2022-06-21 05:30 |  |  | Planned | 2023-04-19 05:30 |  | 2023-05-31 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CLOU064A2303B CSU Ph3 Rollover 2301 and 2302 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Jain, Snehil Rajmal | Jain, Snehil Rajmal | Bhabhe, Nikhil | Ninan, Esther | Simi Bhat | Simi Bhat | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 55 | 0 |  |  | 0 |  |  |  | 610 | 6 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A | CLOU064A2304 | C3004646 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-01-16 05:30 | Study Planned | DB Go-live | 2022-12-20 05:30 |  | 2022-06-01 05:30 |  |  | Planned | 2024-12-17 05:30 |  | 2025-01-27 05:30 |  |  | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A global, multicenter, randomized, double-blind, active-controlled Phase 3b study to assess the efficacy, safety, and tolerability of remibrutinib 25 mg b.i.d. in comparison to omalizumab 300 mg every 4 weeks over 24 weeks in adult patients with chronic spontaneous urticaria inadequately controlled by H1-antihistamines | CLOU064A2304 CSU Ph3b | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Malvankar, Asavari | Bhabhe, Nikhil | Ninan, Esther | Khaleel Ahmad | Khaleel Ahmad | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | [7 empty] | 800 | 8 |  |  | Chronic spontaneous urticaria | No | Global | Open | Yes
CLOU064C1 | CLOU064C12301 | C4011795 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-10-08 05:30 | 2021-11-03 05:30 | 2021-12-15 05:30 | DB Conduct | Final DBL | 2030-01-03 05:30 | 2021-12-16 05:30 | 2021-07-15 05:30 | 2021-07-13 05:30 |  | Active | 2029-11-23 05:30 |  | 2030-01-03 05:30 |  | FALSE | Pioneer | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, double-dummy, parallel-group study, comparing the efficacy and safety of remibrutinib versus teriflunomide 14 mg q.d. in participants with relapsing multiple sclerosis, followed by extended treatment with open-label remibrutinib | CLOU064C12301 RMS study LOU064 vs. Aubagio | P4 Neuroscience | Chaghasbanian, Harut | Bapat, Neha | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Ana Maria Marti | Ana Maria Marti | Ganesan, Dhanalakshmi | Kala, Arpit |  |  |  |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 22Nov2021: SNOW request for LSH PROD set up was raised on 16Nov2021. Ticket number RITM3192988 (For PROD set-up). 9Nov2021: The RF is finalized on 9Nov2021, SNOW05 ticket raised for LSH test set-up (RITM3167659), LSP notified and Checklist finalized. 23Sept2021: No documents received yet. 12Aug2021: The TDM has confirmed that the FPFV will be on 15Dec2021 and the Go-Live will be postponed to 17Nov2021. 06Jul2021 : RF developer assigned with Golive as 08Oct2021. | None | None | 2021-11-16 05:30 |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | Completed | 2021-12-14 | Completed | 2021-12-14 05:30 |  |  | 2021-12-15 05:30 | 2021-12-16 05:30 |  | 2022-01-12 05:30 | [18 empty] | NA | [7 empty] | 75 | 0 |  |  | 0 |  |  |  | 1273 | 18 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2021-12-14 05:30 | [5 empty] | None of the above
CLOU064C1 | CLOU064C12302 | C4011796 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-10-08 05:30 | 2021-11-24 05:30 | 2021-12-15 05:30 | DB Conduct | Final DBL | 2030-01-03 05:30 | 2021-12-13 05:30 | 2021-07-15 05:30 | 2021-07-13 05:30 |  | Active | 2029-11-23 05:30 |  | 2030-01-03 05:30 |  | FALSE | Pioneer | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, double-dummy, parallel-group study, comparing the efficacy and safety of remibrutinib versus teriflunomide 14 mg q.d. in participants with relapsing multiple sclerosis, followed by extended treatment with open-label remibrutinib | CLOU064C12302 RMS study LOU064 vs. Aubagio | P4 Neuroscience | Chaghasbanian, Harut | Sivadasan, Arun | Hirlekar, Minal Vivek | Chitre, Vrushali | Nair, Sreesha | Ana Maria Marti | Ana Maria Marti | Supraja, Samala | Kala, Arpit |  |  | Dhanalakshmi's study released by Supraja |  | DRM | Saha, Saikat | R, Pratheeksha K | Completed | 29Nov2021: RF Checklist finalized on 29-Nov-2021. 26Nov2021: The RF has been finalized in subway on 26Nov2021 and LSH Test and PROD setup requests have been raised (Ticket numbers RITM3232134 and RITM3232200 respectively). Both test and prod setup requests raised on 26Nov2021. 12 Aug2021 : Reassigned to Pratheeksha from Saikat as its clone of CLOU064C12301 06Jul2021 : RF developer assigned with DBgolive as 08Oct2021 | None | None | 2021-11-26 05:30 |  | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2021-12-14 | Completed | 2021-12-15 05:30 |  |  | 2021-12-17 05:30 | 2021-12-20 05:30 |  | 2021-12-30 05:30 |  |  |  | 0 | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 28 | 72 | 0 | 197 | 827 | 0 | 216 | 38 | 231 | 1096 | 13 | 0 |  | Multiple sclerosis | No | Global | Open | Yes |  | Completed | 2021-12-14 05:30 | Completed | 2021-12-15 05:30 | 2021-12-15 05:30 |  |  |  |  | 2021-12-15 05:30 | [5 empty] | None of the above
CLOU064D1 | CLOU064D12201 | C4001360 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-05-24 05:30 | 2019-07-08 05:30 | 2019-07-19 05:30 | DB Locked | Final DBL Achieved |  | 2019-07-18 05:30 | 2019-01-14 05:30 | 2019-01-27 05:30 |  | Completed | 2020-06-25 05:30 | 2020-04-27 05:30 | 2020-09-16 05:30 | 2020-10-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, subject- and investigator- blinded, placebo-controlled study to assess the efficacy and safety of LOU064 in patients with inadequately controlled asthma | CLOU064D12201 Asthma POC | P8 Respiratory | Langlo, Francois | Sneha, Kumari | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Nils Burger | Nils Burger | Yadav, Santosh | Munukutla, Valli |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 24May2019 |  | DRM | Yadav, Santosh | Govula, Shashikanth | Completed | 7JAN2021: SG: No upcoming task. 5May2020: No update is required to Rule file for Rescreen after discussion with TDM. 27Mar2020 : Awaiting repose from SDTM/DATS. 19-Mar-2020: Update to Rule file put on hold. SDTM team is reviewing JReview reports to see if this update of domain mapping is required or not. 02Mar2020 : Rescreen page to be mapped to XI plan to complete it today. 17Feb2020 : All forms and Final DTS are up to date in RF | None | None | 2019-09-02 05:30 | Transition Study and Legacy Process | Tidke, Shyam | Tidke, Shyam | Rohit Varate | Completed | 2019-09-05 | Completed | 2019-09-05 05:30 |  | Pre-requisites not met | 2019-09-06 05:30 | 2019-09-06 05:30 | Pre-requisites not met | 2020-09-01 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-10-07 05:30 | 2020-10-09 05:30 | [9 empty] | NA | [5 empty] | 7 | 9 | 58 | -1 | 96 | 563 | 0 | 160 | 37 | 199 | 799 | 7 | 0 |  | Asthma | No | Global | Completed | Yes | [10 empty] | 2019-09-03 05:30 |  |  |  |  | Girvasiya, Shaili | None of the above | Yes
CLOU064E1 | CLOU064E12201 | C4002091 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-06-20 05:30 | 2019-06-26 05:30 | 2019-07-12 05:30 | DB Conduct | Final DBL | 2024-09-06 05:30 | 2019-07-12 05:30 | 2019-02-21 05:30 | 2019-03-05 05:30 |  | Active | 2024-07-19 05:30 |  | 2024-09-06 05:30 |  | FALSE | DCN Priority | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | An adaptive Phase 2 randomized double-blind, placebocontrolled multi-center study to evaluate the safety and efficacy of multiple LOU064 doses in patients with moderate to severe SjÃ¶grenâs Syndrome (LOUiSSe) | CLOU064E12201 Ph2a/b seamless study in pSS | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Tadakamalla, Pranitha | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Malika Hanser; Simi Bhat | Malika Hanser | Joshi, Alekhya | Gehlawat, Priya | Completed | 2021-07-20 05:30 | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 20Jun2019 |  | DRM | Joshi, Alekhya | Shrivastava, Nikhil | Completed | 31-Jan-2022: Raised SNOW-51 for LSH/SMT updates WRT PPC#08. There is no impact to Rule File. Notified the LSP. 28-Dec-2020: RF V8.0 updated and finalized in CREDI WRT PPC#04. SNOW-51 is raised. LSP and SMT programmer are notified. 26Nov2020: Backup: Angella Whats planned: PPC#04 is in draft state. PPC form is reviewed. Need to include in RF once database is updated. 27-Oct-2020 (SHRIVNI5): As per SDTM and clinical team's confirmation, Subject Status forms (SSG001 and SSG001_1) mapped to 'SS' domain in the Rule File V7.0 and finalized in CREDI. LSP is notified. 19-May-2020 (SHRIVNI5): LBL and QS6L DTS are included in the RF V6.0 and finalized. SNOW-51 request raised for LSH setup. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 03Mar2020 : QS and EG DTS which was pending included in RF version 11Feb2020. No pending forms or DTS. | None | None | 2019-10-01 05:30 | Transition Study | Tidke, Shyam | Varate, Rohit | Rohit Varate | Completed | 2019-10-03 | Completed | 2019-10-04 05:30 |  | Pre-requisites not met | 2019-10-03 05:30 | 2019-10-04 05:30 | Pre-requisites not met | 2020-05-07 05:30 |  |  |  |  | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 7 | 11 | 42 | 0 | 86 | 456 | 0 | 170 | 33 | 139 | 628 | 9 | 0 |  | Sjogren's syndrome | No | Global | Open | Yes | [10 empty] | 2019-10-03 05:30 | [5 empty] | None of the above
CLOU064F1 | CLOU064F12001B | C4011925 | Not Applicable | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-10-10 05:30 | Study Planned | DB Go-live | 2023-09-04 05:30 |  | 2023-11-20 05:30 |  |  | Planned | 2024-09-17 05:30 |  | 2024-10-29 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CLOU064F12001B extension for ped. + adolesc. | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Malvankar, Asavari | Bhabhe, Nikhil | Ninan, Esther |  | Sunil Dutt Pemmaraju | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 9 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064F1 | CLOU064F12101 | C4005972 | Phase I | Other |  |  |  | 2022-10-17 05:30 |  | Final DBL | 2024-03-20 05:30 |  | 2022-08-03 05:30 |  |  | Planned | 2024-01-17 05:30 |  | 2024-03-20 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CLOU064F12101 Vaccination Study (in adults) | P7 Immunology Hepatology and Dermatology | [6 empty] | Nasri Abdallah | [66 empty] | Chronic spontaneous urticaria | No | Global | Open | Yes
CLOU064F1 | CLOU064F12301 | C4005948 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-04-03 05:30 | Study Planned | DB Go-live | 2022-12-12 05:30 |  | 2022-11-11 05:30 |  |  | Planned | 2024-07-31 05:30 |  | 2024-10-09 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CLOU064F12301 Adolescent Ph3 Study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Malvankar, Asavari | Malvankar, Asavari | Bhabhe, Nikhil | Ninan, Esther |  | Sophie Hugot | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 9 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064I1 | CLOU064I12201 | C4014410 | Phase II |  | Rave EDC - Inhouse |  |  | 2022-07-18 05:30 | DB Set-Up | Final DBL | 2024-03-25 05:30 |  | 2022-02-07 05:30 |  |  | Planned | 2024-02-05 05:30 |  | 2024-03-25 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - DAx |  | CLOU064I12201 LOU064 PIE POC in Food Allergy | N5 DAx - NIBR | Langlo, Francois | Bhatkar, Priyanka | Bhatkar, Priyanka | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Leslie Taylor | Leslie Taylor | [17 empty] | Rohit Varate | [48 empty] | Food allergy | No | Global | Open | Yes
CLOU064A0 | CLOU064X1101 | C3001645 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-03-28 05:30 | 2018-04-13 05:30 | DB Locked | Final DBL Achieved |  | 2018-04-13 05:30 | 2018-03-21 05:30 | 2018-01-31 05:30 |  | Completed | 2018-08-10 05:30 | 2018-08-11 05:30 | 2018-09-28 05:30 | 2018-09-26 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI |  | CLOU064X1101 Japanese Ph I study of LOU064 | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Nishi, Nahoko | Temgire, Ganesh | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | SATORU SHINMYO | SATORU SHINMYO | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar |  |  |  |  | Pre-DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 29-NOV-2019: Study has been locked and no pending action items | Study Locked | Study Locked | 2018-05-16 05:30 | Legacy Process | Garje, Sagar |  | Rohit Varate | Completed | 2018-05-28 | Not Applicable |  |  |  | 2018-05-18 05:30 | 2018-05-18 05:30 | Retrospective DRM studies | [5 empty] | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 5 | 14 | 71 | -1 | 238 | 444 | 0 | 148 | 34 | 270 | 748 | 0 | -1 |  | Chronic spontaneous urticaria | No | Global | Completed | Yes | [16 empty] | None of the above
CLOU064A | CLOU064X2101 | C1200429 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-08-18 05:30 |  | 2015-11-30 05:30 |  | Completed | 2020-01-27 05:30 | 2020-01-27 05:30 | 2020-04-22 05:30 | 2020-04-22 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A 6-part first-in-human study of LOU064 consisting of a 4 part randomized, double-blind, placebo-controlled SAD and MAD study to investigate the safety and tolerability in healthy volunteers, subjects with atopic diathesis and subjects with atopic dermatitis, an open-label food effect study and a double-blind formulation effect study in healthy volunteers | CLOU064X2101 6-part FIH study and PoC in AD | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Marta Zambianchi | [15 empty] | Kadam, Sandeep |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [19 empty] | Multiple sclerosis; Rheumatoid arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064X2102 | C1001340 | Phase I | NCDS | CRO - EDC |  |  | 2018-05-07 05:30 | DB Locked |  |  | 2018-04-17 05:30 |  | 2017-11-09 05:30 |  | Completed | 2018-07-31 05:30 | 2018-07-12 05:30 | 2018-10-31 05:30 | 2018-10-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI |  | CLOU064X2102 DDI COC and CYP3A and 2C substrates | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [15 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | Parexel | [19 empty] | Chronic spontaneous urticaria; Multiple sclerosis; Rheumatoid arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064X2103 | C3001647 | Phase I | NCDS | CRO - EDC |  |  | 2018-07-20 05:30 | DB Locked |  |  | 2018-06-27 05:30 | 2018-04-16 05:30 | 2018-04-19 05:30 |  | Completed | 2018-07-09 05:30 | 2018-08-07 05:30 | 2018-11-01 05:30 | 2018-10-29 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI |  | CLOU064X2103 DDI study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [15 empty] | Polagoni, Bharghavi |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | Parexel | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 450 | 2 | 0 |  | Chronic spontaneous urticaria; Rheumatoid arthritis | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A0 | CLOU064X2104 | C1200335 | Phase I | Other | CRO - EDC |  |  | 2019-08-28 05:30 | DB Locked |  |  | 2019-08-29 05:30 | 2019-05-10 05:30 | 2019-05-29 05:30 |  | Active | 2020-12-30 05:30 | 2021-01-06 05:30 | 2021-02-03 05:30 | 2021-04-14 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A single-center, open-label study to evaluate the absorption, distribution, metabolism and excretion (ADME) and pharmacokinetics of LOU064 following a single oral dose of [14C]LOU064 in healthy male and female subjects at steady state | CLOU064X2104 Human ADME | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | PRA Health | [19 empty] | Autoimmune disorder | No | Global | Open | Yes | [16 empty] | None of the above
CLOU064A | CLOU064X2105 | C4000308 | Phase I | NCDS | CRO - EDC |  |  | 2020-06-15 05:30 | DB Locked |  |  | 2020-06-13 05:30 | 2020-02-25 05:30 | 2020-02-28 05:30 |  | Active | 2020-07-08 05:30 | 2020-07-15 05:30 | 2020-08-31 05:30 | 2020-08-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | Relative Bioavailability study LOU064 | CLOU064X2105 Relative Bioavailability study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | Celerion | [19 empty] | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CLRX712A1 | CLRX712A12201 | C4002180 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-11-12 05:30 | 2020-03-20 05:30 | 2020-07-20 05:30 | DB Conduct | Final DBL | 2024-05-20 05:30 | 2020-07-20 05:30 | 2019-09-10 05:30 | 2019-09-13 05:30 |  | Active | 2024-03-04 05:30 |  | 2024-05-20 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A randomized, placebo-controlled, subject and investigator blinded study investigating the safety, tolerability and preliminary efficacy of 8-week treatment with intra-articular LRX712 to regenerate articular cartilage in patients with mild/moderate knee osteoarthritis | CLRX712A12201 PoM study in early OA | N4 MSD - NIBR | Langlo, Francois | Donta, Alekhya Balaiah | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | David Sanchez Ramos | David Sanchez Ramos | Suzuki, Hiroko | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Hiroko Suzuki transitioned the study to Chandana Sarasani on 23-Apr-2020. Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 12Nov2019 |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 3Dec2021: The RF updates for PPC 04 is done and SNOW51 ticket raised on 3Dec2021 (Ticket number - RITM3255503). RF Checklist is also finalized in CREDI 26May2021 : Reassigned the study from Praveen Oguri to Pratheeksha. 26-Apr-2021: RF finalized on 19-Apr-2021 and raised SNOW ticket RITM2479208 for DEG001. 19-Apr-2021: Form included in RF Version 5.0. Peer review in process. RF will be finalized on 19-Apr-2021. 06APr2021 : LC - DEG001 form in missing forms and DTS Report. 05Nov2020: RF finalized and raised SNOW ticket on 16Oct2020. 18Sep2020 : LBG002_TR included in RF and SNOW raised. 11Sep2020: Updated RF and peer review activity is in progress. 02Sep2020 : As per 02Sep2020 missing forms DTS report LBG002_TR form pending. Praveen to update status 10-Aug-2020: Working on RF updates for LBG002_TR PPC04. 29Jul2020: LBL DTS is added in RF Version 3.0 finalized on 08Jul2020. Sent email to LSP for conformation on DTS setup in LSH. 02Jul2020: LBL flagged in missing report. notified DBD. 08Apr2020 : Rule file final included all forms and raised Snow ticket for PreDRM/SMT/LSH setup. Not received any DTSs yet for this study. 06Apr2020 : Fixed peer review comments and sent for 2nd round of Peer review 27Mar2020 : Received Peer review feedback from Bhaskar 19-Mar-2020: Praveen working on RF. Will be released to Peer review on 20-Mar-2020. Study RF activities assigned to Praveen from Shashi as Praveen developed the RF. Notified the DBD. 09Mar2020 : Kranthi working on RF. SDTM annotations pending for 1 form. for rest for the forms RF is ready. 02Mar2020 : Need to followup with SDTM programmer for 3 forms which is holding up the RF. 12Feb2020 : Kranthi will support RF in Shahsi's Absence 10Feb2020 : RF not started. 3 forms SDTM annotations pending. Domain mismatch (ZW to QS) which will impact study design and DBD discussing with CTT. 30-Dec-2019: Awaiting SDTM annotations for some pages. Design issues identified for study specific page, informed DBD to update. | None | None | 2020-04-08 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-04-17 | Completed | 2020-04-24 05:30 |  |  | 2020-04-24 05:30 | 2020-04-24 05:30 |  | 2020-08-25 05:30 |  |  | DDPASS is not yet completed as we don't have enough data in the study. |  | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 6 | 18 | 58 | 0 | 152 | 685 | 0 | 183 | 44 | 159 | 888 | 3 | 0 |  | Osteoarthritis | No | Global | Open | Yes | [10 empty] | 2020-04-22 05:30 | [5 empty] | None of the above
CLRX712A1 | CLRX712X2101 | C1200478 | Phase I | NCDS | CRO - EDC |  |  | 2017-12-01 05:30 | DB Locked |  |  | 2017-11-20 05:30 |  | 2017-08-21 05:30 |  | Completed | 2019-03-26 05:30 | 2019-03-26 05:30 | 2019-06-28 05:30 | 2019-06-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A randomized, placebo controlled, subject and investigator\nblinded, first-in-human, single ascending dose study to\nevaluate the safety, tolerability, and pharmacokinetics after\nintra-articular injection of LRX712 into the knee of\nosteoarthritic patients | CLRX712X2101 FIH in OA | N4 MSD - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | David Sanchez Ramos | David Sanchez Ramos | [15 empty] | Challa, Nandini |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | CMED | [19 empty] | Osteoarthritis knee | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CLSZ102A1 | CLSZ102X2101 | C3000358 | Phase I | NCDS | OC RDC - Inhouse | 2017-08-10 05:30 | 2017-08-10 05:30 | 2018-07-10 05:30 | DB Conduct |  |  | 2016-06-14 05:30 | 2018-02-20 05:30 | 2016-02-03 05:30 |  | Active | 2021-10-15 05:30 | 2021-09-13 05:30 | 2021-11-11 05:30 | 2021-11-23 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I/Ib, open label study of LSZ102 single agent and LSZ102 in combination with either LEE011 (LSZ102 + LEE011) or BYL719 (LSZ102 + BYL719) in patients with advanced or metastatic ER+ breast cancer who have progressed after endocrine therapy\n | CLSZ102X2101 Phase I/Ib Breast Cancer Study | N7 Oncology - NIBR | Langlo, Francois | Vivier, Gregoire | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Renee Pashos | Ourania Pashos | Iliyas, Mohamed | Dadapogu, Jesica Priyadarshini |  | 2020-03-04 05:30 | [11 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | I will schedule DDPASS session near any major timeline. | 100 | OCRDC - Inhouse | Yes | -NA- | 2021-12-17 05:30 | 2021-12-21 05:30 |  |  | ONC | Novartis | ICON | 2016-04-19 05:30 | 2016-04-19 05:30 | Mareedu, Vasu | Gehlawat, Priya | IQVIA | [7 empty] | 174 | 0 |  |  | 0 |  |  |  | 680 | 8 | 0 |  | Breast cancer; Breast cancer metastatic | No | Global | Open | Yes | [14 empty] | DBL |  | None of the above | Yes
CLTP001A1 | CLTP001A12201 | C4004150 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-04-10 05:30 |  | 2022-04-04 05:30 | DB Set-Up | Final DBL | 2024-07-05 05:30 |  | 2021-08-10 05:30 | 2021-07-30 05:30 |  | Planned | 2024-06-10 05:30 |  | 2024-07-05 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomzied, participant- and investigator-blinded, placebo-controlled study to investigate efficacy, safety and tolerability of LTP001 in participants with pulmonary arterial hypertension | CLTP001A12201 PAH PoC | N5 DAx - NIBR | Langlo, Francois | Gundu, Ananth Reddy | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Branson Facemire; Gavin Ryan; Sachin Desai | Sachin Desai | Sinha, Deepakshi | Sinha, Deepakshi | [5 empty] | Saha, Saikat | Saha, Saikat | Ongoing | 15Feb2022: DBD confirmed that the go-live pushed to 21-Feb-2022. 9Feb2022: DBD provided the updated ALS along with the comments. Sent further comments over those and asked for the SOD. 4Feb2022: Reviewed the ALS and provided the comments to the DBD to work on the updates. The Go-live is confirmed on 16-Feb-2022. Started RF build. 3Feb2022: Received the Latest ALS, SRFs and RADA report today. Will review the ALS and provide the comments. The timelines are still under the discussions. 10Jan2022: Asked the DBD for the study docs, study is not ready yet, didn't receive any confirmation on the timelines as well. 1Nov2021 : DBD confirmed that the timelines are still under discussion. Will inform as soon as it gets finalized. 19Oct2021 : Sent mail to the DBD to provide the activity planner and to confirm the database go-live date. |  |  |  |  | Ramayanam, Vinay | Ramayanam, Vinay | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Pulmonary arterial hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CLTP001A1 | CLTP001A12201E1 | C4011884 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-05 05:30 | Study Planned | DB Go-live | 2022-05-03 05:30 |  | 2022-03-09 05:30 |  |  | Planned | 2025-04-09 05:30 |  | 2025-05-14 05:30 |  |  | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP |  | CLTP001A12201E1 Extension study to CLTP001A12201 | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Sachin Desai | Sachin Desai | [17 empty] | Rohit Varate | [45 empty] | 8 |  |  | Pulmonary arterial hypertension | No | Global | Open | Yes
CLTP001A0 | CLTP001X2101 | C1200373 | Phase I | Other | CRO - EDC |  |  | 2019-12-02 05:30 | DB Conduct | Final DBL | 2022-03-08 05:30 | 2019-12-17 05:30 | 2019-08-19 05:30 | 2019-08-19 05:30 |  | Active | 2022-01-14 05:30 |  | 2022-03-08 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CLTP001X2101 FIH SAD/MAD in HV | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Sachin Desai | Sachin Desai | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Pulmonary arterial hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CLTT462A0 | CLTT462A02101 | C4012434 | Phase I | Other |  |  |  | 2023-03-21 05:30 |  | Final DBL | 2023-10-04 05:30 |  | 2022-09-06 05:30 |  |  | Planned | 2023-10-04 05:30 |  | 2023-10-04 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02101 LTT462 Renal Impairment | N7 Oncology - NIBR | [6 empty] | Christine Reynolds | [66 empty] | Melanoma | No | Global | Open | Yes
CLTT462A0 | CLTT462A02102 | C4012429 | Phase I | Other |  |  |  | 2023-04-04 05:30 |  | Final DBL | 2023-05-02 05:30 |  | 2023-02-06 05:30 |  |  | Planned | 2023-05-29 05:30 |  | 2023-05-02 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02102 LTT462 Human ADME | N7 Oncology - NIBR | [6 empty] | Melissa Hackling | [66 empty] | Metastatic melanoma | No | Global | Open | Yes
CLTT462A0 | CLTT462A02103 | C4012431 | Phase I | Other |  |  |  | 2023-01-10 05:30 |  | Final DBL | 2023-11-29 05:30 |  | 2022-08-30 05:30 |  |  | Planned | 2023-07-26 05:30 |  | 2023-11-29 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02103 Hepatic Impairment | N7 Oncology - NIBR | [6 empty] | Christine Reynolds | [66 empty] | Melanoma | No | Global | Open | Yes
CLTT462A0 | CLTT462A02104 | C4012430 | Phase I | Other |  |  |  | 2022-06-23 05:30 |  | Final DBL | 2022-12-20 05:30 |  | 2022-03-08 05:30 |  |  | Planned | 2023-01-06 05:30 |  | 2022-12-20 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02104 LTT462 Food Effect | N7 Oncology - NIBR | [5 empty] | Robert Beecham | Robert Beecham | [66 empty] | Melanoma | No | Global | Open | Yes
CLTT462A0 | CLTT462A02105 | C4012432 | Phase I | Other |  |  |  | 2023-01-24 05:30 |  | Final DBL | 2023-12-13 05:30 |  | 2022-09-13 05:30 |  |  | Planned | 2023-10-11 05:30 |  | 2023-12-13 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02105 DDI, CYP3A4 inhib (perpetrator) | N7 Oncology - NIBR | [6 empty] | Christine Reynolds | [66 empty] | Melanoma | No | Global | Open | Yes
CLTT462A0 | CLTT462A02106 | C4012433 | Phase I | Other |  |  |  | 2023-01-31 05:30 |  | Final DBL | 2023-07-11 05:30 |  | 2022-09-20 05:30 |  |  | Planned | 2023-08-16 05:30 |  | 2023-07-11 05:30 | [5 empty] | FULL Outsourced |  |  | CLTT462A02106 DDI CYP3A4 & 2C8 mod (victim) | N7 Oncology - NIBR | [6 empty] | Christine Reynolds | [66 empty] | Melanoma | No | Global | Open | Yes
CLTT462A1 | CLTT462X2101 | C1001702 | Phase I | NCDS | OC RDC - Inhouse |  | 2012-02-25 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-04-15 05:30 |  | 2015-11-06 05:30 |  | Completed | 2019-07-17 05:30 | 2018-11-21 05:30 | 2019-02-12 05:30 | 2019-02-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I dose finding study of oral LTT462 in adult patients with advanced solid tumors harboring MAPK pathway alterations. | CLTT462X2101 TCO-PhI-FIH-oral-MAPKmut-solid-tumor | N7 Oncology - NIBR | Langlo, Francois | Mocherla, Ramesh | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Helen Evans | Helen Evans | Pilli, Bhaskar | [14 empty] | K, Gunasekaran |  | Rohit Varate | [13 empty] | 100 | OCRDC - Inhouse | Yes | DV;#SV |  |  |  |  | ONC | Novartis | InHouse | 2016-02-25 05:30 | 2016-02-25 05:30 |  |  | NA | [7 empty] | 274 | 0 |  |  | 0 |  |  |  | 776 | 6 | 0 |  | Melanoma; Non-small cell lung cancer; Ovarian cancer; Solid tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CLTW888A1 | CLTW888A11301 | C4001572 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-02-13 05:30 | 2020-07-16 05:30 | 2020-11-24 05:30 | DB Conduct | Interim DBL | 2022-04-27 05:30 | 2020-11-24 05:30 |  | 2019-10-23 05:30 |  | Active | 2026-06-01 05:30 |  | 2026-06-19 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | An open-label, single-arm study to provide efficacy and safety data of voretigene neparvovec administered as subretinal injection in Japanese patients with biallelic RPE65 mutation-associated retinal dystrophy | CLTW888A11301 Phase III_Safety Efficacy_Japan | P5 Ophthalmology | Navarro, Christelle | Ohmori, Hiroko | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | TOMOKO YUTORI | TOMOKO YUTORI | Suzuki, Hiroko | Thomas, Ankit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 13Feb2020 |  | DRM | Bai, Chandrakala | Kuttoboina, Sujan Kumar | Completed | 10JAN22: RF Version 4.0 is final and SNOW 51 RITM3365544 request has been created. Requested to rebuild SV, VE and PR domains as per below changes. SV and VE domains: SVG001 form: ASSNAME_STD has been removed for to resolve downstream issue since no dynamic search list has been added in the database PR domain: PRS001 form: PRBLEB and PRBLEB_RAW fields have been added as part of PPC3 21OCT21: RF V3.0 is final and SNOW 51 RITM3107941 has been created. Requested LSP to rebuild PR, FAPR, CM, DS, SV, ZX and build VE domain as part of PPC3. 12JAN21: Rule file has been finalized as part of PPC1. SNOW 51 request RITM2156618 has been created. Note: DSG005 and SSG001_1 forms have been added in Rule file 07DEC20: All supporting documents are received on 04DEC20 and RF development is ongoing and expected to be completed by 09DEC20. 03OCT20: All supporting documents are not received for to update Rule file. Following up with Lead DBD. 17JUL2020: RF has been finalized and SNOW 05 RITM1615460 request has been created. 07JUL2020: DB golive has been pushed to 17JUL20, RF is ready to finalize. 26JUN2020: DB golive has been pushed to July and FPFV on September. Note; RF completed and final, but CTT discussions ongoing on Protocol amendments and PD page. SNOW 05 request was cancelled. Archived documents will be terminated. 04JUN2020: RF has been finalized and SNOW 05 request has been created. 26May2020: All pending forms which had screen build issues have been included in RF 0.3. DBD has fixed the same in EDC. and sent for peer review. 30APR2020: Released for peer review. (Praveen) on 23Apr2020 excluding "Full-Field Light Sensitivity Threshold Testing (ZXS005/ ZXS005_1) and Protocol Decided Procedure_2 (FAPR)". There is form design issues for ZXwith these pages and notified DBDs . SDTM annotations were pending for FAPR which received yesterday 15Apr2020 : Release for peer review by 20th EOB. 03Apr2020 : as there were issues in screen design for 2 forms had a discussion with TDM. These forms needs an update. these forms were received 31Mar2020 for review. RF development ongoing. Tentativly will be sent for peer review by 15Apr2020. 24MAR2020: Today got approval for one more study specific page and UAT screens will be finalized by 27MAR2020 and DB golive is on 15APRIL2020. 02MAR2020: Rule file development is ongoing and expected date of completion is 17MAR20. On priority review SRFS screens to avoid PPCs. 13Feb2020 : Study assigned to Sujan from Chandrakala on 09Feb2020. Sujan to followup with Hiroko for Unique forms and docs for RF development. 07-Jan-2020:This study is on screen UAT now. 17Jan2020: Screen UAT for standard pages has been done, but study specific pages are not yet. RIS will be postponed, but not formally yet. | None | None | 2020-07-17 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2020-10-23 | Completed | 2020-11-09 05:30 | Study was assigned to Herin Kumar. FPFV happened in Sep 2020, FPFV date should be updated. LSH set up is in progress. |  | 2020-11-09 05:30 | 2020-11-09 05:30 |  | 2020-12-22 05:30 |  |  |  | 94 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 4 | 18 | 64 | 0 | 395 | 574 | 0 | 169 | 37 | 251 | 862 | 1 | 0 |  | Eye disorder | Yes | Global | Open | Yes | [10 empty] | 2020-11-06 05:30 | [5 empty] | None of the above | Yes
CLTW888A1 | CLTW888A11401 | C4002889 | Phase IV |  |  |  |  | 2020-01-06 05:30 |  | Final DBL | 2021-09-24 05:30 |  | 2019-08-16 05:30 |  |  | Planned | 2021-07-16 05:30 |  | 2021-09-24 05:30 | [5 empty] | InHouse |  |  | CLTW888A11401 Japan_PhIV_Post-registration | P5 Ophthalmology | [6 empty] | MAKOTO NAGASAKI | [66 empty] | Retinopathy | No | Global | Open | Yes
CLTW888A1 | CLTW888A12401 | C4001570 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2019-10-15 05:30 | 2019-11-13 05:30 | 2019-12-31 05:30 | DB Conduct | Final DBL | 2030-01-09 05:30 | 2019-12-18 05:30 | 2019-07-30 05:30 | 2019-07-17 05:30 |  | Completed | 2029-11-01 05:30 |  | 2030-01-09 05:30 |  | FALSE | no Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Post-Authorization, Multicenter, Multinational, Longitudinal, Observational Safety Registry Study for Patients Treated with Voretigene Neparvovec | CLTW888A12401 _Post-Approval Safety Study | P5 Ophthalmology | Navarro, Christelle |  | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Steve Burmaster | Steve Burmaster | Kuttoboina, Sujan Kumar | Thomas, Ankit |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Oct2019 |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 09SEP21: RF 9.0 is final and SNOW 51 RITM2959572 Request has been created for to rebuild PR domain as per below request PRSURGYN was renamed to PRYN in previous versons, that variable is kept as PRSURGYN as per the recent communicaton. 13AUG21: RF V8.0 is final and SNOW 51 RITM2874273 request has been created for to rebuild ZX domain. Change: Added new test code as SDTM team requirement. 05AUG21: RF V7.0 is final and SNOW 51 request RITM2839053 has been created, request to you proceed with LSH rebuild for ZX domain. 22JUL21: RF V6.0 is final as per PPC7 and SNOW 51 RITM2798733 has been created for MO, ZX and PR Domains rebuild. 17AUG20: RF was finalized and SNOW 51 RITM1636379 request was created on 24JUL20 . No pending forms are pending DTS as of today. 24JUL20: As part of dry run, new SDTM annotations have been proposed, therefor ZX domain has to be rebuild. RF peer review is ongoing. 07JUL20: As of today, no pending forms and no pending DTS. 30Mar2020 : included all pending forms and sent for LSH setup. (ZXS010_2,ZXS010_1,ZXS010,ZXS009_1,ZXS009,ZXS007_2,ZXS007_1,ZXS007,ZXS006_2,ZXS006_1,ZXS006,ZXS005_2,ZXS005_1,ZXS005,ZXS004_2,ZXS004_1,ZXS004,ZXS003_2,ZXS003_1,ZXS003,ZXS002_2,ZXS002_1,ZXS002,ZXS001,MOS001_2,MOS001_1,MOS001,PRS002, PRS002_1 forms are missi) 02MAR2020: PPC completed on 28Feb2020 and released for RF updates. RF update ongoing and the expected date of Rule file completion is 10MAR2020. 13Feb2020 : PPC is ongoing , Post PPC implementation below pending forms will be included in RF. 22-JAN-20: LSH setup has been completed with following pending forms: ZXS010_2,ZXS010_1,ZXS010,ZXS009_1,ZXS009,ZXS007_2,ZXS007_1,ZXS007,ZXS006_2,ZXS006_1,ZXS006,ZXS005_2,ZXS005_1,ZXS005,ZXS004_2,ZXS004_1,ZXS004,ZXS003_2,ZXS003_1,ZXS003,ZXS002_2,ZXS002_1,ZXS002,ZXS001,MOS001_2,MOS001_1,MOS001,PRS002, PRS002_1. And rest of the forms will be completed by 01-FEB-20 18-DEC-19: Rule file has been finalized with pending domains MO and ZX due to page design issues. 17-DEC-19: Peer review is ongoing 29-NOV-2019: Rule file development is ongoing and expected date of completion is 03-DEC-2019 | None | None | 2020-01-07 05:30 | Legacy Process | Praveen kumar, Chakka Giri | Varate, Rohit | Sai Krishna Mettugari | Completed | 2020-01-09 | Completed | 2020-01-10 05:30 | 16th Dec: Peer review is ongoing SMT development in progress. | Study Transition | 2020-01-10 05:30 | 2020-01-10 05:30 | Study Transition | 2020-03-18 05:30 |  |  |  | 100 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 8 | 2 | 45 | 0 | 65 | 419 | 0 | 92 | 2 | 203 | 624 | 1 | 0 |  | Retinopathy | No | Global | Open | Yes | [10 empty] | 2020-01-10 05:30 |  |  |  |  | Adi, Vishnupriya | HA Commitment | Yes
CLTW980A1 | CLTW980X2101 | C1200451 | Phase I | NCDS | CRO - EDC |  |  | 2018-03-06 05:30 | DB Locked |  |  | 2017-11-16 05:30 |  | 2015-11-16 05:30 |  | Completed | 2020-03-18 05:30 | 2020-03-12 05:30 | 2020-07-24 05:30 | 2020-06-10 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A randomized, subject-blinded, placebo-controlled, singleÂ ascending dose study of subcutaneous LTW980 inÂ healthyÂ subjects | CLTW980X2101 First in human/SAD for LTW980 | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Michael Ferriere | Aruna Vedala | [15 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | -NA- | [11 empty] | CMED | [19 empty] | Hypertriglyceridaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CLUA908A0 | CLUA908X2101 | C1200434 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-10-23 05:30 |  | 2016-11-28 05:30 |  | Completed | 2020-02-10 05:30 | 2019-09-25 05:30 | 2020-04-09 05:30 | 2020-01-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A first-in-human, single ascending dose, randomized,\nsubject-blinded, placebo-controlled, non-confirmatory\nstudy to assess safety, tolerability, PK and PD of\nLUA908 in healthy subjects | CLUA908X2101 FiH and PoM | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Marta Zambianchi | [15 empty] | Polagoni, Bharghavi |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Crohn's disease; Inflammatory bowel disease | No | Global | Completed | Yes | [16 empty] | None of the above
CLUM566A0 | CLUM566X2101 | C1200466 | Phase I | NCDS | [7 empty] | 2015-11-25 05:30 |  | 2015-08-20 05:30 |  | Completed |  | 2016-03-29 05:30 |  | 2016-05-12 05:30 | FALSE |  |  |  | ED InHouse |  | A randomized, open-label study to assess pharmacokinetics including food effect for two lumefantrine solid dispersion formulation variants compared to reference formulation in healthy volunteers | CLUM566X2101 | P6 Global Health | [6 empty] | Yaliang Li | [67 empty] | No | Global | Completed | Yes | [16 empty] | None of the above
CLUM566A0 | CLUM566X2102 | C1202130 | Phase I | NCDS | CRO - EDC |  |  | 2018-09-17 05:30 | DB Locked |  |  | 2018-09-04 05:30 | 2018-04-19 05:30 | 2018-05-18 05:30 |  | Completed | 2019-10-05 05:30 | 2019-10-05 05:30 | 2019-12-17 05:30 | 2019-11-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A two period, open label, randomized, parallel group study to evaluate the relative bioavailability and pharmacokinetics of new lumefantrine formulations in comparison to a reference formulation | CLUM566X2102 LUM Relative BA Study Adult | P6 Global Health | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | IQVIA | [19 empty] | Malaria | No | Global | Open | Yes | [16 empty] | None of the above
CLXE408A1 | CLXE408A12202R | C4006596 | Phase II | Other |  |  |  | 2023-09-12 05:30 |  | Final DBL | 2025-11-05 05:30 |  | 2022-12-26 05:30 |  |  | Planned | 2025-10-01 05:30 |  | 2025-11-05 05:30 |  | FALSE |  |  |  | Outsourced |  |  | CLXE408A12202R PoC in VL (Africa) | P6 Global Health | [6 empty] | Megan Osborn | [66 empty] | Visceral leishmaniasis | No | Global | Open | Yes | [16 empty] | None of the above
CLXE408A1 | CLXE408A12203 | C4006610 | Phase II | NCDS |  |  |  | 2024-07-03 05:30 |  | Final DBL | 2025-10-20 05:30 |  | 2023-09-18 05:30 |  |  | Planned | 2025-09-03 05:30 |  | 2025-10-20 05:30 | [5 empty] | Outsourced |  |  | CLXE408A12203 Ph IIb - DRF in Pediatrics | P6 Global Health | [6 empty] | Kanan Jhala | [66 empty] | Leishmaniasis | No | Global | Open | Yes
CLXE408B1 | CLXE408B12201 | C4014824 | Phase II |  |  |  |  | 2023-03-29 05:30 |  | Final DBL | 2025-03-28 05:30 |  | 2022-08-02 05:30 |  |  | Planned | 2024-12-27 05:30 |  | 2025-03-28 05:30 | [5 empty] | InHouse |  |  | CLXE408B12201 PoC in CICD | R4 NITD - NIBR | [6 empty] | Megan Osborn | [66 empty] | Infection parasitic | No | Global | Open | Yes
CLXE408A0 | CLXE408X2101 | C1200284 | Phase I | NCDS | CRO - EDC |  |  | 2019-01-10 05:30 | DB Locked |  |  | 2018-12-21 05:30 | 2018-09-11 05:30 | 2018-10-26 05:30 |  | Active | 2021-09-24 05:30 | 2021-09-27 05:30 | 2021-11-15 05:30 | 2021-12-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A first-in-human, randomized, subject blinded, placebo controlled, single and multiple ascending dose study to assess the safety, tolerability, and pharmacokinetics of LXE408 in healthy subjects | CLXE408X2101 FIH SAD/MAD | P6 Global Health | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Amanda Nguyen; Raechel Farewell | Amanda Nguyen | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Leishmaniasis | Yes | Global | Open | Yes | [16 empty] | None of the above
CLXH254A0 | CLXH254A02101 | C4012326 | Phase I | Other | CRO - EDC |  |  | 2021-09-14 05:30 | DB Conduct | Final DBL | 2022-02-09 05:30 | 2021-10-04 05:30 | 2021-02-01 05:30 | 2021-05-17 05:30 |  | Active | 2022-02-28 05:30 | 2021-12-05 05:30 | 2022-02-09 05:30 |  |  | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A phase I, randomized, open label, three period, crossover study to evaluate the relative bioavailability of a single dose from three LXH254 formulations in healthy subjects. | CLXH254A02101 rBA study | N7 Oncology - NIBR | Ball, Michael | Shah, Jay Harshadbhai | Shah, Jay Harshadbhai | Sahu, Vandana | Hiriyanna, Srinivas | Andrea Westervelt | Andrea Westervelt | [17 empty] | Sushant Sundar | [28 empty] | Celerion | [7 empty] | 130 | [7 empty] | 1500 | 5 |  |  | Metastatic melanoma | No | Global | Open | Yes
CLXH254C1 | CLXH254C12101 | C4012368 | Phase I | Other |  |  |  | 2021-12-06 05:30 |  | Final DBL | 2022-05-02 05:30 |  | 2021-05-12 05:30 |  |  | Planned | 2022-02-28 05:30 |  | 2022-05-02 05:30 | [5 empty] | FULL Outsourced |  |  | CLXH254C12101 LXH254 Human ADME | N7 Oncology - NIBR | [5 empty] | Melissa Hackling | Melissa Hackling | [66 empty] | Metastatic melanoma | No | Global | Open | Yes
CLXH254C1 | CLXH254C12105 | C4010794 | Phase I | Other |  |  |  | 2022-03-16 05:30 |  | Final DBL | 2022-08-19 05:30 |  | 2022-02-28 05:30 |  |  | Planned | 2022-06-17 05:30 |  | 2022-08-19 05:30 | [5 empty] | FULL Outsourced |  |  | CLXH254C12105 DDI with CYP3A4 inhibitor | N7 Oncology - NIBR | [6 empty] | Amanda Taylor | [66 empty] | Neoadjuvant Melanoma | No | Global | Open | Yes
CLXH254C1 | CLXH254C12106 | C4010822 | Phase I | Other |  |  |  | 2021-11-05 05:30 |  | Final DBL | 2022-06-03 05:30 | 2021-11-02 05:30 |  | 2021-09-20 05:30 |  | Active | 2022-04-29 05:30 |  | 2022-06-03 05:30 | [5 empty] | FULL Outsourced |  | A phase 1, randomized, open-label, three period, cross over study to investigate the effect of food and the effect of the proton-pump inhibitor, rabeprazole on the pharmacokinetics of a single oral dose of LXH254 in healthy participants | CLXH254C12106 DDI with PPI & Food Effect | N7 Oncology - NIBR | [5 empty] | Amanda Taylor | Amanda Taylor | [66 empty] | Melanoma | No | Global | Open: Reapproval | Yes
CLXH254C1 | CLXH254C12201 | C4007872 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-05-25 05:30 | 2020-07-15 05:30 | 2020-10-30 05:30 | DB Conduct | Final DBL | 2023-09-11 05:30 | 2020-10-30 05:30 | 2020-03-16 05:30 | 2020-03-26 05:30 |  | Active | 2023-09-08 05:30 |  | 2023-09-11 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A randomized, open-label, multi-arm, two-part, phase II study to assess the efficacy and safety of multiple LXH254 combinations in patients with previously treated unresectable or metastatic BRAFV600 or NRAS mutant melanoma. | CLXH254C12201 Phase II Melanoma Study | N7 Oncology - NIBR | Langlo, Francois | Thomas, Ashtami Rohan | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Allen Lau | Allen Lau | Bora, Deepthi Reddy | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Deepthi Reddy Borra transitioned the study to Chandana Sarasani on 05-Oct-2020. |  | DRM | Shrivastava, Nikhil | Shrivastava, Nikhil | Completed | 08-Oct-2021: There is no impact on the Rule File for this PPC#05. However for LSH and SMT updates, raised SNOW-51 (RITM3063823) and notified LSP. 21-Jun-2021: There is no impact on the Rule File for this PPC#04. However for LSH and SMT updates, raised SNOW-51 (RITM2691712) and notified LSP. 29-Apr-2021: The Rule File V5.0 updated and finalized for renaming the Lab unit field as per standard. SNOW-51 is raised and LSP is notified. 02-Mar-2021: The Rule File V4.0 WRT PPC#03 is updated and finalized in Subway. SNOW-51 is raised. LSP and SMT programmers are notified. 17-Feb-2021: PPC#03 CRF updates leading to RF impact (ZXS001_2, ZXS001_5). Reviewed the IA of PPC form and provided the comments. PPC is currently ongoing. 31-Dec-2020: Rule File V3.0 updated and finalized in Subway WRT PPC#02. SNOW-51 is raised. LSP and SMT programmers are notified. 27Nov2020: Backup: Sujan Whats planned: HitogeneX DTS is in draft state. Reviewed and provided the comments. Need to include in RF along with Lab DTS once HistogeneX is finalized. 14-Oct-2020 (SHRIVNI5): RF V2.0 updated and finalized WRT PPC#01. SNOW-51 is raised and LSP is notified. 15-Jul-2020 (SHRIVNI5): The rule file V1.0 created and finalized in Subway. SNOW-05 ticket has been raised and LSP and SMT programmer have been notified. 14-Jul-2020 (SHRIVNI5): The rule file was created as a draft version and sent for peer review. Peer review is ongoing. | None | None | 2020-07-15 05:30 |  | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-07-27 | Completed | 2020-07-27 05:30 | Completed |  | 2020-07-27 05:30 | 2020-07-27 05:30 |  | 2020-07-27 05:30 |  |  | FPFV is not happend |  | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 7 | 49 | 115 | 0 | 636 | 1006 | 0 | 279 | 48 | 256 | 1310 | 5 | 0 |  | Melanoma | No | Global | Open | Yes | [10 empty] | 2020-07-23 05:30 | [5 empty] | None of the above
CLXH254C1 | CLXH254C12202 | C4010824 | Phase I | Other |  |  |  | 2022-05-25 05:30 |  | Final DBL | 2022-09-02 05:30 |  | 2021-11-26 05:30 |  |  | Planned | 2022-10-27 05:30 |  | 2022-09-02 05:30 | [5 empty] | FULL Outsourced |  |  | CLXH254C12202 LXH254 Hepatic impairment | N7 Oncology - NIBR | [5 empty] | Amanda Taylor | Amanda Taylor | [66 empty] | Neoadjuvant Melanoma | No | Global | Open: Reapproval | Yes
CLXH254A1 | CLXH254X2101 | C1001704 | Phase I | NCDS | OC RDC - Inhouse |  | 2015-12-15 05:30 |  | DB Conduct | Final DBL | 2022-04-08 05:30 | 2016-01-18 05:30 |  | 2015-09-29 05:30 |  | Active | 2022-02-25 05:30 |  | 2022-04-08 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I dose-finding study of oral LXH254 in adult patients with advanced solid tumors harboring MAPK pathway alterations | CLXH254X2101 TCO-PhI-FIH-oral-MAPKmut-solid-tumors | N7 Oncology - NIBR | Langlo, Francois | Beukes, Ellouise | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Maria Amparo Buigues Vila | Maria Amparo Buigues Vila | Samuel, Giftson | Samuel, Giftson | [13 empty] | Rajhans, Khushbu Kumari |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2015-12-15 05:30 | 2015-12-15 05:30 | Kanchi, Pavan kumar | Mareedu, Vasu | IQVIA | [7 empty] | 240 | 0 |  |  | 0 |  |  |  | 816 | 8 | 0 |  | Melanoma; Non-small cell lung cancer; Ovarian epithelial cancer; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CLXH254B1 | CLXH254X2102 | C3000367 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-01-24 05:30 | 2018-06-08 05:30 | DB Conduct | Final DBL | 2023-02-03 05:30 | 2017-02-24 05:30 | 2018-01-19 05:30 | 2016-11-07 05:30 |  | Active | 2022-11-25 05:30 |  | 2023-02-03 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib, open-label, multicenter study of oral LXH254- centric combinations in adult patients with advanced or metastatic KRAS or BRAF mutant Non-Small Cell Lung Cancer or NRAS mutant melanoma | CLXH254X2102 Phase Ib Malginant Melanoma & NSCLC | N7 Oncology - NIBR | Langlo, Francois | Saddek, Bochra | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Helen Evans; Xuan-Mai Couillebault | Xuan-Mai Couillebault | Katam, Veera Nagendra | Bai, Chandrakala |  | 2020-03-04 05:30 | [11 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | This doesnt have any reporting activity planned, so planned to schedule DDPASS around may 2019 | 0 | OCRDC - Inhouse | No | [5 empty] | ONC | Novartis | ICON | 2017-01-27 05:30 | 2017-01-27 05:30 | Mareedu, Vasu | Gehlawat, Priya | IQVIA | [7 empty] | 171 | 0 |  |  | 0 |  |  |  | 752 | 6 | 0 |  | Malignant melanoma; Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CLXS196A1 | CLXS196X2101 | C1200395 | Phase I | NCDS | OC RDC - Inhouse | 2016-01-08 05:30 | 2016-01-08 05:30 |  | DB Conduct | Final DBL | 2022-02-14 05:30 | 2016-02-01 05:30 |  | 2015-10-15 05:30 |  | Active | 2022-01-07 05:30 |  | 2022-02-14 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I, multi-center, open-label dose, escalation study of LXS196, an oral protein kinase C inhibitor, in patients with metastatic uveal melanoma | CLXS196X2101 | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Adonai Fessehatsion | Adonai Fessehatsion | Joshi, Alekhya | Shewane, Roshni | Completed | 2021-07-16 05:30 | Study Transitioned to Roshni Shewane on 16-Jul-2021. | [10 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2016-01-13 05:30 | 2016-01-13 05:30 | Mareedu, Vasu | Shewane, Roshni | IQVIA | [7 empty] | 212 | 0 |  |  | 0 |  |  |  | 835 | 5 | 0 |  | Melanoma | No | Global | Open | Yes | [16 empty] | None of the above
CLYS006A1 | CLYS006A12201 | C4015068 | Phase II | NCDS_2 |  |  |  | 2023-03-15 05:30 |  | Final DBL | 2025-04-28 05:30 |  | 2022-05-06 05:30 |  |  | Planned | 2025-03-14 05:30 |  | 2025-04-28 05:30 | [5 empty] | InHouse |  |  | CLYS006A12201 Ph2b DRF | P7 Immunology Hepatology and Dermatology | [6 empty] | Marilyn Cines | [54 empty] | 60 | [7 empty] | 800 | 6 |  |  | Acne | No | Global | Open | Yes
CLYS006A0 | CLYS006X1101 | C3002978 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-12-20 05:30 | 2020-12-10 05:30 | 2021-01-30 05:30 | DB Locked | Final DBL Achieved |  | 2021-01-30 05:30 | 2020-09-23 05:30 | 2020-10-05 05:30 |  | Completed | 2021-04-13 05:30 | 2021-04-13 05:30 | 2021-05-25 05:30 | 2021-05-25 05:30 | FALSE | Compound Cross Project | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI |  | CLYS006X1101 Phase I in Japanese | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Oda, Azusa | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | SATORU SHINMYO | SATORU SHINMYO | Musku, Srikanth Reddy | Musku, Srikanth Reddy | Not Started |  | Initial go live as 20Dec2020 when RF developer assigned on 29Jul2020. |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 17May2021: RF v4.0 is finalized for DSG005 logic update as per SDTM team request . 24Mar2021: RF v3.0 with DSG001 logic rectification finalized. 7JAN2021: SG: No upcoming tasks. 10Dec2020 : RF final and SNOW 05 raised 5Nov2020: DB golive planned for 4Dec2020. RF update ongoing. 05Oct2020 : Followup with DBD on current status. | None | None | 2020-12-10 05:30 |  | Ramayanam, Vinay | Varate, Rohit | Rohit Varate | Completed |  | Completed | 2021-01-11 05:30 |  |  | 2021-01-20 05:30 | 2021-01-20 05:30 |  | 2021-01-20 05:30 |  |  |  |  | RaveX - Inhouse | Yes |  | 2021-05-25 05:30 | 2021-05-28 05:30 | [9 empty] | NA | [5 empty] | 2 | 9 | 51 | 0 | 119 | 526 | 0 | 180 | 32 | 153 | 711 | 1 | 0 |  | Acne | No | Global | Open: Reapproval | Yes | [10 empty] | 2021-01-11 05:30 | [5 empty] | None of the above | Yes
CLYS006A0 | CLYS006X2101 | C1200455 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-10-27 05:30 |  | 2016-08-03 05:30 |  | Completed | 2017-11-20 05:30 | 2017-11-27 05:30 | 2018-05-16 05:30 | 2018-02-07 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ATI | A First-in-Human randomized, subject-blinded and investigator-partial blinded, placebo-controlled, ascending single and multiple dose study to explore the safety, tolerability, pharmacokinetics and food effect of orally administered LYS006 in healthy subjects | CLYS006X2101 | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Romain Barnouin | Romain Raphael Barnouin | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | [12 empty] | CMED | [19 empty] | Acne | No | Local | Completed | Yes | [16 empty] | None of the above
CLYS006A0 | CLYS006X2102 | C4002357 | Phase I | NCDS | Other |  |  | 2019-10-10 05:30 | DB Locked |  |  | 2019-08-29 05:30 | 2019-01-31 05:30 | 2019-03-07 05:30 |  | Completed | 2019-11-28 05:30 | 2019-11-18 05:30 | 2019-12-23 05:30 | 2019-12-18 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | An open-label, randomized, multiple-dose, crossover study to determine the bioavailability of LYS006 enteric resistant capsules relative to immediate release capsules. | CLYS006X2102 Bioavailability and food effect | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Pharmacokinetic study | No | Global | Open | Yes | [16 empty] | None of the above
CLYS006A1 | CLYS006X2201 | C1200299 | Phase II | NCDS | CRO - EDC |  |  | 2018-08-31 05:30 | DB Conduct | Final DBL | 2022-05-31 05:30 | 2018-09-10 05:30 | 2018-04-11 05:30 | 2018-02-12 05:30 |  | Active | 2022-03-14 05:30 |  | 2022-05-31 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, subject and investigator blinded, placebo-controlled, multi-center study in parallel groups to assess the efficacy and safety of LYS006 in patients with moderate to severe inflammatory acne - | CLYS006X2201 PoC in Acne. | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Navin Mahajan | Navin Mahajan | [15 empty] | Varate, Rohit |  | Rohit Varate | [13 empty] | 0 | FSOM - Outsourced |  | -NA- | [11 empty] | CMED | [19 empty] | Acne | No | Global | Open | Yes | [16 empty] | None of the above
CLYS006B1 | CLYS006X2202 | C1200326 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-12-04 05:30 | 2020-01-07 05:30 | 2020-02-14 05:30 | DB Conduct | Interim DBL | 2022-08-08 05:30 | 2020-02-03 05:30 | 2019-07-30 05:30 | 2019-07-29 05:30 |  | Active | 2023-08-18 05:30 |  | 2023-10-09 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A randomized, multi-center, subject and investigator blinded, placebo controlled, parallel group study to assess the efficacy, safety and tolerability of LYS006 in patients with mild to moderate ulcerative colitis | CLYS006X2202 Ulcerative colitis | N0 ATI - NIBR | Langlo, Francois | Palav, Mahesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Johanne Sanni | Johanne Sanni | Rao, S Shashikanth | Rao, S Shashikanth | Not Started |  | As of 27Nov 2019 the planned golive is 04Dec2019. |  | DRM | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 17SEP2021: RF 8.0 is final and SNOW 51 request RITM2988464 has been created, requested LSP to rebuild FAMH and DV domains as part of PPC 02JUL2021: RF 7.0 is final and SNOW 51 RITM2735216 request has been created. Changes: ZJ domain: ZJG004_1, ZJG004 forms have been added as per the update request in PPC#04 22JAN2021: Rule file 6.0 has been finalized with following changes and SNOW 51 RITM2193371 request has been raised. 1. QS domain: As per study confirmation MOS001 has been mapped under QS domain and MOS001 form has been removed from MO domain. Note: Going forward MOS001 form would not be used in the study and the domain update only for entered data 2. QS domain: QS1S638_TR Form "QSRESCD_3 and QSRESCD_3_STD" have been renamed to "QSRESCD_3_1 and QSRESCD_3_1_STD" 3. QS domain: QS1L DTS has been added 4. MO domain: MO1L DTS has been added 7JAN2021: SG: Request to map MO to QS for MOS001 page. Received SDTM annotations on 6Jan2021. Also to update MO, QS DTS's received on 7Jan2021. 02Nov2020: RF v5.0 finalized in CREDI and SNOW#51 raised. 1. DDG001: This is not included in RF v5.0 as confirmed by DBD, Death form(DDG001) was added by mistake and no data is present hence in next PPC form will be removed. 2. QS forms: As per PPC#3 Form OIDs have been updated for the below -Patient Global assessment from QS579_TR to QS666_TR -Physician's Global Assessment from QS571_TR to QS622_TR hence, included 'QS666_TR' and 'QS622_TR' missing forms in QS domain via RFv5.0 as per DBP confirmation. 3. LBL dts was already part of RFv4.0. 19Oct2020: RF in review status, awaiting for updated sod from DBD. 05Oct2020 : Chandrakala will work on the penidng forms and DTS. 25Sep2020: Will prioritize and update Pending forms and DTS this week 8Sep2020: PPC changes will be released for review by 11Sep2020. 02Sep2020 : As per 02Sep2020 missing forms DTS report "QS1S579_TR, QS1S666_TR, QS1S571_TR, QS1S622_TR, DDG001" forms pending . There was PA and forms with issues (below updates) have been fixed in PPC-3. Received documents for RF development on 25Aug2020. 11AUG2020: LBL DTS included. PPC not yet implemented. 06Jul2020: Followup email sent to DBD on missing forms and DTS as its been flagged in report. 22Jun2020 : QS1S579_TR, QS1S571_TR, DDG001 forms & LBL DTS are flagged in missing forms/DTS report. requested Angella to look into in Shashi's Absence. 05Jun2020 : QS1S638_TR, QS1S631_TR, FAMHS001_TR, MOS001, G1S001 forms included along with EGL DTS In RF vesrion 2.0 18May2020: DBD comment on PPC implementation 5May2020: "that PPC for the study has been kept on hold. Protocol amendment is expected by 1st week of June and we would be updating the DB once we have got all of requirements to change. " 03Apr2020 : PPC pending 19-Mar-2020: PPC not yet initiated. 02Mar2020 : PPC pending for pending forms 10Feb2020 : Updated under 21st jan comments 21-Jan-2020: Rule file finalized, sent for LSH setup. 10-Jan-2020: FAMHS001_TR, MOS001, G1S001 : SDTM annotations pending. QS1S638_TR, QS1S579_TR, QS1S571_TR, QS1S631_TR : Clarification pending from DBD / TA POD. Questions not available in Reference Metadata DDG001 incorrect form used , need to be updated via PPC 30-Dec-2019: SDTM annotations not complete for Study Specific pages. Sent for SDTM programmers inputs. Identified few issues with DB, informed DBP to update Database. 27-Dec-2019: Planned release for Peer review 02-Jan-2019. | None | None | 2020-01-20 05:30 | Transition Study | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-01-30 | Completed | 2020-01-31 05:30 | 31st Jan 2020 : LSH setup is completed |  | 2020-01-31 05:30 | 2020-01-31 05:30 |  | 2020-05-04 05:30 |  |  |  | 36 | RaveX - Inhouse | No | EC;#ZJ | [11 empty] | NA | [5 empty] | 7 | 9 | 66 | 0 | 175 | 629 | 0 | 203 | 33 | 284 | 946 | 3 | 0 |  | Colitis ulcerative | No | Global | Open | Yes | [10 empty] | 2020-01-30 05:30 |  |  |  |  | Adi, Vishnupriya | None of the above | Yes
CLYS228A0 | CLYS228X2101 | C1001705 | Phase I | NCDS | CRO - EDC |  |  | 2018-03-06 05:30 | DB Locked |  |  | 2016-10-20 05:30 | 2017-11-28 05:30 | 2016-10-04 05:30 |  | Completed | 2018-04-23 05:30 | 2017-08-17 05:30 | 2018-04-04 05:30 | 2018-04-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | A first-in-human, randomized, subject blinded, placebo controlled, single and multiple ascending intravenous dose study to assess the safety, tolerability and pharmacokinetics of LYS228 in healthy subjects | CLYS228X2101 | N3 Infectious Diseases - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Megan Osborn | Theodore Stachulski | [15 empty] | Singari, Nirosha |  | Rohit Varate | [28 empty] | CMED | [19 empty] | Urinary tract infection bacterial | No | Global | Completed | Yes | [16 empty] | None of the above
CLYS228A | CLYS228X2201 | C1001706 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  |  |  | 2017-11-10 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CLYS228X2201 POC in cUTI | N3 Infectious Diseases - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Maria Berkheimer | Maria Berkheimer | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Urinary Tract Infection | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CLYS228B1 | CLYS228X2202 | C1200379 | Phase II | NCDS | CRO - EDC |  |  | 2018-04-30 05:30 | DB Locked |  |  | 2018-05-15 05:30 |  | 2017-08-13 05:30 |  | Completed | 2019-08-29 05:30 | 2018-09-24 05:30 | 2018-11-01 05:30 | 2018-11-01 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, controlled, evaluator-blinded, multi-center study to evaluate LYS228 pharmacokinetics, clinical response, safety and tolerability in patients with complicated intra-abdominal infection | CLYS228X2202 | N3 Infectious Diseases - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Denise Serra | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Intra-abdominal infection | No | Global | Terminated | Yes | [16 empty] | None of the above
CMAA868A0 | CMAA868A1101 | C1001707 | Phase I | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2017-09-28 05:30 |  | 2017-06-20 05:30 |  | Completed | 2018-03-01 05:30 | 2018-03-01 05:30 | 2018-05-24 05:30 | 2018-05-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - CVM | A single ascending dose, randomized, subject and investigator blinded, placebo-controlled, non-confirmatory study to assess safety, tolerability, PK and PD of MAA868 in Japanese healthy subjects | CMAA868A1101 Japan Phase I | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Hagiwara, Yayoi | Sneha, Kumari | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | YASUYUKI TABEI | YASUYUKI TABEI | [15 empty] | Kadam, Sandeep |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | Other | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 354 | 1 | 0 |  | Atrial fibrillation | No | Global | Completed | Yes | [16 empty] | None of the above
CMAA868A | CMAA868A2201 | C3000534 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  |  | DB On hold |  |  |  |  | 2017-09-07 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | Study cancelled | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A multicenter, randomized, open-label, blinded endpoint evaluation, active-controlled Phase 2 study to compare the efficacy and safety of s.c. MAA868 and s.c. enoxaparin in adult patients undergoing unilateral total knee arthroplasty | VTE_Knee_Surgery_Patients_CMAA868A2201 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Musthafa, Mohammed | Arasavalli, Isaac | Tummalapenta, Venkateswarlu | Nair, Sreesha | Vijay Pal Singh | Mojdeh Maboudian | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Cardiovascular event prophylaxis | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CMAA868A | CMAA868A2202 | C3000535 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  |  | DB On hold |  |  |  |  | 2017-10-06 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | Study cancelled | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | DRF_Atrial_Fibrillation_CMAA868A2202 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Dubey, Saumitra | Arasavalli, Isaac | Tummalapenta, Venkateswarlu | Nair, Sreesha | Mojdeh Maboudian | Mojdeh Maboudian | [15 empty] | Kumar, Herin |  | Amit Agavekar | [28 empty] | NA | [19 empty] | Cardiovascular event prophylaxis | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CMAA868A | CMAA868X2101 | C1200433 | Phase I | NCDS | [7 empty] | 2016-06-28 05:30 |  | 2016-05-03 05:30 |  | Completed |  | 2017-05-01 05:30 |  | 2017-06-20 05:30 | FALSE |  |  |  | FULL Outsourced |  | A first-in-human, single ascending dose, randomized, subject and investigator blinded, placebo-controlled, non-confirmatory study to assess safety, tolerability, PK and PD of MAA868 in healthy subjects. | CMAA868X2101 FIH/PoC | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Qi Yin | [66 empty] | Atrial fibrillation | Yes | Global | Completed | Yes | [16 empty] | None of the above
CMAK683A0 | CMAK683A02101 | C4015475 | Phase I | [6 empty] | Final DBL | 2023-05-11 05:30 |  |  |  |  | Stopped (with patients) |  |  | 2023-05-11 05:30 | [5 empty] | InHouse |  |  | CMAK683A02101 MAD HV for SCD indication | N7 Oncology - NIBR | [6 empty] | Prafulla Bhad | [66 empty] | Sickle cell disease | No | Global | Terminated | Yes
CMAK683A0 | CMAK683B12101 | C4015475 | Phase I |  |  |  |  | 2022-04-21 05:30 |  | Final DBL | 2023-05-11 05:30 |  | 2022-02-06 05:30 |  |  | Planned | 2023-03-16 05:30 |  | 2023-05-11 05:30 | [5 empty] | InHouse |  |  | CMAK683A02101 MAD HV for SCD indication | N7 Oncology - NIBR | [6 empty] | Prafulla Bhad | [66 empty] | Sickle cell disease | No | Global
CMAK683A1 | CMAK683X2101 | C1001708 | Phase I+II | NCDS | OC RDC - Inhouse | 2016-09-16 05:30 | 2016-09-16 05:30 |  | DB Conduct | Final DBL | 2023-06-29 05:30 | 2016-10-03 05:30 |  | 2016-06-21 05:30 |  | Active | 2023-04-19 05:30 |  | 2023-06-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I/II, multicenter, open-label study of MAK683 in adult patients with advanced malignancies | CMAK683X2101 TCO-A-phaseI/II-study | N7 Oncology - NIBR | Langlo, Francois | Kubade, Shrikant | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Fangjun Luo; NAOKO NOUMI | Fangjun Luo | Samuel, Giftson | Mareedu, Vasu |  | 2020-07-08 05:30 | [11 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | I will schedule DDPASS session during any major timeline. | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2016-09-17 05:30 | 2016-09-17 05:30 | Gehlawat, Priya | Gehlawat, Priya | NA | [7 empty] | 195 | 0 |  |  | 0 |  |  |  | 787 | 5 | 0 |  | Lymphoma malignant; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CMAS825A0 | CMAS825A02101 | C4002612 | Phase I | NCDS | CRO - EDC |  |  | 2019-06-13 05:30 | DB Conduct | Final DBL | 2022-09-29 05:30 | 2019-06-07 05:30 | 2018-12-12 05:30 | 2018-12-17 05:30 |  | Active | 2022-08-04 05:30 |  | 2022-09-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A first-in-human, randomized, subject-blinded, placebo-controlled, single ascending dose study to investigate the safety, tolerability and pharmacokinetics of MAS825 in healthy volunteers | CMAS825A02101 FIH study with MAS825 - SAD | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Beata Kovacs; Kathryn Radford | Beata Kovacs | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Sickle cell disease | No | Global | Open | Yes | [16 empty] | None of the above
CMAS825D1 | CMAS825D12201 | C4008415 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-12-16 05:30 | 2020-12-16 05:30 | 2020-12-21 05:30 | DB Conduct | Interim DBL | 2022-05-31 05:30 | 2020-12-18 05:30 | 2020-10-16 05:30 | 2020-10-12 05:30 |  | Active | 2027-04-25 05:30 |  | 2027-05-25 05:30 |  | FALSE | NIBR GO | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A three-period multicenter study, with a randomized-withdrawal, double-blinded, placebo-controlled design in Period 2 to evaluate the clinical efficacy, safety and tolerability of MAS825 in NLRC4-GOF patients | CMAS825D12201 PoC NLRC4-MAS | N0 ATI - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Beata Kovacs; Elizabeth McNamara; Rachel Smith | Rachel Smith | Dadapogu, Jesica Priyadarshini | Prasanna Kumar, VTSSR | Not Started |  |  |  | DRM | Shafiudeen, Rehana Banu | Saha, Saikat | Completed | 15Feb2022: DBD is working with the TDM to get the Test Codes to be available in the Metadata and then we can add them into the RF. DBD confirmed on mail that there are no upcoming milestones. 7Feb2022: Received the updated ALS, Difference Report and SDTM annotation. Got notified that the PPC has already been implemented on 13-Jan-2022. Provided all the concerns and challenges to the DBD. 7Dec2021: Received the IA for PPC#4. Reviewed the IA and provided my comments to the DBD. 31-Aug-2021 : The study is transitioned to Saha, Saikat. 31-Aug-2021 : No Pending tasks. 22-Jan-2021 : OPS001, OPS002 forms are included in RF V4.0 and it is finalized in SUBWAY. 21-Jan-2021 : Based on TDM conformation, Working to include the forms in RF. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 OPS001, OPS002 form listed. Please check 17Dec2020 : RF is finalized in Subway 8Dec2020 : RF is developed and sent for peer review. 3Dec2020 : Review of the ALS is complete, awaiting for the Developer's comments. 11Nov2020 : Reviewing the received SRF. 29Oct2020 : Requested DBP for the Study Status and awaiting for reply. 15Oct2020 : Requested DBP for the Study Status and awaiting for reply. | PPC#4 to be implemented | None | 2020-12-17 05:30 | Transition study | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-12-24 | Completed | 2020-12-24 05:30 |  | Pre-requisites not met | 2020-12-24 05:30 | 2020-12-24 05:30 | Pre-requisites not met | 2020-12-24 05:30 |  |  |  |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 4 | 42 | 76 | 0 | 617 | 676 | 0 | 181 | 36 | 203 | 915 | 0 | 0 |  | Autoinflammation with infantile enteroco | No | Global | Open | Yes | [10 empty] | 2020-12-22 05:30 | [5 empty] | None of the above
CMAS825F1 | CMAS825F12201 | C4009253 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-05-08 05:30 | 2020-05-26 05:30 | 2020-06-05 05:30 | DB Locked | Final DBL Achieved |  | 2020-06-11 05:30 | 2020-04-17 05:30 | 2020-04-30 05:30 |  | Active | 2021-04-15 05:30 | 2021-04-21 05:30 | 2021-05-28 05:30 | 2021-06-09 05:30 | TRUE | COVID STUDY | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A Phase 2, randomized, placebo-controlled, participant and investigator blinded, multi-center study to assess efficacy and safety of MAS825 for the treatment of SARS-CoV-2 infected patients with COVID-19 pneumonia and impaired respiratory function | CMAS825F12201 PoC in Covid-19 | N0 ATI - NIBR | Langlo, Francois | Prasanna, Snehalata | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Beata Mehes | Beata Mehes | Mokhamatam, Madhu Purnachandra Rao | Thomas, Ankit |  | 2020-07-24 05:30 |  |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 30-Apr-2021: SNOW-51 is raised for LSH and SMT updates WRT PPC#05. There is no impact to RF. LSP and SMT programmers have been notified. 07-Jan-2020: RF V6.0 updated and finalized in Subway WRT PPC#03. SNOW-51 is raised. LSP and SMT developers are notified. 26Nov2020: Backup: Chandrakala Whats planned: (Covid 19 study) PPC#03 is in draft state. PPC form is reviewed and shared the comments. Need to include in RF once database is updated. 08-Oct-2020 (SHRIVNI5): Renamed newly created variables 'LBRESDAT' to 'RESDAT' and 'LBTIM' to 'RESTIM' for 'LBG003_TR' form in RF V5.0 and finalized. LSP and SMT developers notified to rebuild. 15-Sep-2020 (SHRIVNI5): DSG005 form and new variables (LBRESDAT and LBTIM) included in 'LBG003_TR' form included in RF V4.0 and sent for LSH rebuild. 03-Sep-2020 (SHRIVNI5): LBL DTS included in RF V3.0 and sent for LSH rebuild. 02Sep2020 : As per 02Sep2020 missing forms DTS report LBL pending 06Jul2020:Rule file V2.0 is the latest one. RF will be transitioned from Ashok to Nikhil. 15Jun2020 : RF V2.0 Finalized in Subway. Changes done :Oxygen Flow Rate and Fraction of Inspired Oxygen CMSTDTC mapped to REDTC also. 27May2020 : RF final and ROD raised 30Apr2020: Received Annotations for 13 SRFs and One SRF SDTM annotation is pending. 24Apr2020: received 12 study specific forms for review. Provided initial review feedback. Awaiting SDTM annotations | None | None | 2020-05-27 05:30 | RF finalized within Go-live + 5 days | Tidke, Shyam | Kadam, Sandeep | Rohit Varate | Completed | 2020-05-27 | Completed | 2020-05-27 05:30 | ​Jreview configuration request has been raised. LSH setup is completed and published to JReview and GPS. |  | 2020-05-27 05:30 | 2020-05-27 05:30 |  | 2020-09-01 05:30 |  |  | Scheduled | 100 | RaveX - Inhouse | Yes | -NA-;#Y1 | 2021-06-10 05:30 | 2021-06-14 05:30 | [9 empty] | NA | [5 empty] | 7 | 21 | 57 | 0 | 259 | 603 | 0 | 194 | 37 | 162 | 802 | 1 | 0 |  | Corona virus infection | Yes | Global | Open | Yes | [10 empty] | 2020-05-27 05:30 |  |  |  | DBL |  | COVID19 | Yes
CMAU868A0 | CMAU868X2101 | C1200421 | Phase I | NCDS | [7 empty] | 2016-12-14 05:30 |  | 2016-10-03 05:30 |  | Completed |  | 2017-08-13 05:30 |  | 2017-09-21 05:30 | FALSE |  |  |  | ED Full Outsourced |  |  | CMAU868X2101 | N3 Infectious Diseases - NIBR | [6 empty] | Amanda Nguyen | [66 empty] | BK virus infection | No | Global | Completed | Yes | [16 empty] | None of the above
CMAW106A0 | CMAW106X2101 | C1200758 | Phase I | NCDS | CRO - EDC |  |  | 2018-10-05 05:30 | DB Locked |  |  | 2018-01-04 05:30 | 2018-05-04 05:30 | 2018-05-04 05:30 |  | Completed | 2019-12-11 05:30 | 2019-06-14 05:30 | 2019-09-18 05:30 | 2019-09-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID |  | CMAW106X2101 FIH SAD in HVs | N5 DAx - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Alok Pachori | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02;#ZK03 | [11 empty] | CMED | [19 empty] | Non-alcoholic steatohepatitis | No | Global | Completed | Yes | [15 empty] | Agrawal, Naina | None of the above | Yes
CMBG453B1 | CMBG453B12201 | C4003778 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-04-30 05:30 | 2019-05-03 05:30 | 2019-07-10 05:30 | DB Conduct | Interim DBL | 2022-04-05 05:30 | 2019-06-04 05:30 | 2019-02-27 05:30 | 2019-02-26 05:30 |  | Active | 2024-08-10 05:30 |  | 2024-09-20 05:30 |  | TRUE | Pioneer | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A randomized, double-blind, placebo-controlled phase II multi-center study of intravenous MBG453 added to hypomethylating agents in adult subjects with intermediate, high or very high risk myelodysplastic syndrome (MDS) as per IPSS-R criteria (STIMULUS-MDS1) | CMBG453B12201 Ph2 MBG453 + Vidaza in MDS | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shenoy, Shweta Harimohan | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Flavia Kiertsman | Flavia Kiertsman | Palande, Sujit | Bakka, Sandeep |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 30Apr2019 |  | DRM | Oguri, Praveen | Bairagi, Arpita | Completed | 26May2021 : Reassigned the study from Praveen Oguri to Arpita Bairagi. 15Feb2021: Added B11L and B15L DTS's to RF Version 15.0(RITM2255964). 21Jan2021: Sent Follow up email to study DBD to confirm on DTS finalization. 21Jan2021: B14L DTS included in RF Version 13 finalized on 23-Dec-2020 and raised SNOW ticket (RITM2117833). 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B14L, B11L DTSs listed. Please check 05Nov2020: No Activity. 11Sep2020: No Activity. 11Aug2020 : B13L(VUMC) included in version 11 on 25Jun2020 and final. 18Jun2020 : DBD reviewing the setup and datasets once we get the confirmation will be included in RF v11.0 27May2020: RF has been shared with LSP on 11May2020, LSP is working on the test setup for the DTS wherein they will check if the Transformations using RF are working as per the requirements for the third party data. LSP is facing some challenge with the setup in LSH test and they are taking help of Sujith Kudikala. Expecting LSP setup to be completed by 30-May-2020. 12May2020 : VUMC DTS is a special DTS which requires test LSH setup to review the datasets and shared the RF for the same on 11th .. Once we get confirmation from LSP DTS and RF will be finalized 11May2020 : ECG004 added in RF v9.0. and sent for LSH setup. 30Apr2020 : ECG004_1 included in v8.0 of RF this new form was added as per the PPC and sent for LSH setup 05Apr2020: RF updated with PPC02 updates on 29Apr2020. VUMC DTS development in progress. 20Mar2020 : EG1L,B12L, QS1L, QS2L, QS3L, QS4L pending DTS included in RF and sent for LSH setup. 10Mar2020 : Pending final DTSs (EG1L,B12L, QS1L, QS2L, QS3L, QS4L) to be included in RF. 11Jul19: Initial version v1.0 is processed with SMT & DRM setup on 27May19. Updated RF (FAMH) sent for review 13Jun19: Pending issues DBD to fix via PPC and follow-up with SDTM. Rule file is processed except one Domian ..FA. Also 3rd party domains pending for this study. 03JUL2019:&nbsp; Rule file are sent for review with all&nbsp; domain ( FAMH)&nbsp; update. 3rd party domains are still pending as DTS is not finalized yet. | None | None | 2019-05-27 05:30 | DB Set-Up Issues | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2019-05-30 | Completed | 2019-06-12 05:30 |  |  | 2019-07-01 05:30 | 2019-07-01 05:30 | Study Transition | 2019-08-28 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 12 | 154 | 85 | 0 | 975 | 848 | 0 | 246 | 37 | 248 | 1133 | 13 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes | [10 empty] | 2019-06-11 05:30 | [5 empty] | Pioneer
CMBG453B1 | CMBG453B12203 | C4009590 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-03-16 05:30 | 2021-04-17 05:30 | 2021-06-21 05:30 | DB Conduct | Final DBL | 2026-01-30 05:30 | 2021-05-31 05:30 | 2020-12-11 05:30 | 2020-12-15 05:30 | 2021-03-26 05:30 | Active | 2025-12-06 05:30 |  | 2026-01-30 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A single-arm, open-label, Phase II study of sabatolimab in combination with azacitidine and venetoclax in adult subjects with high or very high risk myelodysplastic syndrome (MDS) as per IPSS-R criteria | CMBG453B12203 single arm Ph2 Triplet vene/aza MDS | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Donthineni, Kalyan | Shenoy, Shweta Harimohan | Fazili, Subeh Mohsin | Krishnan, Kripesh | Flavia Kiertsman | Flavia Kiertsman | Bora, Deepthi Reddy | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 |  |  | DRM | Shrivastava, Nikhil | Shrivastava, Nikhil | Completed | 01-Jun-2021: RF V4.0 updated and finalized WRT updated IRT DTS (V2.0) as per latest global communication. SNOW-51 raised and LSP notified. 18-May-2021: Sent mail to TDM to update the table name of IRT DTS for YD domain. Post DTS updated, RF will be updated. 07-May-2021: RF V3.0 updated and finalized WRT an adhoc issue reported by LSP during setup. LSP is notified. 30-Apr-2021: 3 DTS (LB1L, EG1L and Yx) included in the RF 2.0 and finalized in CREDI. SNOW-51 raised. LSP and SMT programmer have been notified. 19-Apr-2021: Rule File V1.0 is finalized. SNOW-05 is raised and LSP is notified. 15-Apr-2021: IRT, LB and ECG DTS have been drafted and need to include in the Rule File after DTS review. 12-Apr-2021: Rule File V0.1 created and reviewed by the peer reviewer. There is no comment by the reviewer. Rule File is ready to be finalized but waiting for study goLive to happen. 15-Mar-2021: Reviewed the study initial documents and shared the comments with DBD. Waiting for the DBD response. 17-Feb-2021: DBD informed that goLive is moved to 30thMarch2021. DBD will share the documents in the next week. 12-Jan-2021: Sent mail to DBD to provide activity planner, approved SRFs and other necessary documents. 26Nov2020: Backup: Rehana Whats planned: No documents have been received yet. | None | None | 2021-04-19 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2021-05-10 | Completed | 2021-05-21 05:30 |  |  | 2021-05-21 05:30 | 2021-05-21 05:30 |  | 2021-05-25 05:30 |  |  | DDPASS is scheduled and there are issues marked for respective line functions. | 48 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 1 | 185 | 87 | 0 | 800 | 839 | 0 | 236 | 38 | 196 | 1073 | 5 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes | [10 empty] | 2021-05-20 05:30 | [5 empty] | None of the above | Yes
CMBG453B1 | CMBG453B12205 | C4012693 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-13 05:30 | Study Planned | DB Go-live | 2022-04-26 05:30 |  | 2022-01-05 05:30 | 2022-01-05 05:30 |  | Planned | 2027-07-20 05:30 |  | 2027-08-31 05:30 |  |  | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase Ib/II, open label, proof-of-concept study of sabatolimab and magrolimab-based therapy for patients with acute myeloid leukemia or myelodysplastic syndrome | CMBG453B12205 Ph2 HMA + MBG453 + Magrolim PoC | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Donthineni, Kalyan | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Mario Stegert | Mario Stegert | Supraja, Samala | Supraja, Samala | [5 empty] | Mopuru, Satwik | Mopuru, Satwik | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1250 | 6 | 0 |  | Acute myeloid leukaemia; Myelodysplastic syndrome | No | Global | Open: Reapproval | Yes
CMBG453B1 | CMBG453B12206B | C4012864 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-04-13 05:30 | Study Planned | DB Go-live | 2022-03-14 05:30 |  | 2021-12-06 05:30 | 2021-11-17 05:30 |  | Planned | 2027-12-30 05:30 |  | 2028-02-10 05:30 |  |  | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | Open-label, multicenter, roll-over study for patients who have completed a prior Novartis-sponsored sabatolimab (MBG453) study and benefit from continued treatment with sabatolimab | CMBG453B12206B Rollover study (PTA Study) | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Pasari, Laxmi Priya | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Nathalie Guichard | Laurence Bourdeau | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 6 Jan 2022: RF Programmer assigned. 10 Feb 2022: There was delay from SDTM programmer end in providing annotations due to which further activities were delayed. 15 Feb 2022: Reviewed draft ALS and provided comments from RF development perspective. Screen UAT is pending. 18 Feb 2022: OSRM done today and there are few comments from team which needs to be updated in DB. . | [6 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes
CMBG453B1 | CMBG453B12301 | C4003785 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-01-01 05:30 | 2020-02-26 05:30 | 2020-06-02 05:30 | DB Conduct | DB Snapshot | 2022-04-08 05:30 | 2020-06-08 05:30 | 2019-11-19 05:30 | 2019-11-20 05:30 |  | Active | 2027-01-29 05:30 |  | 2027-03-12 05:30 |  | FALSE | Pioneer | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | Phase III randomized study of HMA +/- MBG453 in patients with intermediate, high or very high risk Myelodysplastic syndrome | CMBG453B12301 Ph3 MBG + Azacitidine in MDS | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bhattad, Poonam | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Sabine Hertle | Sabine Hertle | Gandla, Prashanth | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Prashanth Gandla transitioned the study to Chandana Sarasani on 08-Apr-2020. Initial golive as of 04Oct2019 was 01Jan2020 |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 25NOV21: RF V8.0 final and SNOW 51 RITM3220812 has been created. Requested LSP for to create CE, B1 and rebuild B2 domains as part of new DTS and SDTM team requirement 22OCT21: RF V7.0 has been finalized and SNOW 51 RITM3111426 request has been created. Requested LSP to rebuild B2 domain as per latest B2 test codes. 14SEP21: RF 6.0 has been finalized and SNOW 51 request RITM2973782 has been created requested to rebuild SC, DV, LB and B2 domains as part of PPC. 06MAY21: RF has been finalized with following changes and SNOW 51 RITM2543931 request has been created ZW domain: ZW1L and ZW2L DTS have been added. 29OCT20: RF has been finalized with following changes and SNOW 51 RITM1942259 request has been created. VS domain: VSL DTS has been added ZJ domain: ZJG002_3 form has been added LB domain: 1. LB domain has been rebuild due to addition of new fields TROPONI and TROPONIC 2. LB2L DTS has been added DS domain: DSG005 form has been added SC domain: SCS001 and SCS002 forms have been added 07JUL20: As of today, no pending forms and no pending DTS. 02JUL20: RF final and SNOW 51 request has been created 25JUN2020: RF updated as per PPC and send for peer review. 19Jun2020: Pending with RF developer awatied to see if PPC changes reuired RF update. Will inc;due all Pending DTS and finlaize 21MAY2020: 10 QS DTS and 1 LB DTS have been added in Rule file and sent for peer review. Recieved these DTSs on 18May2020 and the DTS trcaker was not updated. Requested DBD to followup and get the DTS tracker updated. 09Mar2020 : RF completed and sent for LSH setup. 03MAR2020: New setup, Peer review completed by Roshan and received comments. Planned to complete by 04Mar2020. 13Feb2020 : 1Form SDTM annotation is pending, discussion ongoing between TA POD and SDTM programmer on Domain. Today received confirmation on approx. 11 forms from SDTM programmer. Working on RF. 03-FEB-20: Rule file development is ongoing 04-DEC-19: Planned Go Live date is Late February. DBP is not sure of the date of Screen UAT completion. 29-Nov-2019: Develper is on leave till 02-DEC-2019. Once developer is back will update status | None | None | 2020-03-09 05:30 |  | Agavekar, Amit | Agavekar, Amit | Amit Agavekar | Completed | 2020-04-09 | Completed | 2020-04-09 05:30 |  |  | 2020-04-09 05:30 | 2020-04-09 05:30 |  | 2020-08-25 05:30 |  |  | DDPASS is still ongoing. | 0 | RaveX - Inhouse | No | -NA-;#Y1;#ZK;#Y5 | [11 empty] | NA | [5 empty] | 6 | 165 | 85 | 0 | 1027 | 889 | 0 | 269 | 39 | 231 | 1159 | 15 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes | [10 empty] | 2020-04-09 05:30 | [5 empty] | Pioneer
CMBG453B1 | CMBG453B12302 | C4009592 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-21 05:30 | Study Cancelled | DB Go-live | 2022-04-15 05:30 |  | 2022-06-30 05:30 |  |  | Planned | 2026-09-04 05:30 |  | 2026-10-16 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology |  | CMBG453B12302 Ph3 Triplet ven/aza in MDS | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Donthineni, Kalyan | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Melissa Taranto | Isabelle Malet | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CMBG453C1 | CMBG453C12201 | C4004140 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-07-08 05:30 | 2020-04-03 05:30 | 2020-10-01 05:30 | DB Conduct | DB Snapshot | 2022-03-22 05:30 | 2020-09-01 05:30 | 2019-09-19 05:30 | 2019-09-20 05:30 |  | Active | 2026-02-17 05:30 |  | 2026-03-31 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase II multi-center, single arm safety and efficacy study of MBG453 in combination with azacitidine and venetoclax for the treatment of Acute Myeloid Leukemia (AML) in adult patients unfit for chemotherapy | CMBG453C12201 MBG+Vidaza+ Venetoclax in Unfit AML | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Mohapatra, Ruchi | Shenoy, Shweta Harimohan | Fazili, Subeh Mohsin | Krishnan, Kripesh | Mario Stegert | Mario Stegert | Mokhamatam, Madhu Purnachandra Rao | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Mokhamatam Madhu transitioned the study to Chandana Sarasani on 14-Apr-2020. moved to 18Nov2019 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 08Jul2019 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 03Feb2022: RF v8.0 is finalized in CREDI for B11L dts table addition and SNOW#51- RITM3455333 Created for SMT/LSH updates. 30Sep2021: RF v7.0 is finalized in CREDI for rectification of LB and AE domain issues in DDPASS. 19Jul2021: RF v6.0 is finalized in CREDI for PPC#4 updates. 26Feb2021: RF v5.0 is finalized for PPC3 updates and FAMH, ODM ,SS domain fixes as per issues observed by TP & SDTM team. 7JAN2021: SG: No upcoming tasks. 5Nov2020: LSP confirmed that issue with DSG005 is now resolved. 23Oct2020 : It seems there is some issues with RecordID’s for DSG005 page no action from RF perspective. 05Oct2020 : DSG005, LB1L, LB2L VSL, QS1L-4L included in RF. DSG005 Page is already included in RF, however still popping up in Tracker. Asked DB lead and LSP to investigate on their end. ALS repository was not updated. Now its uploaded 25Sep2020: Rule file not picked for review. Sent reminder to team. 8Sep2020: Updated Rule file and shared for review. Checking with DB lead and LSP on DSG005 coming up as missing pages. 02Sep2020 : As per 02Sep2020 missing forms DTS report "DSG005" from and LB1L, VSL DTS pending. DBD notifed about PPC implementation only after followup on 25Aug2020. 11AUG2020: 5 more QS DTS's finalized and also fianlized. Planned for including in RF by 18AUG2020. 17Jul2020 : LB1L, VSL flagged in missing report dated 02Jul2020.. DBD missed to share with the RF developer ti incldue in RF. 07Jul2020(Kranthi): DSG005 is added in RF V2.0 06Jul2020: DSG005, LB1L, VSL flagged in missing report dated 02Jul2020. Sent a followup email to RF developer and DBD 22Jun2020 : DSG005 forms is flagged in missing forms/DTS report. Requested Kranthi to look into it in Shashi's absence. Sent an email to DBD 18May2020: Rule file finalized, SNOW ticket raised. 5May2020: Released for Peer review on 29Apr2020. FPFV moved to 17Jun2020 14Apr2020 : will release for peer review by 21st 03Apr20 : RF will be sent for review by 13thApr. 19-Mar-2020: final SDTM annotations for study specific pages received on 19-Mar-2020. Rule file development to start in the week on 23-Mar-2020. 10-Mar-2020: Provided SDTM annotations for Study specific pages to DBP. DBP to get them reviewed by SDTM programmer. Awaiting finalized SDTM annotations. 10Feb2020: Followed up with DBD and awaiting response. 3 SRFs pending from TDM and tentatively be approved by 14Feb2020. Post which will be sent for SDTM annotations. Around 30 SRFs are already shared with SDTM programmer for annotations expecting to get the response by 14th. Post which RF developer can perform the review and start with RF activities | None | None | 2020-05-18 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2020-05-19 | Completed | 2020-06-11 05:30 | ​CE, HO and EG domains are pending due to RF and SMT updates​, FPFV is planned for 16th Jun 2020 |  | 2020-06-11 05:30 | 2020-06-11 05:30 |  | 2020-08-24 05:30 |  |  |  | 72 | RaveX - Inhouse | Yes | -NA- | 2021-10-07 05:30 | 2021-10-08 05:30 | [9 empty] | NA | [5 empty] | 6 | 130 | 79 | 0 | 1038 | 957 | 0 | 316 | 40 | 240 | 1237 | 12 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2020-06-10 05:30 |  |  |  | Interim-Analysis | Nidamanuru, Kalyan Kumar | GDD annual target;#Pioneer | Yes
CMBG453C1 | CMBG453C12202 | C4005672 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-02-16 05:30 | 2020-05-06 05:30 |  | DB On hold | [6 empty] | Stopped (with patients) |  |  |  |  | FALSE | This study was declared cancelled on 23-Jan-2020, DB Phase field does not have Study Cancelled option, thus DB On Hold option is selected. | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A randomized, placebo-controlled, double-blind, phase II multi-center efficacy study of HMA with or without MBG453 as a first-line treatment of subjects with unfit AML | CMBG453C12202 MBG+HMA in Unfit AML | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shenoy, Shweta Harimohan | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Mario Stegert | Vedula, Nagendra | Suzuki, Hiroko |  |  | As per GTM 'Marie Jose' email dated 31Jan2020. Study is cancelled Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 16Feb2020 |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Not Started | Study Cancelled | Study Cancelled | Study Cancelled |  |  |  |  | Amit Agavekar |  |  |  |  | Study Cancelled | [23 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1200 | 8 | 0 |  | Acute myeloid leukaemia | No | Global | Terminated | Yes | [16 empty] | Pioneer
CMBG453D1 | CMBG453D12101 | C4005755 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-01-14 05:30 | 2020-06-25 05:30 | 2020-11-30 05:30 | DB Locked | Final DBL | 2024-06-20 05:30 |  | 2020-01-21 05:30 | 2020-01-22 05:30 |  | Completed | 2024-04-11 05:30 |  | 2024-06-20 05:30 |  | FALSE | Study locked without any subject | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO |  | CMBG453D12101 TCO Phase I Myelofibrosis | N7 Oncology - NIBR | Langlo, Francois | De Kock, Antoinette | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Panagiotis Nikolopoulos | Panagiotis Nikolopoulos | Sinha, Deepakshi | Sarasani, Chandana | Not Started |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 14Jan2020 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 08SEP2020: No update required in RF for PPC1. SMT and LSH update for SV Domain has been notified to SMT/LSP team. 1JUL2020: RF finalized and SNOW#05 raised for SMT creation and New study set-up in LSH. 26Jun2020: Released for peer review. RF development was delayed due to late receipt of Input documents. 24JUN2020: SDTM Annotations Queries raised for clarifications. 18JUN2020: As confirmed by DBD, there were many SRFs updated and DB updates made. Hence, re-initiating the SRF review and RF development from scratch as per the ALS received today morning. 28APR2020: ALS received from DBD to initiate RF activity. 27APR2020: Have only received the SDTM annotations for study specific forms. Waiting for ALS to start the RF development activity. 18MAR2020: Sent a reminder to DBD for UAT status and ref documents to start RF development. 07Feb2020 : Follow-up with DBD 7-JAN-2020: SSD review in progress. Tentative Screen UAT completion date is by End of March 2020. | None | None | 2020-07-01 05:30 |  | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-07-07 | Completed | 2020-07-17 05:30 |  |  | 2020-07-17 05:30 | 2020-07-17 05:30 |  | 2020-08-25 05:30 |  |  | FPFV not reached for this study. | 0 | RaveX - Inhouse | No | -NA- | 2021-01-20 05:30 | 2021-01-21 05:30 | [9 empty] | IQVIA | [5 empty] | 3 | 45 | 113 | 0 | 695 | 1034 | 0 | 294 | 46 | 552 | 1632 | 4 | 0 |  | Myelofibrosis | No | Global | Wind Down | Yes | [10 empty] | 2020-07-14 05:30 |  |  |  |  | R, Harini | Pioneer | Yes
CMBG453E1 | CMBG453E12101 | C4007058 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-02-12 05:30 | 2021-03-26 05:30 | 2021-06-28 05:30 | DB Conduct | Final DBL | 2024-05-16 05:30 | 2021-06-18 05:30 | 2020-08-28 05:30 | 2020-09-11 05:30 |  | Active | 2024-02-16 05:30 |  | 2024-05-16 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase Ib, multicenter, open-label platform study of select drug combinations in adult patients with lower risk (very low, low, or intermediate risk) myelodysplastic syndrome | CMBG453E12101 - TCO Phase Ib in LIR-MDS | N7 Oncology - NIBR | Langlo, Francois | Kocharekar, Poonam Vilas | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Yafang Zhou | Yafang Zhou | Maricherla, Vijayroshan | Maricherla, Vijayroshan |  | 2020-08-21 05:30 | Transition from Madhu to Rohit |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 05AUG21: RF V2.0 is final and Snow request RITM2845954 created. LB domain has been updated and EG1L DTS added. 16APR21: ECG DTS has been finalized and received on 14APR21, needs to be reviewed and update Rule file. 01APR21: Rule file has been finalized and SNOW 05 request RITM2428196 has been created 09MAR21: The expected DB golive is on 19-MAR-21. Requested Lead DBD for all the required documents inorder to start RF development 08JAN21: The tentative date of DB golive is on 13MAR21 and Lead DBD will notify to group head once official communication is rolled out. Note: Old global CRF pages were copied by Rohit and study specific pages were incorrectly designed. Now Roshan taking care of this study design, once all pages are ready will share with Rule file developer for page modeling review. 04JAN21: Rule file development is ongoing and expected date of RF release is 07JAN21. 10NOV20: Following up with lead DBD for ALS, SRF and SDTM annotations for page modeling review. 28OCT20: 24 SRF's have been approved, requested Lead DBD to share ALS, SRF and SDTM annotations for page modeling review. 12OCT20: SRF discussions are ongoing and OSRM has been scheduled on 2OOCT20. 24MAR2020: Study kept on hold due to protocol amendment and golive date will be knowing on 2nd week of April. 02MAR2020: SRF's are in discussion and screens are not finalized. 29-NOV-2019: Screens are not finalized yet | None | None | 2021-04-01 05:30 |  | Ramayanam, Vinay | Varate, Rohit | Rohit Varate | Completed | 2021-04-16 | Completed | 2021-04-20 05:30 |  |  | 2021-04-22 05:30 | 2021-04-22 05:30 |  | 2021-04-22 05:30 |  |  |  | 75 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 28 | 135 | 0 | 676 | 828 | 0 | 224 | 40 | 372 | 1240 | 2 | 0 |  | Myelodysplastic syndrome | No | Global | Open | Yes | [10 empty] | 2021-04-20 05:30 | [5 empty] | Pioneer | Yes
CMBG453F1 | CMBG453F12201 | C4007855 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-10-15 05:30 | 2021-04-21 05:30 | 2021-09-14 05:30 | DB Conduct | Final DBL | 2026-12-15 05:30 | 2021-09-14 05:30 | 2020-10-16 05:30 | 2020-10-13 05:30 |  | Active | 2026-11-03 05:30 |  | 2026-12-15 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | A phase Ib/II, open label study of sabatolimab as a treatment for AML subjects with presence of measurable residual disease after allogeneic stem cell transplantation | CMBG453F12201 AML MRD+ maintenance post aHSCT | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Mohapatra, Ruchi | Magar, Abhijit | Fazili, Subeh Mohsin | Krishnan, Kripesh | Nathalie Guichard | Nathalie Genev��ve Bernadette Guichard | Gupta, Anshu | Gupta, Anshu | Not Started |  | Initial golive 15 Oct2020 as per RaveX master tracker 27Sep2020 as per DM BOW when RF developer assigned on 01Jun2020. |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 08-Feb-2022: CMBG453F12201_Rule file_version 4.0 is now finalized in subway with B11L DTS table included in it. SNOW-51 ticket is raised with ticket number- RITM3470356 for LSH update. LSP has been informed. 14-Jan-2022: Shared comments with the TDM after B11L DTS review 13-Jan-2022: TDM shared the B11L DTS for review 17-Aug-2021: CMBG453F12201_Rule File_version 3.0 is finalized in SUBWAY with Yx DTS included in it. SNOW-51 Ticket is also raised with ticket number- RITM2882685 17-Aug-2021: DBD shared the Yx DTS. Reviewed and provided the comment. 17-Aug-2021: LSP Informed that YD and YR domain is missing in RF. When checked with DBD, she informed she missed to send the Yx DTS for review. 6-July-2021: LSP informed, only after the LB PROD is received they could incorporate the same in DRM and publish, so they closed and skipped the ticket. LSP is waiting for the vendor to send the load after which LSP will update the LSH. 5-July-2021: A communication was shared from IT that RITM2652465 ticket is cancelled. 9-Jun-2021: Finalized Rule file 2.0 with LB1L DTS included. Raised the SNOW51 ticket with ticket no.- RITM2652465 9-Jun-2021: Peer review completed. 4-Jun-2021: Reviewed and included the DTS in Rule file V1.1 and shared it for peer review. 2-Jun-2021: DBD shared LB1L DTS for review 27Apr2021: Finalized Rule file version 1.0 in SUBWAY and raised SNOW05 ticket with ticket no.-RITM2511359. 24Apr2021 : Arpita working on RF on behalf of Kranthi. Nikhil performing Peer review. 01Jun2020: RF Developer assigned with initial go live date as 15Oct2020 from RaveX master tracker. | None | None | 2021-04-27 05:30 |  | Ravichandran, Rajanandhini | Agavekar, Amit | Amit Agavekar | Completed | 2021-05-24 | Completed | 2021-06-18 05:30 |  |  | 2021-06-18 05:30 | 2021-06-18 05:30 |  | 2021-06-22 05:30 |  |  | FPFVV was acheieved on 15-sep-2021. Once there is sufficient amount of data we will proceed with DDPASS | 0 | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 2 | 75 | 82 | 0 | 162 | 1028 | 0 | 317 | 36 | 254 | 1318 | 2 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2021-06-17 05:30 | [5 empty] | Pioneer | No
CMBG453G1 | CMBG453G12201 | C4007856 | Phase II | NCDS_2 |  |  |  | 2023-09-26 05:30 |  | Final DBL | 2027-03-11 05:30 |  | 2023-06-05 05:30 |  |  | Planned | 2027-01-28 05:30 |  | 2027-03-11 05:30 |  | FALSE |  |  |  | InHouse |  |  | CMBG453G12201 MRD+ post Chemo AML maintenance | PA Oncology (Hematology not for MA projects) | [6 empty] | Flavia Kiertsman | [54 empty] | 80 | 0 |  |  | 0 |  |  |  | 1200 | 8 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CMBG453A | CMBG453X2101 | C1001709 | Phase I | NCDS | OC RDC - Inhouse |  | 2015-11-13 05:30 |  | DB Conduct | Final DBL | 2022-08-18 05:30 | 2015-11-23 05:30 |  | 2015-08-20 05:30 |  | Active | 2022-07-13 05:30 |  | 2022-08-18 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I-Ib/II, open-label, multi-center study of the safety and efficacy of MBG453 as single agent and in combination with PDR001 in adult patients with advanced malignancies | CMBG453X2101 TCO-PhIb-followed-by-PhII-solid tumor | N7 Oncology - NIBR | Langlo, Francois | Bubb, Marichen | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sabine Gutzwiller | Sabine Gutzwiller | Ahuja, Mohit | Katam, VeeraNagendra | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | DV;#SV |  |  |  |  | ONC | Novartis | InHouse | 2015-11-13 05:30 | 2015-11-13 05:30 | Shewane, Roshni | Kanchi, Pavan kumar | IQVIA | [7 empty] | 124 | 0 |  |  | 0 |  |  |  | 560 | 7 | 0 |  | Melanoma; Metastatic neoplasm; Non-small cell lung cancer; Renal cell carcinoma; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CMBL949A0 | CMBL949A02101 | C4002271 | Phase I | NCDS | CRO - EDC |  |  | 2019-08-29 05:30 | DB Conduct | Final DBL | 2022-03-21 05:30 | 2019-08-27 05:30 | 2019-05-14 05:30 | 2019-07-08 05:30 |  | Active | 2021-11-03 05:30 |  | 2022-03-21 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A first-in-human, randomized, sponsor open-label, investigator and subject blinded, placebo-controlled, single ascending dose study to explore the safety, tolerability, pharmacokinetics and immunogenicity of subcutaneously administered MBL949 in healthy subjects. | CMBL949A02101 SAD FIH | N1 CVM - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Jul Schofield | Jul Schofield | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Obesity | No | Global | Open | Yes | [16 empty] | None of the above
CMBL949A1 | CMBL949A12201 | C4005568 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-07-02 05:30 | 2021-12-20 05:30 | 2022-02-11 05:30 | DB Set-Up | Final DBL | 2023-06-06 05:30 | 2022-02-10 05:30 | 2021-10-21 05:30 | 2021-10-15 05:30 |  | Active | 2023-03-28 05:30 |  | 2023-06-06 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM | Randomized, placebo-controlled, participant-and investigator-blinded study to evaluate the safety, tolerability, efficacy and pharmacokinetics of subcutaneously administered MBL949 in obese participants with or without type 2 diabetes mellitus | CMBL949A12201 PoC study in obese +/- T2DM | N1 CVM - NIBR | Langlo, Francois | Bhatkar, Priyanka | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Monica Patterson | Jul Schofield | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini |  |  |  |  | DRM | Bai, Chandrakala | Bai, Chandrakala | Completed | 21Dec2021: Snow#05(PROD): RITM3315220 Created. 10Dec2021: RF v1.0 is finalized in Subway and Snow#05(TEST): RITM3281942 Created. 26Oct2021: Screen UAT scheduled for 18-Nov-2021, hence the RF activity from 19th Nov to 22 nov. 29Sep2021: The timelines are updated. Go-Live 15-Dec-2021. 09Aug2021: The timelines are updated. Screen UAT completion is on 15SEP2021 and Go-Live 20-Oct-2021. 06Jul2021: RF developer assigned with FPFV 29Sep2021. | NONE | NONE | 2021-12-21 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2021-12-22 | Completed | 2021-12-22 05:30 | [RAMACHA1, 2021JUL22] Study assigned on 22nd July, 2021 with FPFV 30th September, 2021 [RAMACHA1, 2021DEC14] SNOW05 for LSHTEST setup was raised on 10th Dec, 2021. PREDRM LSH TEST completed on 14th Dec, 2021. Updated FPFV 23rd Dec, 2021. |  | 2021-12-23 05:30 | 2021-12-23 05:30 | [RAMACHA1, 2021DEC14] Pre-requisites not met. DB Go-Live planned on 17th Dec, 2021. SNOW05 for LSH TST setup on 10th Dec, 2021. | 2021-12-29 05:30 |  | [RAMACHA1, 2021] JReview/GPS data published by 23-Dec-2021, on planned FPFV. KPI met. |  |  | RaveX - Inhouse | No | Y1, Y5 | [11 empty] | NA | [5 empty] | 1 | 19 | 58 | 0 | 232 | 621 | 0 | 164 | 48 | 182 | 851 | 0 | 0 |  | Obesity; Type 2 diabetes mellitus | No | Global | Open | Yes | 2021-12-10 05:30 | [9 empty] | 2021-12-22 05:30 | [5 empty] | None of the above
CMBL949B1 | CMBL949B12201 | C4007534 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-09-01 05:30 |  | 2023-03-01 05:30 | Study Planned | DB Go-live | 2022-09-01 05:30 |  | 2022-11-18 05:30 |  |  | Planned | 2024-07-30 05:30 |  | 2024-09-17 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM |  | CMBL949B12201 PIE POC in HFpEF patients | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Julie Mabille | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Heart failure with preserved ejection fr | No | Global | Open | Yes | [16 empty] | None of the above
CMCS110E1 | CMCS110X2201 | C1200233 | Phase II | NCDS | CRO - EDC |  |  | 2018-07-31 05:30 | DB Locked |  |  | 2012-04-23 05:30 | 2018-02-21 05:30 | 2011-10-25 05:30 |  | Completed | 2018-12-31 05:30 | 2018-12-21 05:30 | 2019-04-09 05:30 | 2019-01-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A Phase II randomized, double-blind, placebo controlled study of MCS110 for treatment of pigmented villonodular synovitis (PVNS) | CMCS110X2201 PoC study of MCS110 in PVNS | N4 MSD - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Emilie Francoise Armelle Voltz | Tripathi, Shakuntala | R, Ankit | [13 empty] | K, Gunasekaran |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | [12 empty] | CMED |  | AP21 | CMED Clinical services | asiliman@cmedresearch.com | [15 empty] | Synovitis | No | Global | Open | Yes | [16 empty] | None of the above
CMCS110A0 | CMCS110Z1101 | C1200437 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-09-07 05:30 |  | 2016-06-22 05:30 |  | Completed |  | 2017-04-03 05:30 |  | 2017-04-14 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase I, single-center, open-label, single ascending dose study to assess the safety, tolerability and pharmacokinetics of MCS110 in Japanese healthy volunteers | CMCS110Z1101 | N7 Oncology - NIBR | Molander, Lei Ann | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | RINA MATSURA | [17 empty] | Rohit Varate | [28 empty] | ICON | [19 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CMCS110C | CMCS110Z2102 | C3000362 | Phase I+II | NCDS | OC RDC - Inhouse | 2017-11-07 05:30 | 2017-11-07 05:30 | 2018-06-08 05:30 | DB Locked |  |  | 2016-06-29 05:30 | 2018-01-19 05:30 | 2016-02-11 05:30 |  | Completed | 2020-06-09 05:30 | 2020-06-04 05:30 | 2020-07-03 05:30 | 2020-07-03 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib/II, open label, multicenter study of MCS110 in combination with PDR001 in patients with advanced malignancies | CMCS110Z2102 Phase Ib/II MCS110 in combo w/ PDR001 | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Anne-Laure Marchal | Anne-Laure Marchal | Ahuja, Mohit | Ahuja, Mohit | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | I will schedule DDPASS session when there will be major timeline. | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2016-05-23 05:30 | 2016-05-23 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | IQVIA | [7 empty] | 110 | 0 |  |  | 0 |  |  |  | 691 | 5 | 0 |  | Breast cancer; Melanoma; Ovarian cancer; Pancreatic cancer | No | Global | Open | Yes | [16 empty] | None of the above
CMCS110D1 | CMCS110Z2201 | C3000361 | Phase II | NCDS | OC RDC - Inhouse |  | 2015-02-24 05:30 | 2018-03-20 05:30 | DB Locked |  |  | 2015-08-10 05:30 | 2018-01-19 05:30 | 2015-01-28 05:30 |  | Completed | 2020-06-11 05:30 | 2020-03-23 05:30 | 2020-07-09 05:30 | 2020-05-08 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A randomized phase II study of MCS110 combined with carboplatin and gemcitabine in advanced Triple Negative Breast Cancer (TNBC) | CMCS110Z2201 Randomized Phase II TNBC study | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Xuan-Mai Couillebault | Xuan-Mai Couillebault | Maricherla, Vijayroshan | Maricherla, Vijayroshan | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [12 empty] | Planned DDPASS in Q2 | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2015-05-22 05:30 | 2015-05-22 05:30 |  |  | IQVIA | [7 empty] | 110 | 0 |  |  | 0 |  |  |  | 642 | 7 | 0 |  | Breast cancer metastatic | No | Global | Completed | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | Yes
CMGY825A1 | CMGY825A12101 | C4008046 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-21 05:30 | DB On hold | Final DBL | 2025-01-01 05:30 |  | 2022-02-18 05:30 | 2022-02-02 05:30 |  | Planned | 2024-11-20 05:30 |  | 2025-01-01 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | An open-label, phase I, dose escalation, expansion study of MGY825 in adult patients with advanced solid tumors. | CMGY825A12101 Trial | N7 Oncology - NIBR | Langlo, Francois | OMEYER, Delphine | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Panagiotis Nikolopoulos | Panagiotis Nikolopoulos | Das, Devashish | Das, Devashish | [15 empty] | Rohit Varate | [28 empty] | IQVIA | [7 empty] | 130 | 0 |  |  | 0 |  |  |  | 1500 | 5 | 0 |  | Non-small cell lung cancer | No | Global | Open | Yes | [16 empty] | None of the above
CMHS552D1 | CMHS552A01101 | C4009614 | Phase I |  |  |  |  | 2023-10-06 05:30 |  | Final DBL | 2024-03-05 05:30 |  | 2023-04-28 05:30 |  |  | Planned | 2024-01-30 05:30 |  | 2024-03-05 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CMHS552A01101 J-ESS | N0 ATI - NIBR | [6 empty] | Louise Mooney | [66 empty] | Type 1 diabetes mellitus | No | Global | Open | Yes
CMHS552A0 | CMHS552A12101 | C4000192 | Phase I | NCDS | CRO - EDC |  |  | 2019-10-09 05:30 | DB Locked |  |  | 2019-10-08 05:30 | 2019-05-02 05:30 | 2019-05-03 05:30 |  | Active | 2021-06-29 05:30 | 2021-06-29 05:30 | 2021-08-27 05:30 | 2021-08-26 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A first-in-human, randomized, subject-blinded, placebo-controlled, single ascending dose study to investigate the safety, tolerability and pharmacokinetics of MHS552 in healthy volunteers | CMHS552A12101 FIH SAD | N0 ATI - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Johanne Sanni | Johanne Sanni | [15 empty] | Adi, Vishnupriya |  | Rohit Varate | [6 empty] | 2020-06-24 05:30 | 2020-06-24 05:30 | [6 empty] | CRO |  | ZK02 | 2021-09-23 05:30 | 2021-09-23 05:30 | [9 empty] | CMED | [19 empty] | Vitiligo | No | Global | Open | Yes | [14 empty] | DBL | R, Harini | None of the above | Yes
CMHS552A0 | CMHS552B12101 | C4009437 | Phase I | NCDS | CRO - EDC |  |  | 2022-03-21 05:30 | DB Set-Up | Final DBL | 2024-05-22 05:30 |  | 2021-09-29 05:30 | 2021-09-29 05:30 |  | Planned | 2024-03-14 05:30 |  | 2024-05-22 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, investigator and participant blinded, placebo controlled, multiple ascending dose study to determine the safety, tolerability and pharmacokinetic effects of MHS552 in adults with type 1 diabetes. | CMHS552B12101 MHS552 Ph1b T1D | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Martina Zambianchi | Marta Zambianchi | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Type 1 diabetes mellitus | No | Global | Open | Yes | [16 empty] | None of the above
CMHS552B1 | CMHS552B12202 | C4009602 | Phase II |  |  |  |  | 2024-07-29 05:30 |  | Final DBL | 2028-04-25 05:30 |  | 2023-12-16 05:30 |  |  | Planned | 2028-02-29 05:30 |  | 2028-04-25 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CMHS552B12202 Ph2a in T1D adult patients | N0 ATI - NIBR | [6 empty] | Emma Healy | [66 empty] | Type 1 diabetes mellitus | No | Global | Open | Yes
CMHS552D1 | CMHS552D12101 | C4008519 | Phase I | NCDS | CRO - EDC |  |  | 2022-03-10 05:30 | DB Conduct | Final DBL | 2024-06-26 05:30 |  | 2021-10-01 05:30 | 2021-09-30 05:30 |  | Planned | 2024-04-17 05:30 |  | 2024-06-26 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A 2-part, randomized, investigator- and participant- blinded, placebo-controlled, multiple ascending dose study to determine the safety, tolerability and pharmacokinetics of MHS552 in adults participants with Systemic Lupus Erythematosus (SLE) | CMHS552D12101 MHS552 Ph1b SLE | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Elizabeth McNamara | Elizabeth McNamara | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Systemic lupus erythematosus | No | Global | Open | Yes | [16 empty] | None of the above
CMHU650A0 | CMHU650A12101 | C4004103 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-11-09 05:30 | 2020-11-09 05:30 | 2020-12-04 05:30 | DB Conduct | Final DBL | 2022-06-24 05:30 | 2020-12-10 05:30 | 2020-08-07 05:30 | 2020-08-06 05:30 |  | Active | 2022-03-25 05:30 |  | 2022-06-24 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A first-in-human, open-label, single ascending dose study to assess safety and tolerability of intravitreal MHU650 in participants with macular edema from diabetic macular edema (DME), neovascular age-related macular degeneration (nAMD), or retinal vein occlusion (RVO) | CMHU650A12101 MHU650 Mac Edema FIH | N8 Ophthalmology - NIBR | Langlo, Francois | Kumar, Samoj | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Benjamin Maciejewski; Natalia Baginski | Natalia Baginski | Gandla, Prashanth | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Prashanth Gandla transitioned the study to Chandana Sarasani on 25-Mar-2021. |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 10-may-2021: RF finalized for MO1L, MO2L,MO3L DTS tables and raised SNOW ticket 07-May-2021: Updated RF to include MO1L, MO2L, MO3L DTSs and released for peer review 17-Feb-2021: Finalized RF_V2.0 to include LB and EG DTSs 09Nov2020 : RF final and Snow ticket raised | None | None | 2020-11-09 05:30 |  | Ramayanam, Vinay | Varate, Rohit | Rohit Varate | Completed | 2020-12-07 | Completed | 2020-12-23 05:30 |  | Rule file had issues, prerequisite not met | 2020-12-24 05:30 | 2020-12-24 05:30 |  | 2020-12-24 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 4 | 9 | 59 | 0 | 120 | 442 | 0 | 156 | 33 | 143 | 618 | 3 | 0 |  | Diabetic macular oedema; Neovascular age-related macular degenera; Retinal vein occlusion | No | Global | Open | Yes | [10 empty] | 2020-12-01 05:30 | [5 empty] | None of the above | Yes
CMHU650A1 | CMHU650A12201 | C4009522 | Phase II |  |  |  |  | 2023-04-21 05:30 |  | Final DBL | 2025-02-12 05:30 |  | 2022-09-16 05:30 |  |  | Planned | 2025-01-08 05:30 |  | 2025-02-12 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CMHU650A12201 POC | N8 Ophthalmology - NIBR | [6 empty] | Jen Watts | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Diabetic macular oedema | No | Global | Open | Yes | [16 empty] | None of the above
CMHV370A0 | CMHV370A02101 | C4006333 | Phase I | Other | CRO - EDC | 2021-06-10 05:30 |  | 2021-06-14 05:30 | DB Conduct | Final DBL | 2022-06-02 05:30 | 2021-05-11 05:30 | 2021-03-08 05:30 | 2021-01-22 05:30 |  | Active | 2022-04-07 05:30 |  | 2022-06-02 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A 3-part first-inhumanstudy consisting of randomized, subject-blinded, placebocontrolled, single and multiple ascending oral dose study to investigate the safety, tolerability, pharmacokinetics and pharmacodyna mics of MHV370, and a randomized, open-label cross-over study to investigate food effect in healthy volunteers. | CMHV370A02101 DDI OC & CYP | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Niamh Fagan | Niamh Fagan | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Sjogren's syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CMHV370A1 | CMHV370A12201 | C4005229 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-06-01 05:30 | 2021-10-27 05:30 | 2021-12-08 05:30 | DB Conduct | Final DBL | 2024-04-10 05:30 | 2021-11-30 05:30 | 2021-06-24 05:30 | 2021-06-24 05:30 |  | Active | 2024-01-31 05:30 |  | 2024-04-10 05:30 |  | FALSE | NIBR Go | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A multi-center, randomized, participant and investigator-blinded, placebo-controlled, parallel group basket study to evaluate the safety, tolerability and efficacy of MHV370 in participants with Sjoegrens Syndrome or Mixed Connective Tissue Disease. | CMHV370A12201 PoC SjS | N0 ATI - NIBR | Langlo, Francois | Thorat, Vinayak | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Anca-Aura Bietiger-Badea | Anca-Aura Bietiger-Badea | Porandla, Swapna | Kashyap, Sandeep |  |  |  |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 8Feb2022: LB DTS finalized. RF and Checklist version 3.0 has been finalized with the LB DTS. SNOW51 request RITM3469599 has been raised and notified the LSP. 7Feb2022: Added LB DTS into the RF and sent for the peer review. As per the communication with the TDM and Sandeep Marathe, I will be signing off the DTS since the DBD is unavailable. 4Feb2022: Received the LB DTS from the TDM. Reviewed it and provided my comments in it. Will include it in the RF once it is finalized. 24Jan2022: DTS have been finalized and both the RF and checklist have been finalized in the SubWay. SNOW51 request has been raised and notified the LSP 24Dec2021: RF peer review completed, will finalize once the DTS are finalized. 23Dec2021: Updated the RF with the DTS details in it and released for peer review. 20Dec2021: Provided the review comments. 17Dec2021: EG and IRT DTS received. 28Oct2021 : RF and Checklist finalized in SubWay. Both LSH TEST and PROD set up requests have been raised and notified the LSP. 27Oct2021 : Peer review completed and got the approval from peer reviewer for finalization. Study went on live. 26Oct2021 : Received the updated ALS and SOD from the DBD. Released the RF for peer review with updated RF and ALS. 24Oct2021 : Received the first round peer review comments. Sent the DB related comments to the DBD and made the necessary changes in the RF. 20Oct2021 : DBD sent the updated ALS and SOD incorporating all the changes. RF released for peer review. LSP assigned for the study 18Oct2021 : Sent the review comments to the DBD. 10Oct2021 : Received updated ALS and SOD to review. 5Oct2021 : Go-live date has been pushed to 27th Oct. 1Oct2021 : Discussion is going on for the QS domain and pending with study specific SDTM annotations to receive to finish the RF. 29Sep2021 : Received the comments to review and updated ALS, SOD. 22Sep2021 : Provided the necessary comments to the DBD regarding further updates and pending SDTM annotations. 20Sep2021 : DBD provided the comments along with the SDTM annotations and updated ALS and SOD. 13Sep2021 : Provided necessary comments after the ALS review. DBD is working on the comments. 9Sep2021 : Received updated ALS. 8Sep2021 : Received latest ALS along with SDTM, SRFs and SSD for review. 2Aug2021 : Received updated activity planner from the DBD as this is a priority LSH study. 28Jul2021 : Received the activity planner from the DBD 28Jul2021 : RF developer assigned with DB go-live as 27Sep2021 | None | None | 2021-10-28 05:30 | FPFV delayed | Saranji, Muthu | Girvasiya, Shaili | Rohit Varate | Completed | 2021-11-08 | Completed | 2021-11-22 05:30 |  |  | 2021-11-22 05:30 | 2021-11-22 05:30 | [5 empty] | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 10 | 55 | 0 | 154 | 526 | 0 | 172 | 35 | 206 | 767 | 3 | 0 |  | Sjogren's syndrome | Yes | Global | Open | Yes | 2021-10-28 05:30 | [9 empty] | 2021-11-18 05:30 | [5 empty] | None of the above
CMHV370B1 | CMHV370B12201 | C4008628 | Phase II |  |  |  |  | 2023-02-06 05:30 |  | Final DBL | 2025-07-09 05:30 |  | 2022-09-11 05:30 |  |  | Planned | 2025-06-04 05:30 |  | 2025-07-09 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CMHV370B12201 MHV370 PoC in SLE | N0 ATI - NIBR | [6 empty] | Louise Mooney | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Systemic lupus erythematosus | No | Global | Open | Yes | [16 empty] | None of the above
CMHV370A0 | CMHV370X2101 | C1200279 | Phase I | NCDS | CRO - EDC |  |  | 2018-06-25 05:30 | DB Locked | Final DBL Achieved |  | 2018-06-25 05:30 | 2018-03-08 05:30 | 2018-03-19 05:30 |  | Active | 2021-06-10 05:30 | 2021-03-29 05:30 | 2021-10-08 05:30 | 2021-08-05 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A 3-part first-in-human study consisting of randomized, subject-blinded, placebo-controlled, single and multiple ascending oral dose study to investigate the safety, tolerability, pharmacokinetics and pharmacodynamics of MHV370, and a randomized, open-label cross-over study to investigate food effect in healthy volunteers. | CMHV370X2101 FIH | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Patrycja Misiolek | Patrycja Misiolek | [15 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | -NA- | [11 empty] | CMED | [19 empty] | Autoimmune disorder | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02101 | C4007726 | Phase I | Other | CRO - EDC |  |  | 2021-03-05 05:30 | DB Conduct | Final DBL | 2022-05-20 05:30 | 2021-03-05 05:30 | 2020-12-21 05:30 | 2021-01-04 05:30 |  | Active | 2022-02-25 05:30 |  | 2022-05-20 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A randomized, subject- and investigator-blinded, placebo-controlled, single ascending, subcutaneous dose study to assess the safety, tolerability and pharmacokinetics of MIJ821 in healthy subjects | CMIJ821A02101_SC Bridging Study | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02102 | C4008716 | Phase I |  | Rave EDC - Inhouse |  |  | 2023-05-29 05:30 | Study Planned | Final DBL | 2024-04-19 05:30 |  | 2023-02-27 05:30 |  |  | Planned | 2024-03-08 05:30 |  | 2024-04-19 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - NS |  | CMIJ821A02102 Human abuse and dependence study | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Denise Serra | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Depression | No | Global | Open | Yes
CMIJ821A0 | CMIJ821A02103 | C4008890 | Phase I | Other |  |  |  | 2023-06-29 05:30 |  | Final DBL | 2023-11-03 05:30 |  | 2023-02-07 05:30 |  |  | Planned | 2023-10-06 05:30 |  | 2023-11-03 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CMIJ821A02103 | P4 Neuroscience | [6 empty] | Melissa Hackling | [66 empty] | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02104 | C4008707 | Phase I |  | CRO - EDC |  |  | 2022-04-26 05:30 | Study Planned | Final DBL | 2022-08-03 05:30 |  | 2022-02-06 05:30 |  |  | Planned | 2022-06-29 05:30 |  | 2022-08-03 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - NS |  | CMIJ821A02104 Human ADME study in HS | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | ICON | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02105 | C4008712 | Phase I | Other | Other |  |  | 2021-11-01 05:30 | Study Planned | Final DBL | 2022-02-24 05:30 | 2021-10-13 05:30 | 2021-09-20 05:30 | 2021-09-07 05:30 |  | Active | 2022-01-27 05:30 |  | 2022-02-24 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CMIJ821A02105 OC DDI | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | NA | [19 empty] | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02106 | C4008711 | Phase I | Other |  |  |  | 2022-01-17 05:30 |  | Final DBL | 2022-11-23 05:30 |  | 2022-02-09 05:30 |  |  | Planned | 2022-10-14 05:30 |  | 2022-11-23 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CMIJ821A02106 CYP2D6 DDI | P4 Neuroscience | [5 empty] | Melissa Hackling | Melissa Hackling | [66 empty] | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821A02107 | C4008708 | Phase I | Other |  |  |  | 2023-10-30 05:30 |  | Final DBL | 2024-06-11 05:30 |  | 2023-07-29 05:30 |  |  | Planned | 2024-05-14 05:30 |  | 2024-06-11 05:30 | [5 empty] | FULL Outsourced |  |  | CMIJ821A02107 PK DDI with UGT inhibitor | P4 Neuroscience | [6 empty] | Denise Serra | [66 empty] | Depression | No | Global | Open | Yes
CMIJ821A0 | CMIJ821A02108 | C4008713 | Phase I | Other |  |  |  | 2023-10-30 05:30 |  | Final DBL | 2024-07-23 05:30 |  | 2023-07-02 05:30 |  |  | Planned | 2024-05-28 05:30 |  | 2024-07-23 05:30 | [5 empty] | FULL Outsourced |  |  | CMIJ821A02108 PK hepatic imprd patients/matchedHS | P4 Neuroscience | [6 empty] | Denise Serra | [66 empty] | Depression | No | Global | Open | Yes
CMIJ821A0 | CMIJ821A02109 | C4008715 | Phase I | Other |  |  |  | 2023-06-22 05:30 |  | Final DBL | 2024-04-26 05:30 |  | 2023-05-14 05:30 |  |  | Planned | 2024-03-01 05:30 |  | 2024-04-26 05:30 | [5 empty] | FULL Outsourced |  |  | CMIJ821A02109 PK renal imprd patients/matched HS | P4 Neuroscience | [6 empty] | Denise Serra | [66 empty] | Depression | No | Global | Open | Yes
CMIJ821A0 | CMIJ821A02110 | C4011716 | Phase I |  | Rave EDC - Inhouse |  |  |  | Study Planned | [6 empty] | Planned | [5 empty] | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - NS |  | CMIJ821A02110 human PET RO | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Denise Serra | [17 empty] | Rohit Varate | [36 empty] | 50 | [7 empty] | 700 | 2 |  |  | Depression | No | Global | Open | Yes
CMIJ821A1 | CMIJ821A11101 | C4006593 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-10-12 05:30 | 2020-10-12 05:30 | 2020-10-30 05:30 | DB Locked | Final DBL Achieved |  | 2020-11-02 05:30 | 2020-07-21 05:30 | 2020-07-21 05:30 |  | Completed | 2021-01-06 05:30 | 2021-01-03 05:30 | 2021-02-15 05:30 | 2021-02-19 05:30 | FALSE | Interventional | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS |  | CMIJ821A11101 Japan ES | P4 Neuroscience | Langlo, Francois | Tsukazaki, Mayuka | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | Moses, Leah | Moses, Leah | Not Started |  | Initial go live as 12Oct2020 when RF developer assigned on 29Jul2020. |  | DRM | Shafiudeen, Rehana Banu | Shafiudeen, Rehana Banu | Completed | 12Feb2021 : The rule file 5.0 is finalized in SUBWAY and the LSP is notified. 10Feb2021 : EG2L DTS is removed from RF and sent for peer review. 28Jan2021 : The rule file 4.0 is finalized in SUBWAY and the LSP is notified. 22Jan2021 : EG2L DTS is finalized. It is included in the RF and sent for peer review. 15Jan2021 : I have requested for the current status of the DTS and TDM has mentioned that the DTS setup is undergoing change. 3-Dec-2020 : EG2L DTS that is not finalized yet. Requested for the clean copy of the EG to the TDM. Planned DBL is 09Feb2021 as per iBOW 24Nov2020 : Updated and sent the RF for peer review. 23Nov2020: DB lead has missed to inform about theDTS finalization. Dropped an email to DB lead requesting to share the DTS. 29Oct2020 : Rulefile 2.0 is live including the LB and EG DTS. 28Oct2020 : EG and LB DTS are finalized about to be included in the Fule File. 13Oct2020 : RF final and snow ticket raised. 9Oct2020 : Peer review is completed. Rulefile will be finalized after Go-live(12Oct2020) .1Oct2020 : Peer review completed for the study working on oeer review commnets 25Sep2020 : Sent the rulefile for peer review. 14Sep2020 : All forms reviewed except 1 Study specific form. Awating SDTM annotations. RF development ongoing 1Sep2020: Completed the review for global forms. and 1 Study specific form yet to recieve SDTM annotation for one other study specific form. 14Aug2020: DBD has shared one approved SRF along with ALS. Started reviwing the approved SRF. | None |  | 2020-10-13 05:30 | Transition Study | Girvasiya, Shaili | Kadam, Sandeep | Rohit Varate | Completed | 2020-11-03 | Completed | 2020-11-09 05:30 |  |  | 2020-11-17 05:30 | 2020-11-17 05:30 | Pre-requisites not met | 2020-11-17 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | ZK;#Y1;#Y5 | 2021-02-16 05:30 | 2021-02-19 05:30 | [9 empty] | NA | [5 empty] | 2 | 7 | 95 | 0 | 131 | 764 | 0 | 167 | 38 | 817 | 1619 | 2 | 0 |  | Depression | No | Global | Open | Yes | [10 empty] | 2020-11-09 05:30 | [5 empty] | None of the above | Yes
CMIJ821A1 | CMIJ821A12201 | C4008639 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-01-08 05:30 | 2021-05-13 05:30 | 2021-06-15 05:30 | DB Conduct | DB Snapshot | 2022-05-03 05:30 | 2021-07-20 05:30 | 2020-10-17 05:30 | 2020-10-21 05:30 | 2021-04-14 05:30 | Active | 2024-01-30 05:30 |  | 2024-03-05 05:30 |  | FALSE | DCN Priority | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A double-blind, placebo-controlled, randomized dose-ramging trial to investigate efficacy and safety of intravenous MIJ821 infusion in addition to comprehensive standard of care on the rapid reduction of symptoms of Major Depressive Disorder in subjects who have suicidal ideation with intent | CMIJ821A12201 Ph IIb Dose ranging study | P4 Neuroscience | Chaghasbanian, Harut | Gayathri, Tharra | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Cecilia Bottero | C��cilia Bottero | Kancharla, Susmita | Palande, Sujit | Completed |  | Oct-2021 : Pallabi transitioned study to Sujit 29Apr2021 : Go-live date is 7th May 2021(as of now) and working on the ECS and tSDV. Updated planned go-live date is on 7th May 2021. Initial Golive as 08Jan2021 when DBD assigned |  | DRM | Patnaik, Angella | Bairagi, Arpita | Completed | 14Feb2021:Since PPC03 has no impact on Rule file, SNOW-51 Ticket has been raised with ticket number- RITM3491496 for LSH update. 27Jan2022: DBD shared PPC03 for IA . Reviewed and shared my comments. 02Dec2021: CMIJ821A12201_Rule file_version 4.0 is finalized in Subway with DDG001 form included as per PPC02. SNOW-51 Ticket is also raised with ticket number- RITM3252242 07Sep2021: DBD shared the PPC-2 for IA. Reviewed and shared my comments 11Aug2021 : Reassigned the study from Angella to Arpita. 8JUL2020: PPC#1 implemented. No RF update required. SNOW #51 has been raised for LSH re-build. 13-MAY-2021: RF Version 1.0 finalized in SubWay. SNOW#05 request raised for Study set-up in LSH. 04-MAY-2021: Verifying the RF with the updated ALS and UAT SOD. 20-APR-2021: Released first draft of RF for Peer Review. 12-APR-2021: Received documents for RF creation. | None | None | 2021-05-13 05:30 |  | Polavarapu, Vanaja | Polavarapu, Vanaja | Amit Agavekar | Completed | 2021-07-23 | Completed | 2021-08-05 05:30 |  | Pre-requisites not met | 2021-08-05 05:30 | 2021-08-05 05:30 |  | 2021-08-05 05:30 |  |  | DDPASS is on-going |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 43 | 59 | 0 | 180 | 655 | 0 | 193 | 38 | 203 | 896 | 26 | 0 |  | Acute depression | Yes | Global | Open | Yes | [10 empty] | 2021-06-01 05:30 | [5 empty] | None of the above
CMIJ821B1 | CMIJ821B12201 | C4010155 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-28 05:30 | Study Planned | DB Go-live | 2022-05-15 05:30 |  | 2022-03-21 05:30 |  |  | Planned | 2023-09-11 05:30 |  | 2023-10-26 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS |  | CMIJ821B12201 bridging study TRD | P4 Neuroscience | Langlo, Francois | Palnitkar, Prachi | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Judit Sovago | Daniela Heintz | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 15 Dec 2021: RF programmer assigned. 22 Feb 2022: TDM informed the study will be moving to GDO, No support required from CDDRA. | [6 empty] | Rohit Varate | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Depression | No | Global | Open | Yes | [16 empty] | None of the above
CMIJ821A0 | CMIJ821X2101 | C1200670 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-05-31 05:30 |  | 2017-03-02 05:30 |  | Completed | 2018-12-24 05:30 | 2018-12-05 05:30 | 2019-03-01 05:30 | 2019-03-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A first-in-human, randomized, subject blinded , placebo-controlled, single ascending intravenous doses and a repeated single intravenous dose study, to assess the safety, tolerability and pharmacokinetics of MIJ821 in healthy volunteers | CMIJ821X2101 FIH SAD/Repeated Dose in HV | P4 Neuroscience | Langlo, Francois | Rajput, Namita | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Sachin Desai | Sachin Desai | [15 empty] | Kadam, Sandeep |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | CMED | [19 empty] | Depression | No | Global | Completed | Yes | [16 empty] | None of the above
CMIJ821A1 | CMIJ821X2201 | C1200669 | Phase II | Other | CRO - EDC |  |  | 2019-02-08 05:30 | DB Locked |  |  | 2019-02-08 05:30 | 2018-10-15 05:30 | 2018-10-22 05:30 |  | Completed | 2020-03-23 05:30 | 2020-03-23 05:30 | 2020-07-20 05:30 | 2020-07-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A multi center, randomized, subject and investigator blinded, placebo-controlled, active comparator, parallel group proof of concept study to evaluate the efficacy, safety, tolerability, and pharmacokinetics of MIJ821 in patient with treatment-resistant depression. | CMIJ821X2201 POC in Treatment Resistant Depression | P4 Neuroscience | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Maria Berkheimer | Maria Berkheimer | [15 empty] | Girvasiya, Shaili |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | ZK;#ZK02;#Y1;#YR | [11 empty] | CMED | [19 empty] | Depression | No | Global | Completed | Yes | [16 empty] | None of the above
CMIK665A1 | CMIK665X2101 | C3000368 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-07-12 05:30 | 2018-06-08 05:30 | DB Locked |  |  | 2017-07-12 05:30 | 2018-01-19 05:30 | 2016-10-26 05:30 |  | Completed | 2021-05-31 05:30 | 2019-06-07 05:30 | 2021-08-06 05:30 | 2020-09-29 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase I open label, multi-center study to characterize the safety, tolerability and pharmacokinetics of intravenously administered MIK665, a Mcl-1 inhibitor, in patients with refractory or relapsed lymphoma or multiple myeloma | CMIK665X2101 Phase I Lymphoma and Multiple Myeloma | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Laurent Susini | Laurent Susini | Tadiparthy, Ramakanth | Vedula, Nagendra | [13 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes |  | 2020-10-21 05:30 | 2020-10-23 05:30 |  |  | ONC | Novartis | InHouse | 2017-03-24 05:30 | 2017-03-24 05:30 | Kanchi, Pavan kumar | Shewane, Roshni | IQVIA | [7 empty] | 228 | 0 |  |  | 0 |  |  |  | 876 | 3 | 0 |  | Diffuse large B-cell lymphoma refractory; Haematological malignancy; Multiple myeloma; Non-Hodgkin's lymphoma refractory | No | Global | Open | Yes | [15 empty] | Girvasiya, Shaili | None of the above
CMIW491A0 | CMIW491A02101 | C4006992 | Phase I | Other | CRO - EDC |  |  | 2023-03-06 05:30 | Study Planned | DB Go-live | 2023-03-15 05:30 |  | 2022-11-04 05:30 |  |  | Planned | 2023-10-06 05:30 |  | 2023-11-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - OPHTHA |  | CMIW491A02101 FIH | N8 Ophthalmology - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | JoAnn Whittle | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Dry eye | No | Global | Open | Yes | [16 empty] | None of the above
CMIW491A1 | CMIW491A12201 | C4011577 | Phase II |  |  |  |  | 2024-03-28 05:30 |  | Final DBL | 2025-01-29 05:30 |  | 2023-11-10 05:30 |  |  | Planned | 2024-12-25 05:30 |  | 2025-01-29 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CMIW491A12201 MIW MGD POC | N8 Ophthalmology - NIBR | [6 empty] | Valerie Brooks | [66 empty] | Dry eye | Yes | Global | Open | Yes
CMIW815B1 | CMIW815X2101 | C1200420 | Phase I | NCDS | OC RDC - Inhouse |  | 2016-03-11 05:30 |  | DB Locked |  |  | 2016-04-28 05:30 |  | 2015-12-04 05:30 |  | Completed | 2020-08-06 05:30 | 2020-08-06 05:30 | 2020-09-15 05:30 | 2020-09-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I, open label, multicenter study of the safety and efficacy of MIW815 (ADU-S100) administered by intratumoral injection to patients with advanced/metastatic solid tumors or lymphomas | CMIW815X2101 | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon | Gabriela Mere Villanueva | Gehlawat, Priya | Bai, Chandrakala | [13 empty] | Girvasiya, Shaili |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2016-03-11 05:30 | 2016-03-11 05:30 | Gehlawat, Priya | Mareedu, Vasu | IQVIA | [7 empty] | 186 | 0 |  |  | 0 |  |  |  | 807 | 6 | 0 |  | Lymphoma; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CMIW815C1 | CMIW815X2102J | C1200333 | Phase I | NCDS | OC RDC - Inhouse | 2017-05-23 05:30 | 2017-05-23 05:30 |  | DB Locked |  |  | 2017-09-08 05:30 |  | 2017-03-13 05:30 |  | Completed | 2020-12-18 05:30 | 2020-12-18 05:30 | 2021-03-02 05:30 | 2021-03-02 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib, open label, multicenter study of the safety and efficacy of MIW815 (ADU-S100) administered by intratumoral injection with PDR001 to patients with advanced/metastatic solid tumors or lymphomas | CMIW815X2102J Phase 1 MIW+PDR | N7 Oncology - NIBR | Langlo, Francois | Barnard, Carol | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon | Gabriela Mere Villanueva | Govula, Shashikanth | Gehlawat, Priya | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [12 empty] | No issues identified and all domains reviewed by the team. | 0 | OCRDC - Inhouse | No | -NA- | 2021-03-03 05:30 | 2021-03-04 05:30 |  |  | ONC | Novartis | ICON | 2017-05-26 05:30 | 2017-05-26 05:30 | Gehlawat, Priya | Mareedu, Vasu | IQVIA | [7 empty] | 138 | 0 |  |  | 0 |  |  |  | 837 | 10 | 0 |  | Lymphoma NOS; Solid tumour | No | Global | Open | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | Yes
CMTHDLGY | CMTHDLGY0002 | C1200097 | Not Applicable | Other | CRO - EDC |  |  | 2020-06-19 05:30 | DB Locked |  |  | 2020-06-19 05:30 | 2019-11-28 05:30 | 2019-11-27 05:30 |  | Active | 2021-06-24 05:30 | 2021-06-24 05:30 | 2021-08-26 05:30 | 2021-09-03 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | evaluation of different measures of Cognition | CMTHDLGY0002 NoPHIS in early AD | R1 CBT - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Vanessa Vallejo | Vanessa Vallejo | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Alzheimer's disease; Cognitive impairment | No | Global | Open | Yes | [16 empty] | None of the above
CTIN816A0 | CMTHDLGY0009 | C4003128 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-01-15 05:30 | 2020-06-22 05:30 | 2020-08-12 05:30 | DB Conduct | Final DBL | 2023-01-24 05:30 | 2020-08-06 05:30 | 2020-02-17 05:30 | 2021-08-25 05:30 |  | Active | 2022-12-13 05:30 |  | 2023-01-24 05:30 |  | FALSE | Pioneer | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | MTHDLGY study to identify and validate the key patient profile for patients that would develop Acute Kidney Injury for defining I/E criteria for the PoC | CMTHDLGY0009 to id profile - I/E criteria for poc | N0 ATI - NIBR | Langlo, Francois | Singh, Abhishek Kumar | Temgire, Ganesh | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Nicolas Panchaud | Nicolas Panchaud | Vedula, Nagendra | Rapaka, Sindhuja |  |  | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Jan2020 |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 22-Oct-2021: RF v4.0 finalized for PPC#04 updates 09Jul2021: RF v3.0 is finalized for PPC03 updates . 01Jul2021: RF v2.0 is finalized in CREDI with DSG005 and LSH snow ticket is raised. 18-Jun-2021: Earlier RF developer(Praveen) is in process to finalize the RF v2.0 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 25-May-2021: Working on RF update to include DSG005 and planning to finalize RF by 28-May-2021 05Nov2020: No Activity. 11Sep2020: RF Version 2.0 is updated and shared with team for review. I will finalize it by 11Sep2020: 23Jun2020 : Rule file Version 1.0 has been finalized and have raised SNOW05 ticket(RITM1531878) 18Jun2020 : RF is ready and recieved Peer QC comments and working on the same. 2Forms SRFs PRS001 , PRS003 are still pending from DBD but included in RF. Need those for Review 06Jun2020 : Have received SDTM annoations last week for RF development. 12May2020 : This study has 32 forms out of which 9 SS. Started with standrad forms and awaiting SDTM annotations for SS. DBD following up with SDTM programmer. 19Mar2020 : Sent an followup email to DBD. 17Feb2020 : Followed up with DBD and received 1 Study specific form for review . Awaiting SDTM annotations. No RF activity started | None | None | 2020-06-23 05:30 |  | Saranji, Muthu | Varate, Rohit | Rohit Varate | Completed | 2020-07-02 | Completed | 2020-07-31 05:30 |  |  | 2020-07-31 05:30 | 2020-08-18 05:30 | Pre-requisites not met | 2020-09-01 05:30 |  |  | Due to less data in study we kept status as on hold so once we have sufficeint data will finalze the status and mark it as complete. | 0 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 9 | 46 | 0 | 108 | 363 | 0 | 108 | 18 | 168 | 549 | 1 | 0 |  | Acute kidney injury | No | Global | Open | Yes | [10 empty] | 2020-07-31 05:30 | [5 empty] | None of the above
CMTHDLGY | CMTHDLGY0010 | C4004102 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-12-23 05:30 | 2020-12-24 05:30 | 2020-12-23 05:30 | DB Conduct | Interim DBL | 2022-03-14 05:30 | 2020-12-22 05:30 | 2020-09-30 05:30 | 2020-10-09 05:30 |  | Active | 2027-05-19 05:30 |  | 2027-06-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A prospective study to evaluate the clinical characteristics and disease progression of patients with Meibomian gland dysfunction (MGD) | CMTHDLGY0010 MGD | R1 CBT - NIBR | Langlo, Francois | Thorat, Vinayak | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Mateusz Piksa; Nils Burger | Nils Burger | Dadapogu, Jesica Priyadarshini | Ahuja, Mohit | Not Started |  |  |  | DRM | Choppadandi, Kranthikumar | R, Pratheeksha K | Completed | 17Feb2022: RF Version 3.0 finalized for PPC 3 and SNOW51 ticket raised on 16Feb2022 (SNOW51 Ticket number - RITM3502120) 11Aug2021 : Reassigned the study from Kranthi to Pratheeksha. 02-Dec-2020: Reviewed ALS and SRFs and provided comments from RF development perspective | None | None | 2020-12-24 05:30 | FPFV date to be verified. | Praveen kumar, Chakka Giri |  | Rohit Varate | Completed | 2021-01-15 | Completed | 2021-01-27 05:30 |  | Delay in SMT creation due to issue while accessing GPS | 2021-01-27 05:30 | 2021-01-29 05:30 | Delay in SMT creation due to issue while accessing GPS | 2021-02-03 05:30 |  |  | DDPASS INITIATED ON 25-MAY-21 and planned completion date is 30-JUNE-21 Praveen(19-AUG-21):As per confirmation from TDM (Thorat, Vinayak <vinayak.thorat@novartis.com>) DDPass is on hold , due to back to back PPC and to complete the data entry. | 0 |  | No | [12 empty] | NA | [5 empty] | 3 | 9 | 39 | 0 | 148 | 312 | 0 | 81 | 4 | 103 | 419 | 1 | 0 |  | Eye pain | No | Global | Open | Yes | [10 empty] | 2021-01-22 05:30 | [5 empty] | None of the above | Yes
CMTHDLGY | CMTHDLGY0011 | C4004132 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2020-03-16 05:30 | 2020-11-10 05:30 | 2021-04-14 05:30 | DB Conduct | Final DBL | 2023-08-30 05:30 | 2021-04-14 05:30 | 2020-04-08 05:30 | 2020-09-21 05:30 |  | Active | 2023-05-04 05:30 |  | 2023-08-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A prospective, Limbal Stem Cell Deficiency, natural history study to develop optimized endpoints | CMTHDLGY0011 LSCD | R1 CBT - NIBR | Langlo, Francois | Kumari, Sangita | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Karen Holopigian; Matthias Jecklin | Matthias Jecklin | Thomas, Ankit | Thomas, Ankit | Not Started |  | Study moved from 03May to 17Jul2020 as per DBD confirmation on 24Apr2020 As of 07Jan2020 planned golive is 16Mar2020. Initial go live as 16Mar2020 when RF developer assigned on 10Feb2020. |  | DRM | Govula, Shashikanth | Kuttoboina, Sujan Kumar | Completed | 04AUG21: PPC has been initiated, once ppc is done will update Rule file 21Jul2021 : Forms SCS001,SCE001 are reflecting in 21Jul report as well. 13JUL21: Rule file update is ongoing. SC and QS domains getting failed at LSH side, Rule file update is required and expected date of completion is 15JUL21. 01APR21: LSH setup was done for SC domain during initial RF release as per confirmation with LSP. This form is available in ALS tracker, Rule file and LSH seup. checking the issue why its flagging in report. Also need to check below comment. 7JAN2021: SG: Variable rename for APMH has been requested by LSH. QS character limitation issue. These need Rulefile update. 11Nov2020 : RF Final and snow ticket raised 5Nov2020: DB Golive planned for 6Nov. Rule file is planned for finalization along with Golive. 05Oct2020 : Database updated for below domains and informed to RF programmer on 1-Oct QS, DV, MH, ZX. APMH Domain: SRF being rasied today to include new fields for this page. Awaiting inputs from Statistical programmer before raising SRF. Once SRF is raised DB to be updated. There is a Protoco amendmnt and TDM plan to go for ppc rather than including in initial golive. Notified Appalla. 04Sep2020 : risk on Rule file activities as screens are not yet finalized. Last month we had multiple meetings to discuss on the screen design of a few Study specific pages and appropriate decisions were taken(split pages etc). However screens are not yet released for UAT. I spoke with Ankit and he confirmed that Screen UAT for Unique’s is planned for next week. 12AUG2020: RF activities not yet started. However I have provided inputs on Screen design for few complex study specific pages. Issues now resolved and suggestion to split pages is under consideration for Clinical team's approval. 10Feb2020 : Awaiting response from DBD sent an email. It seems DB golive will be pushed and no development activities started yet. The Protocol finalization date is pushed to 03Mar2020. | SCS001,SCE001 | None | 2020-11-11 05:30 |  | Ramayanam, Vinay | Varate, Rohit | Rohit Varate | Completed | 2020-12-15 | Completed | 2020-12-16 05:30 |  |  | 2021-01-29 05:30 | 2021-01-29 05:30 |  | 2021-01-29 05:30 |  |  |  | 25 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 2 | 7 | 44 | 0 | 107 | 377 | 0 | 90 | 6 | 263 | 646 | 4 | 0 |  | Corneal disorder | No | Global | Open | Yes | [10 empty] | 2020-12-18 05:30 | [5 empty] | None of the above | Yes
CMTHDLGY | CMTHDLGY0020 | C4014481 | Not Applicable |  |  |  |  | 2022-04-25 05:30 |  | Final DBL | 2022-12-26 05:30 |  | 2022-01-14 05:30 |  |  | Planned | 2022-07-26 05:30 |  | 2022-12-26 05:30 | [5 empty] | Outsourced |  |  | CMTHDLGY0020 NoPhis: Science37 digital imaging AD | R1 CBT - NIBR | [5 empty] | Szczepan Baran | Izabela Rozenberg | [66 empty] | Atopic dermatitis | No | Global | Open | Yes
CMTHDLGY | CMTHDLGY0021 | C4015142 | Not Applicable |  |  |  |  | 2022-04-15 05:30 |  | Final DBL | 2022-09-16 05:30 |  | 2022-02-03 05:30 |  |  | Planned | 2022-07-17 05:30 |  | 2022-09-16 05:30 | [5 empty] | ED Undecided Sourcing |  | A Study to evaluate the feasibility, tolerability, and acceptability of using digital technology to conduct remote symptom assessment in 2 to 10 year-old females with Rett syndrome and MECP2 pathogenic variants | CMTHDLGY0021 NoPHIS Rett study | R1 CBT - NIBR | [6 empty] | JoAnn Whittle | [66 empty] | Rett Syndrome | No | Global | Open | Yes
CLXE408B1 | CMTHDLGY0023 | C4016200 | Not Applicable |  |  |  |  | 2023-02-08 05:30 |  | Final DBL | 2025-08-07 05:30 |  | 2022-04-11 05:30 |  |  | Planned | 2025-06-27 05:30 |  | 2025-08-07 05:30 | [5 empty] | InHouse |  |  | CMTHDLGY0023 LXE408B1 NoPHIS in Acute Chagas | R4 NITD - NIBR | [5 empty] | Olga Jurcikova | Olga Jurcikova | [66 empty] | Infection parasitic | Yes | Global | Open | Yes
CNCJ424A0 | CNCJ424A02101 | C4002746 | Phase I | NCDS | CRO - EDC |  |  | 2020-09-23 05:30 | DB Conduct | Final DBL | 2022-03-29 05:30 | 2020-09-23 05:30 | 2020-06-17 05:30 | 2020-05-15 05:30 |  | Active | 2021-11-25 05:30 | 2021-09-28 05:30 | 2022-03-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | A randomized, participant and investigator-blinded, placebo-controlled first-in-human study to assess the safety, tolerability and pharmacokinetics of single and multiple ascending doses of NCJ424 in healthy adult participants | CNCJ424A02101 FIH | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Benjamin Maciejewski | Benjamin Maciejewski | [15 empty] | Tidke, Shyam |  | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Chronic obstructive airways disease | No | Global | Open | Yes | [16 empty] | None of the above
CNCJ424A1 | CNCJ424A12201 | C4005558 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-05-10 05:30 |  | 2022-06-27 05:30 | Study Planned | DB Go-live | 2022-06-14 05:30 |  | 2022-03-18 05:30 |  |  | Planned | 2023-10-13 05:30 |  | 2023-11-17 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP |  | CNCJ424A12201 POC in COPD | N5 DAx - NIBR | Langlo, Francois | Palav, Mahesh | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Benjamin Maciejewski; Marcia Guadalupe Garcia Gonzalez | Benjamin Maciejewski | Gupta, Anshu | Gupta, Anshu | [6 empty] | Kuttoboina, Sujan Kumar | Not Started | [7 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CNCJ424B1 | CNCJ424B12201 | C4009413 | Phase II |  |  |  |  | 2023-11-07 05:30 |  | Final DBL | 2025-05-05 05:30 |  | 2023-05-22 05:30 |  |  | Planned | 2025-03-24 05:30 |  | 2025-05-05 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CNCJ424B12201 PoC in CF | N5 DAx - NIBR | [6 empty] | Therese Swan | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 750 | 8 | 0 |  | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CNGI226A0 | CNGI226A02101 | C4004076 | Phase I | NCDS | Other |  |  | 2020-09-11 05:30 | DB Locked |  |  | 2020-09-11 05:30 | 2020-04-22 05:30 | 2020-04-21 05:30 |  | Completed | 2021-03-12 05:30 | 2021-03-12 05:30 | 2021-05-07 05:30 | 2021-05-10 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD | A first-in-human, randomized, blinded, placebo-controlled single ascending dose study to investigate the safety, tolerability and pharmacokinetics of intravenous NGI226 in healthy participants | CNGI226A02101 FIH-SAD in HV | N4 MSD - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Jiaxin Li | Jiaxin Li | [15 empty] | Adi, Vishnupriya |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02;#ZK03 | 2021-05-24 05:30 | 2021-05-25 05:30 | [9 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Tendonitis | No | Global | Open | Yes | [14 empty] | DBL |  | None of the above | Yes
CNGI226A1 | CNGI226A12201 | C4007733 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-18 05:30 | Study Planned | Final DBL | 2024-11-14 05:30 |  | 2022-03-18 05:30 |  |  | Planned | 2024-10-10 05:30 |  | 2024-11-14 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | Single dose, double blind, placebo controlled study to assess local tolerability, upregulation of JAK pathway and pathway modification of NGI226-PLGA after local PT injection in adult patients with Achilles tendinopathy | CNGI226A12201 PoM in Achilles Tendinopathy | N4 MSD - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Emilie Francoise Voltz | Emilie Francoise Armelle Voltz | [17 empty] | Rohit Varate | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Tendonitis | No | Global | Open | Yes | [16 empty] | None of the above
CNGI226A1 | CNGI226A12202 | C4007953 | Phase II |  |  |  |  | 2023-10-16 05:30 |  | Final DBL | 2025-02-21 05:30 |  | 2023-05-05 05:30 |  |  | Planned | 2025-01-17 05:30 |  | 2025-02-21 05:30 | [5 empty] | ED Undecided Sourcing |  | Randomized, double-blind, placebo- controlled, dose-finding, single dose injection, multicenter (including Japan), | CNGI226A12202 PoC in Rotator Cuff Tendinopathy | N4 MSD - NIBR | [6 empty] | Emilie Francoise Armelle Voltz | [66 empty] | Tendonitis | No | Global | Open | Yes
CNIO752A0 | CNIO752A02101 | C4002742 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-11-20 05:30 | 2020-12-07 05:30 | 2021-03-22 05:30 | DB Conduct | Final DBL | 2024-05-27 05:30 | 2021-02-16 05:30 | 2020-06-16 05:30 | 2020-03-24 05:30 |  | Active | 2024-05-25 05:30 |  | 2024-05-27 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - NS | A Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of Multiple Ascending Doses of Intrathecally Administered NIO752 in Patients With Progressive Supranuclear Palsy | CNIO752A02101 First in Human in PSP pts. | N6 Neuroscience - NIBR | Langlo, Francois | Kumar, Samoj | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Christina Jean-Bart Zamor; Maria Berkheimer | Maria Berkheimer | Sinha, Deepakshi | Palande, Sujit | Not Started |  | Initial go live as 20Nov2020 when RF developer assigned on 06Oct2020. |  | DRM | Oguri, Praveen | Bai, Chandrakala | Completed | 31Jan2022: RF v7.0 finalized for ppc#4 updates and Snow#51-RITM3438169 Created. 09Aug2021: RF v6.0 finalized with PPC#2 updates. 06Aug2021:These forms are added in PPC#2 for which I received the notification today the RF is being updated . 05Aug2021:ZJG002_6, ZJG002_1, ZJG002_2, ZJG002_3, ZJG002_4, ZJG002_5, ZJG006_1, ZJG006_2, ZJG006_3, ZJG006_4, ZJG006_5, ZJG006_6 forms in Missing form report 02Jul2021: RF v5.0 finalized for Yx dts update. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 19-Apr-2021: Added LBL DTS in RF Version 3.0 and raised SNOW ticket. 07Dec2020 : RF final and Snow05 raised 02-Dec-2020: RF Development completed, will share with Kranthi for peer review on 03-Dec-2020. | None | None | 2020-12-07 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-12-21 | Completed | 2020-12-22 05:30 | ​Ticket assigned to LSP on 9th Dec, 2020. SMT generation is in progress. | [RAMACHA1, 1st Feb, 2021] Issues with Rule file. | 2020-12-22 05:30 | 2020-12-22 05:30 | [RAMACHA1, 1st Feb, 2021] FPFV postponed | 2020-12-31 05:30 |  |  | DDPASS not started as FPFV is postponed to 19th Feb, 2021 [RAMACHA1, 9th March, 2021] 7 domains with sufficient data selected for first round of DDPASS on 17th March, 2021 [RAMACHA1, 17th March, 2021] As suggested by team, DDPASS will be initiated on April 9th after all 4 four patients for cohort 1 is screened. [RAMACHA1. 18th May, 2021] DDPASS1 (April 9, 2021) and DDPASS2 (April 16, 2021) were completed. Issues are being followed upon and discussed in DDPASS3 conducted on 18th May, 2021 [RAMACHA1, 10 JUN 2021] Issues identified are being followed upon, some will be fixed after PPC2 implementation. DDPASS Success rate = 68% | 68 | RaveX - Inhouse | Yes | Y1;#Y5;#YR;#YD;#ZK |  |  |  | [RAMACHA1, 2021AUG09] SNOW51 for PPC2 was raised on Aug 9th, 2021. | [7 empty] | NA | [5 empty] | 4 | 20 | 59 | 0 | 242 | 625 | 0 | 190 | 35 | 181 | 841 | 2 | 0 |  | Cognitive disorder; Movements abnormal | Yes | Global | Open | Yes | [10 empty] | 2020-12-21 05:30 |  |  |  |  | Thirugnanasambandam, Nivetha Lakshmi | None of the above | Yes
CNIO752B1 | CNIO752B12201 | C4012838 | Phase I |  |  |  |  | 2022-06-15 05:30 |  | Final DBL | 2024-01-19 05:30 |  | 2022-02-28 05:30 |  |  | Planned | 2023-10-20 05:30 |  | 2024-01-19 05:30 | [5 empty] | ED Undecided Sourcing |  | A Randomized, Participant, Investigator and Sponsor Double Blinded, Placebo Controlled Study to Evaluate the ability of a single intrathecally administered dose of NIO752 in to lowering CSF Total tau in participants with Alzheimerâs Disease | CNIO752B12201 NIO572 PIE PoM AD | N6 Neuroscience - NIBR | [5 empty] | Joseph Bosch; Maria Berkheimer | Maria Berkheimer | [66 empty] | Alzheimer's disease | No | Global | Open | Yes
CNIR178A | CNIR178X2103J | C1200325 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-03-16 05:30 |  | DB Locked | Final DBL | 2022-03-10 05:30 | 2015-10-12 05:30 | 2015-03-23 05:30 | 2015-03-23 05:30 |  | Active | 2021-12-30 05:30 |  | 2022-03-10 05:30 |  | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase I/IB trial of PDR001 plus PBF-509 for patients with advanced NSCLC | CNIR178X2103J | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Liza Morgan; Victoria Nesbitt | Liza Morgan | Yadav, Santosh | Munukutla, Valli |  |  |  |  | DRM (DIAL) | Yadav, Santosh | Sama, Ashok | Completed | 06Jul2020: Rule file V5.0 is the latest. No changes done after transition from Roshan. 02Apr2020:Study is locked. 01Apr2020 : Reassigned RF from Roshan to Ashok 01Apr2020: LSH setup completed. No pending activity 26Mar2020: Rule file updated to fix B12L DTS setup issue and resent for peer review. 10Mar2020 : B12L included in RF on 06th and sent for LSH setup 03MAR2020: Included B12L in Rule file and sent for peer review. | None | None | 2018-12-27 05:30 | Legacy Process | Gandikota, Sree Lakshmi | Kadam, Sandeep | Rohit Varate | Completed | 2019-01-01 | Completed | 2019-07-04 05:30 | T​his is a locked study which is handed over to other sponsor. The study was on hold for more than a year and had only 3 patients. It was locked without any DM validation activities as per CTT agreement. |  | 2019-01-03 05:30 | 2019-01-03 05:30 | Retrospective DRM studies | 2019-06-06 05:30 |  |  | The study is terminated. | 100 | RaveX - Inhouse | Yes | ZK;#ZK03 | [11 empty] | IQVIA | [5 empty] | 6 | 22 | 77 | 0 | 204 | 638 | 0 | 182 | 35 | 384 | 1057 | 0 | 0 |  | Solid tumour | No | Global | Open | Yes | [10 empty] | 2019-07-04 05:30 |  |  |  | DBL | Adi, Vishnupriya | None of the above | Yes
CNIR178B1 | CNIR178X2201 | C3001913 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-08-10 05:30 |  | DB Conduct | Final DBL | 2023-02-23 05:30 | 2017-08-28 05:30 |  | 2017-03-24 05:30 |  | Active | 2022-12-16 05:30 |  | 2023-02-23 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase 2, multi-center, open label study of NIR178 in combination with PDR001 in patients with selected advanced solid tumors and non-Hodgkin lymphoma | CNIR178X2201 Phase II study x2201 | N7 Oncology - NIBR | Langlo, Francois | Parmentier, Delphine | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon; Kim Kornbluth | Kimberly Kornbluth | Gehlawat, Priya | Dadapogu, Jesica Priyadarshini | [13 empty] | Rajhans, Khushbu Kumari |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-08-10 05:30 | 2017-08-10 05:30 | Gehlawat, Priya | Mareedu, Vasu | IQVIA | [7 empty] | 168 | 0 |  |  | 0 |  |  |  | 647 | 11 | 0 |  | Breast cancer; Colonic cancer; Diffuse large B-cell lymphoma; Melanoma; Non-small cell lung cancer; Pancreatic cancer; Prostate cancer metastatic; Renal cell carcinoma; Squamous cell carcinoma of head and neck; Urothelial carcinoma | No | Global | Open | Yes | [16 empty] | None of the above
CNIS793B1 | CNIS793B12201 | C4008001 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-07-01 05:30 | 2020-08-21 05:30 | 2020-10-16 05:30 | DB Conduct | Final DBL | 2023-06-19 05:30 | 2020-10-16 05:30 | 2020-04-13 05:30 | 2020-03-24 05:30 |  | Active | 2023-05-08 05:30 |  | 2023-06-19 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A phase II, open label, randomized, parallel arm study of NIS793 (with and without spartalizumab) in combination with SOC chemotherapy gemcitabine/nab-paclitaxel, and gemcitabine/nab-paclitaxel alone in first-line metastatic pancreatic ductal adenocarcinoma (mPDAC) | CNIS793B12201 Phase II Pancreatic Cancer Study | P0 Oncology (Solid Tumors all MA Onc projects) | Langlo, Francois | Akula, Sukrutha | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Dragana Jankovic; Geraldine Bostel | Geraldine Bostel | Bora, Deepthi Reddy | Rao, S Shashikanth | Not Started |  | Initial go live as 01Jul2020 when RF developer assigned on 26Mar2020. |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 16SEP2021: RF v5.0 is final and SNOW 51 RITM2981826 request created as part of PPC. 28Jan2021 : B11L, B12L DTS added in RF and snow ticket raised. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B11L, B12L DTSs listed. Please check. 19JAN21: B11L, B12L DTS is not shared with Rule file developer and lead DBD is checking with DM for DTS status. 09DEC20: RF finalized and SNOW 51 request RITM2075515 has been createed. Change: FAMH domain has been updated as per updated SDTM annotations. 10SEP20: RF finalized and SNOW 51 request RITM1784056 has been created. Note: As of today, no pending forms and no pending DTS. 09SEP20; RF updated included all B1 domain related forms. Peer review is ongoing. 02SPEP20: As per SRF, domain name given as B1. But these forms should go under ZJ page as per discussion with SDTM programmer. Once SRF is reapproved, these forms will be mapped under ZJ domain. 21AUG20: RF finalized and SNOW 05 RITM1720747 request has been created. 19AUG20: RF peer review is ongoing 03AUG20: RF development is ongoing 24JUL20: One study specifc page review is pending, waiting for the SDTM annotation. 07JUL2020: Today received all study specific SDTM annotations and ALS for review. Will review and provide my comments by 09JUL20. 25JUN2020: Drafted 28 study specific pages, will be sent for review by 01JUL20. 29MAY2020: Study Go-live has been pushed to 14-Aug-2020. And Screen UAT will be completed by 6-July-2020 26May2020 : No update from DBD Sent a follow-up email. | None | None | 2020-08-21 05:30 |  | Gouni, Harita | Girvasiya, Shaili | Rohit Varate | Completed | 2020-09-07 | Completed | 2020-10-27 05:30 |  | DRM was completed but issue was with Jreview and GPS | 2020-10-27 05:30 | 2020-10-27 05:30 | Pre-requisites not met | 2020-10-09 05:30 |  |  |  | 70 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 56 | 127 | 0 | 768 | 1156 | 0 | 310 | 44 | 261 | 1461 | 3 | 0 |  | Pancreatic carcinoma | No | Global | Open | Yes | [10 empty] | 2020-10-07 05:30 | [5 empty] | None of the above
CNIS793B1 | CNIS793B12301 | C4010938 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-07-14 05:30 | 2021-09-15 05:30 | 2021-10-13 05:30 | DB Conduct | Final DBL | 2026-02-12 05:30 | 2020-12-20 05:30 | 2021-05-07 05:30 | 2021-05-05 05:30 | 2021-08-17 05:30 | Active | 2026-01-01 05:30 |  | 2026-02-12 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized, double-blind, phase III study comparing NIS793 in combination with gemcitabine and nab-paclitaxel versus placebo combined with gemcitabine and nab-paclitaxel for first line treatment of metastatic pancreatic ductal adenocarcinoma (mPDAC) | CNIS793B12301 mPDAC PhIII study | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Atri, Minakshi | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Nana Gyambibi | Nana Tiwaa Gyambibi | Supraja, Samala | Supraja, Samala |  |  | 06May2021 : Golive moved to 03Aug2021. Following up with TDM on glive planner and rationale for having more than 4-5 weeks gap between Golive and FPFV. 29Apr2021: This study is now under DO Accelerate and the timelines are still under discussion. As per last DQT meeting- Protocol finalization date is 01 May 2021, go live is planned by the end of Aug 2021 and FPFV planned on 01 Oct 2021. Yet to receive the updated activity planner (~4 May 2021). Yet to start the process in DO accelerate from TDMs end. Inital golive as 14Jul2021 when DBD assigned. | There were frequent updates in SSD by CTT | DRM | Saha, Saikat | Kuttoboina, Sujan Kumar | Completed | 27SEP2021: RF V1.0 is final and SNOW 05 RITM3019239 request has been created. 03SEP2021: Study has been pushed to 14SEP21due to last minute CRF updates. 12AUG2021: Requested DBD to share latest ALS as per changes after 23JUL21. Once receive the latest ALS will work on Rule file development. 11AUG2021: Study golive might be pushed to 01SEP21 or 03SEP21, we will get confirmation on 12AUG21 about DB golive. At present CRF updates are ongoing and screen UAT is not completed yet. Study specific pages have been reviewed. 23JUL2021: ALS and SRF has been shared for review on 23JUL21. Review is ongoing for study specific pages. 01JUN2021: Activity planned has been shared by DBD. Go-live date is planned on 27 Aug 2021. 26May2021: RF developer assigned. |  |  | 2021-09-27 05:30 | Delay in RF finalization due to test codes not available in Reference Metadata. | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2021-09-30 | Completed | 2021-10-12 05:30 | 23-Nov2021:updated rule file received on 09-nov2021. 06-OCT-2021:Rule File sent for update on PR domain. Comments awaited from RF developer | Perquisites delay. LSH setup request Ticket has been received on 27sep2021. | 2021-10-13 05:30 | 2021-10-13 05:30 | KPI met - incorrect source date entry (example FPFV) | 2021-10-16 05:30 |  |  |  | 95 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 1 | 106 | 96 | 0 | 1030 | 1191 | 0 | 308 | 51 | 285 | 1527 | 5 | 0 |  | Pancreatic cancer | No | Global | Open: Reapproval | Yes | [10 empty] | 2021-10-11 05:30 | [5 empty] | None of the above
CNIS793E1 | CNIS793E12201 | C4011167 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-06-09 05:30 | 2021-09-24 05:30 | 2021-11-16 05:30 | DB Conduct | Final DBL | 2025-03-26 05:30 | 2021-11-15 05:30 | 2021-05-18 05:30 | 2021-12-07 05:30 |  | Active | 2025-02-17 05:30 |  | 2025-03-26 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | An open-label, multi-center, phase II platform study evaluating the efficacy and safety of NIS793 and other new investigational drug combinations with standard of care (SOC) anti-cancer therapy for the second line treatment of metastatic colorectal cancer (mCRC) | CNIS793E12201 2L PhII study in mCRC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Sahu, Kalyani | Atri, Minakshi | Soni, Suchitra | Hiriyanna, Srinivas | Priya Deshpande | Priya Deshpande | Maricherla, Vijayroshan | Maricherla, Vijayroshan |  |  | 10May2021 : As discussed with TDM Go-live will push to 1st week of Aug,2021. Documents: Updated SSD and Go-live planner is not provided. Deepthi: 31May2021: As per the latest activity planner go-live has been planned for 9-Sep-2021. And Study Transition to Roshan. |  | DRM | Patnaik, Angella | Mopuru, Satwik | Completed | 02Nov2021: Yx DTS has been added to the Rule file. Rule file 2.0 finalized in the SUBWAY and the LSP is notified. 25Sep2021: Rule file 1.0 finalized in the SUBWAY and the LSP is notified. 15Sep2021: Rule File Peer review is completed. 08Sep2021: Rule File is sent for peer review. 07Sep2021: Rule File development is completed. Go-live is pushed to 23-Sept-2021 03Sep2021: Review of ALS, SRFs, SDTM Annotations are completed and comments are shared with DBD. 31Aug2021: Received ALS, SRFs, SDTM Annotations from Lead DBD. 12Aug2021: Screen UAT status and RF pre-requisite documents not yet received. Reminder sent to DBD. 09Aug2021: Reassigned to Satwik from Angella. 26May2021: RF Developer assigned | None | None | 2021-09-25 05:30 |  | Manoharan, Vivek | Manoharan, Vivek | Sushant Sundar | Completed | 2021-10-23 | Completed | 2021-10-24 05:30 |  |  | 2021-10-24 05:30 | 2021-10-24 05:30 |  | 2021-10-28 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 63 | 87 | 0 | 627 | 1034 | 0 | 297 | 54 | 236 | 1324 | 4 | 0 |  | Colorectal cancer stage IV | Yes | Global | Open | Yes | [10 empty] | 2021-10-24 05:30 |  |  |  |  | Nidamanuru, Kalyan Kumar | None of the above | Yes
CNIS793A1 | CNIS793X2101 | C3000369 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-03-14 05:30 | 2018-06-08 05:30 | DB Conduct |  |  | 2017-04-25 05:30 | 2018-01-19 05:30 | 2016-09-29 05:30 |  | Active | 2021-06-18 05:30 | 2021-06-18 05:30 | 2021-09-28 05:30 | 2021-09-30 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase I/Ib, open-label, multi-center dose escalation study of NIS793 in combination with PDR001 in adult patients with advanced malignancies | CNIS793X2101 Phase I/Ib NIS793 in combo w/ PDR001 | N7 Oncology - NIBR | Langlo, Francois | Barnard, Carol | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Helen Evans; Vasiliki Katsanou | Helen Evans |  | Oguri, Praveen | [13 empty] | Tidke, Shyam |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | No | ZK;#ZK03 | 2021-12-10 05:30 | 2021-12-14 05:30 |  |  | ONC | Novartis | ICON | 2017-03-14 05:30 | 2017-03-14 05:30 |  | Gehlawat, Priya | IQVIA | [7 empty] | 180 | 0 |  |  | 0 |  |  |  | 636 | 8 | 0 |  | Colorectal cancer; Non-small cell lung cancer; Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above | Yes
CNIZ985B1 | CNIZ985B12101 | C4005757 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-02-16 05:30 | 2020-05-08 05:30 | 2020-02-28 05:30 | DB Conduct | Final DBL | 2022-12-02 05:30 | 2020-02-27 05:30 | 2019-11-04 05:30 | 2019-10-21 05:30 |  | Active | 2023-07-10 05:30 |  | 2022-12-02 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/IB study of subcutanious recombinent NIZ985 ((het- IL-15) (IL-15 /sIL-15Î±)) in combination with Spartalizumab (PDR001) in patient with check point Inhibitor (CPI) relapsed advance solid tumor and Lympoma | CNIZ985B12101 alone or combo w/ PDR001 | N7 Oncology - NIBR | Langlo, Francois | HernÃ¡ndez, Fernanda | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Lydia Wang-Lakshman | Lydia Wang-Lakshman | Mokhamatam, Madhu Purnachandra Rao | SUMANA, SOUMYA | Completed | 2022-01-05 05:30 | Chandana Sarasani transitioned the study to Soumya Sumana on 5-Jan-2022. Mokhamatam Madhu transitioned the study to Chandana Sarasani on 11-Aug-2020. This is split golove study. Initial golive on 18 Feb2020. 2nd golive (PPC) 08May2020 |  | DRM | Patnaik, Angella | Bairagi, Arpita | Completed | 11Aug2021 : Reassigned the study from Angella to Arpita. 12-MAR-2021: RF Version 6.0 finalized for LB domain updates. SNOW#51 raised for SMT and LSH updates. 05-MAR-2021: RF Version 5.0 finalized on 5-Mar-2021. SNOW#51 request raised for SMT and LSH updates. 22-FEB-2021: DTS comments have been shared. Awaiting updated DTS for RF updates and Peer Review. 15-JAN-2021: RF Version 4.0 finalized on 6-Jan-2021. SNOW#51 request raised on 15 Jan 2021 for SMT and LSH updates, as the PPC form updates were pending finalization. 07-JUL-2020: RF up to date for all final DTS and Post Production updated till PPC1 implemented in the study. 10JUN2020: Rule file update for Third party DTS table (EG1L) addition and PRO007 form addition (PPC1) has been completed. SNOW#51 is now raised for SMT and LSH updates 19MAY2020: RF updated and sent for Peer Review. 18MAY2020: Received missing DTS report for EG1L. Email sent to DBD for confirmation. 8MAY2020: Received updated ALS for PPC1 for RF updates. 22-FEB-2021: B11L and B12L DTS comments have been shared with the DBD. Once updated DTS are provided RF updates will be released for Peer Review. 05MAR2020: SNOW#05 raised for LSH set-up and SMT creation. 02MAR2020: Peer review comments received. Have requested confirmation from CTT for AEREL. SDTM annotations updated for Lugano-PET. 25FEB2020: Rule file completed and sent for Peer Review. 18FEB2020: Study went live with multiple form and field level updates due to which Inherit option of the Timbre Tool did not work. Started RF development from scratch with PROD SOD. 14FEB2020: All DB set-up issues highlighted to DBD and updated. Waiting for the study Go-live to receive the final ALS for finalizing the rule file and sending for Peer Review. 07Feb2020 : SDTM annotations for 8 forms are pending. RF development in progress 30JAN2020: SDTM annotations for Batch 1 SRFs received. Rule file development started. 7-JAN-2020: Screen build in Progress. Updated Go-live date will be confirmed by 10-JAN-2020. 2-JAN-2020: Study specific SRFs not yet provided to DBD for study build. DBD requested for tentative Go-live date. 17DEC2019: Incorrect FPFV date. Have asked DM to update BOW. DBD has not yet received SSD for study build. | None | None | 2020-03-05 05:30 | SDTM annotations delayed | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2020-03-11 | Completed | 2020-04-06 05:30 | LSH setup got delayed due to installation issue. | Pre-requisites not met | 2020-04-06 05:30 | 2020-04-06 05:30 | Pre-requisites not met | 2020-05-01 05:30 |  |  | DDPASS is not yet started as we don't have data in the study. |  | RaveX - Inhouse | No | -NA- | [11 empty] | IQVIA | [5 empty] | 5 | 87 | 129 | 0 | 967 | 1382 | 0 | 328 | 45 | 556 | 1983 | 3 | 0 |  | Bladder cancer; Breast adenocarcinoma; Breast cancer; Cervical cancer; Gastroenteritis; Head and neck cancer; Lung adenocarcinoma; Lung cancer metastatic; Lymphoma; Melanoma; Mesothelioma; Non-small cell lung cancer; Non-small cell lung cancer metastatic; Pancreatic cancer; Pleural mesothelioma malignant; Sarcoma; Solid tumor; Thymic cancer metastatic | No | Global | Open | Yes | [10 empty] | 2020-03-20 05:30 | [5 empty] | None of the above
CNIZ985A1 | CNIZ985X2102J | C1200316 | Phase I | NCDS_2 | CRO - EDC |  | 2019-01-04 05:30 |  | DB Conduct | Final DBL | 2022-03-21 05:30 | 2017-05-08 05:30 | 2018-10-29 05:30 | 2016-08-24 05:30 |  | Active | 2022-03-01 05:30 |  | 2022-03-21 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/Ib Study of Subcutaneous Recombinant Human NIZ985 ((hetIL-15) (IL15/sIL-15R alpha)) alone and in combination with PDR001 in Adults with Metastatic Cancers\n | CNIZ985X2102J | N7 Oncology - NIBR | Langlo, Francois | Greyling, Alida | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Jessica O'Keeffe | Jessica O'Keeffe | Ambati, Purnachander | Ahuja, Mohit |  |  |  |  | DRM (DIAL) | Ambati, Purnachander | Shrivastava, Nikhil | Completed | 23-Apr-2021: TDM confirmed that "CNIZ985X2102J study has Escalation study which is outsourced and that is reason why CRO-EDC was entered. This part of the study does not use NVS RAVE EDC. But AXIO/Cytel RAVE database.". No further action from CDDRA. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 20-Oct-2020 (SHRIVNI5): B14L DTS included under B1 domain in RF V7.0 and finalized. SNOW-51 ticket raised and LSP is notified. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 13Jan2020 (SHRIVNI5): All the forms and DTS are included in the rule file. | None | None | 2019-02-05 05:30 |  | Varate, Rohit | Kadam, Sandeep | Rohit Varate | Completed | 2019-02-08 | Completed | 2019-07-24 05:30 |  |  | 2019-02-08 05:30 | 2019-02-08 05:30 |  | 2019-08-20 05:30 |  |  | LSP to schedule a meeting for DDPASS reviews. [RAMACHA1, 24JUN2021] Final DDPASS meeting completed | 100 | RaveX - Inhouse | Yes | [12 empty] | Other | [5 empty] | 12 | 357 | 107 | 0 | 2504 | 1211 | 0 | 295 | 36 | 378 | 1625 | 0 | 0 |  | Solid tumour | No | Global | Open | Yes | [10 empty] | 2019-07-23 05:30 | [5 empty] | None of the above
CNJH395A1 | CNJH395X2101 | C1200301 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-06 05:30 | 2018-12-12 05:30 | DB Locked |  |  | 2018-12-27 05:30 | 2018-07-18 05:30 | 2018-06-14 05:30 |  | Completed | 2020-10-22 05:30 | 2020-10-19 05:30 | 2020-12-25 05:30 | 2020-12-15 05:30 | FALSE | TCO Study | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I, multicenter, open-label dose finding study of NJH395, administered intravenously in patients with nonbreast HER2+ Advanced Malignancies | CNJH395X2101 Nonbreast HER2+Adv Malignancies Study | N7 Oncology - NIBR | Langlo, Francois |  | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Ashley Wagner; Stephanie Garnick | Ashley Wagner | Rao, S Shashikanth | Rao, S Shashikanth |  |  |  |  | DRM (DIAL) | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 06-Jul-2020: No pending issues. 29th Nov 19 (Shashi) - No pending domains to be included in the RF Rule file final except LB and 3rd party. 15th Oct- Latest Rule file V4.0 attached. | None | None | 2019-02-07 05:30 | Legacy Process | Mettugari, Sai Krishna | Chitransh, Arpit | Rohit Varate | Completed | 2019-02-19 | Completed | 2019-06-28 05:30 | ​ |  | 2019-03-14 05:30 | 2019-03-14 05:30 | Pre-requisites not met | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-12-23 05:30 | 2020-12-24 05:30 | [9 empty] | IQVIA | [5 empty] | 12 | 31 | 80 | 0 | 201 | 986 | 0 | 285 | 39 | 339 | 1364 | 5 | 0 |  | Gastric cancer; Solid tumour | No | Global | Open | Yes | [10 empty] | 2019-06-28 05:30 |  |  |  | DBL | Gandikota, Sree Lakshmi | None of the above | Yes
CNLR506A | CNLR506A1401 | C3000170 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2008-01-18 05:30 | 2019-04-29 05:30 | 2019-01-08 05:30 |  | Completed | 2023-04-10 05:30 | 2017-10-25 05:30 | 2023-04-10 05:30 | 2017-10-25 05:30 | FALSE |  |  |  | Outsourced |  |  | Japan PMS_NLR506A1401_(GSK112279)/DrugUseInvestiga | P6 Global Health | [5 empty] | ERI ASAYAMA; HARUKA NISHIOKA | ERI ASAYAMA | [66 empty] | Lymphoma | No | Global | Completed | Yes | [16 empty] | None of the above
CNLR506A | CNLR506AUS02T | C3000160 | Phase III | Other | Other |  |  | 2007-01-30 05:30 | DB Locked | Final DBL | 2024-09-23 05:30 | 2007-01-30 05:30 | 2019-12-02 05:30 |  |  | Completed | 2024-07-15 05:30 |  | 2024-09-23 05:30 |  | FALSE |  | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology | Children's Oncology Group AALL0434: Intensified Methotrexate, Compound 506U78 (Nelarabine; IND # 52611) and Augmented BFM Therapy for Children and Young Adults with Newly Diagnosed T-cell Acute Lymphoblastic Leukemia Leukemia | CNLR506AUS02T /acute lymphoblastic leukemia/ | P6 Global Health | Iyer, Srinarayani | Venkataswamy, Pavana | Tripathi, Gaurav Jagdish | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Orna Bornstein | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Acute myeloid leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CNVA237A | CNVA237A1401 | C1001344 | Phase IV | Other |  |  |  | 2013-03-18 05:30 |  |  |  | 2013-03-18 05:30 | 2013-01-08 05:30 | 2013-01-08 05:30 |  | Completed | 2019-08-30 05:30 | 2016-02-02 05:30 | 2019-08-30 05:30 | 2019-08-30 05:30 | FALSE |  |  |  | Outsourced |  | Drug use observational study of Seebri in chronic obstructive pulmonary disease | CNVA237A1401 JPN PMS | P8 Respiratory | [5 empty] | MAKOTO NAGASAKI | YUKIE YOSHIZAWA | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CNVA237A | CNVA237A2320 | C1001343 | Phase IV | NCDS | [7 empty] | 2015-06-24 05:30 |  | 2014-11-13 05:30 |  | Completed |  | 2016-11-16 05:30 |  | 2016-12-05 05:30 | FALSE |  |  |  | FULL Outsourced |  | A randomized, double-blind, parallel group, 26-week study evaluating the efficacy, safety and tolerability of NVA237 given once or twice daily, in patients with moderate and severe chronic obstructive pulmonary disease | EU Post Approval Efficacy Study_CNVA237A2320 | P8 Respiratory | [5 empty] | Nipa Alon | Nipa Alon | [68 empty] | Global | Completed | Yes | [16 empty] | None of the above
CNZV930A1 | CNZV930X2101 | C1200286 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-19 05:30 | 2018-07-02 05:30 | DB Conduct | Final DBL | 2023-07-10 05:30 | 2018-07-18 05:30 | 2018-08-31 05:30 | 2018-02-14 05:30 |  | Active | 2023-02-01 05:30 |  | 2023-07-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I/Ib, open label, multi-center dose escalation and dose expansion studyof the safety and tollerability of NZV930 single agent and in combination with PDR001 and/or NIR178 in patients with advanced malignancies | CNZV930X2101 Ph I/Ib NZV930 Dose Escalation Study | N7 Oncology - NIBR | Langlo, Francois | Pelloni, Luca | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Erica Vieira | Erica Vieira | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022. |  | DRM (DIAL) | Tadiparthy, Ramakanth | Choppadandi, Kranthikumar | Completed | 07-May-2021: RF_version 10 finalized and SNOW ticket raised for LSH set-up 26Apr2021 : Added ECG004_3 form, Added ZJG002_6, ZJG002_7, ZJG006_14 and ZJG006_15 form as per PPC and sent for peer review. Arpita updated the RF on behalf of Kranthi. 01-Sep-2020: Working on PPC11 updates 06-Jul-2020: No pending issues. 29Jun2020 : SNOW ticket raised RITM1549547 22-Jun-2020: LB: LBS001_TR, ZI: ZIS001 and ZIS002, ZR: ZRS001, ZRS002, ZRS003, ZRS004 and ZRS005 are added as per PPC and sent for Peer review 19Jun2020 : Received PPC for RF updates 17Feb2020 : RNA (PAXgene) DTS included in RF last week. All forms and Finalized DTSs in RF Data exposed to J-review & GPS II except Biomarker DTSs. 10-Jan-2020: ECG001 form is inactive and need to include under exclude forms in Rule file next version | None | None | 2018-07-20 05:30 | Legacy Process | Varate, Rohit | Varate, Rohit | Rohit Varate | Completed | 2018-10-03 | Completed | 2019-07-17 05:30 | ​Study transitioned from Naina Aggrawal to Rohit Varate. It was setup as a retrospective PREDRM study. |  | 2018-10-03 05:30 | 2018-10-03 05:30 | Study Transition This study is transitioned from Naina Agrawal. | 2019-06-28 05:30 |  |  |  | 8 | RaveX - Inhouse | Yes | [12 empty] | IQVIA | [5 empty] | 15 | 111 | 116 | 0 | 645 | 903 | 0 | 276 | 35 | 546 | 1484 | 7 | 0 |  | Breast cancer; Colorectal cancer; Non-small cell lung cancer; Ovarian cancer; Pancreatic cancer; Renal cell carcinoma | No | Global | Open | Yes | [10 empty] | 2019-06-12 05:30 | [5 empty] | None of the above
COAV101A1 | COAV101A11401 | C4007147 | Phase IV | Other | Other |  |  | 2020-10-30 05:30 | DB Conduct | Final DBL | 2038-10-29 05:30 |  | 2021-12-28 05:30 | 2021-12-16 05:30 |  | Planned | 2036-06-30 05:30 |  | 2038-10-29 05:30 |  | FALSE | Japan PMS | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Special drug use study of ZOLGENSMA in the patients with SMA | COAV101A11401 RESTORE PMS Registry Study | GTx Gene Therapies | YAMADA, KAYO | Ichinowatari, Mihoko | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | NOBUTAKA NAKAGAWA | NOBUTAKA NAKAGAWA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Spinal muscular atrophy | Yes | Global | Open | Yes | [16 empty] | None of the above
COAV101B1 | COAV101A12102 | C4009245 | Phase I | Other | CRO - EDC |  |  |  | DB Locked | Final DBL | 2024-06-03 05:30 | 2017-12-21 05:30 |  |  |  | Active | 2023-01-20 05:30 | 2021-05-10 05:30 | 2024-06-03 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Phase I, Open-Label, Dose Comparison Study of AVXS-101 for Sitting but Non-ambulatory Patients with Spinal Muscular Atrophy | COAV101A12102 CL102 | GTx Gene Therapies | Chaghasbanian, Harut | Poggi, Marie-Line | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Annabel Webb | Lucien Gazi | [17 empty] | Amit Agavekar | [28 empty] | Syneos Health | [19 empty] | Spinal muscular atrophy | No | Global | Open | Yes
COAV101A1 | COAV101A12103 | C4009285 | Phase III | Other | CRO - EDC |  |  | 2022-10-11 05:30 | DB Conduct | Final DBL | 2036-02-25 05:30 | 2020-02-10 05:30 | 2022-05-27 05:30 | 2021-10-25 05:30 |  | Active | 2035-12-31 05:30 |  | 2036-02-25 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A Long-term Follow-up Study of Patients in the Clinical Trials for Spinal Muscular Atrophy Receiving AVXS-101 | COAV101A12103 LT-002 | GTx Gene Therapies | Chaghasbanian, Harut | Marella, Chaitanya Lakshmi | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Liza Svoboda | Liza Svoboda | [17 empty] | Amit Agavekar | [28 empty] | PRA Health | [19 empty] | Spinal muscular atrophy | No | Global | Open | Yes
COAV101A1 | COAV101A12302 | C4009243 | Phase III |  | Other |  |  | 2022-09-02 05:30 | DB Locked | [6 empty] | Completed |  |  |  | 2019-12-12 05:30 |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Phase 3, Open-Label, Single-Arm, Single-Dose Gene Replacement Therapy Clinical Trial for Patients with Spinal Muscular Atrophy Type 1 with One or Two SMN2 Copies Delivering AVXS-101 by Intravenous Infusion | COAV101A12302 CL303 | GTx Gene Therapies | Chaghasbanian, Harut | Khan, Akhtar Ghous | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha |  | Mow Yee Foo | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Spinal muscular atrophy | No | Global | Open | No
COAV101A1 | COAV101A12303 | C4009244 | Phase III | Other | CRO - EDC |  |  |  | DB Locked | Final DBL | 2021-07-15 05:30 |  |  |  |  | Completed | 2021-06-14 05:30 |  | 2021-07-15 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A Global Study of a Single, One-Time Dose of AVXS-101 Delivered to Infants with Genetically Diagnosed and Pre-symptomatic Spinal Muscular Atrophy with Multiple Copies of SMN2 | COAV101A12303 CL304 | GTx Gene Therapies | Chaghasbanian, Harut | Hirlekar, Minal Vivek | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Amy Lita De Los Reyes | Mow Yee Foo | [17 empty] | Amit Agavekar | [28 empty] | PRA Health | [19 empty] | Spinal muscular atrophy | No | Global | Open | No
COAV101A1 | COAV101A12304 | C4009284 | Phase III | Other | CRO - EDC |  |  |  | DB Locked | Final DBL | 2021-07-30 05:30 |  |  |  |  | Completed | 2021-06-22 05:30 |  | 2021-07-30 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | Phase 3, Open-Label, Single-Arm, Single-Dose Gene Replacement Therapy Clinical Trial for Patients with Spinal Muscular Atrophy Type 1 with One or Two SMN2 Copies Delivering AVXSâ101 by Intravenous Infusion | COAV101A12304 CL-306 | GTx Gene Therapies | Chaghasbanian, Harut | Poggi, Marie-Line | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Amy Lita De Los Reyes | Michael Matthias Rissler | [17 empty] | Amit Agavekar | [28 empty] | PRA Health | [19 empty] | Spinal muscular atrophy | No | Global | Open | No
COAV101A1 | COAV101A12306 | C4011430 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-26 05:30 | 2021-08-26 05:30 | 2021-09-30 05:30 | DB Conduct | Interim DBL | 2022-07-01 05:30 | 2021-09-08 05:30 | 2021-03-22 05:30 | 2021-03-23 05:30 |  | Active | 2023-08-01 05:30 |  | 2023-09-12 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A Phase IIIb, open-label, single-arm, single-dose, multicenter study to evaluate the safety, tolerability and efficacy of gene replacement therapy with intravenous OAV101 (AVXS-101) in pediatric patients with spinal muscular atrophy (SMA) | COAV101A12306 SMA Type 1-2-3 older than 2 years | GTx Gene Therapies | Chaghasbanian, Harut | Khan, Akhtar Ghous | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Kathleen Tomczyk | Kathleen Tomczyk | Das, Devashish | Das, Devashish | Not Started |  | 10May2021 : As discussed with TDM Go-live will push to 02Aug2021. |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 1Feb2022: RF Version 5.0 has been finalized with the ZW2L, ZW3L, ZW4L DTS and SNOW51 request RITM3442818 has been raised, notified the LSP. 31Jan2022: Reviewed and provided my comments for the ZW_BULBAR ASSESSMENT DTS. 28Jan2022: Received ZW_BULBAR ASSESSMENT DTS for review. 19Jan2022: Updated the RF with ZW2L, ZW3L, ZW4L DTS and released for peer review. Received no peer review comments and the RF is ready to be finalized once all the DTS are finalized. 13Jan2022: Received updated ZW_ACTIGRAPHY_SYSNAV DTS for review. Reviewed and provided my comments. 6Jan2022: Received updated ZW_Developmental DTS for review. Reviewed and provided my comments. 23Dec2021: Received ZW_ACTIGRAPHY_SYSNAV DTS for review. Reviewed and provided my comments. 22Dec2021: Received ZW_Developmental DTS for review. Reviewed and provided my comments. 21Dec2021: Received updated copy of ZW_HFSME DTS and provided comments for them. 14Dec2021: Both RF and Checklist have been finalized in SubWay. SNOW51 request has been raised and notified the LSP for LSH Setup. 9Dec2021: Updated the RF with DM domain updates and ZW DTS. Released for peer review. 6Dec2021: Sent the review comments for ZW_HFMSE DTS. 1Dec2021: Sent the review comments for ZW_Actigraphy DTS. Started Developing RF for DM domain. 29Nov2021: SDTM programmer suggested to include the DMG002 page in the SC domain as it is creating duplicate data due to the other DM domain page, received SDTM annotation to make the change. Received ZW_Actigraphy DTS for review. 19Nov2021: RF and Checklist has been finalized. SNOW51 request has been raised and notified LSP. 18Nov2021: FAMHS001 and MHS001 pages have been added in the RF along with CV1L and IRT DTS, since they were pending due to the unavailability of the TEST CODES in the metadata. RF released for peer review 15Nov2021: Received ZW_HFMSE DTS for review. 12Nov2021: Provided the DTS related comments to the TDM 11Nov2021: Received ZW_RULM DTS for review. 22Oct2021 : RF and checklist are finalized in the Subway, LSH ticket RITM3114175 has been raised and notified LSP. 19Oct2021 : Received IRT DTS from TDM to review. Reviewed it and sent the comments to the TDM. Added EG and LB DTS in the RF and sent for peer review. 18Oct2021 : Received CV1L DTS from TDM to review. Reviewed it and sent the comments to the TDM. 12Oct2021 : TDM incorporated all the changes and waiting for the comments from LSP. 7Oct2021 : Received LB DTS for review. Reviewed and sent with comments. 15Sep2021 : Received DTS_EG to review. Completed the review and reverted back with the review comments to TDM. 27Aug2021 : RF v1.0 finalized and snow ticket raised 25Aug2021 : Study went on live. 24Aug2021 : RF Peer review completed with no further peer review comments. Got a confirmation from TAPOD regarding Test Codes, that they will be available within a week post go-live to properly complete further downstream actions. 23Aug2021 : DB go-live has been pushed to 24Aug2021. 20Aug2021 : Received updates requested after the RF peer review from DBD. Working on the RF. 17Aug2021: Communication received from the TDM regarding the go-live has been pushed to 23Aug2021. 16Aug2021 : RF peer review completed and working in the peer review comments. 11Aug2021 : RF developed and sent for peer review with the latest ALS, SOD and SRFs. 06Aug2021 : Provided the comments regarding ALS and elements to be updated. 04Aug2021 : Received the latest ALS, SOD and SDTM annotation for RF development. 14Jul2021 : Received the ALS, SDTM annotations and SRFs for review. 06Jul2021 : RF developer assigned with planned DBD as 09Sep2021. | None | ZW5L DTS to be added | 2021-08-27 05:30 |  | Praveen kumar, Chakka Giri | Praveen kumar, Chakka Giri | Amit Agavekar | Completed | 2021-09-07 | Completed | 2021-09-15 05:30 |  |  | 2021-09-15 05:30 | 2021-09-16 05:30 |  | 2021-10-04 05:30 |  |  | DDPASS IS IN PROGRESS | 70 | RaveX - Inhouse | Yes | NIL | [11 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 11 | 0 |  | Spinal muscular atrophy | No | Global | Open | Yes | [10 empty] | 2021-09-15 05:30 | [5 empty] | None of the above | No
COAV101A1 | COAV101A12308 | C4012889 | Phase III | Other | CRO - EDC |  |  | 2022-06-01 05:30 | Study Planned | Final DBL | 2039-11-15 05:30 |  | 2021-12-31 05:30 | 2021-12-21 05:30 |  | Planned | 2039-10-04 05:30 |  | 2039-11-15 05:30 |  |  | DCN Priority | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | FULL Outsourced | DF NS |  | COAV101A12308 LTFU | GTx Gene Therapies | Chaghasbanian, Harut | Marella, Chaitanya Lakshmi | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Mia DeBarros | Mia DeBarros | Shanmugam BALASUBRAMANIAN, Narendra | Shanmugam BALASUBRAMANIAN, Narendra | [15 empty] | Amit Agavekar | [28 empty] | Parexel | [19 empty] | Spinal muscular atrophy | No | Global | Open | Yes
COAV101A1 | COAV101A12401 | C4009280 | Phase IV | Other | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2033-07-18 05:30 | 2017-09-21 05:30 |  |  |  | Active | 2033-06-21 05:30 |  | 2033-07-18 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A Long-term Follow-up Safety Study of Patients in the AVXS-101- CL-101 Gene Replacement Therapy Clinical Trial for Spinal Muscular Atrophy Type 1 Delivering AVXS-101 | COAV101A12401 LT-001 | GTx Gene Therapies | Chaghasbanian, Harut | Khan, Akhtar Ghous | Khan, Akhtar Ghous | Purra, Shashikanth | Nair, Sreesha | Liza Svoboda | Liza Svoboda | [17 empty] | Amit Agavekar | [28 empty] | Syneos Health | [19 empty] | Spinal muscular atrophy | No | Global | Open | Yes
COAV101B1 | COAV101B12301 | C4011904 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-11-15 05:30 | 2021-12-10 05:30 | 2022-02-01 05:30 | DB Conduct | Final DBL | 2024-11-14 05:30 | 2022-02-02 05:30 | 2021-06-28 05:30 | 2021-07-26 05:30 |  | Active | 2024-10-21 05:30 |  | 2024-11-14 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, sham-controlled, double-blind study to evaluate the efficacy and safety of intrathecal (IT) OAV101 in patients with later onset Type 2 spinal muscular atrophy (SMA) who are â¥ 2 to &lt; 18 years of age, treatment naive, sitting, and never ambulatory | COAV101B12301 IT Controlled Study | GTx Gene Therapies | Chaghasbanian, Harut | Gayathri, Tharra | Mitra, Kaustav | Purra, Shashikanth | Nair, Sreesha | Malay Amin | Malay Amin | Musku, Srikanth Reddy | Pamula, Vinay | Completed | 2022-01-31 05:30 | 29Apr2021 : In Protocol Synopsis Stage. not yet started. Initial Golive planned as 15Nov2021 when DBD is assigned. |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 13Dec2021: LSH PROD request has been raised and notified the LSP 8Dec2021: RF Version 2.0 is updated with the blinding information for some domains and finalized in the SubWay along with the Checklist. SNOW 51 request has been raised and notified the LSP. 3Dec2021: Checklist has been finalized. 2Dec2021: RF Version 1.0 finalized in the SubWay, LSH TEST ticket has been raised, notified LSP. LSH PROD will be raised after study go-live. 1Dec2021: Received updated UAT ALS consisting of all the recent changes. Received updated SOD. 24Nov2021 : RF is built and released for peer review. 23Nov2021 : Received the updated ALS addressing all the comments from the DBD along with the updated SRF, SDTM and SODs 10Nov2021 : Reviewed and provided all the necessary comments to the DBD. 9Nov2021 : Received the study ALS, SRFs and SDTM annotations for review. Go-live is on 30-Nov-2021 27Oct2021 : DBD confirmed the go-live date as 30-Nov-2021 and the Screen UAT is 3-Nov-2021. 22Oct2021 : Asked DBD to share the activity planner and confirm the DB go-live dates, DBD shared the activity planner. 19Aug2021 : RF Developer assigned with DB go-live 30Nov2021. | None | LB, CV, IRT and ZW DTS to be added | 2021-12-13 05:30 |  |  |  | Amit Agavekar | [28 empty] | NA | [5 empty] | 1 | 38 | 86 | 0 | 388 | 902 | 0 | 245 | 42 | 296 | 1240 | 21 | 0 |  | Spinal muscular atrophy | No | Global | Open | Yes | 2021-12-02 05:30 | [9 empty] | 2021-12-23 05:30 | [5 empty] | GDD annual target
COAV101B1 | COAV101B12302 | C4013671 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-08-26 05:30 |  | 2022-09-30 05:30 | DB Set-Up | DB Go-live | 2022-08-26 05:30 |  | 2022-04-09 05:30 |  |  | Planned | 2025-03-10 05:30 |  | 2024-10-01 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | COAV101B12302 STRENGTH | GTx Gene Therapies | Chaghasbanian, Harut | Bindiganavale, Swetha | Mitra, Kaustav | Purra, Shashikanth | Nair, Sreesha | Aparna Valluru | Aparna Valluru | Chiranjeevi, Priyanka Boya | Chiranjeevi, Priyanka Boya | [6 empty] | Choppadandi, Kranthikumar | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 11 | 0 |  | Spinal muscular atrophy | No | Global | Open | Yes
CAEB071A0 | COEB071X2102 | C1200215 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2011-12-20 05:30 |  | 2011-08-22 05:30 |  | Completed | 2019-05-22 05:30 | 2019-05-22 05:30 | 2019-06-24 05:30 | 2019-06-26 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase I study of AEB071, an oral protein kinase C inhibitor, in patients with metastatic uveal melanoma | COEB071X2102 TCO Ph 1 Intraocular Melanoma Study | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Jessica O'Keeffe | Jessica O'Keeffe |  | Gandla, Prashanth | [15 empty] | Rohit Varate | [28 empty] | IQVIA | Oncology | BP21 | Quintiles | mailto:Christopher.Waters@iqvia.com | Earlier DBD: Jugnu Kumari |  |  | 150 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Intraocular melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
COJL332A0 | COJL332A02101 | C4010663 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-01-31 05:30 | Study Planned | Final DBL | 2024-06-10 05:30 |  | 2022-06-24 05:30 |  |  | Planned | 2024-05-06 05:30 |  | 2024-06-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA |  | COJL332A02101 FIH | N8 Ophthalmology - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Valerie Brooks | [17 empty] | Rohit Varate | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Dry eye | No | Global | Open | Yes | [16 empty] | None of the above
COMB157A | COMB157A1401 | C1001712 | Phase IV | Other | Paper |  |  | 2013-04-23 05:30 | DB Conduct | Final DBL | 2022-07-29 05:30 | 2013-07-30 05:30 | 2013-01-01 05:30 | 2013-04-09 05:30 |  | Active | 2022-03-31 05:30 |  | 2022-07-29 05:30 |  | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Drug use observational Study of Arzerra | COMB157A1401 JPN PMS | P6 Global Health | YAMADA, KAYO | IROKAWA, TAKURO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MINE KIMURA | MINE KIMURA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Chronic lymphocytic leukaemia refractory | No | Global | Open | Yes | [16 empty] | None of the above
COMB157A | COMB157A2301 | C1001351 | Phase III | GSK | Other |  |  | 2018-06-08 05:30 | DB Locked | Final DBL Achieved |  | 2009-07-23 05:30 | 2018-01-19 05:30 | 2008-08-22 05:30 |  | Completed | 2019-12-20 05:30 |  | 2018-02-28 05:30 | 2018-03-21 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase III, Open Label, Randomized Trial of Ofatumumab Added to Fludarabine-Cyclophosphamide vs. Fludarabine-Cyclophosphamide Combination in Subjects with Relapsed Chronic Lymphocytic Leukemia (COMPLEMENT 2 STUDY) | COMB157A2301(GSK110913)/COMPLEMENT 2 | P6 Global Health | Breton, Guillaume | Sampangi, Sridevi | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | Ghislaine Vincent | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  | Chronic lymphocytic leukaemia refractory | Yes | Global | Open | Yes | [16 empty] | None of the above
COMB157A | COMB157A2302 | C1001352 | Phase III | GSK | Other |  |  | 2018-06-08 05:30 | DB Locked |  |  | 2011-04-14 05:30 | 2018-01-19 05:30 | 2010-10-25 05:30 |  | Completed | 2019-12-20 05:30 | 2017-04-24 05:30 | 2020-02-28 05:30 | 2017-10-03 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | An Open Label, Multicenter Study Investigating the Safety and Efficacy of Ofatumumab Therapy versus Physicians' Choice in Patients with Bulky Fludarabine Refractory Chronic Lymphocytic Leukaemia (CLL) | COMB157A2302(GSK114242)/PIII/ref CLL/M | P6 Global Health | Breton, Guillaume | Sampangi, Sridevi | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | Ghislaine Vincent | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Chronic lymphocytic leukaemia refractory | No | Global | Completed | Yes | [16 empty] | None of the above
COMB157B | COMB157B2301 | C1001356 | Phase III | GSK | Other |  |  | 2018-06-08 05:30 | DB Locked | Final DBL Achieved |  | 2008-12-22 05:30 | 2018-01-19 05:30 | 2008-07-10 05:30 |  | Completed | 2018-05-17 05:30 |  | 2018-10-12 05:30 | 2018-10-15 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A phase III, open label, randomized, multicenter trial of Ofatumumab added to Chlorambucil vs. Chlorambucil Monotherapy in previously untreated patients with Chronic Lymphocytic Leukemia | COMB157B2301(GSK110911)/(COMPLEMENT 1) | P6 Global Health | Breton, Guillaume | Sampangi, Sridevi | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | Ghislaine Vincent | [17 empty] | Sandeep Kadam | [13 empty] | 70 | [14 empty] | Other | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
COMB157C | COMB157C2301 | C1001357 | Phase III | GSK | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2010-05-06 05:30 |  | 2009-07-14 05:30 |  | Completed | 2018-06-29 05:30 |  | 2018-11-29 05:30 | 2018-11-29 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A phase III, open label, randomized, multicenter trial of ofatumumab maintenance treatment versus no further treatment in subjects with relapsed chronic lymphocytic leukemia (CLL) who have responsed to induction therapy | COMB157C2301 Maintenance treatment CLL (PROLONG) | P6 Global Health | Breton, Guillaume | Sampangi, Sridevi | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther | Petra Hoever | Ghislaine Vincent | [17 empty] | Sandeep Kadam | [28 empty] | Other | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 3 | 0 |  | Chronic lymphocytic leukaemia recurrent | No | Global | Open | Yes | [16 empty] | None of the above
COMB157D | COMB157D2303 | C1001358 | Phase III | GSK | [7 empty] | 2010-10-11 05:30 |  |  |  | Completed |  | 2016-12-19 05:30 |  | 2017-03-30 05:30 | FALSE |  |  |  | Outsourced |  | Phase III randomized, open label study of single agent ofatumumab vs. single agent\nrituximab in indolent B-cell non-Hodgkin lymphoma (iNHL) relapsed after rituximab-containing therapy | COMB157D2303(GSK113676)/(HOMER) | P6 Global Health | [6 empty] | Janet Lasher | [66 empty] | Non-Hodgkin's lymphoma | Yes | Global | Completed | Yes | [16 empty] | None of the above
COMB157D_MA | COMB157D2401 | C1001713 | Phase II | GSK | [7 empty] | 2011-05-17 05:30 |  | 2010-09-27 05:30 |  | Completed |  | 2016-12-20 05:30 |  | 2017-05-15 05:30 | FALSE |  |  |  | Outsourced |  |  | COMB157D2401(GSK114612)/GMA/Open label OMB Benda | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Megan Cannan | [66 empty] | Non-Hodgkin's lymphoma | No | Global | Completed | No | [16 empty] | None of the above
COMB157E | COMB157E2301 | C1001361 | Phase III | GSK | CRO - EDC |  |  | 2019-01-04 05:30 | DB Locked | Final DBL Achieved |  | 2010-08-26 05:30 |  |  |  | Completed | 2018-12-26 05:30 | 2018-12-26 05:30 | 2019-03-20 05:30 | 2019-03-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Randomized, Open Label Study of Ofatumumab and Bendamustine Combination Therapy Compared with Bendamustine Monotherapy in Indolent B-cell Non-Hodgkinâs Lymphoma Unresponsive to Rituximab or a Rituximab-Containing Regimen During or Within Six Months of Treatment\n | COMB157E2301(GSK110918)/(COMPLEMENT A and B) | P6 Global Health | Breton, Guillaume | Chinchansure, Basavraj | Pai, Ujwala | Purra, Shashikanth | Ninan, Esther |  | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | Other | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 5 | 0 |  | Non-Hodgkin's lymphoma | Yes | Global | Completed | Yes | [16 empty] | None of the above
COMB157G | COMB157G1301 | C1001362 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-02-12 05:30 | 2018-03-30 05:30 | DB Locked | Final DBL Achieved |  | 2018-03-15 05:30 |  | 2017-06-27 05:30 |  | Completed | 2020-06-22 05:30 | 2020-07-29 05:30 | 2020-08-03 05:30 | 2020-09-10 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 24-week, randomized, double-blind, placebo-controlled, parallel-group, multicenter study to evaluate the efficacy, safety and pharmacokinetics of ofatumumab in patients with relapsing multiple sclerosis followed by an extended treatment of at least 24 weeks with open-label ofatumumab | COMB157G1301-JAPAN_Registration_Bridging | P4 Neuroscience | Ball, Michael | Nishi, Nahoko | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Daniel Sienkiewicz | Daniel Sienkiewicz | Patnaik, Angella | Rapaka, Sindhuja |  |  |  | DB Go-live planned with respect to FPFV Date. | DRM (DIAL) | Patnaik, Angella | Patnaik, Angella | Completed | 07-JUL-2020: RF up to date for all final DTS and PPCs implemented in the study. 18MAR2020: RF finalized and SNOW#51 raised for LSH set-up. 18MAR2020: Added third party table B11L in Rf and released for Peer Review. 3-DEC-2019: Rule file final for all DTS and till PPC8. | None | None | 2018-05-18 05:30 |  | Nidamanuru, Kalyan Kumar | Varate, Rohit | Amit Agavekar | Completed | 2018-05-30 | Completed | 2020-05-12 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. | Retrospective DRM studies | 2018-05-30 05:30 | 2018-05-30 05:30 | Retrospective DRM studies | 2020-09-02 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | LB;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 11 | 31 | 57 | 0 | 249 | 682 | 0 | 189 | 47 | 290 | 1019 | 5 | 0 |  | Relapsing-remitting multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2020-05-07 05:30 | [5 empty] | GDD annual target | Yes
COMB157G | COMB157G1401 | C3002954 | Phase IV | Other | CRO - EDC |  |  | 2021-07-31 05:30 | DB Conduct | Final DBL | 2026-11-30 05:30 | 2021-06-30 05:30 | 2021-04-30 05:30 | 2021-04-28 05:30 |  | Active | 2026-07-31 05:30 |  | 2026-11-30 05:30 |  | FALSE | Japan PMS | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS |  | COMB157G1401 JPN PMS | P4 Neuroscience | YAMADA, KAYO | Ichinowatari, Mihoko | YAMADA, KAYO | YAMADA, KAYO | Nair, Sreesha | MINE KIMURA | MINE KIMURA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Multiple sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
COMB157G | COMB157G2102 | C1001354 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-31 05:30 | 2018-10-22 05:30 | DB Locked | Final DBL Achieved |  | 2018-09-11 05:30 | 2018-04-05 05:30 | 2018-04-03 05:30 |  | Completed | 2020-05-04 05:30 | 2020-05-05 05:30 | 2020-06-04 05:30 | 2020-06-16 05:30 | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | COMB157G2102 Auto-Injector_BE | P4 Neuroscience | Ball, Michael | Amrutham, Subhash | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Kathleen Tomczyk | Kathleen Tomczyk | Patnaik, Angella | Rapaka, Sindhuja |  |  |  | DB Go-live planned with respect to FPFV Date. | DRM (DIAL) | Patnaik, Angella | Patnaik, Angella | Completed | 07-JUL-2020: RF up to date for all final DTS and PPCs implemented in the study. 3-DEC-2019: Rule file final for all DTS and till PPC6. | None | None | 2018-09-25 05:30 |  | Tidke, Shyam | Ramaraju, Bhargav | Amit Agavekar | Completed | 2018-10-05 | Completed | 2018-08-31 05:30 |  | Retrospective DRM studies | 2018-10-01 05:30 | 2018-10-01 05:30 | Retrospective DRM studies | 2019-09-17 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 6 | 25 | 54 | 0 | 175 | 586 | 0 | 187 | 33 | 288 | 907 | 5 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2019-03-01 05:30 |  |  |  | DBL | Girvasiya, Shaili | None of the above | No
COMB157G | COMB157G2301 | C1001363 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-07-25 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-09-20 05:30 |  | 2016-04-12 05:30 |  | Completed | 2020-08-21 05:30 | 2020-07-20 05:30 | 2020-09-29 05:30 | 2020-10-08 05:30 | FALSE | Mission Possible | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, double-dummy, parallel-group study comparing the efficacy and safety of ofatumumab versus teriflunomide in patients with relapsing multiple sclerosis. | ASCLEPIOS_I_COMB157G2301 | P4 Neuroscience | Chaghasbanian, Harut | Bindiganavale, Swetha | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Cecilia Bottero | C��cilia Bottero | Patnaik, Angella | Shewane, Roshni | Completed | 2019-12-05 05:30 | Study Transitioned to Roshni Shewane on 05-Dec-2019. | [10 empty] | Sundar, N Sushant |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | ICON | 2016-07-04 05:30 | 2016-07-04 05:30 | Shewane, Roshni | Rajhans, Khushbu Kumari | NA | [7 empty] | 137 | 0 |  |  | 0 |  |  |  | 1266 | 5 | 0 |  | Relapsing-remitting multiple sclerosis | No | Global | Open | Yes | [14 empty] | DBL | Agavekar, Amit | None of the above | No
COMB157G | COMB157G2302 | C1001364 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-07-04 05:30 |  | DB Locked |  |  | 2016-08-26 05:30 |  | 2016-04-22 05:30 |  | Completed | 2020-10-01 05:30 |  |  |  | FALSE | Mission Possible | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A randomized, double-blind, double-dummy, parallel-group study comparing the efficacy and safety of ofatumumab versus teriflunomide in patients with relapsing multiple sclerosis. | ASCLEPIOS_II_COMB157G2302 | P4 Neuroscience | Chaghasbanian, Harut | Bindiganavale, Swetha | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Cecilia Bottero; Nicola Barbara Rennie | C��cilia Bottero | Patnaik, Angella | Shewane, Roshni | Completed | 2019-12-04 05:30 | Study Transitioned to Roshni Shewane on 04-Dec-2019. | [10 empty] | Sundar, N Sushant |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | ICON | 2016-07-25 05:30 | 2016-07-25 05:30 | Shewane, Roshni | Rajhans, Khushbu Kumari | NA | [7 empty] | 137 | 0 |  |  | 0 |  |  |  | 1266 | 5 | 0 |  | Relapsing-remitting multiple sclerosis | No | Global | Open | Yes | [14 empty] | DBL |  | None of the above | Yes
COMB157G_MA | COMB157G23101 | C3002538 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-02-10 05:30 | 2020-06-15 05:30 | 2020-07-28 05:30 | DB Conduct | DB Snapshot | 2022-03-25 05:30 | 2020-07-14 05:30 | 2019-11-08 05:30 | 2019-11-12 05:30 |  | Active | 2025-01-06 05:30 |  | 2025-02-24 05:30 |  | FALSE | DCN Priority | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A single-arm, prospective, multicentre, open-label study to evaluate ofatumumab treatment effectiveness and patient-reported outcomes in patients with relapsing multiple sclerosis transitioning from dimethyl fumarate or fingolimod therapy | COMB157G23101 ARTIOS Treatment Optimization | P4 Neuroscience | Chaghasbanian, Harut | Baratam, Krishnaveni | Kanani, Pooja | Purra, Shashikanth | Nair, Sreesha | Daniel Sienkiewicz | Daniel Sienkiewicz | Kancharla, Susmita | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 |  |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 20OCT21: RF V12.0 is final and SNOW 51 request RITM3101600 has been created for the addition of YDL DTS 01OCT21: RF V11.0 is final and Snow 51 RITM3033223 has been created. Request you to rebuild FAAE, EC, EX and CM domains 14SEP21: RF V10.0 is final and SNOW 51 RITM2977593 created. CEN001 is updated as per standard crf CEN004_TR as per SDTM team request. 13AUG21: RF V9.0 is final and SNOW 51 RITM2874367 request has been created. Requested for to rebuild SV domain and create VE domain as per PPC. 30JUL21: RF V8.0 is finalized and SNOW 51 request RITM2824907 has been created for to rebuild ZX, FAMH and FAAE domains as per latest SDTM annotations and Reference Test codes. 19JUL21: RF V7.0 is finalized and SNOW 51 request RITM2787491 has been created for to rebuild FAAE domain as per SDTM team request 24JUN21: RF V6.0 final and SNOW 51 request created for to fix LB issue for Quantitative parameter. 21APR21: RF final and SNOW 51 RITM2488395 request has been created as part of PPC1. Rule file changes: 1. DS domain: DSG005 form has been added 2. ZW domain: ZWS001 and ZWS002 forms have been added 3. SC domain: "Dominant hand" field has been added in SC domain from ZWS001 and DTS001 forms as per SDTM team request 4. DI and DT domain: DTS001 form has been added 5. B1 domain: B11L DTS has been added 12MAR21: RF final and SNOW 51 RITM2357233 request created. Changes: QS2L, QS7L and QS8L DTS's have been added. 09FEB21: Rule file has been finalized with addition of following DTS's and SNOW 51 has been raised on 09FEB21. 04FEB21: QS1L, QS3L, QS4L, QS5L, QS6L, MO1L and ZW1L DTS have been received. Rule file development is ongoing and expected date of completion is 05FEB21 19JAN21: MO1L DTS was finalized but not shared with Rule file developer. Requested DM for to share final DTS. 07JUL20: As of today, no pending forms and no pending DTS. 17JUN20: RF has been re-approved on 17JUN20 and SNOW 05 RITM1510234 Request has been created. 16JUN20: RF has been finalized on 12JUN20 before golive 15JUN20. CREDI SR has been raised for to terminate Initial archival of the documents and send for re-approval on 17JUN20 and same has been notified to LSP for to close the request RITM1498473. Once RF is finalized, will raise a new SNOW 05 request. 12JUN2020: RF has been finalized and SNOW 05 request has been created on 12JUN2020. 01Jun2020: RF has been released for peer review.(Kranthi) Peer review is ongoing. 24MAR2020: Study specific screens have been reviewed and suggested to change screen design and study go live has been post phoned to 30APR2020 13MAR2020: SDTM discussions are ongoing for the study specific pages and tentative date of completion is 20MAR20 02MAR2020: SRF's and SDTM discussion ongoing and the expected date of screens finalization is 13MAR2020. 13Feb2020 : Not received any update from DBD. Sujan to followup with DBD. 29-NOV-2019: Screens are not finalized yet | None | None | 2020-06-17 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Amit Agavekar |  | 2020-07-15 |  | 2020-07-20 05:30 |  |  | 2020-07-20 05:30 | 2020-07-20 05:30 | Study Trasition | 2020-07-20 05:30 |  |  | DDPASS is ongoing for the study | 0 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 19 | 51 | 0 | 137 | 740 | 0 | 209 | 32 | 232 | 1004 | 14 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2020-07-20 05:30 | [5 empty] | GDD annual target
COMB157G | COMB157G2399 | C3001064 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-14 05:30 | 2018-12-28 05:30 | DB Conduct | DB Snapshot | 2022-09-23 05:30 | 2018-11-22 05:30 | 2018-07-09 05:30 | 2018-07-18 05:30 |  | Active | 2028-10-03 05:30 |  | 2029-02-05 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | COMB157G2399_ALITHIOS_OLE | P4 Neuroscience | Chaghasbanian, Harut | Bindiganavale, Swetha | Mitra, Kaustav | Purra, Shashikanth | Nair, Sreesha | Nicola Barbara Rennie | Nicola Barbara Rennie | Patnaik, Angella | SIRIPURAM, RAJSHEKHAR TIRUPATI |  |  | Jan 2022 : Sindhuja Rapaka transitioned studies to Rajshekhar. | DB Go-live planned with respect to FPFV Date. | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 24-OCT-2021: RF Version 10.0 finalized for DS domain DDPASS updates. SNOW#51 raised for SMT/LSH updates. 22-OCT-2021: RF Version 9.0 finalized for PPC #11 updates. SNOW#51 raised for SMT/LSH updates. 21-SEP-2021: PPC #11 Rule File queries for QS and FADS test codes raised to DBD and TDM. Once confirmed RF will be finalized. 9-AUG-2021: PPC #11 IA review completed. Comments shared with DBD. 10-MAR-2021: SNOW#51 raised for SMT and LSH updates pertaining to PPC#9. 02-MAR-2021: PPC9 form review. No RF updates. DBD to notify once PPC is implemented in Production to raise SNOW#51 for SMT/LSH updates. (CR#90¦AEG001¦New field added: OPCODCON) 29-JAN-2021: RF Version 8.0 finalized for B11L DTS table addition. SNOW#51 raised for SMT/LSH updates. 12-DEC-2020: DTS comments shared. 04-DEC-2020: RF updated for B11L DTS table addition and released for Peer Review. 09NOV2020: RF V7.0 finalized in CREDI. SNOW#51 raised for LSH updates. LSP informed. 06NOV2020: PPC8 updates released for Peer Review. 07SEP2020: RF Version 6.0 finalized for PPC7, SNOW#51 raised and LSP notified. 25AUG2020: RF sent for Peer Review. 02Sep2020 : As per 02Sep2020 missing forms DTS report 'DSG007, SSG001_1, SVG001_1, SVG002_1, UPVG001_1, DSG002_1, IEG001_1, VSG002, CMS001_1, CMS001_2, CMS001_4, CMS001_3, ZJG002, ZJG002_1, ZJG002_2, ZJG002_3, ZJG002_4, DSG003_1, ZJG006_2, ZJG006_3, ZJG006_4, ZJG006_5, ZJG006_6,' pending forms 11AUG2020: RF updated initiated for PPC7. 07-JUL-2020: Confirmation pending from study team on implementation of Vaccine sub-study via PPC to initiate the RF. 27 DEC 2018 is the FPFV. Peer review completed Rule file final. SNOW5 ticket to be raised for LSH setup | None | None | 2018-12-27 05:30 |  | Sundar, N Sushant | Ramaraju, Bhargav | Amit Agavekar | Completed | 2019-01-02 | Completed | 2019-03-27 05:30 | DRM 2nd Pilot study | System or Application issues (RAVE/LSH/JReview/GPS) | 2019-01-02 05:30 | 2019-01-02 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2019-09-06 05:30 |  |  |  | 45 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 12 | 51 | 90 | 0 | 382 | 1223 | 0 | 302 | 38 | 328 | 1589 | 7 | 0 |  | Multiple sclerosis | No | Global | Open | Yes | [10 empty] | 2019-03-14 05:30 | [5 empty] | None of the above
COMB157G | COMB157G2402 | C4009145 | Phase IV |  | Rave EDC - Inhouse |  |  | 2022-08-22 05:30 | DB Set-Up | DB Go-live | 2022-05-20 05:30 |  | 2021-11-26 05:30 | 2021-11-15 05:30 |  | Planned | 2026-10-30 05:30 |  | 2026-12-11 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS | A 12-month, open-label, prospective, multicenter, interventional, single-arm study assessing the efficacy and safety of Ofatumumab 20 mg in relapsing multiple sclerosis (RMS) patients in China | COMB157G2402 China PAC (Post Approval Commitment) | P4 Neuroscience | Chaghasbanian, Harut | Baratam, Krishnaveni | Mitra, Kaustav | Purra, Shashikanth | Nair, Sreesha | Coco Liang | Hongzi Liang | Sinha, Deepakshi | Sinha, Deepakshi | [15 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Multiple sclerosis relapse | No | Global | Open | Yes
COMB157G | COMB157G2403 | C4010588 | Phase IV | [9 empty] | 2020-04-01 05:30 | 2022-01-17 05:30 |  | Planned | [8 empty] | FULL Outsourced |  |  | COMB157G2403 (#1-OTISw/BAF+ #2-Prof Hellwig) | P4 Neuroscience | [5 empty] | Shad Razac | Shad Razac | [66 empty] | Multiple sclerosis | No | Global | Open | Yes
COMB157G | COMB157G2406 | C4010469 | Phase IV | [9 empty] | 2022-05-31 05:30 |  |  | Planned | [8 empty] | Outsourced |  |  | COMB157G2406 PASS | P4 Neuroscience | [6 empty] | Christie Doerr | [66 empty] | Multiple sclerosis relapse | No | Global | Open | No
COMB157G_MA | COMB157G2408 | C4015130 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-29 05:30 | DB On hold | Final DBL | 2026-04-28 05:30 |  | 2022-01-26 05:30 | 2022-01-25 05:30 |  | Planned | 2026-03-31 05:30 |  | 2026-04-28 05:30 |  |  | Submission | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | InHouse | DF NS |  | COMB157G2408 Efficacy of Ofatumumab in MS | P4 Neuroscience | Chaghasbanian, Harut | Somalanka, Shesh Kumar | Mitra, Kaustav | Purra, Shashikanth | Nair, Sreesha |  | Christie Doerr | VINOD JAISWAL, POOJA | VINOD JAISWAL, POOJA | [6 empty] | Kuttoboina, Sujan Kumar | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 30 | [7 empty] | 500 | 15 |  |  | Multiple sclerosis | No | Global | Open | Yes
CPCA062A1 | CPCA062X2101 | C1001715 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-04-15 05:30 |  | 2014-09-29 05:30 |  | Completed | 2019-03-07 05:30 | 2018-07-17 05:30 | 2018-10-15 05:30 | 2018-10-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | NIBR - CVM | A phase I, multicenter, open-label dose escalation and expansion study of PCA062, administered intravenously in adult patients with pCAD-positive tumors | CPCA062X2101 TCO-Dose-Escal/Expan-in-pCAD+pts-Exec | N7 Oncology - NIBR |  |  | Ward, Anthea | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Maria Cintrao Dos Santos Rosa | Maria Joao Cintrao Dos Santos Rosa | Govula, Shashikanth | [14 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | ONC | Novartis | InHouse | 2015-03-30 05:30 | 2015-03-30 05:30 |  |  | IQVIA | [7 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Esophageal cancer; Head and neck cancer; Solid tumour; Triple negative breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CACZ885U | CPDR001C2101 | C1001365 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-04-13 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-05-24 05:30 |  | 2017-01-06 05:30 |  | Active | 2021-07-28 05:30 | 2021-07-28 05:30 | 2021-09-27 05:30 | 2021-09-28 05:30 | FALSE | 2 | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | Phase Ib, multicenter, open label study of PDR001 in combination with platinum-doublet chemotherapy and other immuno-oncology agents in PD-L1 unselected, metastatic NSCLC patients | CPDR001C2101 PDR Combo IO agents in PD-L1 NSCLC | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Kobagapu, Shalini | Singh, Parul | Sharma, Atul | Hiriyanna, Srinivas | Shweta Malhotra | Shweta Malhotra | Bai, Chandrakala | Gehlawat, Priya | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [12 empty] | Study transitioned Recently | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-04-13 05:30 | 2017-04-13 05:30 | Gehlawat, Priya | Mareedu, Vasu | NA | [7 empty] | 353 | 0 |  |  | 0 |  |  |  | 889 | 11 | 0 |  | Non-small cell lung cancer | Yes | Global | Open | Yes | [14 empty] | Interim-Analysis | Munusamy, Tamilarasan | None of the above | Yes
CPDR001E | CPDR001E2201 | C1001367 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-01-20 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-02-14 05:30 |  | 2016-10-28 05:30 |  | Completed | 2020-05-13 05:30 | 2020-05-13 05:30 | 2020-06-19 05:30 | 2020-06-17 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | An open label phase II study to evaluate the efficacy and safety of PDR001 in patients with advanced or metastatic, well-differentiated, non-functional neuroendocrine tumors of pancreatic, gastrointestinal (GI), or thoracic origin or poorly-differentiated gastroenteropancreatic neuroendocrine carcinoma (GEP-NEC), that have progressed on prior treatment | CPDR001E2201 NET of Pancreatic GI GEP-NEC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Girme, Abhijit | Singh, Parul | Kumar, Rohit | Hiriyanna, Srinivas | Nana Gyambibi | Nana Tiwaa Gyambibi | Joshi, Alekhya | Joshi, Alekhya | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [13 empty] | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-01-20 05:30 | 2017-01-20 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 156 | 0 |  |  | 0 |  |  |  | 906 | 9 | 0 |  | Gastric cancer; Lung cancer metastatic; Neuroendocrine tumour; Pancreatic neuroendocrine tumour | Yes | Global | Completed | Yes | [16 empty] | None of the above
CPDR001F | CPDR001F2301 | C1001368 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-02-02 05:30 |  | DB Conduct | Final DBL | 2023-08-21 05:30 | 2017-02-17 05:30 |  | 2016-11-08 05:30 |  | Active | 2023-07-17 05:30 |  | 2023-08-21 05:30 |  | FALSE | 2 | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | A randomized, double-blind, placebo-controlled, phase III study comparing the combination of PDR001, dabrafenib and trametinib versus placebo, dabrafenib and trametinib in previously untreated patients with unresectable or metastatic BRAF V600 mutant melanoma | CPDR001F2301 TAF MEK PDR001 BRAFV600mut melanoma | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Kobagapu, Shalini | Singh, Parul | Sharma, Atul | Hiriyanna, Srinivas | Jared Kenneth Thornton | Jared Kenneth Thornton | Ramaraju, Bhargav | Mareedu, Vasu |  | 2020-07-01 05:30 | [11 empty] | Manoharan, Vivek |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | Y1;#Y5;#YD;#ZK |  |  |  |  | ONC | Novartis | ICON | 2017-02-02 05:30 | 2017-02-02 05:30 | Mareedu, Vasu | Gehlawat, Priya | NA | [7 empty] | 376 | 0 |  |  | 0 |  |  |  | 1018 | 14 | 0 |  | Melanoma | Yes | Global | Wind Down | Yes | [14 empty] | Interim-Analysis | Nagalla, Lakshmi Naga Lavanya | None of the above | Yes
CPDR001F | CPDR001FCN01 | C4008913 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-12 05:30 |  | Final DBL | 2023-05-08 05:30 |  | 2022-05-03 05:30 |  |  | Stopped (with patients) | 2023-03-28 05:30 |  | 2023-05-08 05:30 |  | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized, double-blind, placebo-controlled, phase II study comparing the combination of spartalizumab, dabrafenib and trametinib versus placebo, dabrafenib and trametinib in previously untreated Chinese patients with unresectable or metastatic BRAF V600 mutant melanoma | CPDR001FCN01 COMBI-i China PhII | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Dhamat, Rahul | Singh, Parul | Kumar, Rohit | Hiriyanna, Srinivas |  | Zheyong Ma | [17 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1100 | 10 | 0 |  | Metastatic melanoma | No | Global | Wind Down | Yes | [16 empty] | None of the above
CPDR001G | CPDR001G2101 | C1001369 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-03-03 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-04-20 05:30 |  | 2016-11-23 05:30 |  | Completed | 2020-02-27 05:30 | 2020-02-27 05:30 | 2020-04-02 05:30 | 2020-04-01 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | A phase Ib study of PDR001 in combination with sorafenib in patients with advanced hepatocellular carcinoma (HCC). | CPDR001G2101 Phase Ib PDR001 and sorafenib in HCC | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Dhyawala, Palak | Singh, Parul | Kachchhava, Avinash Balasaheb | Hiriyanna, Srinivas | Nathalie Smith | Nathalie Smith | Mokhamatam, Madhu Purnachandra Rao | [14 empty] | Manoharan, Vivek |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-03-03 05:30 | 2017-03-03 05:30 | Kanchi, Pavan kumar | Mareedu, Vasu | NA | [7 empty] | 140 | 0 |  |  | 0 |  |  |  | 1944 | 5 | 0 |  | Hepatocellular carcinoma | Yes | Global | Open | Yes | [16 empty] | None of the above
CPDR001I | CPDR001I2101 | C1001370 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-09-25 05:30 |  | 2017-05-18 05:30 |  | Stopped (with patients) | 2018-01-30 05:30 | 2018-01-30 05:30 | 2018-04-11 05:30 | 2018-04-10 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | ElevatION: CRC-101: A Phase Ib study of PDR001 in combination with bevacizumab and mFOLFOX6 as first line therapy in patients with metastatic MSS colorectal cancer | CPDR001I2101 CRC_L1_2C | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Kumar, Ranjani | Chougule, Poornima | Varatharaj, Sathiyaraj | Hiriyanna, Srinivas |  | Nana Tiwaa Gyambibi | Yadav, Santosh | [14 empty] | Genga, Vardhini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-07-24 05:30 | 2017-07-24 05:30 |  |  | NA | [19 empty] | Colorectal cancer | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CPDR001I | CPDR001I2102 | C1001371 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-05-23 05:30 | 2017-10-31 05:30 | DB Locked | Final DBL Achieved |  | 2017-06-09 05:30 |  | 2017-02-27 05:30 |  | Completed | 2019-06-05 05:30 | 2019-05-07 05:30 | 2019-06-24 05:30 | 2019-05-27 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | Phase Ib study of PDR001 in combination with regorafenib in adult patients with previously treated metastatic microsatellite stable (MSS) colorectal cancer | CPDR001I2102 MSS Colorectal Cancer | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Dhamat, Rahul | Derashri, Ashutosh | Varatharaj, Sathiyaraj | Hiriyanna, Srinivas | Nana Gyambibi | Nana Tiwaa Gyambibi | Bai, Chandrakala | [14 empty] | Challa, Nandini |  | Sushant Sundar | [12 empty] | all the issues were addressed and disscussed | 100 | OCRDC - Inhouse | Yes | [5 empty] | ONC | Novartis | InHouse | 2017-05-23 05:30 | 2017-05-23 05:30 |  |  | NA | [7 empty] | 114 | 0 |  |  | 0 |  |  |  | 977 | 5 | 0 |  | Colorectal cancer | Yes | Global | Completed | Yes | [14 empty] | DBL | Sahu, Ahallad | None of the above | No
CPDR001J | CPDR001J2201 | C3002826 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-13 05:30 | 2018-09-11 05:30 | DB Conduct | Final DBL | 2023-04-14 05:30 | 2018-09-10 05:30 | 2018-03-30 05:30 | 2018-03-23 05:30 |  | Active | 2023-03-03 05:30 |  | 2023-04-14 05:30 |  | FALSE | DM Study priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Immuno-Oncology | A randomized, open-label, phase II open platform study evaluating the efficacy and safety of novel spartalizumab (PDR001) combinations in previously treated unresectable or metastatic melanoma | CPDR001J2201 Platform Melanoma Trial | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Laugel, Catherine | Singh, Parul | Sharma, Atul | Hiriyanna, Srinivas | MALIKA DORBOZ | MALIKA DORBOZ | Yadav, Santosh | Rapaka, Sindhuja |  |  |  |  | DRM (DIAL) | Govula, Shashikanth | Bai, Chandrakala | Completed | 23Aug2021: PPC#17 has no impact to RF hence only Snow#51 RITM2901829 Created. 13Jan2021: RF v11.0 - Updated the variable from 'STNRCLBL' to 'STNRCLB' as per LB dts to rectify LSH set-up issue . 7JAN2021: SG: No upcoming tasks. 09Sep2020 : B15L included in RF and SNow Raised 7Sep2020: Rule file updated and sent for review. 02Sep2020 : As per 02Sep2020 missing forms DTS report B15LDTS pending. DTS received on 10Aug2020. 30Mar2020 : Pending form Primary ODM included and sent for LSH Setup 27Mar2020 : Primary / ODM form update in Rule file due to PPC. DB was updated but RF was not updated. RF update ongoing and will be sent for peer review today. | None | None | 2018-11-13 05:30 | Legacy Process | Challa, Nandini | Kumar D, Santosh | Sushant Sundar | Completed | 2018-12-19 | Completed | 2019-06-06 05:30 |  | Study Transition | 2018-11-16 05:30 | 2018-11-16 05:30 | Study Transition | 2019-09-17 05:30 |  |  | In progress - 1st DDPASS meeting is completed | 17 | RaveX - Inhouse | Yes | ZK;#ZK03;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 19 | 57 | 98 | 0 | 600 | 1409 | 0 | 363 | 38 | 303 | 1750 | 9 | 0 |  | Melanoma | Yes | Global | Open | Yes | [10 empty] | 2019-06-04 05:30 | [5 empty] | None of the above | Yes
CPDR001J | CPDR001J2301C | C4000282 | Phase III | NCDS_2 |  |  |  | 2023-10-01 05:30 |  | Final DBL | 2026-10-30 05:30 |  | 2023-09-20 05:30 |  |  | Planned | 2026-08-21 05:30 |  | 2026-10-30 05:30 |  | FALSE |  |  |  | InHouse |  |  | CPDR001J2301C Melanoma Registrational Trial | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Mimi Leung | [54 empty] | 130 | 0 |  |  | 0 |  |  |  | 1400 | 10 | 0 |  | Malignant melanoma | No | Global | Open | Yes | [16 empty] | None of the above
CPDR001Q1 | CPDR001X1101 | C1001719 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-02-19 05:30 |  | 2015-11-18 05:30 |  | Completed |  | 2017-09-01 05:30 |  | 2017-10-24 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase I study of PDR001 in advanced malignancies for Japanese patients. | CPDR001X1101 Japan P-I | N7 Oncology - NIBR | Molander, Lei Ann | Ohmori, Hiroko | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | KAE ISHIHARA | KAE ISHIHARA | [15 empty] | Tidke, Shyam |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | [12 empty] | NA | [7 empty] | 137 | 0 | [10 empty] | Solid tumour | No | Global | Open | Yes | [16 empty] | None of the above
CPDR001R1 | CPDR001X2101 | C1001718 | Phase I+II | NCDS | OC RDC - Inhouse | 2015-04-10 05:30 | 2015-04-10 05:30 |  | DB Locked |  |  | 2015-04-27 05:30 |  | 2015-01-27 05:30 |  | Completed |  | 2020-07-21 05:30 | 2020-09-29 05:30 | 2020-09-01 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Open label multicenter Phase l/ll study of the safety and efficacy of PDR001 administered to patients with advanced malignancies | CPDR001X2101 Phase I/II Advanced Malignancies | N7 Oncology - NIBR | Langlo, Francois | Meyer, Ruth | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Emilie Bossuge | Emilie Bossuge | Ahuja, Mohit | Ahuja, Mohit | [13 empty] | Tidke, Shyam |  | Rohit Varate | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2015-04-10 05:30 | 2015-04-10 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | IQVIA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 701 | 8 | 0 |  | Anaplastic thyroid cancer; Breast cancer; Melanoma; Non-small cell lung cancer | No | Global | Open | Yes | [15 empty] | Challa, Nandini | None of the above
CPDR001P1 | CPDR001X2102 | C1001720 | Phase I | NCDS | OC RDC - Inhouse | 2016-10-14 05:30 | 2016-10-14 05:30 |  | DB Conduct | Final DBL | 2022-04-07 05:30 | 2016-10-14 05:30 |  | 2016-03-30 05:30 |  | Active | 2022-02-22 05:30 |  | 2022-04-07 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase Ib, open-label, multi-center study to characterize the safety, tolerability and pharmacodynamics (PD) of PDR001 in combination with LCL161, everolimus (RAD001) or panobinostat (LBH589) | CPDR001X2102 TCO PhI Early biomarker assess-IOcomb | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Marjohn Azizy | Marjohn Azizy | Joshi, Alekhya | Mareedu, Vasu | Completed | 2021-07-20 05:30 | [11 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [12 empty] | No REPORTING ACTIVITY so trying to plan around may 2019 | 0 | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2016-07-05 05:30 | 2016-07-01 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | IQVIA | [7 empty] | 161 | 0 |  |  | 0 |  |  |  | 758 | 7 | 0 |  | Breast cancer; Colorectal cancer; Non-small cell lung cancer; Renal cell carcinoma | No | Global | Open | Yes | [16 empty] | None of the above
CPDR001U1 | CPDR001X2103 | C1001716 | Phase I | NCDS | OC RDC - Inhouse |  | 2016-07-01 05:30 |  | DB Conduct |  |  | 2016-08-23 05:30 |  | 2016-03-31 05:30 |  | Completed | 2021-03-18 05:30 | 2021-03-17 05:30 | 2021-05-04 05:30 | 2021-05-06 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase Ib, open-label, multi-center study to characterize the safety, tolerability and pharmacodynamics (PD) of PDR001 in combination with CJM112, EGF816, IlarisÂ® (canakinumab) or MekinistÂ® (trametinib | CPDR001X2103 Phase Ib, open-label, multi-center | N7 Oncology - NIBR | Langlo, Francois | Mcleod, Meghan | Mcleod, Meghan | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Stavros Milatos | Stavros Milatos | Oguri, Praveen | Dadapogu, Jesica Priyadarshini | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [12 empty] | DDPASS seestion will be scheduled in next month | 0 | OCRDC - Inhouse | No | -NA- | 2021-05-20 05:30 | 2021-05-26 05:30 |  |  | ONC | Novartis | InHouse | 2016-07-05 05:30 | 2016-07-05 05:30 | Mareedu, Vasu | Gehlawat, Priya | IQVIA | [7 empty] | 181 | 0 |  |  | 0 |  |  |  | 807 | 11 | 0 |  | Breast cancer; Colonic cancer; Non-small cell lung cancer | No | Global | Open | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CPDR001N1 | CPDR001X2105 | C1200339 | Phase I | NCDS | OC RDC - Inhouse | 2015-03-30 05:30 | 2015-03-30 05:30 |  | DB Conduct | Final DBL | 2022-09-07 05:30 | 2017-07-06 05:30 |  | 2017-01-26 05:30 |  | Active | 2022-06-30 05:30 |  | 2022-09-07 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase 1b, multi-arm, open-label study of PDR001 and/or MBG453 in combination with decitabine in patients with acute myeloid leukemia or high risk myelodysplastic syndrome | CPDR001X2105 | N7 Oncology - NIBR | Langlo, Francois | Barnard, Carol | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Anisa Mohammed | Anisa Mohammed | Gehlawat, Priya | Ahuja, Mohit | [13 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | No | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-06-05 05:30 | 2017-06-05 05:30 | Gehlawat, Priya | Mareedu, Vasu | IQVIA | [7 empty] | 233 | 0 |  |  | 0 |  |  |  | 599 | 8 | 0 |  | Acute myeloid leukaemia; Myelodysplastic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CPDR001M1 | CPDR001X2106 | C1001717 | Phase I | NCDS | OC RDC - Inhouse |  |  | 2017-12-22 05:30 | DB Locked |  |  | 2017-12-18 05:30 |  | 2017-02-02 05:30 |  | Completed | 2020-02-29 05:30 | 2020-03-02 05:30 | 2020-07-10 05:30 | 2020-07-09 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase I/Ib, multi-center, open-label, study of single agent CJM112, and PDR001 in combination with LCL161 or CJM112 in patients with relapsed and/or refractory multiple myeloma | CPDR001X2106 Phase I/Ib Multiple Myeloma Study | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Daniel Carreon | Norma Angelica Cuevas Garibay | Joshi, Alekhya | Joshi, Alekhya | [13 empty] | Challa, Nandini |  | Rohit Varate | [12 empty] | DDpass starts on 18mar2019, already scheduled | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-05-11 05:30 | 2017-05-11 05:30 | Gehlawat, Priya | Mareedu, Vasu | IQVIA | [7 empty] | 137 | 0 |  |  | 0 |  |  |  | 901 | 5 | 0 |  | Multiple myeloma | No | Global | Completed | Yes | [14 empty] | DBL |  | None of the above | Yes
CPDR001S1 | CPDR001X2201 | C1200673 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-04-20 05:30 |  | 2015-04-18 05:30 |  | Completed | 2021-03-01 05:30 | 2021-02-19 05:30 | 2021-03-24 05:30 | 2021-03-24 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase II, open-label, randomized controlled study of PDR001 in patients with moderately differentiated/undifferentiated locally advanced recurrent or metastatic nasopharyngeal carcinoma who progressed on standard treatment | CPDR001X2201 | N7 Oncology - NIBR | Langlo, Francois |  | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Yafang Zhou | Yafang Zhou | Govula, Shashikanth | Samuel, Giftson | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate |  |  | Not Applicable | [10 empty] | 100 | OCRDC - Inhouse | Yes | -NA- | 2021-03-24 05:30 | 2021-03-26 05:30 |  |  | ONC | Novartis | InHouse | 2016-03-22 05:30 | 2016-03-22 05:30 | Kanchi, Pavan kumar | Gehlawat, Priya | IQVIA | [7 empty] | 119 | 0 |  |  | 0 |  |  |  | 832 | 13 | 0 |  | Nasopharyngeal cancer | No | Global | Open | Yes | [14 empty] | DBL | Challa, Nandini | None of the above | Yes
CPDR001T1 | CPDR001X2X01B | C1200350 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-08-08 05:30 | 2019-08-13 05:30 | 2019-10-31 05:30 | DB Conduct | Final DBL | 2025-03-27 05:30 | 2019-10-31 05:30 | 2019-04-17 05:30 | 2019-04-25 05:30 |  | Active | 2025-01-16 05:30 |  | 2025-03-27 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | An open-label, multi-center rollover protocol for continued characterization of safety and tolerability for subjects who have participated in a Novartis-sponsored spartalizumab study as single agent or in combination with other study treatments | CPDR001X2X01B | N7 Oncology - NIBR | Langlo, Francois | Rocha, Gabriela | Gibbens, Nadia | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Nicolas Carlo Blanco | Nicolas Carlo Blanco | Bai, Chandrakala | Ahuja, Mohit | Completed | 2019-10-30 05:30 |  |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 22-Jun-2021: RF V7.0 finalized with 7 new EC forms WRT PPC#05. Snow-51 raised and LSP has been notified. 03-Jun-2021: Created Rule File V7.0 by including all the 7 new Study Treatment forms (ECG002_9,ECG002_10,ECG002_11,ECG002_12,ECG002_13,ECG002_14,ECG002_15) under EC domain and released for peer review. 18Dec2020: RF V6.0 WRT PPC#04 finalized in CREDI. SNOW-51 raised and LSP and SMT developer notified. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 13Aug2020 (SHRIVNI5): RF V5.0 updated and finalized for CM and FACM domains. SNOW-51 raised and LSP notified. 30Jul2020: Rule file V4.0 is finalized in CREDI which the latest one. 23Jul2020: Rule file V3.0 is finalized in CREDI. 20Nov2019: RF v2.0 finalized and sent for SMT update. | None | None | 2019-08-14 05:30 |  | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2019-09-06 | Completed | 2019-09-06 05:30 |  |  | 2019-09-06 05:30 | 2019-09-06 05:30 |  | 2020-05-05 05:30 |  |  | All the domains passed the DDPASS. | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 7 | 81 | 56 | 0 | 212 | 555 | 0 | 153 | 36 | 309 | 900 | 1 | 0 |  | Breast cancer; Melanoma; Non-small cell lung cancer; Solid tumor | No | Global | Open | Yes | [10 empty] | 2019-09-04 05:30 | [5 empty] | None of the above
CPEA001A1 | CPEA001A12201 | C4001712 | Phase II | NCDS | Other |  |  | 2018-12-11 05:30 | DB Locked |  |  | 2018-12-10 05:30 | 2018-07-30 05:30 | 2018-08-06 05:30 |  | Completed | 2019-09-26 05:30 | 2019-09-26 05:30 | 2019-11-04 05:30 | 2019-11-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS |  | CPEA001A12201 Pear in Schiz- | N6 Neuroscience - NIBR | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Patricia Wagner | Patricia Wagner | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Schizophrenia | No | Global | Completed | Yes | [16 empty] | None of the above
CPHE885B1 | CPHE885B12201 | C4010497 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-11-11 05:30 | 2022-02-03 05:30 | 2022-02-22 05:30 | DB Conduct | Final DBL | 2025-08-28 05:30 |  | 2021-09-10 05:30 | 2021-09-22 05:30 |  | Planned | 2025-07-17 05:30 |  | 2025-08-28 05:30 |  |  | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A Phase 2 study of PHE885, B-cell maturation Antigen (BCMA)-directed CAR-T Cells in adult participants with relapsed and refractory multiple myeloma | CPHE885B12201 BCMA 4L Study | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kotamarthi, Jyothi | Bathini, Murali Krushna | Bhartendu, Rishav | Nair, Sreesha | Sreekanth Kunchetty | Sreekanth Kunchetty | Kabra, Pratik Govind | Kabra, Pratik Govind |  |  | As per email received from PDM on 22 Sep 2021 - as per quick discussion with GTD of the study, updated timelines with go-live date as 13th Dec 2021. There were delays in the SSD and ECS and the quality of the documents was not up to the mark. As per email received from PDM on 10 Dec 2022 - CPHE885B12201 study FPFV date has been moved to Jan 2022 due to unavailability of site resources in Australia and we are revisiting the DB Go-live timelines and again as per email received on 24 Jan 2022 from GTD about further delays in FPFV dates. Database was almost ready by 16-Dec-2021. However, as RIS got delayed due to pending approvals in Australia site, DB Go-Live was moved ahead. |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 4Feb2022: Study pushed to production. SNOW 05 request RITM3457721 has been raised for PROD LSH Set up and notified the LSP. 12Jan2022: DBD updated the ALS as per the communication shared and RF updated accordingly. Both the RF version 2.0 and Checklist have been finalized and SNOW51 request RITM3375312 has been raised. 11Jan2022: LSP flagged an issue regarding TUTRS001 page where EVLNUM is having data format inconsistencies w.r.t other pages and needs to be corrected since it's failing. DBD will update after discussing this with the study team and updated timelines received. No confirmation yet regarding the go-live. 5Jan2022: Study DQT has been finalized and Study folder created in the GPS. Raised the LSH TEST ticket once again and notified the LSP. 4Jan2022: Cancelled the LSH TEST ticket since the DQT was not finalized and the study was not created in the GPS so LSP could not proceed. Will raise the ticket again once the DQT is finalized and the study is created in GPS. 24Dec2021: Finalized the RF version 1.0 and Checklist on the SubWay. LSH Test Ticket has been raised. LSH Prod will be raised once the study has been pushed to the production. Notified the LSP.. 22Dec2021: Sent the RF for peer review incorporating all the changes and updates happened after the first round. 20Dec2021: Received 3 DTS to review. Reviewed and sent the comments regarding them. 16Dec2021: Go-live date has been pushed to 30th Dec. Received an update that 2 more pages are to be added in the study. 14Dec2021: Received the Peer review comments and shared the DB related comments to the DBD. Updated the RF as per the comments received. 10Dec2021: Go-live date has been pushed to 17th Dec. RF released for the peer review. 3Dec2021: Received the updates regarding the Bone Marrow pages and latest SDTM annotation and SOD 1Dec2021: Reviewed the docs and shared my comments to the DBD to address them. Received the latest ALS with 2 pending pages and the SDTM annotation. Started the 26Nov2021: Received the updated ALS, SDTM and SRFs. Was notified that 2 pages are still pending with the UAT. Go-live is pushed to 13Dec2021. Started the RF development 19Nov2021: Received 2 more ALS with updates, raised the concern to Appalla and received the update as to wait till the UAT is performed. 17Nov2021: Received the latest ALS, SDTM annotations and SRFs for review. Raised the concerns since the UAT is not yet performed and simultaneous updates are happening in ALS, inconvenience in reviewing. 19Aug2021 : RF developer assigned with go-live as 11NOv2021. | None | QS1L, QS2L, QS3L DTS to be added | 2022-02-04 05:30 |  | CHILUKESHWARAM, AKHIL | Thirugnanasambandam, Nivetha Lakshmi | Amit Agavekar | Completed | 2022-02-10 | Completed | 2022-02-16 05:30 |  |  | 2022-02-16 05:30 | 2022-02-16 05:30 | [5 empty] | 0 | [14 empty] | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 1100 | 10 | 0 |  | Multiple myeloma progression | No | Global | Open | Yes | 2022-01-05 05:30 | Completed | 2022-01-05 05:30 | Completed | 2022-01-11 05:30 | 2022-01-14 05:30 |  |  |  |  | 2022-01-13 05:30
CPHE885B1 | CPHE885B12301 | C4012562 | Phase III | NCDS_2 |  |  |  | 2022-09-13 05:30 |  | Final DBL | 2023-04-10 05:30 |  | 2022-05-27 05:30 |  |  | Planned | 2023-02-27 05:30 |  | 2023-04-10 05:30 | [5 empty] | InHouse |  |  | CPHE885B12301 PHE885 4LMM Ph3 RCT | PA Oncology (Hematology not for MA projects) | [6 empty] | Ian Miller | [54 empty] | 80 | [7 empty] | 1100 | 10 |  |  | Multiple myeloma | No | Global | Open | Yes
CPHE885C1 | CPHE885C12301 | C4010498 | Phase III |  |  |  |  | 2023-09-06 05:30 |  | Final DBL | 2024-04-02 05:30 |  | 2023-05-22 05:30 |  |  | Planned | 2024-02-20 05:30 |  | 2024-04-02 05:30 | [5 empty] | InHouse |  |  | CPHE885C12301 PHE885 BCMA 2L MM Study | PA Oncology (Hematology not for MA projects) | [6 empty] | Ian Miller | [66 empty] | Multiple myeloma progression | No | Global | Open | Yes
CPIM447C1 | CPIM447X2104C | C3000370 | Phase I | NCDS | OC RDC - Inhouse |  | 2015-02-27 05:30 |  | DB Locked |  |  | 2015-05-21 05:30 |  | 2014-11-10 05:30 |  | Completed | 2020-11-09 05:30 | 2020-11-09 05:30 | 2021-03-01 05:30 | 2021-03-01 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A Phase Ib, multi-center, open-label, dose-escalation study of PIM447 in combination with ruxolitinib (INC424) and LEE011 administered orally in patients with myelofibrosis | CPIM447X2104C Phase Ib Myelofibrosis Study | N7 Oncology - NIBR | Langlo, Francois | Vivier, Gregoire | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Sarah DiDominick | Sarah DiDominick | Samuel, Giftson | Samuel, Giftson | [13 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [12 empty] | No issues identified and all the domains were reviewed by the team. | 0 | OCRDC - Inhouse | No | -NA- | 2021-03-03 05:30 | 2021-03-04 05:30 |  |  | ONC | Novartis | InHouse | 2015-02-27 05:30 | 2015-02-27 05:30 | Mareedu, Vasu | Shewane, Roshni | IQVIA | [7 empty] | 132 | 0 |  |  | 0 |  |  |  | 509 | 5 | 0 |  | Myelofibrosis | No | Global | Open | Yes | [14 empty] | DBL | Manoharan, Vivek | None of the above | Yes
CMTHDLGY | CPJMR0062112 | C1200705 | Not Applicable | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-06-09 05:30 |  | 2014-12-08 05:30 |  | Completed | 2018-02-14 05:30 | 2018-02-14 05:30 | 2018-04-05 05:30 | 2018-03-27 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - MSD | An investigation of quantitative MRI endpoints as imaging\nbiomarkers for cartilage degeneration | CPJMR0062112 | R1 CBT - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Ewa Kubiak | Ewa Kubiak | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Cartilage injury | No | Global | Completed | Yes | [16 empty] | None of the above
CMTHDLGY | CPJMR0062113 | C1200390 | Not Applicable | NOVDD | [7 empty] | 2016-01-12 05:30 |  | 2015-07-15 05:30 |  | Completed |  | 2017-07-05 05:30 |  | 2017-08-02 05:30 | FALSE |  |  |  | ED Full Outsourced |  | Tendon stiffness as a biomarker to quantify tendon healing\nafter Achilles tendon rupture | CPJMR0062113 | R1 CBT - NIBR | [5 empty] | Emilie Francoise Voltz | Fr��d��rique Chaperon | [66 empty] | Diagnostic procedure | No | Global | Completed | Yes | [16 empty] | None of the above
CCPK850A0 | CPJMR0092105 | C1200023 | Not Applicable | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2013-09-16 05:30 |  | 2012-07-16 05:30 |  | Active | 2019-06-11 05:30 |  | 2020-01-10 05:30 | 2020-02-13 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - OPHTHA | Natural History Study of Patients with Retinal Dystrophy Due to Mutation in the RLBP1 Gene | CPJMR0092105 natural history study | N8 Ophthalmology - NIBR | Langlo, Francois | Somasundar, Karan | Rajput, Namita | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Karen Holopigian; Lisa Jimmink_TAP | Karen Holopigian | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | Other | Pharma | AP21 | [17 empty] | Diagnostic procedure | No | Global | Completed | Yes | [16 empty] | None of the above
CPKC412A_MA | CPKC412A2001X | C1001723 | Not Applicable | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-06-16 05:30 |  | 2016-06-07 05:30 |  | Completed |  | 2018-07-15 05:30 |  | 2018-12-21 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | An open-labeled, multi-center, Expanded Treatment Protocol (ETP) of midostaurin (PKC412) in patients 18 years of age or older with newly-diagnosed FLT3-mutated acute myeloid leukemia (AML) who are eligible for standard induction and consolidation chemotherapy | CPKC412A2001X_PIV-AML/FLT3mut, under 60y/L1-C | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kurup, Rashmi | Prajapati, Vaishali | Purra, Shashikanth | Nair, Sreesha | Anne Ruault | Anne Ruault | Bonam, Rajesh Babu | [14 empty] | Genga, Vardhini |  | Amit Agavekar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2017-03-22 05:30 | 2017-03-22 05:30 |  |  | NA | [7 empty] | 65 | 0 |  |  | 0 |  |  |  | 602 | 0 | 0 |  | Acute myeloid leukaemia | No | Global | Completed | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | No
CPKC412A | CPKC412A2116 | C1001376 | Phase I | NOVDD | Paper |  |  |  | DB Locked |  |  | 2011-03-07 05:30 |  | 2010-09-03 05:30 |  | Completed | 2020-05-09 05:30 | 2020-05-09 05:30 | 2020-07-20 05:30 | 2020-07-17 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open-label, multiple dose, parallel group, phase I study to assess the pharmacokinetics and safety of midostaurin in subjects with impaired hepatic function and subjects with normal hepatic function | CPKC412A2116 PI-PK and Safety/Hepatic Impaired pts | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kumar HC, Vijay | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Bourdeau | Laurence Bourdeau |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | Parexel | Oncology | BP21 | Parexel | Anja Klawisch (Anja.Klawisch@parexel.com) | Earlier DBD: Brinda Shree | [14 empty] | Hepatic impairment | No | Global | Open | Yes | [16 empty] | None of the above
CPKC412A | CPKC412A2121 | C3003182 | Phase I | NCDS | CRO - EDC |  |  | 2019-05-27 05:30 | DB Locked |  |  | 2019-04-18 05:30 | 2018-10-02 05:30 | 2018-07-17 05:30 |  | Completed | 2019-08-09 05:30 | 2019-09-11 05:30 | 2019-08-26 05:30 | 2019-10-31 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A Phase I, open-label, drug-drug interaction study to assess the impact of a single oral dose administration of midostaurin on P-gp, BCRP and CYP2D6 substrates (digoxin, rosuvastatin and dextromethorphan) pharmacokinetics in adult healthy subjects | CPKC412A2121 DDI PMR study single dose | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Kohli, Deepti | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Carolin Sachs | Flavia Kiertsman | Ahuja, Mohit | Ahuja, Mohit | [13 empty] | Varate, Rohit |  | Amit Agavekar | [14 empty] | CRO | [6 empty] | ONC | Parexel | Outsourced |  |  | Mareedu, Vasu | Gehlawat, Priya | Parexel | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 1 | 0 |  | Pharmacokinetic study | No | Global | Completed | Yes | [16 empty] | None of the above
CPKC412A | CPKC412A2122 | C3003181 | Phase I | NCDS | CRO - EDC |  |  | 2019-06-14 05:30 | DB Locked |  |  | 2019-06-14 05:30 | 2018-11-09 05:30 | 2018-12-05 05:30 |  | Completed | 2019-11-05 05:30 | 2019-11-25 05:30 | 2019-12-10 05:30 | 2020-01-13 05:30 | FALSE |  |  | Cluster D (TM,TCO,Coding) | FULL Outsourced |  | A Phase 1, open-label, two-arm, two fixed-sequence, drug-drug interaction study in healthy adult subjects to assess the impact of repeated oral dose midostaurin (Rydapt) on the pharmacokinetics of CYP3A, CYP2B6, and CYP2C8 drug substrates (midazolam, bupropion, and pioglitazone) | CPKC412A2122 DDI PMR study_multiple dose | PA Oncology (Hematology not for MA projects) | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Cathy Gray | Amanda Taylor | [46 empty] | Parexel | [19 empty] | Cancer; Systemic mastocytosis | No | Global | Open | Yes | [16 empty] | None of the above
CPKC412A | CPKC412A2123 | C3003344 | Phase I | NCDS | CRO - EDC |  |  | 2019-08-15 05:30 | DB Locked |  |  | 2019-08-16 05:30 | 2018-11-16 05:30 | 2018-12-12 05:30 |  | Completed | 2020-01-14 05:30 | 2020-01-08 05:30 | 2020-02-12 05:30 | 2020-02-10 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - Oncology | A Phase I, open-label, drug-drug interaction study to assess the effect of multiple oral dose midostaurin on a single dose of oral contraceptive in healthy post-menopausal women | CPKC412A2123 DDI PMR study_Oral contraceptive | PA Oncology (Hematology not for MA projects) | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Cathy Gray | Amanda Taylor | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Abdominal lymphadenopathy | No | Global | Open | Yes | [16 empty] | None of the above
CPKC412G1 | CPKC412A2218 | C1001372 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-23 05:30 | 2019-02-28 05:30 | DB Conduct | Final DBL | 2029-03-29 05:30 | 2019-03-13 05:30 | 2018-07-11 05:30 | 2018-06-12 05:30 |  | Active | 2029-02-15 05:30 |  | 2029-03-29 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase II, open-label, single arm study to evaluate the safety, efficacy, and pharmacokinetics of twice daily midostaurin (PKC412) combined with standard chemotherapy and as a single agent post-consolidation therapy in children with untreated FLT3-mutated AML | PII-AML/FLT3mut/L1-C/Ped_PKC412A2218 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Deshpandey, Vinayak | Subramanian, Mahaveeran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Laurence Bourdeau | Lisa Burgmeyer | Rao, S Shashikanth | Rao, S Shashikanth |  |  |  |  | DRM | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 06-Jul-2020: No pending issues. 04-Jun-2020: Included B11L in RF Version 4.0 and raised SNOW ticket for LSH update 18-May-2020: Requested DBP to share all the required documents to include the B11L DTS in RF. It has been flagged in missing DTS report 05Feb2020 : Verison 3.0 is uploaded in credi and BMO002 form is inactivated in study. In next version of rule file need to incldue this form in 'Excluded forms tab' ​21-Jan-2020(Kranthi): Shashi has to upload RF Version 3.0 in CREDI with all the domains missing in earlier version 29th Nov 19- (Shashi) LB, XG, RP, XS domains to be included in the RF. Planned FPFV 16th Jan 2019. Rule file creation to be initiated this week. | None | None | 2019-04-02 05:30 | Legacy Process | Agavekar, Amit | Chitransh, Arpit | Amit Agavekar | Completed | 2019-03-12 | Completed | 2019-04-15 05:30 | This is one of the Pilot DRM study. |  | 2019-04-17 05:30 | 2019-04-17 05:30 | Pre-requisites not met | 2019-08-20 05:30 |  |  |  | 100 | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 10 | 117 | 91 | 0 | 8 | 1135 | 0 | 207 | 32 | 435 | 1602 | 2 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [10 empty] | 2019-04-12 05:30 | [5 empty] | HA Commitment
CPKC412A | CPKC412A2220 | C1001373 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2017-11-02 05:30 | 2018-04-27 05:30 | DB Conduct | Final DBL | 2022-12-26 05:30 | 2018-04-06 05:30 |  | 2017-06-28 05:30 |  | Active | 2022-11-21 05:30 |  | 2022-12-26 05:30 |  | FALSE | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase II, randomized, double-blind, multi-center, placebo-controlled study to evaluate the efficacy and safety of twice daily oral midostaurin in combination with daunorubicin/cytarabine induction, highdose cytarabine consolidation, and midostaurin single agent continuation therapy in newly diagnosed patients with FLT3-mutated acute myeloid leukemia (AML) | PII-AML/FLT3mut/L1-C_PKC412A2220 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Okuzono, Seigou | Subramanian, Mahaveeran | Okuzono, Seigou | Nair, Sreesha | HIROMI TAKEUCHI | HIROMI TAKEUCHI | Bakka, Sandeep | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Govula, Shashikanth | Bai, Chandrakala | Completed | 27Jan2022:Rule File V12.0 is finalized in CREDI and the SNOW#51 ticket- RITM3428248 has been raised to fix LSH issue by Pratiksha(back-up). 7JAN2021: No upcoming tasks. 10Feb2020 : As per missing DTS report B11L is pending but the Table name is updated from B11L to B1L as per DTS. Report can be ignored. DDG001 This is not required we have DDG002 now in the study. DDG001 to be included in Excluded forms tab of RF | None | None | 2018-05-28 05:30 | Legacy Process | Polagoni, Bharghavi | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2018-05-31 | Completed | 2020-05-13 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. | Pre-requisites not met | 2018-05-31 05:30 | 2018-05-31 05:30 | Pre-requisites not met | 2020-06-04 05:30 |  |  |  | 93 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 17 | 105 | 79 | 0 | 726 | 706 | 0 | 189 | 39 | 331 | 1076 | 9 | 0 |  | Acute myeloid leukaemia | Yes | Global | Open | Yes | [10 empty] | 2020-05-10 05:30 | [5 empty] | None of the above
CPKC412A | CPKC412A2301 | C1001375 | Phase III | NOVDD | Other |  |  |  | DB Conduct | Final DBL | 2022-04-08 05:30 | 2008-05-08 05:30 |  | 2008-03-17 05:30 |  | Active | 2022-01-17 05:30 |  | 2022-04-08 05:30 |  | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A Phase III Randomized, Double-Blind Study of Induction (Daunorubicin/Cytarabine) and Consolidation (High-Dose Cytarabine) Chemotherapy + Midostaurin (PKC412)(IND# 101261) or Placebo in Newly Diagnosed Patients less than 60 years of Age With FLT3 Mutated Acute Myeloid Leukemia (AML) | CPKC4121 2301 ML/FLT3mut-under 60y/L1-C RATIFY | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Bulusu, Sravani | Subramanian, Mahaveeran | Bhartendu, Rishav | Nair, Sreesha | Laurence Bourdeau | Lisa Burgmeyer | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Acute myeloid leukaemia | Yes | Global | Open | Yes | [16 empty] | None of the above
CPKC412A | CPKC412A2408 | C1001721 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-09-21 05:30 | 2018-02-13 05:30 | DB Locked | Final DBL Achieved |  | 2018-02-13 05:30 |  | 2017-08-10 05:30 |  | Active | 2021-07-06 05:30 | 2021-07-09 05:30 | 2021-08-23 05:30 | 2021-08-24 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | An open-labeled, multicenter, Phase IIIb study of midostaurin (PKC412) in patients 18 years of age or older with newly-diagnosed FLT3-mutated acute myeloid leukemia (AML) who are eligible for standard induction and consolidation chemotherapy | CPKC412A2408 PIIIb-AML FLT3mut,y L1-C | PA Oncology (Hematology not for MA projects) | Vithala, Srinivas | Khatua, Sandeep | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Geralyn Gilotti | Hassan El Gazri | Meda, Sreelakshmi | Meda, Sreelakshmi | [13 empty] | Agavekar, Amit |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | Yes | -NA- | 2021-08-24 05:30 | 2021-08-26 05:30 |  |  | ONC | Novartis | ICON | 2017-09-21 05:30 | 2017-09-21 05:30 | Meda, Sreelakshmi |  | NA | [7 empty] | 53 | 0 |  |  | 0 |  |  |  | 667 | 2 | 0 |  | Acute myeloid leukaemia | No | Global | Open | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CPKC412D | CPKC412D2201 | C1001379 | Phase II | NOVDD | Other |  |  |  | DB Locked |  |  | 2008-10-13 05:30 |  | 2008-04-23 05:30 |  | Completed |  | 2017-08-24 05:30 |  | 2017-10-23 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A Single Arm, Phase II, Open-Label Study to Determine the Efficacy of 100mg Twice Daily Oral Dosing of Midostaurin Administered to Patients with Aggressive Systemic Mastocytosis or Mast Cell Leukemia +/- an Associated Hematological Clonal Non-Mast Cell Lineage Disease | PKC412D2201 PII-ASM and MCL/L1-M_= | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Vadla, Nagarajachari | K R, Chandran | Lateefuddin, Shariff Mohd | Nair, Sreesha | Sophie Ifrah | Sophie Ifrah | [17 empty] | Amit Agavekar | [28 empty] | IQVIA | [19 empty] | Aggressive systemic mastocytosis; Mastocytic leukaemia | No | Global | Completed | Yes | [16 empty] | None of the above
CPKC412E | CPKC412E2301 | C1001380 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-04-26 05:30 | 2018-07-12 05:30 | DB Locked | Final DBL Achieved |  | 2018-07-20 05:30 | 2017-12-29 05:30 | 2018-01-10 05:30 |  | Completed | 2021-02-12 05:30 | 2021-02-12 05:30 | 2021-03-26 05:30 | 2021-03-31 05:30 | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A phase III, randomized, double-blind study of induction (daunorubicin/cytarabine) and consolidation (high-dose cytarabine) chemotherapy plus midostaurin (PCK412) or placebo in newly diagnosed patients with FLT3-wild type (FLT3-wt) acute myeloid leukemia (AML) | PIII-AML/FLT3 WT/L1 CPKC412E2301 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Subramanian, Mahaveeran | Subramanian, Mahaveeran | Bhartendu, Rishav | Nair, Sreesha | Nathalie Guichard | Nathalie Genev��ve Bernadette Guichard | Maricherla, Vijayroshan | Tadiparthy, Ramakanth |  |  |  |  | DRM (DIAL) | Oguri, Praveen | Bai, Chandrakala | Completed | 08Jul2021: RF v12.0 finalized for LSH error rectification in 'B110L' dts table. 26May2021 : Reassigned the study from Praveen Oguri to Chandrakala Bai. 21-Jan-2021: Sent email to LSP to confirm whether DTS is setup in LSH or not. 17-Dec-2020: B19L DTS added in RF Version 9.0 and SNOW ticket raised on 01-Dec-2020 (RITM2042183) 05Nov2020: No Activity. 11Sep2020: No Activity. 06Jul2020: Rule file V8.0 is the latest version. Study will be transitioned to Praveen from Ashok. 04Jun2020: Rule File V8.0 is finalized in CREDI to include all the pending forms and DTS. B16L,B17L,B18L DTS included. B1S001_TR, B1S002_TR, B1S003_TR, B1S004 and B1S005, OPS001 and XSS001 pages included. 21May2020 : Included : B1S001_TR, B1S002_TR, B1S003_TR, B1S004, B1S005, OPS001 and XSS001 DTS : B16L,B17L,B18L as per the PPC and finalized DTS and sent for peer review 30Apr2020 : PPC is in progress. 25Apr2020 : followed up with DBD on PPC 01Apr2020 : Reassigned RF from Roshan to Ashok 01Apr2020: PPC to be completed by 10 Apr2020. Rule file update to be initiated on 06Apr2020. 26MAR2020: Awaiting PPC implementation to initiate RF development. For XSS001, B1S004, B1S005, B1S001_TR, B1S002_TR, B1S003_TR1 Will include in next version. Initially the plan was to batch upload from other study, now the plan is to enter the data. decision ongoing with study team. 10Mar20 : DTS for B18L final and shared to include in RF on 05Mar. 03MAR2020: LSH setup completed. 15 Jan 20: SNOW 51 raised for SMT and LSH rebuild. 14 Jan 20: Rule File Peer review completed for adding B15L. Uploaded rule file for approval in CREDI. 09 Jan 20: Initiated rule file development for adding DTS domain. | None | None | 2018-06-19 05:30 |  | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2018-12-24 | Completed | 2019-06-21 05:30 |  | Retrospective DRM studies | 2018-10-03 05:30 | 2018-10-03 05:30 | LSH System issues | 2019-08-22 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes |  | 2021-04-01 05:30 | 2021-04-06 05:30 | [9 empty] | NA | [5 empty] | 14 | 115 | 82 | 0 | 895 | 752 | 0 | 221 | 32 | 327 | 1111 | 12 | 0 |  | Acute myeloid leukaemia | Yes | Global | Open | Yes | [10 empty] | 2019-06-21 05:30 |  |  |  | DBL | Girvasiya, Shaili | None of the above | Yes
CMTHDLGY | CPLATFRM2107 | C1200727 | Not Applicable | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-07-13 05:30 |  | 2014-12-29 05:30 |  | Completed | 2018-02-06 05:30 | 2018-02-07 05:30 | 2018-04-10 05:30 | 2018-05-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | Portal Hypertension biomarker study in HCV patients\nundergoing curative anti-viral therapy | CPLATFRM2107 | R1 CBT - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Florine Polus | Florine Polus | Tripathi, Shakuntala | R, Ankit | [15 empty] | Rohit Varate | [28 empty] | CMED |  | AP21 | CMED Clinical services | [16 empty] | Pulmonary arterial hypertension | No | Global | Completed | Yes | [16 empty] | None of the above
CPMZ725B | CPMZ725B2301 | C1001382 | Phase III | NCDS_2 | [9 empty] | 2017-10-18 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE |  |  |  | InHouse |  | A three-month, multicenter, double-masked study of the efficacy and safety of travoprost 0.0015%/timolol 0.1% viscous solution compared to travoprost 0.0015% viscous solution and timolol 0.1% viscous solution in patients with open-angle glaucoma or ocular hypertension | PMZ725B_Phase III_CPMZ725B2301_DuoTrav US | P6 Global Health | [5 empty] | Liza Svoboda | Liza Svoboda | [66 empty] | Glaucoma; Ocular hypertension | No | Global | Terminated | Yes | [16 empty] | None of the above
CPMZ725B | CPMZ725B2302 | C3000245 | Phase III | NCDS_2 | [9 empty] | 2017-10-17 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE |  |  |  | InHouse |  | A three-month, multicenter, double-masked study of the efficacy and safety of travoprost 0.0015%/timolol 0.1% viscous solution, compared to travoprost 0.004% and timolol 0.5% dosed concomitantly, in patients with open angle glaucoma or ocular hypertension | PMZ725B_Phase III_CPMZ725B2302_DuoTrav US | P6 Global Health | [5 empty] | Christine Rosko; Liza Svoboda | Liza Svoboda | [66 empty] | Glaucoma; Ocular hypertension | No | Global | Terminated | Yes | [16 empty] | None of the above
CPZP034A | CPZP034A1401 | C1001726 | Phase IV | Other |  |  |  | 2014-08-19 05:30 |  |  |  | 2014-08-19 05:30 | 2014-04-29 05:30 | 2014-04-29 05:30 |  | Completed | 2019-09-30 05:30 | 2017-03-08 05:30 | 2019-09-30 05:30 | 2019-09-27 05:30 | FALSE |  |  |  | Outsourced |  | VotrientÂ® Tablets (Investigation in Patients with Renal Cell Carcinoma) | CPZP034A1401 JPN PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | MINE KIMURA | MINE KIMURA | [66 empty] | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034A0 | CPZP034A2101 | C1001387 | Phase I | GSK | CRO - EDC |  |  | 2018-08-31 05:30 | DB Locked | Final DBL Achieved |  | 2013-12-27 05:30 | 2017-10-31 05:30 | 2013-09-13 05:30 |  | Completed | 2019-02-15 05:30 | 2019-02-27 05:30 | 2019-03-29 05:30 | 2019-04-03 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase I/II study to assess the safety and efficacy of pazopanib and MK 3475 in patients with advanced Renal Cell Carcinoma | CPZP034A2101 (200249 GSK)_PhI-Exp/RCC-C (MK3475) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Suryawanshi, Sandip | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther | Laurence Descamps | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | TCS | [7 empty] | 150 | 0 |  |  | 0 |  |  |  | 600 | 4 | 0 |  | Renal cell carcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CPZP034A | CPZP034A2201 | C1001383 | Phase II | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2010-05-19 05:30 |  | 2009-07-09 05:30 |  | Active | 2021-06-30 05:30 |  | 2021-09-07 05:30 | 2021-11-03 05:30 | FALSE | No submission planned | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | GW786034 A Phase II study to evaluate efficacy and safety of pazopanib and sunitinib in Advanced RCC patients from Asian | PhII-advRCC/L1-M_CPZP034A2201(113078COMPARZ Asian) | P0 Oncology (Solid Tumors all MA Onc projects) | Paigaonkar, Gargi | Sinkar, Abhijeet | Mali, Astik | Sonmale, Pravin | Ninan, Esther | Janet Lasher | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  |  | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034A | CPZP034A2301 | C1001384 | Phase III | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2008-08-14 05:30 |  | 2008-05-22 05:30 |  | Active | 2018-06-29 05:30 | 2021-03-24 05:30 | 2021-05-06 05:30 | 2021-05-04 05:30 | FALSE | No submission planned | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | Study VEG108844, A study of Pazopanib versus Sunitinib in the Treatment of Subjects with Locally Advanced and/or Metastatic Renal Cell Carcinoma | PhIII-advRCC/L1-M_CPZP034A2301 (108844 COMPARZ) | P0 Oncology (Solid Tumors all MA Onc projects) | Paigaonkar, Gargi | Sinkar, Abhijeet | Padigela, Hari | Sonmale, Pravin | Ninan, Esther | Janet Lasher | Janet Lasher | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 10 | 0 |  |  | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034A_MA | CPZP034A2401 | C1001727 | Phase IV | GSK | CRO - EDC |  |  |  | DB Locked |  |  | 2012-07-19 05:30 |  | 2012-03-02 05:30 |  | Completed | 2018-07-18 05:30 | 2017-07-03 05:30 |  | 2017-10-13 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A prospective observational study to capture real world treatment patterns and determine treatment outcomes in patients with advanced or metastatic renal cell carcinoma (RCC) receiving pazopanib. | CPZP034A2401 115232 PRINCIPAL | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Suryawanshi, Sandip | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Yulia Hirschberg | Yulia Hirschberg | [17 empty] | Sandeep Kadam | [28 empty] | IQVIA | [19 empty] | Renal cell carcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CPZP034A_MA | CPZP034A2406 | C1001728 | Phase II | GSK | [7 empty] | 2012-04-19 05:30 |  | 2011-05-25 05:30 |  | Stopped (with patients) |  | 2016-11-18 05:30 |  | 2017-03-04 05:30 | FALSE |  |  |  | Outsourced |  | CATChEz: Continuous Access to advanced and metastatic renal cell Carcinoma therapy with Everolimus post pazopanib treatment | CPZP034A2406 114907 CATCHeZ | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Yulia Hirschberg | Yulia Hirschberg | [66 empty] | Renal cell carcinoma | No | Global | Terminated | No | [16 empty] | None of the above
CPZP034A_MA | CPZP034A2410 | C1001385 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-07-14 05:30 | 2017-10-20 05:30 | DB Locked | Final DBL | 2021-09-29 05:30 | 2017-11-14 05:30 |  | 2017-04-07 05:30 |  | Active | 2021-08-13 05:30 | 2021-10-20 05:30 | 2021-09-29 05:30 |  | FALSE | No submission planned | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A prospective international multicenter phase II study to evaluate the efficacy, safety and quality of life of oral daily pazopanib in patients with advanced and/or metastatic RCC after previous therapy with checkpoint inhibitor treatment | CPZP034A2410 Post IO pazo | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sharma, Mokshitaa | Padigela, Hari | Sonmale, Pravin | Ninan, Esther | Heather Patino | Heather Patino | Shewane, Roshni | Katam, Veera Nagendra | Completed | 2021-01-28 05:30 | Study Transitioned to Nagendra Katam on 28 Jan 2021. | [10 empty] | Garje, Sagar |  | Sandeep Kadam | [13 empty] | 19 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2017-07-13 05:30 | 2017-07-13 05:30 | Shewane, Roshni | Meda, Sreelakshmi | NA | [7 empty] | 95 | 0 |  |  | 0 |  |  |  | 1109 | 3 | 0 |  | Renal cell carcinoma | No | Global | Open | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CPZP034A | CPZP034A2414 | C4000439 | Phase IV | Other |  |  |  | 2020-07-22 05:30 |  | Final DBL | 2023-01-05 05:30 | 2020-05-19 05:30 | 2018-08-03 05:30 | 2018-10-09 05:30 |  | Active | 2022-12-02 05:30 |  | 2023-01-05 05:30 |  | FALSE |  |  |  | Outsourced |  |  | CPZP034A2414 PhIV RWE China PASS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Keira Ding | Liju Ding | [66 empty] | Renal cell carcinoma | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034A_MA | CPZP034A2X01B | C1001729 | Phase IV | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2006-06-20 05:30 |  | 2005-12-19 05:30 |  | Completed |  | 2018-03-08 05:30 |  | 2018-05-30 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK |  | PhI-Solid Tumors-M_CPZP034A2X01B (105430 Rollover) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Vankayala, Vijay | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Yulia Hirschberg | Yulia Hirschberg | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Renal cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CPZP034B | CPZP034B1402 | C1001731 | Phase IV | Other |  |  |  | 2012-12-25 05:30 |  |  |  | 2012-12-25 05:30 | 2019-04-29 05:30 | 2012-09-04 05:30 |  | Completed | 2019-09-30 05:30 | 2017-04-30 05:30 | 2019-09-30 05:30 | 2019-09-30 05:30 | FALSE |  |  |  | Outsourced |  | VotrientÂ® Tablets (The drug use investigation) | CPZP034B1402 JPN PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | MINE KIMURA | MINE KIMURA | [66 empty] | Soft tissue neoplasm | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034C | CPZP034C2301 | C1001388 | Phase III | GSK | Other |  |  |  | DB Locked |  |  | 2009-05-26 05:30 | 2019-07-16 05:30 | 2016-06-16 05:30 |  | Completed |  |  |  | 2017-09-29 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A Phase III Study to Evaluate the Efficacy and Safety of Pazopanib Monotherapy Versus Placebo in Women Who Have not Progressed after First Line Chemotherapy for Epithelial Ovarian, Fallopian Tube, or Primary | CPZP034C2301 (110655 OVAR16)_PhIII-advOvarian/L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Parmar, Dhirendra | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther | Janet Taylor | Jennifer Omadoye | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [20 empty] | No | Global | Open | Yes | [16 empty] | None of the above
CPZP034D | CPZP034D2301 | C1001389 | Phase III | GSK | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2010-11-30 05:30 | 2019-07-16 05:30 | 2010-07-28 05:30 |  | Completed | 2019-04-30 05:30 | 2019-04-14 05:30 | 2019-05-28 05:30 | 2019-05-29 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A randomized, double-blind, placebo-controlled phase III study to evaluate the efficacy and safety of pazopanib as adjuvant therapy for subjects with localized or locally advanced RCC following nephrectomy | PhIII-AdjRCC/adjuvant-M_PZP034D2301(113387PROTECT) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Parmar, Dhirendra | Kumar, Amresh | Purra, Shashikanth | Ninan, Esther | Amy Zhou | Yan Zhou | [17 empty] | Sandeep Kadam | [28 empty] | TCS | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 600 | 1 | 0 |  | Renal cancer | No | Global | Completed | No | [16 empty] | None of the above
CPZP034A0 | CPZP034X2203 | C1001733 | Phase II | GSK | CRO - EDC |  |  | 2014-10-08 05:30 | DB Locked |  |  | 2014-10-08 05:30 |  | 2013-05-24 05:30 |  | Completed | 2019-11-26 05:30 |  | 2019-12-30 05:30 | 2020-01-17 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A Phase II Study of Pazopanib (GW786034, NSC# 737754) in Children, Adolescents and Young Adults with Refractory Solid Tumors | PhI/II-Pediatric Sarcomas -M_CPZP034X2203 (116731) | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Parmar, Dhirendra | Kumar, Amresh | Sonmale, Pravin | Ninan, Esther | Amy Zhou | Yan Zhou | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Sarcoma | No | Global | Wind Down | Yes | [16 empty] | None of the above
CQAB149B | CQAB149B1402 | C1001390 | Phase IV | Other |  |  |  | 2012-05-15 05:30 |  |  |  | 2012-05-15 05:30 | 2012-02-27 05:30 | 2012-02-27 05:30 |  | Completed | 2018-12-31 05:30 | 2015-09-29 05:30 | 2018-12-31 05:30 | 2018-12-18 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of Onblez in COPD | CQAB149B1402 JPN PMS | P8 Respiratory | [5 empty] | MAKOTO NAGASAKI | MAKOTO NAGASAKI | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQAS523A1 | CQAS523X2101 | C1200651 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-07-22 05:30 |  | 2015-05-05 05:30 |  | Completed | 2018-07-27 05:30 | 2018-05-20 05:30 | 2018-09-17 05:30 | 2018-07-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - MSD | First in human single and multiple dose escalation study of QAS523 for safety, tolerability, pharmacokinetics and pharmacodynamics in healthy adult volunteers | CQAS523X2101 FIH | N4 MSD - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Carolina Cunha | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Disuse muscle atrophy | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A1102 | C1001411 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-12-21 05:30 | 2019-01-24 05:30 | DB Locked | Final DBL Achieved |  | 2019-01-24 05:30 | 2018-10-22 05:30 | 2018-10-17 05:30 |  | Completed | 2019-03-15 05:30 | 2019-02-28 05:30 | 2019-05-20 05:30 | 2019-04-10 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP |  | CQAW039A1102 Japan FE | P8 Respiratory | Langlo, Francois | Ushijiama, Sachiko | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | Suzuki, Hiroko | Suzuki, Hiroko |  |  |  |  | Pre-DRM | Suzuki, Hiroko | Suzuki, Hiroko | Completed | Study Locked | Study Locked | Study Locked | 2019-01-16 05:30 | Legacy Process | Gandikota, Sree Lakshmi |  | Rohit Varate | Completed | 2019-01-16 | Not Applicable |  |  |  | 2019-01-17 05:30 | 2019-01-17 05:30 |  |  |  |  | The DDPASS meetinsg are conducted and received the confirmation from the team that all the data is clean. | 100 | RaveX - Inhouse | Yes |  | 2019-04-22 05:30 | 2019-04-25 05:30 | [9 empty] | NA | [5 empty] | 2 | 14 | 44 | -1 | 95 | 342 | 0 | 125 | 32 | 164 | 538 | 1 | 0 |  | Asthma | No | Global | Completed | Yes | [15 empty] | Agrawal, Naina | None of the above | Yes
CQAW039A0 | CQAW039A2107 | C1001399 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-07-05 05:30 |  | 2017-03-09 05:30 |  | Completed | 2018-09-18 05:30 | 2018-08-07 05:30 | 2018-10-19 05:30 | 2018-09-21 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | An open-label, single-dose, parallel group study to assess the pharmacokinitics of fevipiprant (QAW039) in patients with end-stage renal disease on hemodialysis and optionally in patients with severe to moderate and mild impairment compared to matched healthy volunteers including a cross-over assessment in end-statge renal disease patients on the effect of dialysis on fevipiprant paharmacokinitics | CQAW039A2107 Renal impairment study | P8 Respiratory | Langlo, Francois | Chamarthi, Yasaswini | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Therese Swan | Therese Swan | Joshi, Alekhya | [14 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [15 empty] | Yes | [5 empty] | Pharma | Novartis | InHouse | 2017-06-06 05:30 | 2017-06-06 05:30 |  |  | NA | [7 empty] | 125 | 0 |  |  | 0 |  |  |  | 413 | 1 | 0 |  | Renal impairment | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2108 | C1001400 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-05-31 05:30 |  | 2017-01-16 05:30 |  | Completed | 2019-04-24 05:30 | 2019-04-22 05:30 | 2019-07-03 05:30 | 2019-05-31 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | An open-label, single-dose, parallel-group study to assess the pharmacokinetics of Fevipiprant (QAW039) in patients with hepatic impairment compared to matched healthy subjects | CQAW039A2108 Hepatic impairment study | P8 Respiratory | Langlo, Francois | Bhoite, Raviraj Vijay | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Therese Swan | Therese Swan | Joshi, Alekhya | [14 empty] | Shah, Manasi |  | Rohit Varate | [12 empty] | I will schedule DDPASS session for this study soon. | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | InHouse | 2017-05-12 05:30 | 2017-05-12 05:30 |  |  | NA | [7 empty] | 87 | 0 |  |  | 0 |  |  |  | 378 | 1 | 0 |  | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2114 | C1001402 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-06-05 05:30 |  | 2017-03-20 05:30 |  | Completed |  | 2017-07-24 05:30 |  | 2017-10-27 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - RESP | An open-label, randomized, three-period, crossover study to determine the relative bioavailability of 225 mg fevipiprant (QAW039) of film-coated tablet, chewable tablet, and oral suspension formulations in healthy adult subjects | CQAW039A2114 Adult PK with Ped formulation | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [15 empty] | Kumar, Ranjeet |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | PPD | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2116 | C1001403 | Phase I | NCDS | [7 empty] | 2017-01-05 05:30 |  | 2016-12-14 05:30 |  | Completed |  | 2017-02-18 05:30 |  | 2017-03-31 05:30 | FALSE |  |  |  | ED Full Outsourced |  | An open-label, single sequence, cross-over study to evaluate the effect of cyclosporine on the pharmacokinetics of fevipiprant (QAW039) in healthy volunteers including an optional relative bioavailability part | CQAW039A2116 DDI Cyclosporin and iv microdose | P8 Respiratory | [5 empty] | Diego Albrecht; Elizabeth McNamara | Elizabeth McNamara | [66 empty] | Drug interaction |  | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2119 | C1001404 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2019-04-08 05:30 | 2019-04-01 05:30 | DB Locked | Final DBL Achieved |  | 2019-04-01 05:30 | 2018-06-25 05:30 | 2018-06-19 05:30 |  | Completed | 2019-05-06 05:30 | 2019-04-25 05:30 | 2019-07-22 05:30 | 2019-08-01 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP |  | CQAW039A2119 China PK | P8 Respiratory | Langlo, Francois | Gundu, Ananth Reddy | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Lihuei Kao | Joshi, Alekhya | Joshi, Alekhya |  |  | Updated to Locked as per DM BoW |  | DRM | Joshi, Alekhya | Joshi, Alekhya | Completed |  | Study Locked | Study Locked | 2019-05-16 05:30 | Legacy Process | Tidke, Shyam | Sahu, Ahallad | Rohit Varate | Completed | 2019-05-21 | Completed | 2019-05-22 05:30 | Study is locked | Pre-requisites not met | 2019-05-22 05:30 | 2019-05-22 05:30 | Pre-requisites not met | 2019-06-03 05:30 |  |  |  |  | RaveX - Inhouse | Yes | -NA- | 2019-10-26 05:30 | 2019-10-29 05:30 | [9 empty] | NA | [5 empty] | 2 | 21 | 49 | -1 | 139 | 419 | 0 | 146 | 35 | 264 | 718 | 0 | 0 |  | Asthma | No | Global | Completed | Yes | [10 empty] | 2019-08-22 05:30 | [5 empty] | None of the above
CQAW039A0 | CQAW039A2120 | C1001405 | Phase I | NCDS | CRO - EDC |  |  | 2018-04-13 05:30 | DB Locked |  |  | 2017-10-20 05:30 |  | 2017-07-13 05:30 |  | Completed | 2018-04-02 05:30 | 2017-12-12 05:30 | 2018-09-18 05:30 | 2018-03-12 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - RESP |  | CQAW039A2120 DDI Probenecid | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Wendy Weis | [15 empty] | Pagolu, Sahithi Venkata |  | Rohit Varate | [14 empty] | FSOM - Outsourced |  | -NA- | [11 empty] | IQVIA | [19 empty] | Drug interaction | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2121 | C1001406 | Phase I | NCDS | [7 empty] | 2016-01-12 05:30 |  | 2015-09-30 05:30 |  | Completed |  |  |  | 2016-08-05 05:30 | FALSE |  |  |  | IDMA Shared |  |  | High Dose SAD/MAD_CQAW039A2121 | P8 Respiratory | [6 empty] | David Workman | [66 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2123 | C1001407 | Phase I | NCDS | CRO - EDC |  |  | 2018-08-07 05:30 | DB Locked |  |  | 2018-08-07 05:30 | 2018-07-26 05:30 | 2018-06-25 05:30 |  | Completed | 2018-09-14 05:30 | 2018-09-07 05:30 | 2018-11-26 05:30 | 2018-11-27 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | An open-label, single sequence, cross-over study to evaluate the effect of fevipiprant (QAW039) on the pharmacokinetics of zidovudine and penicillin G in healthy subjects. | CQAW039A2123 DDI Study | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Cathy Gray | Catherine Gray | [15 empty] | Mettugari, Sai Krishna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK;#ZK02 | [11 empty] | IQVIA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 450 | 2 | 0 |  | Asthma | No | Global | Wind Down | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2125 | C1001409 | Phase I | NCDS | [7 empty] | 2017-02-24 05:30 |  | 2016-11-18 05:30 |  | Completed |  | 2017-06-23 05:30 |  | 2017-07-28 05:30 | FALSE |  |  |  | ED Full Outsourced |  | An open-label, randomized, two sequence, cross-over study to determine the bioequivalence between Fevipiprant (QAW039) film-coated tablets produced at pilot scale and full scale in healthy subjects | CQAW039A2125 BE with full production scale FCTs | P8 Respiratory | [5 empty] | Melissa Hackling | Melissa Hackling | [66 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2126 | C3001673 | Phase I | NCDS | CRO - EDC |  |  | 2018-10-10 05:30 | DB Locked |  |  | 2018-10-10 05:30 | 2018-06-19 05:30 | 2018-06-25 05:30 |  | Completed | 2019-04-22 05:30 | 2019-04-21 05:30 | 2019-05-24 05:30 | 2019-05-29 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | A randomized, partially blinded, placebo-, and positive-controlled (moxifloxacin), cross-over study to assess the effects of therapeutic and supratherapeutic doses of fevipiprant on corrected QTc intervals in healthy men | CQAW039A2126 Thorough QT Study | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Asthma | No | Global | Wind Down | Yes | [16 empty] | None of the above
CQAW039A0 | CQAW039A2127 | C3002807 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-09-19 05:30 | 2020-09-01 05:30 | DB On hold | Final DBL | 2022-07-25 05:30 |  | 2019-04-15 05:30 | 2019-04-01 05:30 |  | Completed | 2022-05-02 05:30 |  | 2022-07-25 05:30 |  | FALSE | Study was terminated before FPFV | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | Randomized, double blind, placebo-controlled, parallel design\nMoA to demonstrate fevipiprant effects on eosinophils in induced sputum in severe asthma patients \n | CQAW039A2127 Mechanistic Study | P8 Respiratory | Langlo, Francois | Ohtaka, Masahiro | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Kristin Belmore | Therese Swan | Oguri, Praveen | Oguri, Praveen |  |  |  |  | DRM | Oguri, Praveen | Oguri, Praveen | Completed | 13Jan2020 (SHRIVNI5): Study got cancelled. | Study Cancelled | Study Cancelled | 2019-10-14 05:30 |  | Varate, Rohit | Varate, Rohit | Rohit Varate | Completed | 2019-10-21 | Completed | 2019-10-23 05:30 | Study was terminated before FPFV |  | 2019-10-23 05:30 | 2019-10-23 05:30 | [5 empty] | 0 | RaveX - Inhouse | [13 empty] | NA | [5 empty] | 1 | 12 | 49 | -1 | 144 | 495 | 0 | 164 | 32 | 191 | 718 | 0 | 0 |  | Asthma | No | Global | Completed | Yes | [10 empty] | 2019-10-20 05:30 | [5 empty] | None of the above
CQAW039A | CQAW039A2128 | C4004939 | Phase I | NCDS | CRO - EDC |  |  | 2019-07-01 05:30 | DB Locked |  |  | 2019-07-01 05:30 | 2019-06-14 05:30 | 2019-06-07 05:30 |  | Completed | 2019-08-22 05:30 | 2019-09-03 05:30 | 2019-10-15 05:30 | 2019-10-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP | A drug interaction study with acid reducing agent (PPI) | CQAW039A2128 DDI Acid Reducer Study | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Catherine Gray | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Asthma | No | Global | Wind Down | Yes | [16 empty] | None of the above
CQAW039A | CQAW039A2214 | C1001391 | Phase II | NCDS | [7 empty] | 2013-03-12 05:30 |  | 2013-01-25 05:30 |  | Completed |  | 2016-02-04 05:30 |  | 2016-03-14 05:30 | FALSE |  |  |  | IDMA Shared |  | A double-blind, placebo-controlled, study examining the effect of orally administered QAW039 (450 mg QD) on FEV1 and ACQ in non-atopic, asthmatic patients with a baseline, pre-bronchodilator FEV1 of 40-80% predicted, inadequately controlled with low dose ICS therapy | CQAW039A2214 Safety and Efficacy | P8 Respiratory | [5 empty] | Sarita Barsainya | Sarita Gajendrapratap Barsainya | [66 empty] | Asthma |  | Global | Completed | Yes | [16 empty] | None of the above
CQAW039A | CQAW039A2307 | C1001392 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2015-12-11 05:30 |  | 2015-08-05 05:30 |  | Completed | 2019-11-14 05:30 | 2019-11-04 05:30 | 2019-12-03 05:30 | 2019-12-04 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 52-week, multicenter, randomized, double-blind, placebo-controlled study to assess the efficacy and safety of QAW039 when added to existing asthma therapy in patients with uncontrolled severe asthma | CQAW039A2307 52 wk excaberation in Severe Asthma | P8 Respiratory | Mahajan, Vinay | Singh, Parul | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Diane Bonagura; Janet Taylor | Diane Bonagura | Bonam, Rajesh Babu | Samuel, Giftson | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | DV;#SV |  |  |  |  | Pharma | Novartis | InHouse | 2015-11-04 05:30 | 2015-11-04 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | NA | [7 empty] | 114 | 0 |  |  | 0 |  |  |  | 749 | 8 | 0 |  | Asthma | Yes | Global | Open | Yes | [16 empty] | None of the above
CQAW039A | CQAW039A2314 | C1001393 | Phase III | NCDS | OC RDC - Inhouse |  | 2015-12-03 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-12-03 05:30 |  | 2015-08-05 05:30 |  | Completed | 2019-08-01 05:30 | 2019-08-02 05:30 | 2019-08-28 05:30 | 2019-08-27 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 52-week, multicenter, randomized, double-blind, placebo-controlled study to assess the efficacy and safety of QAW039 when added to existing asthma therapy in patients with uncontrolled severe asthma | CQAW039A2314 52 wk excaberation in Severe Asthma | P8 Respiratory | Mahajan, Vinay | Singh, Parul | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Diane Bonagura; Volker Moeckel | Volker M��ckel | Nikhare, Aparna | [14 empty] | Nagalla, Lakshmi Naga Lavanya |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | InHouse | 2015-11-17 05:30 | 2015-11-17 05:30 | Kanchi, Pavan kumar | Gehlawat, Priya | NA | [7 empty] | 114 | 0 |  |  | 0 |  |  |  | 745 | 14 | 0 |  | Asthma | Yes | Global | Open | Yes | [14 empty] | DBL | Polagoni, Bharghavi | None of the above | Yes
CQAW039A | CQAW039A2315 | C1001394 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-12-15 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-03-21 05:30 |  | 2016-11-04 05:30 |  | Completed | 2020-04-28 05:30 | 2020-03-16 05:30 | 2020-05-06 05:30 | 2020-04-07 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A two treatment epoch, randomized placebo-controlled, multi-centered parallel group study to assess the safety of QAW039 when added to existing asthma therapy in patients with uncontrolled severe asthma. | CQAW039A2315 Safety Extension | P8 Respiratory | Mahajan, Vinay | Medisetti, Yugeshwar | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Mary Smolen | Nikhare, Aparna | Shewane, Roshni | Completed | 2020-04-07 05:30 | Study Transitioned to Roshni Shewane on 07-Apr-2020 | [10 empty] | Manoharan, Vivek |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | DV;#SV |  |  |  |  | Pharma | Novartis | ICON | 2017-02-17 05:30 | 2017-02-17 05:30 | Shewane, Roshni | Meda, Sreelakshmi | NA | [7 empty] | 85 | 0 |  |  | 0 |  |  |  | 609 | 5 | 0 |  | Asthma | Yes | Global | Wind Down | Yes | [16 empty] | None of the above
CQAW039A | CQAW039A2316 | C1001395 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-09-11 05:30 |  | DB Locked |  |  | 2017-11-01 05:30 |  | 2017-05-12 05:30 |  | Completed | 2019-08-01 05:30 | 2019-07-30 05:30 | 2019-10-03 05:30 | 2019-09-06 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | DF RESP | A 12-week, multicenter, randomized, double-blind, placebo controlled study to assess the efficacy and safety of QAW039 when added to standard-of-care asthma therapy in patients with uncontrolled asthma. | CQAW039A2316 12 week lung function study | P8 Respiratory | Mahajan, Vinay | Rajguru, Gaurav | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Edna Cahill | Edna Cahill | Nikhare, Aparna | [14 empty] | Chakravarthy, Meghna |  | Sushant Sundar | [13 empty] | 90 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | InHouse | 2017-09-11 05:30 | 2017-09-11 05:30 | Gehlawat, Priya | Mareedu, Vasu | NA | [7 empty] | 75 | 0 |  |  | 0 |  |  |  | 587 | 10 | 0 |  | Asthma | Yes | Global | Open | Yes | [16 empty] | None of the above
CQAW039A | CQAW039A2317 | C1001396 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-10-10 05:30 | 2019-06-03 05:30 | DB Locked |  |  | 2017-10-31 05:30 |  | 2017-05-12 05:30 |  | Completed | 2019-08-02 05:30 | 2019-08-01 05:30 | 2019-09-11 05:30 | 2019-09-11 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | DF RESP | A 12-week, multicenter, randomized, double-blind, placebo controlled study to assess the efficacy and safety of QAW039 when added to standard-of-care asthma therapy in patients with uncontrolled asthma. | 12 week lung function study_CQAW039A2317 | P8 Respiratory | Mahajan, Vinay | Rajguru, Gaurav | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Vishal Mishra | Vishal Mishra | Nikhare, Aparna | [14 empty] | Nagalla, Lakshmi Naga Lavanya |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | YR |  |  |  |  | Pharma | Novartis | InHouse | 2017-10-10 05:30 | 2017-10-10 05:30 | Gehlawat, Priya | Mareedu, Vasu | NA | [7 empty] | 75 | 0 |  |  | 0 |  |  |  | 587 | 10 | 0 |  | Asthma | Yes | Global | Completed | Yes | [14 empty] | DBL | Kommu, Ranjith Kumar | None of the above | No
CQAW039A_MA | CQAW039A2322 | C3001795 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-01-16 05:30 | 2019-04-04 05:30 | DB Locked | Final DBL Achieved |  | 2019-03-26 05:30 | 2018-09-20 05:30 | 2018-08-08 05:30 |  | Completed | 2020-06-11 05:30 | 2020-06-10 05:30 | 2020-07-27 05:30 | 2020-07-27 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, randomized, double-blind, parallel-group, placebo-controlled study of fevipiprant once daily plus standard-of-care (SoC) for assessment of the efficacy in reduction of nasal polyps size in patients with nasal polyposis and concomitant asthma | CQAW039A2322 Nasal P | P8 Respiratory | Mahajan, Vinay | Vithanala, Kiran Kumar | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | David Steele | David Steele | Yadav, Santosh | Munukutla, Valli |  |  | Final lock 27Jul2020 |  | DRM (DIAL) | Yadav, Santosh | Govula, Shashikanth | Completed | 7JAN2021: SG: No upcoming tasks. 09Mar2020 : As per the discussion with the DATs and SDTM team no update required for Re-screen. No action required on RF. 02Mar2020 : Request to update Re-screen to XI. DATS approval received | None | None | 2019-03-21 05:30 | Transition Study and Legacy Process | Sundar, N Sushant | Agavekar, Amit | Sushant Sundar | Completed | 2019-03-26 | Completed | 2019-07-22 05:30 | The list of domains for DIAL are - AE, CM, DD, DM, DS, DV, EC, ​EG, FA​MH, IE, MH, QS, VS and SV.​​ |  | 2019-03-26 05:30 | 2019-03-26 05:30 |  | 2019-08-21 05:30 |  |  |  |  | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 8 | 9 | 42 | 0 | 84 | 453 | 0 | 149 | 33 | 158 | 644 | 7 | 0 |  | Asthma; Nasal polyps | Yes | Global | Open | Yes | [10 empty] | 2019-05-30 05:30 | [5 empty] | None of the above
CQAW039A_MA | CQAW039A2323 | C3000165 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-10-26 05:30 | 2018-12-10 05:30 | DB Locked | Final DBL Achieved |  | 2018-12-13 05:30 | 2018-07-10 05:30 | 2018-07-10 05:30 |  | Completed | 2020-02-17 05:30 | 2020-02-28 05:30 | 2020-05-20 05:30 | 2020-05-22 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 52-week, multicenter, randomized, double-blind, double-dummy, parallel-group, placebo-controlled study of fevipiprant once daily plus standard-of-care (SoC) for reduction of systemic corticosteroids (oral and parenteral) use in patients with severe asthma | CQAW039A2323 SHIELD | P8 Respiratory | Mahajan, Vinay | Gijo, Ani | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Ioannis Strigkas | Nicolas Horovitz | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR |  |  | CQAW039A2323 Final Database Lock was completed on 22nd MAY 2020 |  | DRM (DIAL) | Singh, Prasoon | Maricherla, Vijayroshan | Completed | 01Apr2020: LSH setup completed. No pending activity. 07Feb2020: All the DTSs included in RF and sent for SMT development on 04Feb2020 14 jan 20: Awaiting DTS files from Lead DBP and TDM. Follow up sent again today for the same. 26Nov2019: Updated rule file to include EG DTS and made few corrections. Sent for Rule file Peer Review on 25Nov2019. | None | None | 2018-09-21 05:30 |  | Sundar, N Sushant | Sahu, Ahallad | Sushant Sundar | Completed | 2018-12-10 | Completed | 2019-07-22 05:30 |  |  | 2018-12-10 05:30 | 2018-12-10 05:30 |  | 2019-08-21 05:30 |  |  |  | 29 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 8 | 12 | 39 | 0 | 76 | 493 | 0 | 161 | 35 | 143 | 671 | 9 | 0 |  | Asthma | No | Global | Wind Down | Yes | [10 empty] | 2019-05-29 05:30 | [5 empty] | None of the above
CQAW039A0 | CQAW039B2104 | C1001410 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-05-09 05:30 |  | 2017-01-30 05:30 |  | Completed |  | 2017-07-27 05:30 |  | 2017-09-07 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | Study to analyze the expression of the DP2 receptor on peripheral blood eosinophils in healthy volunteers of different age groups | CQAW039B2104 Single blood draw cellular biomarker | P8 Respiratory | Langlo, Francois | Sharma, Anju | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Sarah Cross | [15 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [13 empty] | NA | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQAW039B | CQAW039B2201 | C1001412 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-02 05:30 | 2019-04-30 05:30 | DB Locked | Final DBL Achieved |  | 2019-05-01 05:30 | 2018-06-15 05:30 | 2018-07-18 05:30 |  | Completed | 2020-07-23 05:30 | 2020-01-22 05:30 | 2020-03-04 05:30 | 2020-03-11 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, open-label, 8 day treatment study to assess the pharmacokinetics, safety and tolerability of fevipiprant delivered via once daily chewable tablet in children aged 6 to &lt;12 years with asthma | CQAW039B2201 Ped Asthma 6-12 | P8 Respiratory | Mahajan, Vinay | Rajguru, Gaurav | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Michele Valentin | Michele Valentin | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR |  |  |  |  | DRM (DIAL) | Singh, Prasoon | Oguri, Praveen | Completed | 05Nov2020: No Activity. 11Sep2020: No Activity 01Apr2020 : Reassigned RF from Roshan to Praveen 01Apr2020: No pending activity 03Mar2020: LSH setup completed. 07Feb2020 : Rule file updated to include pending forms and sent for SMT development on 03Feb2020 23Jan2020 : Will be sent for peer review today 14 Jan 20: Updated Rule file for adding ECG003_1,ECG003_3 . Awaiting UAT SOD to initiate peer review. 09 Jan 20: Initiated updation of rule file. Awaiting DBD to confirm transition details | None | None | 2019-01-11 05:30 |  | Tidke, Shyam | Chitransh, Arpit | Sushant Sundar | Completed | 2019-01-16 | Completed | 2019-05-15 05:30 |  |  | 2019-01-15 05:30 | 2019-01-15 05:30 |  | 2019-07-23 05:30 |  |  | No Data |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 5 | 5 | 48 | 0 | 57 | 404 | 0 | 136 | 38 | 216 | 658 | 2 | 0 |  | Asthma | Yes | Global | Wind Down | Yes | [10 empty] | 2019-05-15 05:30 | [5 empty] | HA Commitment
CQAW039E1 | CQAW039E12201 | C4002194 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-05-16 05:30 | 2019-05-27 05:30 | 2019-05-24 05:30 | DB Locked | Final DBL Achieved |  | 2019-05-21 05:30 | 2019-01-10 05:30 | 2019-01-09 05:30 |  | Completed | 2020-01-16 05:30 | 2020-01-16 05:30 | 2020-03-27 05:30 | 2020-04-30 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A multi-center, proof-of-mechanism study of multiple, oral doses of fevipiprant (QAW039) in COPD patients with sputum eosinophilia | CQAW039E12201 PIE POC in EOS COPD | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Kristina Wagner; Natalia Baginski | Natalia Baginski | Rao, S Shashikanth | Rao, S Shashikanth |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 16May2019 |  | DRM | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 06-Jul-2020: No pending issues. 27Mar2020 : Pending form FAMHR001_TR included in RF version 4.0 and raised SNOW ticket RITM1208250 09Mar2020 : received SDTM annotations from DBD for pending form. 03Mar2020: Requested DBP to follow up with SDTM programmer on annotations for FAMHR001_TR form 17Feb2020 : FAMHR001_TR form to be included in RF. No data available so far in FA in EDC. 05Feb2020 : RF 2.0 in credi with LB and RE DTS 21-Jan-2020(Kranthi): Shashi has to upload the RF Version 2.0 in CREDI with all the domains/DTS missing in earlier version 29th Nov 19- (Shashi) LB and RE third party data domain to be included in RF. DTS not yet finalized. | None | None | 2019-08-01 05:30 | Legacy Process | Girvasiya, Shaili | Kadam, Sandeep | Rohit Varate | Completed | 2019-07-23 | Completed | 2019-08-14 05:30 | ​ |  | 2019-08-16 05:30 | 2019-08-16 05:30 | Pre-requisites not met | [5 empty] | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 7 | 7 | 63 | -1 | 92 | 392 | 8 | 151 | 33 | 254 | 679 | 4 | 0 |  | Chronic obstructive pulmonary disease | Yes | Global | Terminated | Yes | [10 empty] | 2019-08-14 05:30 | [5 empty] | None of the above
CQBW251A0 | CQBW251A2102 | C3000296 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-09 05:30 | 2018-11-07 05:30 | DB Locked | Final DBL Achieved |  | 2018-11-07 05:30 | 2018-06-29 05:30 | 2018-08-17 05:30 |  | Completed | 2019-01-07 05:30 | 2019-01-06 05:30 | 2019-02-20 05:30 | 2019-02-25 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP |  | CQBW251A2102 hADME | P8 Respiratory | Langlo, Francois | Chamarthi, Yasaswini | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | Govula, Shashikanth | Govula, Shashikanth |  |  |  |  | Pre-DRM | Govula, Shashikanth | Govula, Shashikanth | Completed | 8JAN2021: SG: Study locked. No upcoming tasks. | None | None | 2018-12-14 05:30 | Legacy Process | Sundar, N Sushant |  | Rohit Varate | Completed | 2018-12-19 | Not Applicable |  | FPFV date in DM BOW incorrect. Followed up with PDM | DRM is not applicable for the study. Study was locked before DRM went live | 2018-12-19 05:30 | 2018-12-19 05:30 | Retrospective DRM studies |  |  |  |  | 100 | RaveX - Inhouse | Yes |  | 2019-04-10 05:30 | 2019-04-12 05:30 | [9 empty] | NA | [5 empty] | 2 | 24 | 41 | -1 | 183 | 377 | -123 | 123 | 31 | 171 | 579 | 1 | 0 |  | Cystic fibrosis | No | Global | Completed | Yes | [15 empty] | Kadam, Sandeep | None of the above | Yes
CQBW251A0 | CQBW251A2103 | C3000299 | Phase I | NCDS | CRO - EDC |  |  | 2018-11-06 05:30 | DB Locked |  |  | 2018-11-06 05:30 | 2018-08-13 05:30 | 2018-07-13 05:30 |  | Completed | 2018-12-31 05:30 | 2018-12-24 05:30 | 2019-03-28 05:30 | 2019-02-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CQBW251A2103 BA with FMI | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Cystic fibrosis | No | Global | Wind Down | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251A2104 | C3000298 | Phase I | NCDS |  |  |  | 2020-10-30 05:30 |  | Final DBL | 2022-10-05 05:30 | 2020-10-30 05:30 | 2020-08-12 05:30 | 2020-08-11 05:30 |  | Active | 2022-08-30 05:30 |  | 2022-10-05 05:30 |  | FALSE |  |  |  | FULL Outsourced |  | A phase 1, open-label, single-dose, parallel group study to evaluate the pharmacokinetics of QBW251 in subjects with mild, moderate or severe hepatic impairment compared to healthy control subjects | CQBW251A2104 Hepatic Impairment | P8 Respiratory | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251A2105 | C3000297 | Phase I | NCDS |  |  |  | 2020-07-24 05:30 |  |  |  | 2020-07-16 05:30 | 2020-06-23 05:30 | 2020-06-26 05:30 |  | Completed | 2021-02-16 05:30 | 2021-02-16 05:30 | 2021-04-27 05:30 | 2021-03-26 05:30 | FALSE |  |  |  | FULL Outsourced |  |  | CQBW251A2105 TQT | P8 Respiratory | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251A2106 | C3001192 | Phase I | Other |  |  |  | 2022-05-10 05:30 |  | Final DBL | 2022-09-14 05:30 |  | 2021-07-16 05:30 | 2021-07-16 05:30 |  | Planned | 2022-08-02 05:30 |  | 2022-09-14 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CQBW251A2106 QBW as victim (UGT DDI) | P8 Respiratory | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251A2107 | C3001808 | Phase I | Other | CRO - EDC |  |  | 2021-04-05 05:30 | DB Conduct |  |  | 2021-03-31 05:30 | 2021-04-05 05:30 | 2021-03-05 05:30 |  | Active | 2021-08-10 05:30 | 2021-05-18 05:30 | 2021-08-18 05:30 | 2021-07-19 05:30 | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CQBW251A2107 QBW as perpetrator (CYP DDI) | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Wendy Weis | Wendy Weis | [17 empty] | Rohit Varate | [28 empty] | Celerion | [19 empty] | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251A2108 | C3000510 | Phase I | Other |  |  |  | 2022-05-31 05:30 |  | Final DBL | 2022-09-13 05:30 |  | 2022-05-02 05:30 |  |  | Planned | 2022-08-02 05:30 |  | 2022-09-13 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CQBW251A2108 PPI or other DDI (based on hADME) | P8 Respiratory | [6 empty] | Wendy Weis | [54 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  |  | Global | Open | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251B1101 | C1001734 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-11-29 05:30 | 2018-04-18 05:30 | DB Locked |  |  | 2017-12-04 05:30 |  | 2017-10-03 05:30 |  | Completed | 2018-03-05 05:30 | 2018-03-02 05:30 | 2018-04-23 05:30 | 2018-04-20 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA Shared JP | NIBR - RESP | A randomized, placebo-controlled, subject-blinded study to assess the safety, tolerability and pharmacokinetics of\nsingle ascending doses and multiple doses of QBW251 in\nJapanese healthy subjects | CQBW251B1101 Japan ES | P8 Respiratory | Langlo, Francois | Nishi, Nahoko | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | Samuel, Giftson | [14 empty] | Kumar, Ranjeet |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | Pharma | Novartis | InHouse | 2017-11-28 05:30 | 2017-11-28 05:30 |  |  | NA | [7 empty] | 117 | 0 |  |  | 0 |  |  |  | 580 | 1 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Completed | Yes | [16 empty] | None of the above
CQBW251A0 | CQBW251B2102 | C3001807 | Phase I | Other |  |  |  | 2022-11-10 05:30 |  | Final DBL | 2022-12-06 05:30 |  | 2022-09-21 05:30 |  |  | Planned | 2022-10-11 05:30 |  | 2022-12-06 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CQBW251B2102 COPD conmeds (rosuvastatin DDI) | P8 Respiratory | [5 empty] | Pascale Pinot | Pascale Emilie Genevi��ve Pinot | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251B | CQBW251B2103 | C3001834 | Phase I |  |  |  |  | 2023-07-05 05:30 |  | Final DBL | 2023-10-17 05:30 |  | 2022-08-26 05:30 |  |  | Planned | 2023-09-12 05:30 |  | 2023-10-17 05:30 |  | FALSE |  |  |  | ED Undecided Sourcing |  |  | CQBW251B2103 China PK | P8 Respiratory | [5 empty] | Jamie Zhou; Katie Li | Shiyang Zhou | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CQBW251B | CQBW251B2104 | C4008775 | Phase I | Other |  |  |  | 2020-12-21 05:30 |  |  |  | 2020-12-21 05:30 | 2020-11-20 05:30 | 2020-12-04 05:30 |  | Completed | 2021-03-26 05:30 | 2021-02-08 05:30 | 2021-03-30 05:30 | 2021-04-07 05:30 | FALSE |  |  |  | FULL Outsourced |  |  | CQBW251B2104 Relative BA Study_FMI2 vs FMI3 (CM) | P8 Respiratory | [5 empty] | Wendy Weis | Wendy Weis | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251B | CQBW251B2201 | C3001687 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-06-10 05:30 | 2019-08-27 05:30 | 2019-09-23 05:30 | DB Conduct | Final DBL | 2022-03-01 05:30 | 2019-09-12 05:30 | 2019-03-22 05:30 | 2019-03-28 05:30 |  | Active | 2022-02-01 05:30 |  | 2022-03-01 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 24-week multi-center, double-blind, placebo controlled Dose-range finding study to investigate the efficacy and Safety of oral QBW251 in COPD patients on triple inhaled Therapy (LABA/LAMA/ICS) | CQBW251B2201 Ph II 26wk DRF | P8 Respiratory | Mahajan, Vinay | Vithanala, Kiran Kumar | Dubey, Rohit | Sahu, Vandana | Hiriyanna, Srinivas | Diane Bonagura | Diane Bonagura | Bakka, Sandeep | Bakka, Sandeep |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 10Jun2019 |  | DRM | Govula, Shashikanth | Bai, Chandrakala | Completed | 05Jan2022:No RF update hence created SNOW#51- RITM3350908 for PPC#13 updates in SMT/LSH. 31May2021:The forms SUG001 and SUS001 were in the initial release and were later replaced with SUS004 and SUS005. DBD confirmed this will be handled in the next upcoming PPC - removing SUG001 and SUS001 from the study database as these are mentioned in the 'Excluded forms' of RF . 07-May-2021: Rule File version 5.0 is finalized for the PPC#10 updates. SUG001 and SUS001 : Mentioned in excluded forms-Pages are active in study. However they are not mapped to any visit. DBP has confirmed that these will be inactivated in the next PPC. 05-May-2021: The forms SUG001 and SUS001 were in the initial release and were later replaced with SUS004 and SUS005. We will get them removed in the next PPC confirmed DBD(Sandeep Bakka). 7JAN2021: SG: No upcoming tasks. after DB-GO LIVE at 27aug2019 rule file is completed on 11oct2019 and there was update to the same in all forms row and updated rulefile was given at 14thoct2019 and SMT files received on 18oct2019 | None | None | 2019-10-11 05:30 | SDTM annotations delayed | Challa, Nandini | Agavekar, Amit | Sushant Sundar | Completed | 2019-10-14 | Completed | 2019-10-18 05:30 | @20Sep: Released for Peer Review. Will finalize in the following week. snow 05 Ticket raised but pending rule file and SMT files | Pre-requisites not met | 2019-10-18 05:30 | 2019-10-18 05:30 | KPI met - incorrect source date entry (example FPFV) | 2019-11-26 05:30 |  |  | ZW is thirdpart data for which test transfer is not yet received so not eyt reviewed Major issues with VISITNUM and EPOCH faced-SOURCE CODE UPDATE WAS DONE at LSH level to consider UN% also as unplannend issue with - not poopulating As expected in Numeric RERESN column, Study fix is implented Usubjid-not populating for records with unplanned thirdparty-SMT was update to flow SUBJID downstream FATESTCD=CPXPTR/LSTEXC as these are not in the reference test category, Kindly check with the TDM and standards team couple of data issues which has been Clarifed | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 13 | 13 | 55 | 0 | 107 | 640 | 0 | 194 | 34 | 171 | 845 | 15 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [10 empty] | 2019-10-18 05:30 | [5 empty] | GDD annual target
CQBW251B | CQBW251B2202 | C1202099 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-10-15 05:30 | 2020-06-12 05:30 | 2020-09-10 05:30 | DB Conduct | Final DBL | 2023-03-09 05:30 | 2020-09-10 05:30 | 2019-10-02 05:30 | 2019-10-02 05:30 |  | Active | 2023-01-06 05:30 |  | 2023-03-09 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | Mechanistic MoA study in COPD pats ( A randomized, subjects and investigator blinded, placebo controlled parallel group study to assess the mode of action of QBW251 in patients with Chronic Obstructive Pulmonary Disease (COPD)) | CQBW251B2202 MoA in COPD | P8 Respiratory | Langlo, Francois | Marripati, Sai Amrutha | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Chiara Pazzagli; Leslie Taylor | Leslie Taylor | R, Ankit | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 15Oct2019 |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 1Dec2021: RF (Version 9.0) for PPC 06 finalized and SNOW51 ticket raised on 12Nov2021 (SNOW51 Ticket number - RITM3182221). However, there was an error in the RF. The error rectified and RF updated and RF Version 10.0 was finalized on 25Nov2021. 26May2021 : Reassigned the study from Praveen Oguri to Pratheeksha. 26-Apr-2021: MO1L DTS added in RF, finalized on 16-Apr-2021 and raised SNOW51 ticket RITM2472359. 19-Apr-2021: MB1L DTS is included in RF Version 7.0 and finalized on11-Mar-2021. Added MO1L and Version 8.0 is in peer review process. 16-Feb-2021: RF Version 6.0 finalized (RITM2270539). 15-Feb-2021: ECG003_1 CRF added in RF Version 6.0 and shared with team for peer review. 05Nov2020: RF Finalized and raised SNOW ticket on 23Oct2020. 05Oct2020 : QS6L, QS7L included in RF and SNOW raised. 24-Sep-2020: Updated RF to include QS6L, QS7L and shared with team for peer review. This is flagged in report 22Sep. 11Sep2020: No Activity. 23JUN2020: RF has been finalized on 19JUN20 and SNOW 05 request has been created. 12May2020 : received updated ALS on 07th for updating RF. Assessing the changes to update the RF as RF was ready and new upadtes done in DB. 19-Mar-2020: Peer review feedback to be addressed by 19-Mar-2020. Study RF activities assigned to Praveen from Shashi as Praveen developed the RF. Notified the DBD. 05Mar2020 : Peer review feedback received from Sujan. 02Mar2020 : Praveen has developed the RF and sent for peer review on 25Feb2020. Sujan performing peer review. 12Feb2020 : Kranthi/Praveen will support RF in Shahsi's Absence 10Feb2020 : All the SS forms reviewed and RF tentatively completed by 12Feb2020. Golive date will be pushed as there is no clarity on COPD medication page. Team to update on exact go-live date 30-Dec-2019: Received required documents. Planned release to Peer review 21-Jan. 17-Dec: Uniques to be finalized by 20-Dec. | None | None | 2020-06-19 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-06-22 | Completed | 2020-06-29 05:30 | SNOW05 raised on 19th June, 2020. 22nd June 2020 : Rule file validation failed for CM and ODM domains, information communicated to RFD. 29th June 2020 : Except ODM and CM, other domains DRM setup is completed and published . |  | 2020-06-29 05:30 | 2020-06-29 05:30 |  | 2020-08-25 05:30 |  |  | DDPASS 1 rescheduled to 9th Nov, 2020 as per availability. [RAMACHA1, 2nd Feb, 2021] 3 rounds of DDPASS were conducted. 4 domains have passed. 7 domains failed, issues are being resolved by TDM. Rest of the domains does not contain sufficient data for review. It will be reviewed when the data is available. [RAMACHA1, 16th Feb, 2021] 8 domains passed review. 7 domains failed review, it is being followed upon by TDM and third party vendor. 7 other domains do not have sufficient data for review. [RAMACHA1,10JUN2021] 3 new domains were added (third party domains). Follow up meeting is scheduled for 16JUN2021 | 36 | RaveX - Inhouse | Yes | -NA- |  |  |  | [RAMACHA1, 2021JUL26] PPC5 SNOW51 (RITM2806024) was raised on 26th Jul, 2021. [RAMACHA1, 2021JUL28] PPC5 implementation was completed by 28th and DDPASS was scheduled for 30th July, 2021. | [7 empty] | NA | [5 empty] | 7 | 7 | 62 | 0 | 106 | 591 | 0 | 178 | 32 | 212 | 835 | 13 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [10 empty] | 2020-06-29 05:30 |  |  |  |  | Adi, Vishnupriya | None of the above | Yes
CQBW251B | CQBW251B2301 | C3001721 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-02-01 05:30 | Study Planned | Final DBL | 2024-11-20 05:30 |  | 2022-09-16 05:30 |  |  | Planned | 2024-09-11 05:30 |  | 2024-11-20 05:30 |  | FALSE | None | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQBW251B2301 PhIII pivotal 1_24 wk | P8 Respiratory | Molander, Lei Ann | Sahu, Vandana | Sahu, Vandana | Sahu, Vandana | Hiriyanna, Srinivas |  | Diane Bonagura | [17 empty] | Sushant Sundar | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251B | CQBW251B2302 | C3002688 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-05-08 05:30 | Study Planned | Final DBL | 2025-04-04 05:30 |  | 2022-10-03 05:30 |  |  | Planned | 2025-01-24 05:30 |  | 2025-04-04 05:30 |  | FALSE | None | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQBW251B2302 PhIII pivotal 2_24 wk study | P8 Respiratory | Molander, Lei Ann | Sahu, Vandana | Sahu, Vandana | Sahu, Vandana | Hiriyanna, Srinivas | Diane Bonagura | Diane Bonagura | [17 empty] | Sushant Sundar | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQBW251B | CQBW251B2303 | C4012656 | Phase III | NCDS_2 |  |  |  | 2023-10-02 05:30 |  | Final DBL | 2026-07-31 05:30 |  | 2023-01-20 05:30 |  |  | Planned | 2026-06-19 05:30 |  | 2026-07-31 05:30 | [5 empty] | InHouse |  |  | QBW251B2303 PhIII pivotal_52wks_exab study | P8 Respiratory | [6 empty] | Diane Bonagura | [54 empty] | 40 | [7 empty] | 800 | 8 |  |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes
CQBW251B | CQBW251B2304 | C4012697 | Phase III | NCDS_2 |  |  |  | 2023-05-15 05:30 |  | Final DBL | 2025-07-18 05:30 |  | 2023-01-26 05:30 |  |  | Planned | 2025-06-06 05:30 |  | 2025-07-18 05:30 | [5 empty] | InHouse |  |  | CQBW251B2304 Ph3_24 wks_ COPD w/o prior Exab | P8 Respiratory | [6 empty] | Diane Bonagura | [54 empty] | 40 | [7 empty] | 800 | 8 |  |  | Chronic obstructive pulmonary disease | No | Global | Open | Yes
CQBW251C1 | CQBW251C12201 | C4001539 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-01-19 05:30 | 2021-01-21 05:30 | 2021-01-29 05:30 | DB Conduct | Final DBL | 2024-01-30 05:30 | 2021-02-02 05:30 | 2020-01-17 05:30 | 2020-01-15 05:30 | 2020-12-18 05:30 | Active | 2023-11-30 05:30 |  | 2024-01-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, patient- and investigator-blinded, placebo-controlled, parallel group study to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of QBW251 in patients with bronchiectasis | CQBW251C12201 QBW251 Bronchiectasis | N5 DAx - NIBR | Langlo, Francois | Bhole, Prajakta Baban | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Katie Li | Yaliang Li | Bonam, Rajesh Babu | Iliyas, Mohamed | Not Started |  | Oct-2021 : Pallabi transitioned stud to Iliyas |  | DRM | Sama, Ashok | Shrivastava, Nikhil | Completed | 07-Feb-2022: DTS table MO1L included in RF V4.0 and finalized in CREDI. SNOW-51 (RITM3464639) raised and notified the LSP. 04-Oct-2021: TDM updated the DTS and finalized the next versions. Rule File V3.0 finalized WRT all 9 final DTS. Snow-51 is raised and LSP has been notified. 13-Sep-2021: 9 DTS (LB1L, LB2L, EG1L, RE1L, QS1L, QS2L, QS3L, QS4L and QS5L) are final in CREDI but RF programmer is not informed. Reviewed all the DTS now and shared the comments with DBD and TDM. 8-July-2021: RF V2.0 updated and finalized WRT PPC#01 for including new form (DSG005). SNOW-51 raised and LSP is notified. 08-June-2021: Reviewed the PPC form and provided the comments. Waiting for the input documents to start the RF update. 21-Jan-2021: Rule File V1.0 created and finalized in CREDI. SNOW-05 ticket raised and notified both LSP and SMT programmers. 12-Jan-2021: Created and reviewed Rule File V0.1 and released for peer review. Waiting for Peer Review Comment. 12-Jan-2021: DBD updated the database for most of the comments but for some comments database is still not updated. Requested DBD to update the database and provide updated ALS and SOD of UAT environment. 06-Jan-2021: Reviewed all the CRF forms, SRF and SDTM annotations. Provided my comments to DBD. Waiting for his reply. 26Nov2020: Backup: Rehana Whats planned: No documents have been received yet. 12-Nov-2020: DBD confirmed that GoLive date is shifted to 19th Jan 2021. SRF is not yet approved. DBD will share the documents in the 1st week of Dec. 28-Oct-2020 (SHRIVNI5): DBD informed that GoLive is pushed to Jan 2021 but has not yet confirmed the exact goLive date. Not yet received any document from DBD. 17-Sep-2020 (SHRIVNI5): Sent mail to study DBD to provide study status and study related documents. Waiting the reply. 02Apr20 : Reassigned from Ashok to Nikhil as Golive moved from June to Oct. | None | None | 2021-01-21 05:30 | RF finalized within Go-live + 5 days | Ramayanam, Vinay | Varate, Rohit | Rohit Varate | Completed | 2021-02-08 | Completed | 2021-02-09 05:30 |  | Rule file had issues, prerequisite not met | 2021-02-16 05:30 | 2021-02-17 05:30 |  | 2021-01-16 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 7 | 54 | 0 | 94 | 624 | 0 | 200 | 39 | 176 | 839 | 5 | 0 |  | Bronchiectasis | No | Global | Open | Yes | [10 empty] | 2021-02-08 05:30 | [5 empty] | None of the above | Yes
CQBW251E1 | CQBW251E12201 | C4011071 | Phase II |  |  |  |  | 2023-01-13 05:30 |  | Final DBL | 2024-05-23 05:30 |  | 2022-08-04 05:30 |  |  | Planned | 2024-04-18 05:30 |  | 2024-05-23 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CQBW251E12201 PIE PoC chronic pancreatitis | N5 DAx - NIBR | [6 empty] | Martha Watkins | [54 empty] | 60 | [7 empty] | 800 | 6 |  |  | Pancreatic disorder | Yes | Global | Open | Yes
CQBW251B | CQBW251X2201 | C1200760 | Phase II | NOVDD | [7 empty] | 2015-04-30 05:30 |  | 2014-09-22 05:30 |  | Completed |  | 2017-01-23 05:30 |  | 2017-03-10 05:30 | FALSE |  |  |  | ED Full Outsourced |  | A randomized, double blind, placebo controlled study to assess the safety, tolerability, pharmacokinetics and efficacy of multiple doses of QBW251 in patients with COPD | CQBW251X2201 PoC in COPD | P8 Respiratory | [5 empty] | Katy Hayes | Katherine Hayes | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Completed | Yes | [16 empty] | None of the above
CQBW276A1 | CQBW276X2201 | C1200243 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-09-27 05:30 |  | 2015-09-04 05:30 |  | Completed | 2019-09-11 05:30 | 2018-04-24 05:30 | 2018-11-20 05:30 | 2018-11-15 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - RESP | A randomized, double blind, placebo-controlled study to\nassess the safety, tolerability, pharmacokinetics, and\npharmacodynamics of multiple doses of inhaled QBW276\nin patients with cystic fibrosis | CQBW276X2201 Multiple dose in Cystic Fibrosis | N5 DAx - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Kristina Wagner | Kristina Wagner | [15 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | [12 empty] | CMED | [19 empty] | Cystic fibrosis | No | Global | Completed | Yes | [16 empty] | None of the above
CQCC374A1 | CQCC374X2201 | C1200417 | Phase II | RAVE_SDTM | Rave EDC - Inhouse |  |  |  | DB Locked |  |  | 2017-09-19 05:30 |  | 2016-09-30 05:30 |  | Completed | 2018-12-27 05:30 | 2018-06-07 05:30 | 2018-11-14 05:30 | 2018-11-13 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Alcon InHouse | NIBR - CVM | A randomized, parallel-group, placebo-controlled subject\nand investigator blinded study to assess the safety,\ntolerability, pharmacokinetics and efficacy of QCC374 in\nthe treatment of pulmonary arterial hypertension | CQCC374X2201 PoC in PAH | N5 DAx - NIBR | Langlo, Francois |  | Young, Pamela | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Koeun Im | [15 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | [12 empty] | ICON | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Pulmonary arterial hypertension | No | Global | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CQCC374A1 | CQCC374X2201E1 | C1200456 | Phase II | RAVE_SDTM | Rave EDC - Inhouse |  |  | 2018-02-12 05:30 | DB Locked |  |  | 2018-02-01 05:30 |  | 2016-10-12 05:30 |  | Completed | 2019-04-29 05:30 | 2018-11-06 05:30 | 2019-04-11 05:30 | 2019-04-18 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Alcon InHouse | NIBR - OPHTHA | Long-term, open label, multicenter, extension study to evaluate the safety and tolerability of QCC374 in patients with PAH | CQCC374X2201E1 PAH Extension Study | N5 DAx - NIBR | Langlo, Francois |  | Young, Pamela | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Koeun Im | [17 empty] | Rohit Varate | [28 empty] | ICON | [19 empty] | Pulmonary arterial hypertension | No | Global | Completed | Yes | [16 empty] | None of the above
CQGE031B | CQGE031B2201E1 | C1001421 | Phase II | NCDS | [7 empty] | 2014-03-27 05:30 |  | 2013-11-12 05:30 |  | Stopped (with patients) |  | 2016-03-22 05:30 |  | 2016-05-26 05:30 | FALSE |  |  | Cluster C (fGSK,IHD,Sandoz) | IDMA |  | An open-label, multi-center, extension study to evaluate the long-term safety of subcutaneous 240 mg QGE031 given every 4 weeks for 52 weeks in allergic asthma patients who completed study CQGE031B2201 | CQGE031B2201E1 - Study Terminated | P8 Respiratory |  |  |  | Gracey Sugunan, Unni Krishnan | Ninan, Esther | [68 empty] | Asthma | No | Global | Terminated | [17 empty] | None of the above
CQGE031C | CQGE031C1301 | C3001466 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-03-05 05:30 | 2019-04-05 05:30 | DB Conduct | Final DBL | 2022-03-09 05:30 | 2019-04-13 05:30 | 2018-10-19 05:30 | 2018-11-01 05:30 |  | Active | 2022-02-01 05:30 | 2022-01-26 05:30 | 2022-03-09 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, open-label study to investigate the safety/tolerability and efficacy of ligelizumab (QGE031) in the treatment of adult Japanese patients with Chronic Spontaneous Urticaria (CSU) inadequately controlled with H1 antihistamines | CQGE031C1301 Ph3 JP 1yr safety study | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Nishi, Nahoko | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | NAOKO YAMADA | NAOKO YAMADA | Bonam, Rajesh Babu | TEMBHARE, HITESH |  |  |  |  | DRM | Sama, Ashok | Kuttoboina, Sujan Kumar | Completed | 07JUL2021: We’ve finalized RF V8.0 and SNOW 51 RITM2744631 request has been created for the addition of FAAA1L DTS. 06Jul2021 : FAAA1L reflecting in missing form DTS report 06Jul2020: RF will be transitioned from Ashok to Sujan 13Mar2020 : RFV7.0 is finalized in CREDI. RF transitioned from Chandrakala to Ashok 13Feb2020 : As per missing DTS report CM1L, ZW1L, ZW2L are not included in RF. DBD (Hitesh) confirmed that these are included in RF. DBD to check with LSP / SMT programmer whether these have been setup in LSH and Need to check with Bhaskar why its flagging in report. Email sent for these actions. 24Dec2019: Transition completed | None | None | 2019-05-24 05:30 | Transition Study and Legacy process | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sandeep Kadam | Completed | 2019-04-18 | Completed | 2019-05-23 05:30 | Rajesh(28Nov2019): Two new DTSs (ZW1L, ZW2L) and CM1L DTS is added in Rule file version 5.0 and this version is currently under peerreview status. 11Dec2019: Rf v5.0 to be finalized , peer review completed. ​ | Study Transition | 2019-05-24 05:30 | 2019-05-24 05:30 | Study Transition | 2019-07-22 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 9 | 19 | 56 | 0 | 139 | 703 | 0 | 208 | 32 | 173 | 908 | 10 | 0 |  | Chronic spontaneous urticaria | No | Local | Open | Yes | [10 empty] | 2019-04-18 05:30 | [5 empty] | None of the above
CQGE031C | CQGE031C2101 | C3001465 | Phase I | Other | CRO - EDC |  |  | 2019-11-07 05:30 | DB Locked |  |  | 2019-11-07 05:30 | 2019-09-30 05:30 | 2019-10-03 05:30 |  | Active | 2021-04-22 05:30 | 2021-04-06 05:30 |  |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI |  | CQGE031C2101 bioavailability LIVI vs PFS | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Felicitas Thom | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | Other | [19 empty] | Chronic spontaneous urticaria | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CQGE031C | CQGE031C2201 | C1001424 | Phase II | NCDS | [7 empty] | 2015-07-15 05:30 |  | 2015-02-27 05:30 |  | Completed |  | 2017-06-12 05:30 |  | 2017-09-28 05:30 | FALSE |  |  | Cluster C (fGSK,IHD,Sandoz) | IDMA |  | A multicenter, randomized, double-blind, placebo and active-controlled phase 2b dose-finding study of QGE031 as add-on therapy to investigate the efficacy and safety in patients with Chronic Spontaneous Urticaria (CSU) | CQGE031C2201 Ph2B DRF | P7 Immunology Hepatology and Dermatology |  |  |  | Gracey Sugunan, Unni Krishnan | Ninan, Esther | Isabelle Indermuehle | Isabelle Inderm��hle | [66 empty] | Urticaria | Yes | Global | Open | Yes | [16 empty] | None of the above
CQGE031C | CQGE031C2201E1 | C1001423 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2016-05-24 05:30 |  | 2015-10-15 05:30 |  | Completed | 2019-05-07 05:30 |  | 2019-06-21 05:30 | 2019-06-26 05:30 | FALSE | None | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | External Full | DF ID | Long term open label safety and efficacy study of QGE031 in patients with Chronic Spontaneous Urticaria (CSU) | CQGE031C2201E1_Ph2 LT OL Ext | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Parveez, Mohamed | Fasih, Arshad | Kadam, Abhishek Vilas | Ninan, Esther | Isabelle Indermuehle | Isabelle Inderm��hle | Killamsetty, Nanari Ram | [14 empty] | Ghate, Dhananjay |  | Sandeep Kadam | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full |  |  |  |  | ICON | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Urticaria | Yes | Global | Open | Yes | [16 empty] | None of the above
CQGE031D1 | CQGE031C2202 | C1001420 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-04-30 05:30 | 2018-07-30 05:30 | DB Locked | Final DBL Achieved |  | 2018-08-01 05:30 | 2017-12-20 05:30 | 2018-01-15 05:30 |  | Completed | 2021-03-01 05:30 | 2021-02-03 05:30 | 2021-03-17 05:30 | 2021-03-17 05:30 | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CQGE031C2202 Ped PK/PD in CSU | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Vadla, Nagarajachari | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Miriam Guigue | Miriam Guigue | Rana, Aamir | Rana, Aamir |  |  |  |  | DRM (DIAL) | Rana, Aamir | Patnaik, Angella | Completed | 15-MAR-2021: RF Version 8.0 is finalized for FAMH domain update. SNOW#51 raised for LSH updates. 11-MAR-2021: SNOW#51 raised for PPC8 LSH updates. 03-MAR-2021: PPC7 implemented. No update to RF, SMT or LSH. 16-FEB-2021: RF Version 7.0 finalized for FAAA1L, FAAA2L, FAAA3L DTS tables. SNOW#51 raised for LSH updates. 07-JUL-2020: RF up to date for all final DTS and PPCs implemented in the study. 3APR2020: RF V6.0 for LB updates final in CREDI. 31MAR2020: Updated V6.0 RF for LB domain released for Peer review. 6FEB2020: Rule file V5.0 finalized in CREDI. SNOW#51 raised for LSH update (SMT update) for DS and LB domain. 5FEB2020: Rule file 5.0 updated for including SSG004 form and LBL table. Released for Peer Review. 11Dec19 : Rule file for PPC (1 missing form) will be sent for peer review (Angella) on 11Dec19. | None | None | 2018-08-03 05:30 |  | Sundar, N Sushant | Agavekar, Amit | Sandeep Kadam | Completed | 2018-07-20 | Completed | 2019-07-25 05:30 | The list of domains for DIAL are - AE, CM​, DM, DS, DV, EC, ​EG, FA​MH, IE, MH, VS and SV.​​ |  | 2018-08-09 05:30 | 2018-08-09 05:30 | Retrospective DRM studies | 2019-07-25 05:30 |  |  | DM, SP confirmed no issues at the moment | 100 | RaveX - Inhouse | Yes | -NA- | 2021-03-17 05:30 | 2021-03-19 05:30 | LSH PK Lock - 10May2021 LSH Unlock for LB- 30June2021 LSH ReLock- 6July2021 | [8 empty] | NA | [5 empty] | 6 | 14 | 44 | 0 | 122 | 539 | 0 | 174 | 39 | 127 | 705 | 7 | 0 |  | Urticaria | No | Global | Open | Yes | [10 empty] | 2019-06-13 05:30 | [5 empty] | None of the above
CQGE031C | CQGE031C2203 | C3001470 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-01-17 05:30 | 2020-06-11 05:30 | 2020-07-30 05:30 | DB Conduct | Final DBL | 2023-06-29 05:30 | 2020-08-05 05:30 | 2019-11-08 05:30 | 2019-11-08 05:30 |  | Active | 2023-04-13 05:30 |  | 2023-06-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A two-part exploratory study combining a pilot study in healthy subjects and chronic spontaneous urticaria patients (Part 1) and a randomized, subject, investigator and sponsor-blinded, placebo controlled, study (Part 2) to assess the MechAniSm of acTion of ligElizumab (QGE031) in patients with chronic uRticaria (MASTER) | CQGE031C2203 MoA in CSU | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Bhatkar, Priyanka | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Ozana Fischer | Ozana Fischer | Kancharla, Susmita | SHETTY, PRASHANT PRABHAKAR | Completed | 2022-01-10 05:30 |  |  | DRM | Choppadandi, Kranthikumar | R, Pratheeksha K | Completed | 31Jan2022: PPC 04 did not have any impact on the Rule File. I have raised SNOW51 ticket for LSH rebuild. Ticket number - RITM3438520 14Oct2021: EGG001_1, QS1S767, SRS001_2, SRS001_3, ZJS001_1, SRS002, SRS003, ZJG002_5 forms, LB1L, QS1L DTSs have been added in the RF during PPC 03(08Aug2021). 11Aug2021 : Reassigned the study from Kranthi to Pratheeksha. 06-Aug-2021: Updated RF to include forms(EGG001_1, QS1S767, SRS001_2, SRS001_3, ZJS001_1, SRS002, SRS003, ZJG002_5), DTSs(LB1L, QS1L) and released for peer review 21Jul2021 : Forms EGG001_1, QS1S767, SRS001_2, SRS001_3, ZJS001_1, SRS002, SRS003, ZJG002_5 and LB1L DTS reflecting in 21Jul report. 06Jul2020: Rule file V1.0 is the latest one. RF will be reassigned to Kranthi from Ashok 12Jun2020: RF final and raised ROD ticket for SMT LSH Setup 30Apr2020: I have reviewed the SRFs and provided my comments and some SRFs are in discussion and needed SDTM annotations for the same. 30Mar2020 : Re-assigned the study to Ashok from Kranthi and notifed DBD. 19Mar2020 : Screen UAT completed and 1 Domain name changed and needs to be updated in study. Awating SDTM annotations which is expected to receive by tomorrow. 03Mar2020 : SRFs and Study specific forms / ALS review ongoing. Screen UAT not completed yet. 17Feb2020 : Received approx. 15 SRFs for review on 14Feb. 05Feb2020: Requested for documents for SS review and RF | None | None | 2020-06-12 05:30 |  | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2020-06-25 | Completed | 2020-06-30 05:30 |  |  | 2020-07-02 05:30 | 2020-07-02 05:30 |  | 2020-09-01 05:30 |  |  | Initial DDPASS is going on we have done DDPASS for 5 domains. Due to less data in all domains we have kept all domains on hold. Once we have sufficient data again will review those domains and finalize them. | 0 | RaveX - Inhouse | Yes | ZK;#Y1 | [11 empty] | NA | [5 empty] | 4 | 12 | 74 | 0 | 194 | 611 | 0 | 182 | 37 | 203 | 851 | 3 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [10 empty] | 2020-06-29 05:30 | [5 empty] | None of the above
CQGE031C | CQGE031C2302 | C1001426 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-14 05:30 | 2018-09-28 05:30 | DB Conduct | Final DBL | 2022-08-03 05:30 | 2018-10-17 05:30 | 2018-03-21 05:30 | 2018-03-23 05:30 |  | Active | 2022-06-22 05:30 |  | 2022-08-03 05:30 |  | TRUE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, randomized, double-blind, active and placebo-controlled study to investigate the efficacy and safety of ligelizumab (QGE031) in the treatment of Chronic Spontaneous Urticaria (CSU) in adolescents and adults inadequately controlled with H1-antihistamines | CQGE031C2302 Ph3 pivotal 1 - PEARL 1 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | B S, Marulasiddaiah | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Darshna Modi | Darshna Modi | Patnaik, Angella | Kala, Arpit |  | 2022-02-10 05:30 | 06SEP2020- Study had been transitioned from Aamir to Jyoti 10FEB2022- Study has been transitioned from Jyoti to Arpit. | DB Go-live planned with respect to FPFV Date. | DRM (DIAL) | Patnaik, Angella | Patnaik, Angella | Completed | 08-JUN-2021: RF Version 9.0 finalized for SS domain addition as per SDTM requirements. SNOW#51 raised for LSH updates. 11-MAR-2021: RF Version 8.0 finalized. SNOW#51 raised for LSH updates. 05-MAR-2021: RF Version 8.0 released for Peer Review. 07SEP2020: RF Finalized for FAAA1L, FAAA2L, FAAA3L DTS. SNOW#51 raised for LSH updates. 13AUG2020: RF update for addition of FAAA1L, FAAA2L, FAAA3L DTS tables sent for Peer Review. 11AUG2020: Requested DBD for DTS confirmation to initiate RF update. 07-JUL-2020: RF up to date for all final DTS and Post Production updated till PPC5 implemented in the study. 1JUN2020: DS Domain issue resolved with RF update. 27MAY2020: RF finalized and SNOW#51 raised for SMT and LSH updates. 20MAY2020: RF updated and sent for Peer Review. 18MAY2020: PPC5 form received for RF updates. 03-DEC-2019: Rule file final for all DTS and till PPC3. | None | None | 2018-10-09 05:30 |  | Kokane, Swapnil | Kokane, Swapnil | Sandeep Kadam | Completed | 2018-11-15 | Completed | 2019-09-16 05:30 |  |  | 2018-11-15 05:30 | 2018-11-15 05:30 | Retrospective DRM studies | 2019-09-16 05:30 |  |  |  | 40 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK;#ZK03 | [11 empty] | NA | [5 empty] | 10 | 20 | 60 | 0 | 172 | 1065 | 0 | 276 | 35 | 188 | 1288 | 11 | 0 |  | Urticaria | Yes | Global | Open | Yes | [10 empty] | 2019-05-15 05:30 |  |  |  |  | Agavekar, Amit | GDD annual target | Yes
CQGE031C | CQGE031C2302E1 | C4005051 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-02-01 05:30 | 2020-03-10 05:30 | 2020-04-30 05:30 | DB Conduct | Final DBL | 2026-08-25 05:30 | 2020-04-08 05:30 | 2019-12-13 05:30 | 2019-12-12 05:30 |  | Active | 2026-07-14 05:30 |  | 2026-08-25 05:30 |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, double-blinded and open-label extension study to evaluate the efficacy and safety of ligelizumab as retreatment, self-administered therapy and monotherapy in Chronic Spontaneous Urticaria patients who completed studies CQGE031C2302, CQGE031C2303, CQGE031C2202 or CQGE031C1301 | CQGE031C2302E1 Ph3 Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Pawaskar, Madhura | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Isabelle Indermuehle | Isabelle Inderm��hle | Gandla, Prashanth | Rana, Aamir |  |  | 15-Dec-2021 : Arpit Kala will be backup for Aamir till 15-Mar-2022 Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 01Feb2020 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 03-DEC-2021: RF Version 8.0 has been finalized for SS domain update as per SDTM requirements. SNOW#51 (RITM3256942) raised for SMT/LSH updates. 09-NOV-2021: RF Version 7.0 has been finalized for PPC #4 updates and FAAA1L DTS table addition. SNOW#51 (RITM3168689) raised for SMT/LSH updates. 24-SEP-2021: RF Version 6.0 has been finalized for SDTM updates for Safety Phone Call data (SV, VE Domains). SNOW#51 raised for SMT/LSH updates. 30-JUL-2021: No impact on RF for PPC #3. SNOW#51 has been raised for SMT/LSH updates. 10MAY2021: RF Version 5.0 has been finalized for PPC #5 updates. SNOW#51 raised for SMT/LSH updates. 13OCT2020: RF V4.0 has been finalzied for the Urine Dipstick Parameter issue resolution. SNOW#51 raised and LSP notified. 12OCT2020: RF V3.0 finalized for PPC1 and DDPASS updates. SNOW#51 raised and LSP notified. EG1L DTS table has no issues in the current tracker. 02Jul2020: EG1L flagged in missing DTS report. 13MAY2020: RF V2.0 updated for 7 DTS tables - EG1L, LBL, QS1L, QS2L, QS3L, QS4L, QS5L. SNOW#51 raised for SMT and LSH updates. Team notified. 16MAR2020: Rule file finalized and SNOW#05 raised for LSH set-up. 09MAR2020: RF sent for Peer Review. 3MAR2020: RF development completed for Global forms. 2MAR2020: Incorrect domains approved in SRFs. Have asked for re-approval. 28FEB2020: ALS, SRFs and SDTM annotations reviewed. DB updates and domain confirmation requested. 07Feb2020 : ALS, SRFs, Study specific forms shared on 04Feb2020. Will start on RF development 7-JAN-2020: Screen build in progress. DB Go-live date: 21-FEB-2020. | None | None | 2020-03-16 05:30 |  | Praveen kumar, Chakka Giri | Kadam, Sandeep | Sandeep Kadam | Completed | 2020-04-08 | Completed | 2020-04-13 05:30 |  | Study Transition | 2020-04-13 05:30 | 2020-04-13 05:30 | Study Transition | 2020-06-08 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | YR;#Y1;#Y5 | [11 empty] | NA | [5 empty] | 6 | 57 | 69 | 0 | 311 | 1041 | 0 | 295 | 46 | 184 | 1271 | 8 | 0 |  | Urticaria | No | Global | Open | Yes | [10 empty] | 2020-04-09 05:30 | [5 empty] | None of the above | Yes
CQGE031C | CQGE031C2303 | C1001427 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-08-21 05:30 | 2018-10-03 05:30 | DB Conduct | Final DBL | 2022-08-02 05:30 | 2018-10-20 05:30 | 2018-02-28 05:30 | 2018-03-23 05:30 |  | Active | 2022-06-21 05:30 |  | 2022-08-02 05:30 |  | TRUE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, randomized, double-blind, active and placebo-controlled study to investigate the efficacy and safety of ligelizumab (QGE031) in the treatment of Chronic Spontaneous Urticaria (CSU) in adolescents and adults inadequately controlled with H1-antihistamines. | CQGE031C2303 Ph3 Pivotal 2 - PEARL 2 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sampangi, Sridevi | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Kerstin Letzelter | Kerstin Letzelter | Rana, Aamir | Kala, Arpit | Completed | 2022-02-10 05:30 | Study transitioned from Angella Patnaik to Aamir Rana on 5-Feb-2020. Study transitioned from Aamir Rana to Jyoti Kumari on 17-Nov-2020. 10FEB2022- Study has been transitioned from Jyoti to Arpit. | DB Go-live planned with respect to FPFV Date. | DRM (DIAL) | Patnaik, Angella | Patnaik, Angella | Completed | 08-JUN-2021: RF Version 10.0 finalized for SS domain addition as per SDTM requirements. SNOW#51 raised for LSH updates. 07OCT2020: RF V7.0 finalized for PPC6 updates. SNOW#51 raised for SMT and LSH updates. 07SEP2020: RF Finalized for FAAA1L, FAAA2L, FAAA3L DTS. SNOW#51 raised for LSH updates. 13AUG2020: RF update for addition of FAAA1L, FAAA2L, FAAA3L DTS tables sent for Peer Review. 11AUG2020: Requested DBD for DTS confirmation to initiate RF update. 07-JUL-2020: RF up to date for all final DTS and Post Production updated till PPC5 implemented in the study. 01-JUN-2020: RF V5.0 updated with addition of DSG005 form for PPC5. SNOW#51 raised for SMT and LSH updates (RITM1458490). 3-DEC-2019: Rule file final for all DTS and till PPC3. | None | None | 2018-11-05 05:30 |  | Kokane, Swapnil | Kokane, Swapnil | Sandeep Kadam | Completed | 2018-12-18 | Completed | 2019-08-15 05:30 |  |  | 2018-11-14 05:30 | 2018-11-16 05:30 | Retrospective DRM studies | 2019-08-15 05:30 |  |  |  | 40 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK;#ZK03 | [11 empty] | NA | [5 empty] | 9 | 20 | 60 | 0 | 169 | 1077 | 0 | 279 | 35 | 188 | 1300 | 11 | 0 |  | Urticaria | Yes | Global | Open | Yes | [10 empty] | 2019-05-17 05:30 |  |  |  |  | Sundar, N Sushant | GDD annual target | Yes
CQGE031D1 | CQGE031C2305 | C3000498 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-14 05:30 | Study Planned | DB Go-live | 2022-07-06 05:30 |  | 2021-10-05 05:30 | 2021-10-05 05:30 |  | Planned | 2028-12-27 05:30 |  | 2029-02-07 05:30 |  | FALSE | TBC | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Open-label trial to evaluate pharmacokinetics, safety and activity of ligelizumab in children from 2 to less than 12 years of age with chronic spontaneous urticaria | CQGE031C2305 Pediatric study PEARL mini | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sampara, Suresh | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Aude Lacombe | Aude Eleonore Lacombe | Maricherla, Vijayroshan | Maricherla, Vijayroshan | [5 empty] | Saha, Saikat | Saha, Saikat | Not Started | [7 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 48 | 0 |  |  | 0 |  |  |  | 535 | 5 | 0 |  | Chronic spontaneous urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CQGE031C_MA | CQGE031C2402 | C4014318 | Phase III | NCDS_2 |  |  |  | 2022-12-15 05:30 |  | Final DBL | 2024-04-12 05:30 |  | 2022-04-15 05:30 |  |  | Planned | 2024-03-15 05:30 |  | 2024-04-12 05:30 | [5 empty] | InHouse |  | Bring target CSU outcomes in patients treated with ligelizumab in a clinical setting: the BRIDGE II study | CQGE031C2402 BRIDGE II | P7 Immunology Hepatology and Dermatology | [6 empty] | Marilyn Cines | [54 empty] | 40 | [7 empty] | 500 | 3 |  |  | Chronic spontaneous urticaria | No | Global | Open | Yes
CQGE031E1 | CQGE031E12301 | C4006341 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-01-15 05:30 |  | 2021-11-08 05:30 | DB Conduct | Final DBL | 2025-02-10 05:30 | 2021-11-16 05:30 | 2021-07-16 05:30 | 2021-07-14 05:30 |  | Active | 2024-12-27 05:30 |  | 2025-02-10 05:30 |  | FALSE | Pioneer | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A multi-center, randomized, double-blind, placebo controlled study of ligelizumab (QGE031) in the treatment of Chronic Inducible Urticaria (CINDU) in adolescents and adults inadequately controlled by H1-antihistamines | CQGE031E12301 Ph3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | B S, Marulasiddaiah | Fasih, Arshad | Kanani, Pooja | Ninan, Esther | Miriam Guigue | Miriam Guigue | Das, Devashish | Das, Devashish | Not Started |  | 03May2021 : As per Arshad FPFV would be Mar-Apr 2022, and will be indicated in iBOW. DB golive updated tentatively as 11Feb2022 16Apr2021 : As per TDM Juneja, Twinkle There is a delay in the timelines (due to delay in protocol finalization) and I haven’t yet received the concrete timelines from CTT. Moving the Golive date from 15-Apr-2021 to end of June as per udpated timelines from TDM. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 15Jan2021 |  | DRM | Govula, Shashikanth | R, Pratheeksha K | Completed | 14Nov2021: The RF was finalized on 9-Nov2021 and LSH test setup request raised with SNOW 05 Ticket number RITM3170810. Checklist finalized in subway. 10Aug2021: The DBD has confirmed that the go-live date is postponed to 19 Oct 2021. I have asked the DBD to get the iBoW updated by the TDM. 7JAN2021: SG: DB activities not yet started. | None | None | 2021-11-09 05:30 |  | Kokane, Swapnil | Kokane, Swapnil | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Urticaria | Yes | Global | Open | Yes | [10 empty] | 2022-01-12 05:30 | [5 empty] | None of the above
CQGE031F1 | CQGE031F12101 | C4008111 | Phase I | Other |  |  |  | 2023-02-08 05:30 |  | Final DBL | 2024-01-17 05:30 |  | 2022-11-16 05:30 |  |  | Planned | 2023-12-20 05:30 |  | 2024-01-17 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CQGE031F12101 bioavailability PFS vs AI | P7 Immunology Hepatology and Dermatology | [6 empty] | Izabela Rozenberg | [66 empty] | Urticaria | No | Global | Open | Yes | [16 empty] | None of the above
CQGE031G1 | CQGE031G11302 | C4011520 | Phase III | NCDS_2 |  |  |  | 2023-09-08 05:30 |  | Final DBL | 2024-04-04 05:30 |  | 2023-04-26 05:30 |  |  | Planned | 2024-02-22 05:30 |  | 2024-04-04 05:30 | [5 empty] | InHouse |  |  | CQGE031G11302 Regional Regulatory study (Japan) | P8 Respiratory | [6 empty] | Kenneth Harper | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Food allergy | No | Global | Open | Yes
CQGE031G1 | CQGE031G12101 | C4011379 | Phase I | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-21 05:30 | Study Planned | Final DBL | 2023-06-16 05:30 |  | 2022-07-07 05:30 |  |  | Planned | 2023-05-05 05:30 |  | 2023-06-16 05:30 |  |  | No priority assigned | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQGE031G12101 Vaccine study | P8 Respiratory | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas | Linda Tormey | Linda Tormey | SRIVASTAVA, ANIKET | SRIVASTAVA, ANIKET | [6 empty] | Choppadandi, Kranthikumar | Not Started | [7 empty] | Sushant Sundar | [36 empty] | 50 | [7 empty] | 700 | 2 |  |  | Chronic spontaneous urticaria; Food allergy | No | Global | Open | Yes
CQGE031G1 | CQGE031G12201 | C4013386 | Phase II | NCDS_2 |  |  |  | 2022-04-04 05:30 |  | Final DBL | 2025-02-27 05:30 |  | 2022-03-29 05:30 |  |  | Planned | 2026-08-15 05:30 |  | 2025-02-27 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CQGE031G12201 MoA study (New WP) | P8 Respiratory | [5 empty] | Leslie Taylor | Leslie Taylor | [54 empty] | 60 | [7 empty] | 800 | 6 |  |  | Food allergy | No | Global | Open | Yes
CQGE031G1 | CQGE031G12301 | C4008794 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-07-12 05:30 | 2021-10-28 05:30 | 2021-12-10 05:30 | DB Conduct | Final DBL | 2025-07-08 05:30 | 2021-12-07 05:30 | 2021-04-16 05:30 | 2021-04-14 05:30 |  | Active | 2025-05-27 05:30 |  | 2025-07-08 05:30 |  | FALSE | Priority Not Known | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A 52 week, multi-center, randomized, double-blind placebo-controlled study to assess the clinical efficacy and safety of ligelizumab (QGE031) in decreasing the sensitivity to peanuts in patients with peanut allergy | CQGE031G12301 PhIII Registration study (Peanut) | P8 Respiratory | Mahajan, Vinay | Mishra, Amit Kumar | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Lisa Satlin | Lisa Satlin | Das, Devashish | Das, Devashish |  |  | 15-Dec-2021 : Vinay Pamula will be backup for Aamir till 15-Mar-2022 29Apr2021 : Started with global pages since FPP submission is on first week of May. Initial golive as 12Jul2021 when DBD assigned. |  | DRM | Saha, Saikat | Saha, Saikat | Completed | 3Feb2022: RF and Checklist Version 4.0 have been finalized in SubWay with 9 QS and 1 LB DTS in it. SNOW51 Request RITM3453340 has been raised and notified the LSP. 31Jan2022: Received QS1L and QS7L DTS for review. Reviewed and provided the comments. Once all the QS DTS are finalized, will finalize the RF. 28Jan2022: TDM sent the updated DTS. Confirmed that they are good to go. Released the RF for peer review 25Jan2022: Reviewed all the DTS and the comments to the TDM to update. 24Jan2022: Received 7 QS DTS to review. 10Jan2021: Received an issue regarding the FAOBJ variable from LSP to update the FAMH domain. Updated the FAMH domain and finalized the RF along with the EG DTS. Both RF and checklist have been finalized and SNOW 51 request raised. Notified the LSP. 4Jan2022: Received updated DTS for QS domain and LB domain. Reviewed and sent back some queries. 15Dec2021: PPC01 has been implemented. No updated were required from the RF side. 13Dec2021: Reviewed all the DTS and sent back the comments to update. 9Dec2021: Received 13 DTS from the TDM to review. 24Nov2021 : TDM re-shared the DTS, updated with the comments, reviewed and no further comments were added. 19Nov2021 : Received EG DTS from the TDM, reviewed it and sent back my comments to make the updates in the DTS 18Nov2021 : RF and Checklist are finalized in the SubWay. SNOW 51 ticket raised and notified LSP. 17Nov2021 : Received IRT DTS to review and add it in the RF. RF updated and released for Peer Reveiew 29Oct2021 : RF and Checklist has been finalized in the SubWay. LSH PROD and TEST tickets has been raised. Notified LSP. 28Oct2021 : Study went live. 27Oct2021 : RF is ready to be finalized. Go-live date pushed to 28Oct2021. 26Oct2021 : Received the Peer Review comments and shared them to DBD to make the necessary changes in the ALS. 21Oct2021 : RF has been released for peer review. Go-live date has been pushed to 27-Oct-2021 19Oct2021 : RF updated is going on, asked TDM to raise study specific test codes request and still pending with one page annotation and SODs. 18Oct2021 : Provided comments regarding incomplete SDTM annotation and asked for the SODs for RF development. 17Oct2021 : Received the updated ALS and SDTM annotations from the DBD. 6Oct2021 : Yet to receive the updated ALS and SDTM annotation to proceed with the RF. Sent the reminder mail to the DBD and TDM. 27Sep2021 : TDM shared the updated SOD data for pending pages. 14Sep2021 : Discussion is going on for FAMHS001 page design and yet to receive the updated ALS and latest SOD for RF development from the DBD. 06Sep2021 : Started RF development, had some SDTM annotation confusion, asked the SDTM programmer for clarification. Study go-live postponed to end of the month. 01Sep2021 : DBD shared the latest ALS with the updates. 30Aug2021 : Had a discussion with the DBD regarding the review comments and waiting for the DBD to revert back with the changes. 23Aug2021 : Completed ALS review and sent the review comments to the DBD. 19Aug2021 : Received the Study specific SRF and SDTM annotations. 13Aug2021 : Asked for the Study Specific SRF and SDTM annotations for complete review. 12Aug2021 : Received ALS, SRF and SDTM annotations from the DBD for review. 06Jul2021 : RF developer assigned with go-live date as 20Sep2021. | None | None | 2021-10-29 05:30 |  | Sultana, Salma | Sultana, Salma | Sushant Sundar | Completed | 2021-11-08 | Completed | 2021-11-19 05:30 |  |  | 2021-11-19 05:30 | 2021-11-19 05:30 |  | 2021-11-19 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 1 | 24 | 46 | 0 | 172 | 644 | 0 | 179 | 37 | 127 | 808 | 13 | 0 |  | Food allergy | Yes | Global | Open | Yes | 2021-10-29 05:30 | [9 empty] | 2021-11-17 05:30 | [5 empty] | None of the above
CQGE031G1 | CQGE031G12302 | C4009953 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-08-12 05:30 |  | 2022-07-13 05:30 | Study Planned | DB Go-live | 2022-04-04 05:30 |  | 2021-10-29 05:30 | 2021-11-02 05:30 |  | Planned | 2025-05-27 05:30 |  | 2025-07-08 05:30 |  | FALSE | Priority not known | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQGE031G12302 PhIII Registration study (Milk/Egg) | P8 Respiratory | Mahajan, Vinay | Mishra, Amit Kumar | Gijo, Ani | Regula, Ramakrishna | Hiriyanna, Srinivas | Lisa Satlin | Lisa Satlin | Supraja, Samala | Supraja, Samala | [5 empty] | R, Pratheeksha K | R, Pratheeksha K | Not Started | [7 empty] | Sushant Sundar | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Food allergy | Yes | Global | Open | Yes | [16 empty] | None of the above
CQGE031G1 | CQGE031G12303B | C4010263 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-25 05:30 | Study Planned | Final DBL | 2028-12-26 05:30 |  | 2022-06-30 05:30 |  |  | Planned | 2028-11-14 05:30 |  | 2028-12-26 05:30 |  |  | Resp DU Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQGE031G12303B Basket for all FA studies | P8 Respiratory | Mahajan, Vinay | Regula, Ramakrishna | Regula, Ramakrishna | Regula, Ramakrishna | Hiriyanna, Srinivas | Linda Tormey | Linda Tormey | CHAUGHULE, JAGRUTI SUDHIR | CHAUGHULE, JAGRUTI SUDHIR | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | [7 empty] | Sushant Sundar | [36 empty] | 40 | [7 empty] | 1000 | 5 |  |  | Food allergy | No | Global | Open | Yes
CQGE031G1 | CQGE031G12304 | C4009992 | Phase III | NCDS_2 |  |  |  | 2023-05-17 05:30 |  | Final DBL | 2025-10-20 05:30 |  | 2023-01-03 05:30 |  |  | Planned | 2025-09-08 05:30 |  | 2025-10-20 05:30 | [5 empty] | InHouse |  |  | CQGE031G12304 Hazelnut study | P8 Respiratory | [6 empty] | Kenneth Harper | [54 empty] | 50 | [7 empty] | 800 | 8 |  |  | Food allergy | No | Global | Open | Yes
CQGE031G1_MA | CQGE031G12307 | C4013962 | Phase III | [6 empty] | Final DBL | 2023-04-10 05:30 |  | 2022-05-27 05:30 |  |  | Planned |  |  | 2023-04-10 05:30 | [5 empty] | InHouse |  | A 12-week, multicenter, randomized, double-blind, placebo-controlled study to assess the clinical efficacy and safety of Ligelizumab (QGE031) in decreasing the sensitivity to shrimp in patients with shellfish allergy. | CQGE031G12307 Ph3b QGE031 in Shellfish FA | P8 Respiratory | [6 empty] | Nicolas Horovitz | [66 empty] | Food allergy | No | Global | Draft | Yes
CQMF149E | CQMF149E1401 | C3001312 | Phase IV | Other | Other |  |  | 2022-12-30 05:30 | DB Set-Up | DB Go-live | 2022-02-28 05:30 |  | 2022-05-10 05:30 |  |  | Planned | 2024-12-31 05:30 |  | 2024-12-31 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | DF RESP | A database study to assess the relative risk of cardiovascular events in Japanese patients with asthma on indacaterol acetate/mometasone furoate (QMF149) in Japan | CQMF149E1401 | P8 Respiratory | YAMADA, KAYO | MORI, YUMIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | YUKIE YOSHIZAWA | YUKIE YOSHIZAWA | [17 empty] | Sushant Sundar | [28 empty] | NA | [19 empty] | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CQMF149G | CQMF149G2202 | C1001429 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-04-18 05:30 |  | 2016-07-04 05:30 |  | Completed | 2019-08-05 05:30 | 2019-07-17 05:30 | 2019-09-10 05:30 | 2019-08-30 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | External Full | DF RESP | A multicenter, randomized, double-blind, active-controlled, 2 week treatment, parallel-group study to assess the efficacy and safety of indacaterol acetate delivered via the Concept1 inhalation device in children greater or equal to 6 and less than 12 years of age with asthma | CQMF149G2202 Peds QAB dose bridging | P8 Respiratory | Mahajan, Vinay | Krishnan, Vasudevan | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Michele Valentin; Motoi Hosoe | Michele Valentin | Meda, Sreelakshmi | [14 empty] | Munusamy, Tamilarasan |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | ICON | External Full | 2017-01-31 05:30 | 2017-01-31 05:30 | Meda, Sreelakshmi | Killamsetty, Nanari Ram | ICON | [7 empty] | 85 | 0 |  |  | 0 |  |  |  | 724 | 7 | 0 |  | Asthma | Yes | Global | Open | Yes | [14 empty] | DBL | Tidke, Shyam | None of the above | No
CQMF149G | CQMF149G2203 | C4008284 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-02-05 05:30 | 2021-02-05 05:30 | 2021-06-25 05:30 | DB Conduct | Final DBL | 2022-05-16 05:30 | 2021-06-07 05:30 | 2020-08-28 05:30 | 2020-08-27 05:30 | 2021-02-04 05:30 | Active | 2022-04-04 05:30 |  | 2022-05-16 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | An open-label, two-period, single-sequence, crossover study to compare the systemic exposure of a single inhaled dose of mometasone furoate (MF) when administered alone via the MF TwisthalerÂ® (TH) to a single inhaled dose of QMF149 indacaterol acetate/MF fixed dose combination when administered via the Concept 1 (BreezhalerÂ®) device in â¥ 6 to &lt;12 year old asthma patients | CQMF149G2203 Pediatric PK study | P8 Respiratory | Mahajan, Vinay | Medisetti, Yugeshwar | Ravi, Sapna | Sahu, Vandana | Hiriyanna, Srinivas | Kathleen Scott | Kathleen Scott | Kancharla, Susmita | Mareedu, Vasu | Completed |  | Oct 2021 : Pallabi transitioned study to Vasu DTS finalization is in progress. Once DTS finalized transition will be initiated. |  | DRM | Kuttoboina, Sujan Kumar | Kuttoboina, Sujan Kumar | Completed | 09SEP2021: RF V5.0 is final and SNOW 51 request RITM2963992 has been created. Requested for to create SS domain and rebuild FACM domain as per latest SDTM annotations 03AUG2021: RF 4.0 is final and snow 51 RITM2834934 has been created, requested to rebuild EC and add LB domain in LSH. LB1L DTS added. 29JUL2021: RF 3.0 final and SNOW 51 request RITM2822035 has been created. YDL DTS added. 11MAR2021: RF final and SNOW 51 request RITM2354598 has been created. Change: EG1L DTS has been added 09Feb2021 : RF final and Snow05 Raised. 01FEB21: SDTM annotations are received on 28JAN21, RF development is ongoing and for peer review will be released on 01FEB21 04FEB21: Rule file has been released for peer review 19JAN21: Lead DBD is following up with SDTM programmer for SDTM annotations. Once we've SDTM annotations in place, will start Rule file development. 12JAN21: Following up with lead DBD for the required documents for RF development. 07JAN21: Screens are not yet finalized. Following up with Lead DBD. 10NOV20: Following up with lead DBD for to share ALS, SRF and SDTM annotations for page modeling review. 28OCT20: DB golive is on 18DEC20. SRF approval is in progress. 20OCT20: As per discussion with Lead DBD, the expected DB Golive is on 18-DEC-20. Requested to update same in DM BOW and Rave Master study list. 12OCT20: Lead DBD is facing access isssues with Rave Architect. Will update status on the end of today 24SEP20: Only the global forms are copied in the study and SRF’s are yet to be approved. Once DBD Started working on the Study specific forms, will start Rule file activities. 02SEP20; As of now DBD copied only the global forms and need to get the initial version of SSD. Discussions are ongoing on the study specific pages. 17AUG20: Protocol not finalized yet and Protocol is released for QC and tentitive date of protoco finalization is 21AUG20 | None | None | 2021-02-09 05:30 |  | Sultana, Salma | Sahu, Ahallad | Sushant Sundar | Completed | 2021-02-23 | Completed | 2021-03-01 05:30 |  | Delay in SMT files. | 2021-03-04 05:30 | 2021-03-04 05:30 |  | 2021-03-08 05:30 |  |  |  | 90 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 5 | 38 | 0 | 37 | 615 | 0 | 202 | 36 | 106 | 757 | 3 | 0 |  | Asthma | No | Global | Open | Yes | [10 empty] | 2021-03-01 05:30 | [5 empty] | None of the above
CQMF149G | CQMF149G2301 | C1001430 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-25 05:30 | Study Planned | Final DBL | 2025-12-24 05:30 |  | 2022-03-24 05:30 |  |  | Planned | 2025-11-05 05:30 |  | 2025-12-24 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | QMF 6-11 yrs Ph3_CQMF149G2301 | P8 Respiratory | Mahajan, Vinay | Medisetti, Yugeshwar | Ravi, Sapna | Sahu, Vandana | Hiriyanna, Srinivas | Kathleen Scott | Kathleen Scott | [17 empty] | Sushant Sundar | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CQUC398A0 | CQUC398A02101 | C4013126 | Phase I | [6 empty] | Final DBL | 2021-04-30 05:30 |  |  | 2021-09-03 05:30 |  | Planned |  |  | 2021-04-30 05:30 | [5 empty] | FULL Outsourced |  | A Single-Center, Phase I, Randomized, Double-Blind, Placebo-Controlled, First-In-Human Trial to Assess the Safety, Tolerability, Immunogenicity, Pharmacokinetics, and Pharmacodynamics of Single Ascending Doses of Subcutaneous Injected M6495 (Anti-ADAMTS-5 Nanobody) in Healthy Male Subjects | CQUC398A02101 SAD in HV with Merck compound | N4 MSD - NIBR | [6 empty] | Emilie Francoise Armelle Voltz | [66 empty] | Osteoarthritis knee | No | Global | Open | No
CQUC398A1 | CQUC398A12201 | C4011597 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-04 05:30 | DB Set-Up | DB Go-live | 2022-04-15 05:30 |  | 2021-12-02 05:30 | 2021-12-02 05:30 |  | Planned | 2024-09-02 05:30 |  | 2024-11-25 05:30 |  |  | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - MSD | A randomized, two-arm, placebo-controlled, participant, investigator and sponsor-blinded, proof-of-concept study investigating the efficacy, safety and tolerability of QUC398 in patients with symptomatic knee osteoarthritis | CQUC398A12201 PoC study in knee OA | N4 MSD - NIBR | Langlo, Francois | Kumar, Samoj | Mane, Kunal Yashavant | Swain, Swayam | Gupta Bhaya, Soumya Kanti | David Sanchez Ramos | David Sanchez Ramos | Das, Devashish | Das, Devashish | [6 empty] | R, Pratheeksha K | Not Started | [7 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Osteoarthritis knee | No | Global | Open | Yes
CQVA149A | CQVA149A1401 | C3000043 | Phase IV | Other |  |  |  | 2014-01-23 05:30 |  |  |  | 2014-01-23 05:30 | 2013-09-13 05:30 | 2013-09-13 05:30 |  | Completed | 2019-08-30 05:30 | 2016-12-02 05:30 | 2019-08-30 05:30 | 2019-08-30 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational study of QVA149 in chronic obstructive pulmonary disease | CQVA149A1401 JPN PMS | P8 Respiratory | [5 empty] | CHIHIRO KATO; YOKO INABA | YUKIE YOSHIZAWA | [66 empty] | Chronic obstructive pulmonary disease | No | Global | Open | Yes | [16 empty] | None of the above
CQVA149A0 | CQVA149A2325 | C3000031 | Phase III | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-06-03 05:30 |  | 2015-10-05 05:30 |  | Completed |  | 2017-09-26 05:30 |  | 2017-12-11 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED InHouse | NIBR - RESP | A randomized, double-blind, placebo-controlled, two-period crossover study to assess the effect of inhaled QVA149 on global and regional lung function and gas exchange in patients with moderate to severe COPD | CQVA149A2325 QVA mech effic imaging receptor effs | P8 Respiratory | Langlo, Francois | Khanke, Sanjay | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Kristin Belmore | Elizabeth McNamara | [15 empty] | Singari, Nirosha |  | Rohit Varate | [28 empty] | NA | [19 empty] | Chronic obstructive pulmonary disease |  | Global | Completed | Yes | [16 empty] | None of the above
CQVJ499A | CQVJ499A2301 | C1001431 | Phase III | RAVE_RAW | [7 empty] | 2015-04-14 05:30 |  | 2014-09-29 05:30 |  | Completed |  | 2016-11-01 05:30 |  | 2016-12-08 05:30 | FALSE |  |  |  | Alcon InHouse |  | Efficacy and Safety of Brinzolamide 10 mg/mL/Brimonidine 2 mg/mL Eye Drops, Suspension Compared to Brinzolamide 10 mg/mL Eye Drops, Suspension plus Brimonidine 2 mg/mL Eye Drops, Solution in Subjects with Open-Angle Glaucoma or Ocular Hypertension | Phase 3_Brinzolamide_CQVJ499A2301 | P6 Global Health | [5 empty] | Liza Svoboda | Liza Svoboda | [66 empty] | Glaucoma | No | Global | Open | Yes | [16 empty] | None of the above
CQVJ499A_MA | CQVJ499A2401 | C1001736 | Phase IV | RAVE_RAW | [7 empty] | 2015-08-07 05:30 |  | 2015-03-11 05:30 |  | Completed | 2018-05-18 05:30 | 2018-02-27 05:30 | 2018-03-16 05:30 | 2018-03-15 05:30 | FALSE |  |  |  | Alcon InHouse |  | Additive Effect of Twice Daily Brinzolamide 1% /Brimonidine 0.2% Fixed Dose Combination as an Adjunctive Therapy to a Prostaglandin Analogue | CQVJ499A2401 Phase 4_Simbrinza | P6 Global Health | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Glaucoma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVJ499A_MA | CQVJ499A2402 | C1001737 | Phase IV | RAVE_RAW | [7 empty] | 2016-06-24 05:30 |  | 2016-02-11 05:30 |  | Completed | 2018-07-11 05:30 | 2018-07-13 05:30 | 2019-02-04 05:30 | 2018-07-30 05:30 | FALSE |  |  |  | Alcon InHouse |  | Safety and Efficacy with Twice Daily Brinzolamide 1% / Brimonidine 0.2% (SIMBRINZA) as an Adjunctive Therapy to Travoprost 0.004% / Timolol 0.5% (DUOTRAV) | CQVJ499A2402 Ph4_Simb | P6 Global Health | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Glaucoma | No | Global | Open | Yes | [16 empty] | None of the above
CQVJ499A_MA | CQVJ499A2403 | C1001739 | Phase IV | RAVE_RAW | [7 empty] | 2016-05-23 05:30 |  | 2016-03-23 05:30 |  | Completed |  | 2017-01-14 05:30 |  | 2017-02-01 05:30 | FALSE |  |  |  | Alcon InHouse |  | 24-hr Intraocular Pressure Control With SIMBRINZA Â® | Phase 4_Brinzolamide_QVJ499A2403 | P6 Global Health | [5 empty] | Steve Burmaster | Steve Burmaster | [66 empty] | Glaucoma |  | Global | Completed | Yes | [16 empty] | None of the above
CQVJ499A_MA | CQVJ499A2404 | C1001738 | Phase IV | RAVE_SDTM | [7 empty] | 2017-09-21 05:30 |  | 2017-02-14 05:30 |  | Completed | 2019-04-03 05:30 | 2017-12-04 05:30 | 2018-03-01 05:30 | 2018-03-01 05:30 | FALSE |  |  |  | Alcon InHouse |  | A 6-week, double masked, placebo-controlled study to evaluate the efficacy and safety of twice-daily brinzolamide 1% / brimonidine 0.2% fixed dose combination as an adjunctive therapy to travoprost 0.004% in reducing intraocular pressure in patients with normal tension glaucoma. | Phase 4_Simbrinza_QVJ499A2404 | P6 Global Health | [6 empty] | Sue-zette Valera | [66 empty] | Glaucoma | No | Global | Completed | No | [16 empty] | None of the above
CQVM149A0 | CQVM149B1101 | C1001432 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2017-07-21 05:30 |  | 2016-12-22 05:30 |  | Completed | 2018-10-29 05:30 | 2017-10-25 05:30 | 2018-01-19 05:30 | 2018-01-24 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | IDMA Shared JP | NIBR - RESP |  | CQVM149B1101 PK Ethnic senstivity | P8 Respiratory | Langlo, Francois | Hagiwara, Yayoi | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | YOHEI SAKITA | YOHEI SAKITA | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 119 | 0 |  |  | 0 |  |  |  | 501 | 1 | 0 |  | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B1304 | C1001437 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-04-11 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-04-28 05:30 |  | 2016-11-15 05:30 |  | Completed | 2019-04-08 05:30 | 2019-04-08 05:30 | 2019-05-17 05:30 | 2019-05-17 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, open-label, single arm, 52-week treatment study to assess the safety of QVM149 in Japanese patients with asthma | CQVM149B1304 JP QVM LT safety | P8 Respiratory | Mahajan, Vinay | Hagiwara, Yayoi | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas |  | MAKI YAMAGUCHI | Dadapogu, Jesica Priyadarshini | [14 empty] | Bhosale, Pritam |  | Sushant Sundar | [21 empty] | Pharma | Novartis | InHouse | 2017-04-11 05:30 | 2017-04-11 05:30 |  |  | NA | [7 empty] | 81 | 0 |  |  | 0 |  |  |  | 487 | 9 | 0 |  | Asthma | Yes | Global | Completed | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B1305 | C1001438 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-04-10 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-04-25 05:30 |  | 2016-11-15 05:30 |  | Completed | 2019-02-12 05:30 | 2019-02-12 05:30 | 2019-03-11 05:30 | 2019-03-08 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, open-label, single arm, 52-week treatment study to assess the safety of QMF149 in Japanese patients with asthma | CQVM149B1305 JP QMF LT safety | P8 Respiratory | Mahajan, Vinay | Tsukazaki, Mayuka | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas |  | MAKI YAMAGUCHI | Dadapogu, Jesica Priyadarshini | [14 empty] | Genga, Vardhini |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | InHouse | 2017-04-10 05:30 | 2017-04-10 05:30 |  |  | NA | [7 empty] | 79 | 0 |  |  | 0 |  |  |  | 491 | 9 | 0 |  | Asthma | Yes | Global | Completed | Yes | [14 empty] | DBL | Bhosale, Pritam | None of the above | Yes
CQVM149B | CQVM149B1401 | C3001309 | Phase IV | Other | Other |  |  | 2022-12-30 05:30 | DB Set-Up | DB Go-live | 2022-02-23 05:30 |  | 2022-05-10 05:30 |  |  | Planned | 2024-12-31 05:30 |  | 2024-12-31 05:30 |  | FALSE | Japan PMS | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | DF RESP | A database study to assess the relative risk of cardiovascular events in Japanese patients with asthma on indacaterol acetate/glycopyrronium bromide/mometasone furoate (QVM149) in Japan | CQVM149B1401 | P8 Respiratory | YAMADA, KAYO | MORI, YUMIKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | YUKIE YOSHIZAWA | YUKIE YOSHIZAWA | [17 empty] | Sushant Sundar | [28 empty] | NA | [19 empty] | Asthma | No | Global | Open | Yes | [16 empty] | None of the above
CQVM149A0 | CQVM149B2102 | C1001433 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-10-16 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-10-13 05:30 |  | 2017-02-06 05:30 |  | Completed | 2018-03-15 05:30 | 2018-03-03 05:30 | 2018-07-31 05:30 | 2018-05-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, open-label, control balanced, crossover study to evaluate the potential for pharmacokinetic interation following multiple inhaled doses of indacaterol (QAB149) acetate, glycopyrronium bromide (NVA237) and mometasone furoate (MF) delivered in fixed combination (QVM149) via the Copncept1 device 1 in healthy subjects | CQVM149B2Chrome Component Interaction | P8 Respiratory | Langlo, Francois | Chamarthi, Yasaswini | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti |  | Michael Hahn | Narasetty, Indumathi | [14 empty] | Ramu, Harikrishnan |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2017-10-16 05:30 | 2017-10-16 05:30 |  |  | NA | [7 empty] | 243 | 0 |  |  | 0 |  |  |  | 279 | 2 | 0 |  |  |  | Global | Completed | Yes | [16 empty] | None of the above
CQVM149A0 | CQVM149B2103 | C1001446 | Phase I | NCDS | CRO - EDC |  |  | 2018-11-09 05:30 | DB Locked |  |  | 2018-11-08 05:30 |  | 2017-09-27 05:30 |  | Completed | 2018-12-05 05:30 | 2018-12-05 05:30 | 2019-03-29 05:30 | 2019-02-28 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CQVM149B2103 China QVM PK | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Katie Li | Yaliang Li | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149A0 | CQVM149B2104 | C1001441 | Phase I | Other | CRO - EDC |  |  | 2019-01-18 05:30 | DB Locked |  |  | 2018-11-20 05:30 |  | 2017-09-20 05:30 |  | Completed | 2019-02-11 05:30 | 2018-12-17 05:30 | 2019-04-29 05:30 | 2019-03-05 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - RESP |  | CQVM149B2104 China QMF PK | P8 Respiratory | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Yaliang Li | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149A0 | CQVM149B2203 | C1001434 | Phase II | NCDS | OC RDC - Inhouse |  |  | 2018-06-29 05:30 | DB Locked | Final DBL Achieved |  | 2017-09-05 05:30 | 2018-01-19 05:30 | 2017-02-27 05:30 |  | Completed | 2018-01-29 05:30 | 2018-01-18 05:30 | 2018-05-10 05:30 | 2018-05-10 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, double-blind, placebo-controlled, three-period cross-over study to assess the pharmacodynamics, safety, tolerability, and pharmacokinetics of two orally inhaled indacaterol salts (maleate and acetate) delivered via the Concept1 inhalation device in patients with asthma | CQVM149B2203 Salt bridging | P8 Respiratory | Langlo, Francois | Singh, Namrata | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Pascale Pinot | Kristina Wagner | Joshi, Alekhya | [14 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2017-08-24 05:30 | 2017-08-24 05:30 |  |  | NA | [7 empty] | 91 | 0 |  |  | 0 |  |  |  | 392 | 6 | 0 |  | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B2204 | C1001439 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-04-24 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-05-04 05:30 |  | 2016-11-09 05:30 |  | Completed | 2017-12-29 05:30 | 2017-12-29 05:30 | 2018-02-15 05:30 | 2018-02-12 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, randomized, double-blind, placebo-controlled 3-period complete cross-over study to assess the bronchodilator effects and safety of glycopyrronium bromide (NAV237) (25 and 50 ug o.d.) in asthma patients | CQVM149B2204 Silver NVA DRF | P8 Respiratory | Mahajan, Vinay | Rode, Prathamesh | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas |  | Olivia Burgos Le Leon | Dadapogu, Jesica Priyadarshini | [14 empty] | Bothe, Dnyanesh |  | Sushant Sundar | [13 empty] | 100 | [7 empty] | Pharma | Novartis | InHouse | 2017-04-24 05:30 | 2017-04-24 05:30 |  |  | NA | [7 empty] | 64 | 0 |  |  | 0 |  |  |  | 521 | 6 | 0 |  | Asthma | Yes | Global | Open | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B2208 | C1001435 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2017-01-21 05:30 |  | 2017-03-20 05:30 |  | Completed | 2018-08-01 05:30 | 2018-08-02 05:30 | 2018-10-09 05:30 | 2018-10-09 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, double-blind, double-dummy, active- controlled, 3-period complete cross-over study to assess the bronchodilator effect and safety of two doses of QVM149 compared to a fixed dose combination of salmeterol/fluticasone in patients with asthma | CQVM149B2208 Serial spirometry | P8 Respiratory | Langlo, Francois | Kshetrapal, Abhishek | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Ruobing Li | Ruobing Li | Joshi, Alekhya | [14 empty] | Nagalla, Lakshmi Naga Lavanya |  | Rohit Varate | [15 empty] | Yes | [5 empty] | Pharma | Novartis | InHouse | 2017-05-15 05:30 | 2017-05-15 05:30 |  |  | NA | [7 empty] | 66 | 0 |  |  | 0 |  |  |  | 204 | 5 | 0 |  | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B2209 | C1001442 | Phase II | NCDS | OC RDC - Inhouse |  |  | 2017-06-26 05:30 | DB Locked | Final DBL Achieved |  | 2017-06-26 05:30 |  | 2017-03-10 05:30 |  | Completed | 2018-04-06 05:30 | 2018-02-24 05:30 | 2018-08-28 05:30 | 2018-06-12 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - RESP | A randomized, double-blind, repeat dose cross-over study to assess the bronchodilator effects of once daily QVM149 following morning or evening dosing for 14 days compared to placebo in patients with asthma | CQVM149B2209 AM PM dosing study | P8 Respiratory | Langlo, Francois | Bhoite, Raviraj Vijay | Soni, Kushal | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Pascale Pinot | Pascale Emilie Genevi��ve Pinot | Joshi, Alekhya | [14 empty] | Kadam, Sandeep |  | Rohit Varate | [14 empty] | OCRDC - Inhouse | [6 empty] | Pharma | Novartis | InHouse | 2017-07-03 05:30 | 2017-07-03 05:30 |  |  | NA | [7 empty] | 63 | 0 |  |  | 0 |  |  |  | 284 | 5 | 0 |  | Asthma | No | Global | Completed | Yes | [16 empty] | None of the above
CQVM149B | CQVM149B2301 | C1001436 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2008-05-29 05:30 |  | 2015-07-14 05:30 |  | Completed | 2019-08-01 05:30 |  | 2019-08-19 05:30 | 2019-08-07 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | DF RESP | A multi-center, randomized, 52 weeks treatment, double-blind, triple-dummy study to assess the efficacy and safety of QMF149 compared with mometasone furoate and salmeterol/fluticasone | CQVM149B2301 Palladium QMF Ph3 pivotal | P8 Respiratory | Mahajan, Vinay | Dubey, Rohit | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Kamin Personett | Kamin Personett | Meda, Sreelakshmi | [14 empty] | Rajhans, Khushbu Kumari |  | Sushant Sundar | [13 empty] | 100 | [7 empty] | Pharma | ICON | External Full | 2015-10-27 05:30 | 2015-10-27 05:30 |  |  | NA | [7 empty] | 102 | 0 |  |  | 0 |  |  |  | 684 | 15 | 0 |  | Asthma | Yes | Global | Open | Yes | [14 empty] | DBL | Kommu, Ranjith Kumar | None of the above | Yes
CQVM149B | CQVM149B2302 | C1001440 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-12-08 05:30 |  | 2015-07-20 05:30 |  | Completed | 2019-09-30 05:30 | 2019-06-14 05:30 | 2019-10-15 05:30 | 2019-07-19 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | IDMA Transaction | DF RESP | A multicenter, randomized, 52-week, double-blind, parallelgroup, active controlled study to compare the efficacy and safety of QVM149 with QMF149 in patients with asthma | CQVM149B2302 Iridium QVM Ph3 pivotal | P8 Respiratory | Mahajan, Vinay | Dubey, Rohit | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Kamin Personett | Kamin Personett | Meda, Sreelakshmi | [14 empty] | Rajhans, Khushbu Kumari |  | Sushant Sundar | [13 empty] | 100 | [7 empty] | Pharma | ICON | External Full | 2015-11-09 05:30 | 2015-11-09 05:30 |  |  | NA | [7 empty] | 91 | 0 |  |  | 0 |  |  |  | 671 | 16 | 0 |  | Asthma | Yes | Global | Open | Yes | [14 empty] | DBL | Kommu, Ranjith Kumar | None of the above | Yes
CQVM149B | CQVM149B2303 | C1001443 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-02-22 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-01-16 05:30 |  | 2018-03-02 05:30 |  | Completed | 2019-05-06 05:30 | 2018-11-30 05:30 | 2019-03-13 05:30 | 2019-01-11 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multi-center, randomized, 12 -week treatment, double-blind study to assess the efficacy and safety of QMF149 (150/80Âµg) compared with MF Twisthaler (200Âµg) in adult and adolescent patients with asthma | Quartz QMF low dose Ph3_CQVM149B2303 | P8 Respiratory | Mahajan, Vinay | Rode, Prathamesh | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Lisa Satlin; Norbert Ahlers | Lisa Satlin | Dadapogu, Jesica Priyadarshini | [14 empty] | Tidke, Shyam |  | Sushant Sundar | [14 empty] | OCRDC - Inhouse | No | [5 empty] | Pharma | Novartis | InHouse | 2017-02-21 05:30 | 2017-02-21 05:30 |  |  | NA | [7 empty] | 99 | 0 |  |  | 0 |  |  |  | 654 | 13 | 0 |  | Asthma | Yes | Global | Open | Yes | [14 empty] | DBL | Sahu, Ahallad | None of the above | Yes
CQVM149B_MA | CQVM149B2306 | C1001740 | Phase III | NCDS | OC RDC - Inhouse |  | 2017-12-15 05:30 | 2018-02-05 05:30 | DB Locked | Final DBL Achieved |  | 2018-02-05 05:30 |  | 2017-11-20 05:30 |  | Completed | 2019-07-18 05:30 | 2019-07-19 05:30 | 2019-10-14 05:30 | 2019-09-26 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP | A multicenter, open-label, randomized, 26-week, parallel-group, non-inferiority, active controlled study to compare the efficacy and safety of QVM149 with a free triple combination of salmeterol/fluticasone + tiotropium in patients with uncontrolled asthma. | CQVM149B2306 Argon l | P8 Respiratory | Mahajan, Vinay | Gijo, Ani | P M, Prasanth Kumar | Regula, Ramakrishna | Hiriyanna, Srinivas | Michele Sauer | Michele Sauer | Dadapogu, Jesica Priyadarshini | [14 empty] | Manoharan, Vivek |  | Sushant Sundar | [13 empty] | 78 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | Pharma | Novartis | InHouse |  | 2017-12-15 05:30 | Shewane, Roshni | Gehlawat, Priya | NA | [7 empty] | 68 | 0 |  |  | 0 |  |  |  | 462 | 13 | 0 |  | Asthma | Yes | Global | Open | Yes | [16 empty] | None of the above
CQVM149C | CQVM149C2201 | C3000386 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-05-24 05:30 | DB Set-Up | DB Go-live | 2022-04-15 05:30 |  | 2021-11-12 05:30 | 2021-11-15 05:30 |  | Planned | 2023-12-18 05:30 |  | 2024-01-29 05:30 |  | FALSE | Submission | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | DF RESP |  | CQVM149C2201 NVA DRF in 6-11 yo | P8 Respiratory | Mahajan, Vinay | Rasegaonkar, Sneha Nitin | Dubey, Rohit | Sahu, Vandana | Hiriyanna, Srinivas | Kathleen Scott | Kathleen Scott | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR | [6 empty] | Shrivastava, Nikhil | Not Started | [7 empty] | Sushant Sundar | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Asthma |  | Global | Open | Yes | [16 empty] | None of the above
CQVM149C | CQVM149C2301 | C3000512 | Phase III | NCDS_2 |  |  |  | 2023-01-26 05:30 |  | Final DBL | 2026-04-22 05:30 |  | 2022-08-15 05:30 |  |  | Planned | 2026-03-18 05:30 |  | 2026-04-22 05:30 |  | FALSE |  |  |  | InHouse |  |  | CQVM149C2301 QVM Adolescent Ph3 | P8 Respiratory | [5 empty] | Michele Valentin | Michele Valentin | [54 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Asthma |  | Global | Open | Yes | [16 empty] | None of the above
CRAD001A | CRAD001A1401 | C1001449 | Phase IV | Paper | [7 empty] | 2007-11-06 05:30 |  | 2007-01-24 05:30 |  | Completed |  | 2017-09-01 05:30 |  | 2017-09-01 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational investigation of Certican tablet for use in heart transplantation | CRAD001A1401_JPN PMS | P6 Global Health | [5 empty] | MARIKO YAMADA | YOSHIHISA SATOU | [66 empty] | Cardiac transplant | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001A | CRAD001A1402 | C1001447 | Phase IV | Other | [7 empty] | 2012-04-19 05:30 |  | 2011-11-01 05:30 |  | Completed | 2023-04-10 05:30 | 2017-03-01 05:30 | 2023-04-10 05:30 | 2017-03-01 05:30 | FALSE |  |  |  | Outsourced |  |  | CRAD001A1402 | P6 Global Health | [6 empty] | YOSHIHISA SATOU | [66 empty] | Renal disease; Transplant | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001A | CRAD001A2314 | C1001448 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-08-17 05:30 |  | 2011-05-12 05:30 |  | Completed | 2018-10-05 05:30 | 2018-09-24 05:30 | 2018-10-29 05:30 | 2018-10-29 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A 12-month, multicenter, open label, randomized, controlled study to evaluate the efficacy, tolerability and safety of early introduction of everolimus, reduced CNI, and early steroid elimination compared to standard CNI, mycophenolate mofetil and steroid regimen in paediatric renal transplant recipients with a 24-month additional safety follow-up. | CRAD001A2314 everolimus in paediatrics | P6 Global Health | Vithala, Srinivas | Somasundar, Karan | Bhabhe, Nikhil | Gracey Sugunan, Unni Krishnan | Krishnan, Kripesh | Kimberly Holmes | Kanan Jhala | Tripathi, Shakuntala | R, Ankit | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD |  | BP21 | PPD |  |  |  |  | 76 | 0 |  |  | 0 |  |  |  | 471 | 0 | 0 |  | Renal transplant | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001A_MA | CRAD001A2433 | C1001745 | Phase IV | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2013-12-03 05:30 |  | 2013-07-03 05:30 |  | Completed | 2018-01-15 05:30 | 2018-01-17 05:30 | 2018-03-19 05:30 | 2018-03-20 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA Transaction | DF ID | A 24 month, multicenter, randomized, open-label safety and efficacy study of concentration controlled Everolimus with reduced calcineurin inhibitor vs mycophenolate with standard calcineurin inhibitor in de novo renal transplantation&#xD; | CRAD001A2433 | P6 Global Health | Paigaonkar, Gargi | Sen, Sujoy | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther | Ana Maria Marti | Ana Maria Marti | [15 empty] | Rathinasabapathy, Mehala |  | Sandeep Kadam | [21 empty] | Pharma | ICON | External Full |  | 2013-09-13 05:30 |  |  | ICON | [7 empty] | 54 | 0 |  |  | 0 |  |  |  | 490 | 2 | 0 |  | Transplant | No | Global | Completed | Yes | [16 empty] | None of the above
CRAD001A_MA | CRAD001AJP01 | C1201706 | Phase IV | Other | [7 empty] | 2014-12-16 05:30 |  |  |  | Completed |  | 2018-08-31 05:30 |  |  | FALSE |  |  |  | Outsourced |  | 2-year, prospective, observational study to evaluate the renal function in maintenance kidney transplant patients with calcineurin inhibitor plus Certican regimen | CRAD001AJP01 | P6 Global Health | [5 empty] | MARIKO YAMADA | TOMOMI MIKAMI | [66 empty] | Liver transplant | No | Local | Terminated | Yes | [16 empty] | None of the above
CRAD001C | CRAD001C1X01B | C1001451 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-01-16 05:30 |  | 2013-10-03 05:30 |  | Completed | 2019-05-08 05:30 | 2019-04-25 05:30 | 2019-06-06 05:30 | 2019-06-06 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | An open-label, multi-center everolimus roll-over protocol for patients who have completed a previous Novartis-sponsored everolimus study and are judged by the investigator to benefit from continued everolimus treatment. | Japan_RAD001C1X01B_Rollover | P0 Oncology (Solid Tumors all MA Onc projects) |  | Kikawa, Mirai | Okuzono, Seigou | Okuzono, Seigou | Hiriyanna, Srinivas | HIROMI TAKEUCHI | HIROMI TAKEUCHI |  | Gupta, Anshu | [15 empty] | Sushant Sundar | [28 empty] | PPD | Oncology | AP21 | PPD | Jeannette.Welsch@ppdi.com | Earlier DBD: Jugnu Kumari | [14 empty] | Metastatic neoplasm | No | Global | Completed | Yes | [16 empty] | None of the above
CRAD001C | CRAD001C2X01B | C1001749 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-05-14 05:30 |  | 2012-12-11 05:30 |  | Completed | 2020-08-28 05:30 | 2020-08-28 05:30 | 2020-11-05 05:30 | 2020-09-15 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | An open-label multi-center everolimus roll-over protocol for patients who have completed a previous Novartis-sponsored everolimus study and are judged by the investigator to benefit from continued everolimus treatment. | PhIV-Basket/Rollover Protocol_CRAD001C2X01B | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vadla, Ravinder | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas | Janet Lasher | Janet Lasher |  | Sinha, Deepakshi | [15 empty] | Sushant Sundar | [28 empty] | PPD | Oncology | AP21 | PPD | Racquel.Silva@ppdi.com | Earlier DBD: Asha Rajanna |  |  | 26 | 0 |  |  | 0 |  |  |  | 206 |  |  |  | Metastatic neoplasm | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001H | CRAD001H1401 | C1001455 | Phase IV | Other | CRO - EDC |  |  | 2018-05-31 05:30 | DB Locked |  |  | 2018-07-19 05:30 | 2018-08-07 05:30 | 2017-08-15 05:30 |  | Completed | 2020-11-30 05:30 | 2020-10-30 05:30 | 2021-09-30 05:30 | 2021-09-30 05:30 | FALSE | Japan PMS | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | DF ID | Special drug use observational investigation protocol of CERTICANÂ® tablet for use in liver transplantation | CRAD001H1401 JPN PMS | P6 Global Health | YAMADA, KAYO | Ichinowatari, Mihoko | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | KEIKO FUJINO | HARUKA NISHIOKA | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Liver transplant | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001H | CRAD001H2305 | C1001453 | Phase III | NOVDD | [7 empty] | 2012-10-09 05:30 |  | 2012-02-18 05:30 |  | Completed |  | 2016-06-01 05:30 |  | 2016-06-27 05:30 | FALSE |  |  |  | Outsourced |  |  | CRAD001H2305 | P6 Global Health | [73 empty] | Liver transplant | No | Global | Terminated | [17 empty] | None of the above
CRAD001H | CRAD001H2307 | C1001750 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2013-09-25 05:30 |  | 2012-12-22 05:30 |  | Completed |  | 2017-10-10 05:30 | 2017-12-19 05:30 | 2017-11-24 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | IDMA Transaction | DF ID | A 24 month, randomized, controlled, study to evaluate the efficacy and safety of concentration-controlled everolimus plus reduced tacrolimus compared to standard tacrolimus in recipients of living donor liver transplants | CRAD001H2307 | P6 Global Health | Paigaonkar, Gargi | Sharma, Tanvi | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther | Carole Sips | Carole Sips | [15 empty] | Kommu, Ranjith Kumar |  | Sandeep Kadam | [14 empty] | CRO | [13 empty] | Cognizant | [19 empty] | Liver transplant rejection | Yes | Global | Open | Yes | [16 empty] | None of the above
CRAD001H | CRAD001H2307E1 | C1001454 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2015-12-21 05:30 |  | 2015-08-12 05:30 |  | Completed | 2018-04-13 05:30 | 2018-04-20 05:30 | 2018-07-10 05:30 | 2018-07-03 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | ICON | DF ID | Study extension of RAD001H2307 - LDLT recipients | CRAD001H2307E1 | P6 Global Health | Paigaonkar, Gargi | Singh, Ambuj | Sharma, Tanvi | Bhoir, Vinit Kisan | Ninan, Esther | Carole Sips | TAKAMITSU HIRANO | Meda, Sreelakshmi | [14 empty] | Ghate, Dhananjay |  | Sandeep Kadam | [21 empty] | Pharma | ICON | External Full | 2015-11-23 05:30 | 2015-11-23 05:30 |  |  | ICON | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 509 | 1 | 0 |  | Liver transplant | Yes | Global | Completed | Yes | [16 empty] | None of the above
CRAD001H | CRAD001H2406 | C4001217 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2018-10-31 05:30 | 2018-12-27 05:30 | DB Locked | Final DBL Achieved |  | 2018-12-12 05:30 | 2018-06-29 05:30 | 2018-08-17 05:30 |  | Completed | 2020-12-30 05:30 | 2020-11-24 05:30 | 2021-02-26 05:30 | 2021-01-19 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A long-term prospective non-interventional observational study extension in Living Donor Liver Transplant Recipients (LDLTRs) treated with CerticanÂ®/ZortressÂ® (everolimus) plus reduced tacrolimus (TAC) versus standard TAC control | CRAD001H2406 Observational HCC Patients | P6 Global Health | Vithala, Srinivas | Dorepalli, Saidulu | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Abhishek Sople | Kanan Jhala | Oguri, Praveen | Prasanna Kumar, VTSSR | In Progress | 2020-01-20 05:30 |  |  | DRM (DIAL) | Chitransh, Arpit | Patnaik, Angella | Completed | 8-Jan-2021: RF updated for duplicate AFP parameter value for PPC3 updates as per DDPASS comments. SNOW#51 raised for SMT and LSH updates. 25AUG2020: PPC#4 form verified. No RF update required. ALS shared for SMT updates. 07-JUL-2020: RF up to date for all final DTS and PPPCs implemented in the study. 07Feb2020: No pending forms . No DTS in the study 24JAN2020: DM confirmed on 12 forms data not available in J-review. Rule file has all the domains included. LSP to confirm. No issues. Rule file sent for Peer review (Arpit) | None | None | 2019-01-03 05:30 |  | Praveen kumar, Chakka Giri | Varate, Rohit | Sai Krishna Mettugari | Completed | 2019-01-09 | Completed | 2019-06-07 05:30 |  |  | 2019-01-09 05:30 | 2019-01-09 05:30 | Study Transition | 2020-05-06 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2021-01-20 05:30 | 2021-01-22 05:30 | [9 empty] | NA | [5 empty] | 5 | 17 | 30 | 0 | 196 | 404 | 0 | 82 | 4 | 113 | 521 | 1 | 0 |  | Liver transplant | No | Global | Open | Yes | [10 empty] | 2019-06-06 05:30 | [5 empty] | None of the above
CRAD001J | CRAD001J2301 | C1001456 | Phase III | NOVDD | Paper |  |  |  | DB Locked |  |  | 2009-09-10 05:30 |  | 2009-03-17 05:30 |  | Completed | 2018-02-20 05:30 | 2017-10-23 05:30 | 2018-02-21 05:30 | 2018-02-23 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A randomized double-blinded study of RAD001 in combination with Herceptin and Paclitaxel versus Herceptin and Paclitaxel alone in the treatment of patients with HER2 positive breast cancer | CRAD001J2301(BOLERO1) PhIII-mBC/HER2p/L1-C(tra/pac | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vadla, Nagarajachari | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas | Florence Noel-Baron | Florence Marion Claude Noel-Baron |  | Gupta, Anshu | [15 empty] | Sushant Sundar | [28 empty] | Other | Oncology | BP21 | TRIO | david.arguello@trioncology.org | Earlier DBD: Jugnu Kumari | [14 empty] | Breast cancer | Yes | Global | Terminated | Yes | [16 empty] | None of the above
CRAD001L | CRAD001L1401 | C1001457 | Phase IV | Other |  |  |  | 2010-03-10 05:30 |  |  |  | 2010-04-12 05:30 | 2009-12-21 05:30 | 2010-01-27 05:30 |  | Completed | 2018-01-19 05:30 | 2018-01-17 05:30 | 2018-01-19 05:30 | 2018-01-17 05:30 | FALSE |  |  |  | Outsourced |  | A special drug use observational study of Afinitor in patients for unresectable and/or metastatic renal cell carcinoma | Japan PMS_RAD001L1401 mRCC | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | NAOKO USHIDA | NAOKO USHIDA | [66 empty] | Renal cell carcinoma | No | Global | Completed | Yes | [16 empty] | None of the above
CRAD001M | CRAD001M1401 | C1001753 | Phase IV | Paper |  |  |  | 2012-12-05 05:30 |  |  |  | 2012-12-05 05:30 | 2012-08-29 05:30 | 2012-11-15 05:30 |  | Completed | 2019-01-31 05:30 | 2019-01-31 05:30 | 2019-01-31 05:30 | 2019-01-31 05:30 | FALSE |  |  |  | Outsourced |  | TSCspecial observation | CRAD001M1401 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | MACHIKO MORISHITA | KAZUAKI YAMAGUCHI | [66 empty] | Tuberous sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001M | CRAD001M2304 | C1001458 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-04-29 05:30 |  | 2012-09-07 05:30 |  | Completed |  | 2017-10-25 05:30 | 2018-01-05 05:30 | 2017-11-30 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A three-arm, randomized, double-blind, placebo-controlled study of the efficacy and safety of two trough-ranges of everolimus as adjunctive therapy in patients with tuberous sclerosis complex (TSC) who have refractory partial-onset&#xD; seizures | CRAD001M2304 (EXIST-3)_PhIII-TSC/Seizure/L3-M | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vavasseur, Celine | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas | Nathalie Pognan | Nathalie Pognan |  | Gupta, Anshu | [15 empty] | Sushant Sundar | [28 empty] | IQVIA | Oncology | BP21 | Quintiles | Grégory Sautejeau (gregory.sautejeau@quintiles.com) | Earlier DBD: Asha Rajanna | [14 empty] | Tuberous sclerosis | Yes | Global | Completed | Yes | [16 empty] | None of the above
CRAD001M | CRAD001M2305 | C1001459 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2026-11-06 05:30 | 2014-12-17 05:30 |  | 2013-11-25 05:30 |  | Active | 2026-09-25 05:30 |  | 2026-11-06 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Long-term follow-up study to monitor the growth and development of pediatric patients previously treated with everolimus in study CRAD001M2301 (EXIST-LT) | CRAD001M2305 (EXIST LT)_PhIV-TSC/SEGA/L1-M -LTFU | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Chavan, Rohan Prakash | Shah, Jay Harshadbhai | Mayekar, Meera | Hiriyanna, Srinivas | Janet Ng-Sikorski | Janet Ng-Sikorski |  | Lingampalli, Rohit | [15 empty] | Sushant Sundar | [28 empty] | IQVIA | Oncology | BP21 | Quintiles | Celine.Moscherosch@quintiles.com> | Earlier DBD: Jugnu Kumari | [14 empty] | Tuberous sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001M | CRAD001M2401 | C3001377 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2018-09-27 05:30 | 2018-11-28 05:30 | DB Locked | Final DBL Achieved |  | 2018-11-09 05:30 | 2018-01-23 05:30 | 2018-01-10 05:30 |  | Completed | 2020-10-26 05:30 | 2020-09-25 05:30 | 2020-11-09 05:30 | 2020-11-06 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | Phase IV, single arm study of efficacy and safety of everolimus in Chinese adults with Tuberous Sclerosis Complex who has renal Angiomyolipomas not requiring immediate surgery | CRAD001M2401 (PAC China) PhIV-TSC/AML | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Chandrakant, Khilari | Sardesai, Pallavi Sharad | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Amy Zhou | Yan Zhou | Oguri, Praveen | Prasanna Kumar, VTSSR | In Progress |  | Study locked 06Nov2020 |  | DRM (DIAL) | Chitransh, Arpit | Patnaik, Angella | Completed | 20AUG2020: RF finalized for PPC6 updates. SNOW#51 raised for SMT and LSH updates. 19AUG2020: RF V6.0 for PPC6 updates released for Peer Review. 28JUL2020: Already confirmed that PRIMARY001 form will not be included in the RF. Already included in excluded forms tab. 07-JUL-2020: No RF updates for PPC5. SMT and LSH updates have been notified to the team. 17FEB2020: Team confirmed they do not require Primary form data. Hence, not included in the RF. 4FEB2020: As confirmed by the study lead Tuberous Sclerosis Complex (TSC) Diagnostic (issue currently added in PPC). There is no update to the Rule file required for this. SR05- Raised on 18Jan2019, Rule file in development with Arpit | None | None | 2019-01-18 05:30 |  | Nagalla, Lakshmi Naga Lavanya | Kadam, Sandeep | Sai Krishna Mettugari | Completed | 2019-01-24 | Completed | 2019-06-18 05:30 | Domains published for DIAL: AE.CM,DD,DM,DS,DV,EC,EG,IE,LB,MH,ODM,PR,QS,SS,SV,VS,ZF,ZT,TV |  | 2019-01-24 05:30 | 2019-01-24 05:30 | SNOW 05 was raised after FPFV,Pre-requisites not met | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | 2020-11-06 05:30 | 2020-11-09 05:30 | [9 empty] | NA | [5 empty] | 6 | 10 | 44 | 0 | 97 | 399 | 0 | 151 | 34 | 167 | 600 | 2 | 0 |  | Tuberous sclerosis | No | Global | Open | Yes | [10 empty] | 2019-06-18 05:30 |  |  |  | DBL |  | None of the above | Yes
CRAD001M | CRAD001M2X02B | C1001460 | Phase III | NCDS | OC RDC - Inhouse | 2019-07-09 05:30 | 2019-07-09 05:30 |  | DB Conduct | Final DBL | 2027-09-13 05:30 | 2017-04-02 05:30 |  | 2016-10-25 05:30 |  | Active | 2027-08-04 05:30 |  | 2027-09-13 05:30 |  | FALSE | NA | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | An open-label, IIIB, multi-center everolimus roll-over protocol for patients have completed EXIST-3, a Novartis-sponsored everolimus study in patients with tuberous sclerosis complex (TSC) who have refractory partial-onset seizures, and who are judged by the investigator to benefit from continued everolimus treatment. | CRAD001M2X02B (EXIST3 Rollover) PhIV-TSC/Seizures | P0 Oncology (Solid Tumors all MA Onc projects) | Ball, Michael | Chavan, Rohan Prakash | Shah, Jay Harshadbhai | Mayekar, Meera | Hiriyanna, Srinivas | Fabian Romen | Fabian Romen | Killamsetty, Nanari Ram | Meda, Sreelakshmi | [13 empty] | Manoharan, Vivek |  | Sushant Sundar | [13 empty] | 100 | OCRDC - Inhouse | No | -NA-;#ZK;#ZK02;#ZK03 |  |  |  |  | ONC | ICON | ICON | 2017-03-10 05:30 | 2017-03-10 05:30 | Meda, Sreelakshmi |  | NA | [7 empty] | 43 | 0 |  |  | 0 |  |  |  | 175 | 0 | 0 |  | Tuberous sclerosis | No | Global | Open | Yes | [16 empty] | None of the above
CRAD001C_MA | CRAD001MIC03 | P1003009 | Phase IV | Other | CRO - EDC |  |  |  | DB Locked |  |  | 2012-08-10 05:30 |  | 2014-08-07 05:30 |  | Completed | 2020-01-22 05:30 | 2020-01-22 05:30 | 2020-03-04 05:30 | 2020-03-09 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | An International Registry Collecting Data on Manifestations, Interventions and Outcomes in Patients with Tuberous Sclerosis Complex. TOSCA | CRAD001MIC03 TSC Registry TOSCA | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Varshney, Kapil | Varshney, Kapil | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Yulia Hirschberg | Yulia Hirschberg | [17 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | [7 empty] | 89 | 0 |  |  | 0 |  |  |  | 1019 |  |  |  | Tuberous sclerosis | No | Regional | Open | Yes | [16 empty] | None of the above
CRAD001M_MA | CRAD001MJP04 | C1201504 | Phase II | NOVDD | Paper |  |  |  | DB Locked |  |  | 2013-07-02 05:30 |  | 2013-05-17 05:30 |  | Completed |  | 2017-09-25 05:30 |  | 2017-11-17 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | Exploratory study of the efficacy of everolimus on autism spectrum disorder (ASD) in patients with tuberous sclerosis complex (TSC) | CRAD001MJP04 | P0 Oncology (Solid Tumors all MA Onc projects) |  | SAITO, MIWA |  |  | Hiriyanna, Srinivas | MASAYUKI ITO | MASAE KAI | [17 empty] | Sushant Sundar | [28 empty] | Other | [19 empty] | Tuberous sclerosis | No | Local | Completed | Yes | [16 empty] | None of the above
CRAD001P | CRAD001P1401 | C1001462 | Phase IV | Other | [7 empty] | 2011-12-26 05:30 | 2011-09-19 05:30 | 2011-12-09 05:30 |  | Completed | 2023-04-10 05:30 | 2018-01-18 05:30 | 2018-01-18 05:30 | 2018-01-18 05:30 | FALSE |  |  |  | Outsourced |  | Special Drug use investigation (observational study) of Afinitor in Neuroendcrine tumors (NET) | Japan PMS_RAD001P1401_ pNET | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | KAZUAKI YAMAGUCHI; MINAKO KATO | KAZUAKI YAMAGUCHI | [66 empty] | Pancreatic neuroendocrine tumour | No | Global | Completed | Yes | [16 empty] | None of the above
CRAD001T | CRAD001T2302 | C1001463 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2012-03-30 05:30 |  | 2011-11-04 05:30 |  | Completed |  | 2020-08-07 05:30 | 2020-09-17 05:30 | 2020-09-18 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A randomized, double-blind, multicenter, Phase III study of everolimus (RAD001) plus best supportive care versus placebo plus best supportive care in the treatment of patients with advanced NET of GI or lung origin | CRAD001T2302 (RADIANT-4)_PhIII-GI Lung NET/L1-M | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vadla, Ravinder | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas | Janet Ng-Sikorski | Janet Ng-Sikorski |  | Gupta, Anshu | [15 empty] | Sushant Sundar | [28 empty] | PPD | Oncology | BP21 | PPD | David.Dunn@ppdi.com | Earlier DBD: Asha Rajanna | [14 empty] | Carcinoid tumour | Yes | Global | Open | Yes | [16 empty] | None of the above
CRAD001Y | CRAD001Y2201 | C1001464 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-02-26 05:30 |  | 2012-11-26 05:30 |  | Completed | 2018-08-31 05:30 | 2018-07-30 05:30 | 2018-08-28 05:30 | 2018-08-29 05:30 | FALSE |  | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | Outsourced | Solid Tumor | A three-arm, randomized, open-label, phase II study of everolimus in combination with exemestane versus everolimus alone versus capecitabine in the treatment of postmenopausal women with estrogen resceptor position, locally advanced, recurrent, or metastatic breast cancer after recurrence or progression on prior letrozole or anastrozole | CRAD001Y2201 (BOLERO6)_PhII-mBC/ERp/L2,3-C (ev/ex) | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Vadla, Nagarajachari | Vavasseur, Celine | Kumar, Rohit | Hiriyanna, Srinivas | Nathalie Pognan | Nathalie Pognan |  | Gupta, Anshu | [15 empty] | Sushant Sundar | [28 empty] | IQVIA | Oncology | BP21 | Quintiles | mailto:Delphine.Valette@Quintiles.com/Marion.Dehlinger@iqvia.com | Earlier DBD: Asha Rajanna | [14 empty] | Breast cancer | No | Global | Completed | Yes | [16 empty] | None of the above
CRAD001Y_MA | CRAD001Y24135 | C1001744 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-03-07 05:30 |  | 2012-08-13 05:30 |  | Completed | 2021-01-29 05:30 | 2021-01-13 05:30 | 2021-04-09 05:30 | 2021-02-26 05:30 | FALSE | Outsourced | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | An open-label, phase II, single-arm study of everolimus in combination with letrozole in the treatment of postmenopausal women with estrogen receptor positive HER2 negative metastatic or locally advanced breast cancer | CRAD001Y24135 (BOLERO4)_PhIII-mBC/ERp/L1-C(letr) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Vaibhav, Soni | Sardesai, Pallavi Sharad | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | LaTonya Smith | LaTonya Smith |  | Lingampalli, Rohit | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | Oncology |  | Quintiles | Celine.Moscherosch@iqvia.com | Earlier DBD: Chandrima /Jugnu | [14 empty] | Breast cancer | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002A | CRFB002A1401 | C1001471 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2009-04-15 05:30 | 2009-01-07 05:30 | 2009-02-06 05:30 |  | Completed | 2018-09-25 05:30 | 2018-09-26 05:30 | 2018-09-25 05:30 | 2018-09-26 05:30 | FALSE |  |  |  | Outsourced |  | Special observational investigation of Lucentis | CRFB002A1401 Japan PMS | P5 Ophthalmology | [5 empty] | Lisa Jimmink_TAP | YOSHIHISA SATOU | [66 empty] | Age-related macular degeneration | No | Global | Completed | Yes | [16 empty] | None of the above
CRFB002A | CRFB002A1402 | C1001465 | Phase IV | Other | [7 empty] | 2009-09-11 05:30 |  | 2009-02-06 05:30 |  | Completed | 2018-09-25 05:30 | 2018-09-26 05:30 | 2018-09-25 05:30 | 2018-09-26 05:30 | FALSE |  |  |  | Outsourced |  | Special observational investigation of Lucentis; ETDRS | CRFB002A1402 Japan PMS | P5 Ophthalmology | [5 empty] | Lisa Jimmink_TAP | YOSHIHISA SATOU | [66 empty] | Age-related macular degeneration | No | Global | Completed | Yes | [16 empty] | None of the above
CRFB002A_MA | CRFB002A2406 | C1001467 | Phase IV | NOVDD | [7 empty] | 2011-03-16 05:30 |  | 2010-08-10 05:30 |  | Completed |  | 2016-04-27 05:30 |  | 2016-12-08 05:30 | FALSE |  |  |  | Outsourced |  | LUMINOUS: Study to observe the effectiveness and safety of Ranibizumab through individualized patient treatment and associated outcomes | CRFB002A2406 LUMINOUS | P5 Ophthalmology | [6 empty] | Vinod Pabbisetty | [69 empty] | Completed | [17 empty] | None of the above
CRFB002A_MA | CRFB002A2412 | C1001469 | Phase IV | NOVDD | [7 empty] | 2013-08-07 05:30 |  | 2012-12-17 05:30 |  | Completed |  | 2017-03-02 05:30 |  | 2017-04-07 05:30 | FALSE |  |  |  | IDMA |  | Study of the effect of Lucentis versus the combination of Lucentis and Visudyne in patients with Polypoidal Choroidal Vasculopathy (PCV) | EVEREST II GMA Study_RFB002A2412 | P5 Ophthalmology | [5 empty] | Andrea Suhner Grotzfeld; Chintan B Mehta; Nicole Frank Gruber | Chintan B Mehta | [66 empty] | Age-related macular degeneration; Polypoidal choroidal vasculopathy |  | Global | Completed | Yes | [16 empty] | None of the above
CRFB002D | CRFB002D1401 | C1001472 | Phase IV | Other | [7 empty] | 2014-06-24 05:30 | 2018-01-19 05:30 | 2014-04-11 05:30 |  | Completed | 2019-05-20 05:30 | 2016-10-30 05:30 | 2019-03-20 05:30 | 2019-03-20 05:30 | FALSE |  |  |  | Outsourced |  | Drug use observational study of Lucentis in diabetic mucular edema | CRFB002D1401 JPN PMS | P5 Ophthalmology | [5 empty] | Lisa Jimmink_TAP | MAKOTO NAGASAKI | [66 empty] | Diabetic macular oedema | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002D | CRFB002D2305 | C1001473 | Phase III | NOVDD | [7 empty] | 2014-11-05 05:30 |  | 2014-06-10 05:30 |  | Completed |  | 2017-01-17 05:30 |  | 2017-03-07 05:30 | FALSE |  |  |  | IDMA Transaction |  | A 12-month, randomized, double-masked, multicenter, laser-controlled phase III study assessing the efficacy and safety of 0.5 mg ranibizumab dosed PRN in subjects with visual impairment due to diabetic macular edema in Chinese patients | DME in China Study_RFB002D2305 | P5 Ophthalmology | [5 empty] | Arthur Foo | Norbert Bernhard Ahlers | [67 empty] | No | Global | Completed | Yes | [16 empty] | None of the above
CRFB002E | CRFB002E1401 | C1001477 | Phase IV | Other | [7 empty] | 2014-01-16 05:30 | 2018-01-19 05:30 | 2013-07-12 05:30 |  | Completed | 2018-11-07 05:30 | 2018-10-31 05:30 | 2019-06-06 05:30 | 2019-06-11 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational investigation of Lucentis in macular edema secondary to retinal vein occlussion | CRFB002E1401 JPN PMS | P5 Ophthalmology | [5 empty] | Lisa Jimmink_TAP | MAKOTO NAGASAKI | [66 empty] | Retinal vein occlusion | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002E | CRFB002E1402 | C1001474 | Phase IV | Other | [7 empty] | 2014-02-10 05:30 | 2018-01-19 05:30 | 2013-07-12 05:30 |  | Completed | 2019-05-20 05:30 | 2017-09-29 05:30 | 2019-06-06 05:30 | 2019-06-11 05:30 | FALSE |  |  |  | Outsourced |  | Special drug use observational investigation of Lucentis in macular edema secondary to retinal vein occlussion in ETDRS | CRFB002E1402 JPN PMS | P5 Ophthalmology | [5 empty] | KUMI TAKAMIYA; Lisa Jimmink_TAP | MAKOTO NAGASAKI | [66 empty] | Retinal vein occlusion | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002E | CRFB002E2302 | C1001475 | Phase III | NOVDD | [7 empty] | 2013-11-12 05:30 |  | 2013-05-28 05:30 |  | Completed |  | 2016-03-14 05:30 |  | 2016-04-28 05:30 | FALSE |  |  |  | IDMA Shared |  |  | CRVO China Phase III_RFB002E2302 | P5 Ophthalmology | [6 empty] | Vinod Pabbisetty | [66 empty] | Retinal vein occlusion | No | Global | Open | [17 empty] | None of the above
CRFB002E | CRFB002E2303 | C1001476 | Phase III | NOVDD | [7 empty] | 2013-11-12 05:30 |  | 2013-05-28 05:30 |  | Completed |  | 2016-03-28 05:30 |  | 2016-06-01 05:30 | FALSE |  |  |  | IDMA Shared |  |  | BRVO China Phase III_RFB002E2303 | P5 Ophthalmology | [6 empty] | Vinod Pabbisetty | [66 empty] | Retinal vein occlusion | No | Global | Open | [17 empty] | None of the above
CRFB002F | CRFB002F1401 | C1001478 | Phase IV | Other | [7 empty] | 2014-03-27 05:30 |  | 2013-12-19 05:30 |  | Completed | 2019-05-20 05:30 | 2017-03-30 05:30 | 2019-03-20 05:30 | 2019-03-20 05:30 | FALSE |  |  |  | Outsourced |  | Drug use observational study of Lucentis in choroidal neovasc.sec. in pathologic myopia | CRFB002F1401 JPN Study | P5 Ophthalmology | [6 empty] | MAKOTO NAGASAKI | [66 empty] | Pathologic myopia | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002F | CRFB002F2302 | C1001479 | Phase III | NOVDD | [7 empty] | 2013-09-11 05:30 |  | 2013-04-12 05:30 |  | Completed |  | 2016-09-14 05:30 |  | 2016-11-29 05:30 | FALSE |  |  |  | IDMA Transaction |  | 12-mo, multi-center, double masked, active-controlled in patients with CNV due to PM | Phase 3_China Study_RFB002F2302 | P5 Ophthalmology | [5 empty] | Arthur Foo | Norbert Bernhard Ahlers | [66 empty] | Choroidal neovascularisation | No | Global | Completed | Yes | [16 empty] | None of the above
CRFB002F | CRFB002F2401 | C1001480 | Phase IV | NCDS | OC RDC - Inhouse |  | 2015-06-17 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-06-18 05:30 |  | 2015-01-16 05:30 |  | Completed | 2019-05-24 05:30 | 2019-05-23 05:30 | 2019-06-21 05:30 | 2019-06-26 05:30 | FALSE |  | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 36 month observational study to describe the long-term efficacy and safety of ranibizumab 0.5 mg treatment in patients with visual impairment due to choroidal neovascularization (CNV) secondary to pathologic myopia (PM) | CRFB002F2401 Phase 4_Confirmation of Reg | P5 Ophthalmology | Ball, Michael | Beerla, Shirisha | Venugopal, Vijay | Datta, Debtanu | Krishnan, Kripesh | Lisa Jimmink_TAP; Nicole Frank Gruber; Sue-zette Valera; Volker Moeckel | Karin Edfors | Sama, Ashok | [14 empty] | Kommu, Ranjith Kumar |  | Sai Krishna Mettugari | [13 empty] | 100 | OCRDC - Inhouse | Yes | [5 empty] | Pharma | Novartis | InHouse | 2015-06-17 05:30 | 2015-06-17 05:30 |  |  | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 350 | 1 | 0 |  | Choroidal neovascularisation | No | Global | Terminated | Yes | [14 empty] | DMC/Dry-Run/Snapshot | Jadhav, Yogesh | None of the above | Yes
CRFB002H | CRFB002H1401 | C4003240 | Phase IV | Other | CRO - EDC |  |  | 2020-10-30 05:30 | DB Conduct | Final DBL | 2026-03-30 05:30 | 2020-10-19 05:30 | 2020-03-31 05:30 | 2020-03-18 05:30 |  | Active | 2026-01-01 05:30 |  | 2026-03-30 05:30 |  | FALSE | Japan PMS | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | DF OPHTHA |  | CRFB002H1401 JPN PMS | P5 Ophthalmology | YAMADA, KAYO | MORI, YUMIKO | YAMADA, KAYO | YAMADA, KAYO | Krishnan, Kripesh | KEIKO FUJINO | KEIKO FUJINO | [17 empty] | Sai Krishna Mettugari | [28 empty] | Other | [19 empty] | Retinopathy | No | Global | Open | Yes | [16 empty] | None of the above
CRFB002H | CRFB002H2301 | C1001482 | Phase III | NCDS | OC RDC - Inhouse |  | 2015-12-30 05:30 |  | DB Locked | Final DBL Achieved |  | 2015-12-30 05:30 |  | 2014-11-17 05:30 |  | Completed | 2018-03-20 05:30 | 2017-12-14 05:30 | 2017-12-29 05:30 | 2018-01-24 05:30 | FALSE |  | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | RAINBOW study: a randomized, controlled study evaluating the efficacy and safety of RAnibizumab compared with laser therapy for the treatment of Infants BOrn prematurely With retinopathy of prematurity | Phase 3 RAINBOW_CRFB002H2301 | P5 Ophthalmology | Ball, Michael | Venugopal, Vijay | Venugopal, Vijay | Datta, Debtanu | Krishnan, Kripesh | Dana Sager | Dana Sager | Patnaik, Angella | [14 empty] | Sahu, Ahallad |  | Sai Krishna Mettugari | [21 empty] | Pharma | Novartis | InHouse | 2015-11-10 05:30 | 2015-11-10 05:30 |  |  | NA | [19 empty] | Retinopathy | Yes | Global | Completed | Yes | [16 empty] | None of the above
CRFB002H | CRFB002H2301E1 | C1001481 | Phase III | NCDS | OC RDC - Inhouse |  | 2016-06-09 05:30 |  | DB Conduct | Final DBL | 2022-06-28 05:30 | 2016-06-16 05:30 |  | 2015-12-14 05:30 |  | Active | 2022-05-18 05:30 |  | 2022-06-28 05:30 |  | FALSE | no Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | RAINBOW extension study: an extension study to evaluate the long term efficacy and safety of RAnibizumab compared with laser therapy for the treatment of Infants BOrn prematurely With retinopathy of prematurity | CRFB002H2301E1 Phase 3 RAINBOW Extension Study | P5 Ophthalmology | Navarro, Christelle | Beerla, Shirisha | Beerla, Shirisha | Datta, Debtanu | Krishnan, Kripesh | Steve Burmaster | Steve Burmaster | Sama, Ashok | Shewane, Roshni | Completed | 2020-01-21 05:30 | Study transitioned to Roshni Shewane to 21-Jan-2020. | [10 empty] | Kadam, Sandeep |  | Sai Krishna Mettugari | [14 empty] | OCRDC - Inhouse | [6 empty] | Pharma | Novartis | ICON | 2016-05-20 05:30 | 2016-05-20 05:30 | Shewane, Roshni | Meda, Sreelakshmi | NA | [7 empty] | 51 | 0 |  |  | 0 |  |  |  | 595 | 1 | 0 |  | Retinopathy | Yes | Global | Open | Yes | [16 empty] | None of the above
CRFB002H | CRFB002H2403 | C4015437 | Phase IV |  |  |  |  | 2022-12-27 05:30 |  | Final DBL | 2024-06-27 05:30 |  | 2022-04-22 05:30 |  |  | Planned | 2024-05-16 05:30 |  | 2024-06-27 05:30 | [5 empty] | Outsourced |  |  | CRFB002H2403 China ROP Clinical Study | P5 Ophthalmology | [6 empty] | Liju Ding | [66 empty] | Retinopathy of Prematurity | No | Global | Open | Yes
CRHH646A0 | CRHH646A02101 | C4007535 | Phase I | Other | Other | 2021-04-26 05:30 |  | 2021-06-30 05:30 | DB Conduct | Final DBL | 2022-08-01 05:30 | 2021-07-01 05:30 | 2021-04-22 05:30 | 2021-04-22 05:30 |  | Active | 2022-06-27 05:30 |  | 2022-08-01 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - MSD |  | CRHH646A02101 FIH in HV | N4 MSD - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Robert Beecham | Robert Beecham | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Tendonitis | No | Global | Open | Yes | [16 empty] | None of the above
CRHH646A1 | CRHH646A12201 | C4011829 | Phase II |  |  |  |  | 2023-02-08 05:30 |  | Final DBL | 2025-04-17 05:30 |  | 2022-08-31 05:30 |  |  | Planned | 2025-03-13 05:30 |  | 2025-04-17 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CRHH646A12201 PoC in knee OA | N4 MSD - NIBR | [6 empty] | Emilie Francoise Armelle Voltz | [66 empty] | Osteoarthritis knee | No | Global | Open | Yes
CRLX030A | CRLX030A2203 | C1001483 | Phase II | NOVDD | [7 empty] | 2014-02-03 05:30 |  | 2013-04-22 05:30 |  | Completed |  | 2016-08-17 05:30 |  | 2016-11-17 05:30 | FALSE |  |  |  | IDMA |  | A multicenter, double blind, randomized, parallel group, placebo controlled study to evaluate the effects of intravenous serelaxin infusion on micro- and macro-vascular function in patients with coronary artery disease | CRLX030A2203 Serelaxin vascu func CorArtDis | P9 Cardiovascular Renal and Metabolism (CRM) | [6 empty] | Jose Alcantara Rodriguez | [66 empty] | Cardiac failure acute |  | Global | Completed | Yes | [16 empty] | None of the above
CRLX030B | CRLX030A2208 | C1001496 | Phase II | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-09-05 05:30 |  | 2013-10-25 05:30 |  | Stopped (with patients) |  | 2017-04-03 05:30 |  |  | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | Ped PK and Safety_RLX030B2208 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Varshney, Kajal | Arasavalli, Isaac | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Richard Gerber | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Acute decompensated heart failure | Yes | Global | Open | Yes | [16 empty] | None of the above
CRLX030A | CRLX030A2209 | C1001484 | Phase II | NCDS | [7 empty] | 2014-05-12 05:30 |  | 2013-08-19 05:30 |  | Completed |  | 2015-09-23 05:30 |  | 2015-11-20 05:30 | FALSE |  |  |  | IDMA Transaction |  | Prospective, double-blind, multicenter study evaluating the safety of repeat doses of IV serelaxin in subjects with chronic heart failure | CRLX030A2209 Repeat dose study/immunogenicity | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Linda Wraith | Linda Wraith | [66 empty] | Heart failure | No | Global | Open | Yes | [16 empty] | None of the above
CRLX030A | CRLX030A2301 | C1001491 | Phase III | NCDS | [7 empty] | 2013-10-02 05:30 |  | 2013-05-24 05:30 |  | Completed |  | 2017-02-01 05:30 |  | 2017-03-16 05:30 | FALSE |  |  |  | InHouse |  | A multicenter, randomized, double-blind, placebo-controlled Phase III study to evaluate the efficacy, safety and tolerability of Serelaxin when added to standard therapy in acute heart failure patients | RELAX-AHF-2_RLX030A2301 | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Ioannis Strigkas; Nicole Hagner | Volker Scherhammer | [66 empty] | Acute decompensated heart failure | Yes | Global | Open | Yes | [16 empty] | None of the above
CRLX030A | CRLX030A2302 | C1001492 | Phase III | NCDS | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2014-03-12 05:30 |  | 2013-10-24 05:30 |  | Stopped (with patients) |  | 2017-06-16 05:30 |  |  | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | RELAX-AHF-ASIA_RLX030A2302 | P9 Cardiovascular Renal and Metabolism (CRM) | Bhattacharya, Sangeeta | Shedge, Vijay | Arasavalli, Isaac | Tummalapenta, Venkateswarlu | Nair, Sreesha |  | Richard Gerber | [15 empty] | Nilesh Nighot, Dnyaneshwari |  | Amit Agavekar | [28 empty] | NA | [19 empty] | Acute decompensated heart failure | Yes | Global | Open | Yes | [16 empty] | None of the above
CRTH258A | CRTH258A1401 | C3003654 | Phase IV | Other | CRO - EDC |  |  | 2020-11-30 05:30 | DB Conduct | Final DBL | 2023-03-10 05:30 | 2020-11-16 05:30 | 2020-05-20 05:30 | 2020-06-16 05:30 |  | Active | 2022-11-10 05:30 |  | 2023-03-10 05:30 |  | FALSE | Japan PMS | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | DF OPHTHA |  | CRTH258A1401 JPN PMS | P5 Ophthalmology | YAMADA, KAYO | MARUYAMA, KYOKO | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | MINE KIMURA | MINE KIMURA | [17 empty] | Sai Krishna Mettugari | [28 empty] | Other | [19 empty] | Age-related macular degeneration | No | Global | Open | Yes | [16 empty] | None of the above
CRTH258A | CRTH258A2201 | C1001503 | Phase II | RAVE_SDTM | [7 empty] | 2015-08-24 05:30 |  | 2015-06-19 05:30 |  | Completed |  | 2016-09-06 05:30 |  | 2016-12-13 05:30 | FALSE |  |  | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Alcon InHouse |  | A Randomized, Double Masked, Three Dose Safety and Pharmacokinetic Study of RTH258 Following Intravitreal (IVT) Injection in Subjects with Neovascular Age-Related Macular Degeneration | CRTH258A2201 Safety and Pharmacokinetics of RTH258 | P5 Ophthalmology |  |  |  | Datta, Debtanu | Krishnan, Kripesh | Lisa Jimmink_TAP; Liza Svoboda | Liza Svoboda | [66 empty] | Age-related macular degeneration | Yes | Global | Open | Yes | [16 empty] | None of the above
CRTH258A | CRTH258A2301 | C1001502 | Phase III | Other | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2014-12-16 05:30 |  | 2014-11-11 05:30 |  | Completed | 2018-04-02 05:30 | 2018-03-28 05:30 | 2018-04-20 05:30 | 2018-04-23 05:30 | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Two Year, Randomized, Double-Masked, Multicenter, Three-Arm Study Comparing the Safety and Efficacy of RTH258 versus Aflibercept in Subjects with Neovascular Age-Related Macular Degeneration | HAWK_CRTH258A2301 | P5 Ophthalmology | Bhattacharya, Sangeeta | Griselda Garnica, Monica | Ortega, Alexis | Datta, Debtanu | Krishnan, Kripesh |  | Abdelkader Si Bouazza | [17 empty] | Sai Krishna Mettugari | [28 empty] | GCE | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Age-related macular degeneration | Yes | Global | Open | Yes | [16 empty] | None of the above
CRTH258A | CRTH258A2301E1 | C3004040 | Phase III | Other | Rave EDC - Inhouse |  |  |  | DB Locked |  |  | 2018-01-15 05:30 | 2017-12-05 05:30 | 2017-12-05 05:30 |  | Completed | 2018-09-10 05:30 | 2018-09-06 05:30 | 2018-09-27 05:30 | 2018-09-27 05:30 | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Alcon InHouse | DF OPHTHA | A 24-week, double-masked, multicenter, two-arm extension study to collect safety and efficacy data on brolucizumab 6mg drug product intended for commercialization in patients with neovascular age-related macular degeneration who have completed the CRTH258A2301 study | HAWK Extension Study_CRTH258A2301E1 | P5 Ophthalmology | Bhattacharya, Sangeeta | Ayala Gonzalez, Victor Eduardo | Ortega, Alexis | Datta, Debtanu | Krishnan, Kripesh | Abdelkader Si Bouazza | James Carten | [17 empty] | Sai Krishna Mettugari | [28 empty] | GCE | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 650 | 10 | 0 |  | Age-related macular degeneration | No | Global | Open | Yes | [16 empty] | None of the above
CRTH258A | CRTH258A2302 | C1001501 | Phase III | Other | Other |  |  |  | DB Locked | Final DBL Achieved |  | 2015-07-28 05:30 |  | 2015-02-13 05:30 |  | Completed | 2018-03-07 05:30 | 2018-03-08 05:30 | 2018-03-28 05:30 | 2018-03-28 05:30 | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Two-Year, Randomized, Double-Masked, Multicenter, Two-Arm Study Comparing the Efficacy and Safety of RTH258 6 mg versus Aflibercept in Subjects with Neovascular Age Related Macular Degeneration | CRTH258A2302 HARRIER | P5 Ophthalmology | Bhattacharya, Sangeeta | Ayala Gonzalez, Victor Eduardo | Ortega, Alexis | Datta, Debtanu | Krishnan, Kripesh | Arthur Foo | Mow Yee Foo | [17 empty] | Sai Krishna Mettugari | [28 empty] | GCE | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Macular degeneration | Yes | Global | Open | Yes | [16 empty] | None of the above
CRTH258A_MA | CRTH258A2303 | C1001764 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2019-08-13 05:30 | 2019-09-30 05:30 | DB Conduct | Final DBL | 2022-04-05 05:30 | 2019-09-25 05:30 | 2019-04-05 05:30 | 2019-04-05 05:30 |  | Active | 2022-01-24 05:30 |  | 2022-04-05 05:30 |  | FALSE | no Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 64-week, two-arm, randomized, double-masked, multicenter, phase IIIb study assessing the efficacy and safety of brolucizumab 6 mg compared to aflibercept 2 mg in a treat-to-control regimen in patients with neovascular age-related macular degeneration (TALON) | CRTH258A2303 TALON | P5 Ophthalmology | Navarro, Christelle | Bangera, Payal | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Karin Edfors | Karin Edfors | Munukutla, Valli | Katam, Veera Nagendra | Completed | 2021-06-23 05:30 | 22Jun2021 : Transition from Valli Munukutla to Katam, Veera Nagendra PPC-07 is ongoing. Need to provide the IA Transition from Indumathi Narasetty to Valli Munukutla |  | DRM | Oguri, Praveen | Bairagi, Arpita | Completed | 29Jun2021: SNOW-51 Ticket is raised with ticket number-RITM2719878 for LSH refresh. LSP has been informed for the LSH update. 25Jun2021 : DBD shared the PPC for impact analysis on Rule file. Review completed, PPC has no impact on Rule file. 26May2021 : Reassigned the study from Praveen Oguri to Arpita Bairagi. 19-Apr-2021: Added in RF Version 4.0 and raised SNOW ticket on 23-Mar-2021 05Nov2020: No Activity. 11Sep2020: No Activity. 18Jun2020 : ZXN007, ZXN008, OPS001 included in RF and snow ticket raised on 08Jun2020 27May2020 : Pending forms OPS001, ZXN007, ZXN008 as per Missing forms/DTs report 22Jan2020 (SHRIVNI5): Cross checked the final DTS in the rule file. Rule file is updated. Test load is also successful. LSP currently waiting for the production transfer. 20-JAN-20: [SK]: No peding forms. 20-JAN-20: [SK]: No Pending DTS 20-JAN-20: [SK]: Rule file completed, no pending issues. Ticket is not yet raised with Rule File | None | None | 2019-10-10 05:30 | DB Set-Up Issues | Praveen kumar, Chakka Giri | Sahu, Ahallad | Sai Krishna Mettugari | Completed | 2019-10-15 | Completed | 2019-11-07 05:30 |  | Study Transition | 2019-11-07 05:30 | 2019-11-07 05:30 | Study Transition | 2020-03-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 10 | 31 | 42 | 0 | 366 | 428 | 0 | 161 | 34 | 99 | 561 | 4 | 0 |  | Age-related macular degeneration | No | Global | Open | Yes | [10 empty] | 2019-10-30 05:30 | [5 empty] | GDD annual target | Yes
CRTH258A_MA | CRTH258A2303E1 | C4007168 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-11-10 05:30 | 2020-11-20 05:30 | 2020-12-23 05:30 | DB Conduct | Final DBL | 2023-05-12 05:30 | 2020-12-16 05:30 | 2020-06-29 05:30 | 2021-11-03 05:30 |  | Active | 2023-03-31 05:30 |  | 2023-05-12 05:30 |  | FALSE | no Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 56-week phase IIIb/IV, open-label, one-arm extension study to assess the efficacy and safety of brolucizumab 6 mg in a Treat-to-Control regimen with maximum treatment intervals up to 20 weeks for the treatment of patients with neovascular age-related macular degeneration who have completed the CRTH258A2303 study (TALON) | CRTH258A2303E1 TALON Extension | P5 Ophthalmology | Navarro, Christelle | Mekala, Anvesh Janagama | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Karin Edfors | Karin Edfors | Katam, Veera Nagendra | Katam, Veera Nagendra | Completed | 2021-09-02 05:30 | Initial go live as 10Nov2020 when RF developer assigned on 27Jul2020. |  | DRM | Oguri, Praveen | Bairagi, Arpita | Completed | 20Jul2021: DBD informed that PPC 1 for this study is completed. 05Jul2021: DBD shared the PPC for Impact analysis on Rule file. Reviewed the PPC. PPC is not impacting the Rule file. 26May2021 : Reassigned the study from Praveen Oguri to Arpita Bairagi. 23Nov2020 : RF final and snow 05 raised FPFV moved to 23Dec2020 | None | None | 2020-11-23 05:30 |  | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2020-12-10 | Completed | 2020-12-17 05:30 |  | Pre-requisites not met | 2020-12-17 05:30 | 2020-12-17 05:30 | Pre-requisites not met | 2020-12-22 05:30 |  |  |  | 89 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 3 | 30 | 43 | 0 | 364 | 417 | 0 | 158 | 37 | 115 | 569 | 2 | 0 |  | Age-related macular degeneration | No | Global | Open | Yes | [10 empty] | 2020-12-14 05:30 | [5 empty] | None of the above | Yes
CRTH258A | CRTH258A2307 | C4000958 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-05-13 05:30 | 2019-09-30 05:30 | 2019-11-29 05:30 | DB Conduct | Final DBL | 2024-07-10 05:30 | 2019-11-29 05:30 | 2019-06-24 05:30 | 2018-11-27 05:30 |  | Active | 2024-05-29 05:30 |  | 2024-07-10 05:30 |  | FALSE | Mission Possible | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Twelve-Month, Randomized, Double-Masked,Multicenter, Phase III, Two-Arm Study Comparing the Efficacy and Safety of Brolucizumab 6 mg versus Aflibercept in Chinese Patients with Neovascular Age-Related Macular Degeneration | CRTH258A2307 China Ph3 Registration Study | P5 Ophthalmology | Navarro, Christelle | Niu, Mengmeng | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Angela Xiao | Yi Ni Xiao | Lingampalli, Rohit | Rana, Aamir |  |  | 15-Dec-2021 : Vinay Pamula will be backup for Aamir till 15-Mar-2022 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 13May2019 |  | DRM | Lingampalli, Rohit | Shrivastava, Nikhil | Completed | 21-May-2021: Death form (DDG001) included in Rule File V5.0 and finalized. SNOW-51 is raised and LSP is notified. 20-May-2021: Included the DDG001 form in the RF and released for peer review. Waiting for the comment/confirmation 22-Feb-2021: PPC#07 PPC form is reviewed. RF will be impacted. PPC currently ongoing. 26Nov2020: Backup: Rehana Whats planned: Nothing planned as of now. 25JUN2020 [SK]: RF V4.0 has been finalized and SNOW 51 RITM1538660 has been raised on 25JUN20. 19Jun2020 : MO1L, MO2L, MO3L, MO4L flagged in missing DTS report. DBD missed to share the DTS to include in RF. 12-Jun-2020 (SHRIVNI5): RF V3.0 finalized for addition of 2 new ZX pages. Sent for LSH rebuild. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 22Jan2020 (SHRIVNI5): Rule file version 2.0 updated for including Lab and QS DTS. Sent for peer review. 22Jan2020 (SHRIVNI5): Included in the rule file version 2.0. 20-JAN-20: [SK] Two DTS 1. Laboratoy 20-JAN-20: [SK]: No missing forms | None | None | 2020-01-06 05:30 | Transition Study | Praveen kumar, Chakka Giri | Varate, Rohit | Sai Krishna Mettugari | Completed | 2020-01-07 | Completed | 2020-01-09 05:30 | 16Dec2019: Rulefile completed and raise SNOW ticket on 12Dec19. Requested for SMT creation 28Nov19: Provided initial peer review comments. | Study Transition | 2020-01-09 05:30 | 2020-01-09 05:30 | Study Transition | 2020-01-09 05:30 |  |  | 4-SEP-2020 : DDPass completion date is 25-SEP-2020 | 100 | RaveX - Inhouse | Yes | DV | [11 empty] | NA | [5 empty] | 10 | 20 | 45 | 0 | 196 | 558 | 0 | 183 | 32 | 103 | 693 | 3 | 0 |  | Age-related macular degeneration | No | Global | Open | Yes | [10 empty] | 2020-01-08 05:30 | [5 empty] | None of the above | Yes
CRTH258A | CRTH258A2308 | C4003015 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-03-29 05:30 | 2019-05-15 05:30 | 2019-05-28 05:30 | DB Locked | Final DBL Achieved |  | 2019-05-23 05:30 | 2018-11-30 05:30 | 2019-01-16 05:30 |  | Completed | 2019-07-04 05:30 | 2019-07-02 05:30 | 2019-08-16 05:30 | 2019-08-16 05:30 | FALSE |  | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | An Open-Label, Single-Arm, Multicenter Phase IIIb Study in Patients with Neovascular Age-Related Macular Degeneration to Evaluate the Safety of Brolucizumab 6 mg in Prefilled Syringe. | CRTH258A2308 PFS User Study | P5 Ophthalmology | Ball, Michael | Naik, Akshay | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh |  | Godelieve Convents | Rao, S Shashikanth | Rao, S Shashikanth |  |  | Status changed to Locked as per DM BoW Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 29Mar2019 |  | DRM | Rao, S Shashikanth | Rao, S Shashikanth | Completed |  | Study Locked | Study Locked | 2019-06-04 05:30 | Legacy Process | Tidke, Shyam | Sahu, Ahallad | Sai Krishna Mettugari | Completed | 2019-06-13 | Completed | 2019-06-13 05:30 |  | Pre-requisites not met | 2019-06-13 05:30 | 2019-06-13 05:30 | Pre-requisites not met |  |  | No DIAL onboarding done for this study before final LSH lock. |  |  | RaveX - Inhouse |  | -NA- | 2019-08-21 05:30 | 2019-08-23 05:30 | [9 empty] | NA | [5 empty] | 4 | 5 | 31 | -1 | 23 | 301 | 4 | 119 | 32 | 97 | 430 | 0 | 0 |  | Age-related macular degeneration | No | Global | Completed | Yes | [10 empty] | 2019-06-07 05:30 | [5 empty] | None of the above
CRTH258A | CRTH258A2309 | C4004622 | Phase I | Other | CRO - EDC | 2019-04-29 05:30 |  | 2019-06-07 05:30 | DB Locked | Final DBL Achieved |  | 2019-06-07 05:30 | 2019-03-15 05:30 | 2019-03-19 05:30 |  | Completed | 2019-07-11 05:30 | 2019-07-31 05:30 | 2019-09-02 05:30 | 2019-09-03 05:30 | FALSE |  | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Single-Arm, Open-Label, Multicenter, Phase IIIb Study to Collect Safety and Electrocardiogram Data on Brolucizumab 6 mg Intravitreal Treatment in Patients with Neovascular Age-Related Macular Degeneration | CRTH258A2309 ECG Study | P5 Ophthalmology | Langlo, Francois | Rajput, Namita | Rajput, Namita | Kshetrapal, Abhishek | Krishnan, Kripesh | Jen Watts | Jen Watts | Rao, S Shashikanth |  |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 24Apr2019 | [12 empty] | Sai Krishna Mettugari | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Age-related macular degeneration | No | Global | Completed | Yes | [16 empty] | None of the above
CRTH258B | CRTH258B1401 | C3001624 | Phase IV | Other |  |  |  | 2022-09-30 05:30 |  | Final DBL | 2025-01-20 05:30 |  | 2022-07-29 05:30 |  |  | Planned | 2024-09-30 05:30 |  | 2025-01-20 05:30 | [5 empty] | Outsourced |  |  | CRTH258B1401 JPN PMS | P5 Ophthalmology | [5 empty] | MINE KIMURA | MINE KIMURA | [66 empty] | Diabetic macular oedema | No | Global | Open | Yes
CRTH258B | CRTH258B2301 | C1001505 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-06-20 05:30 | 2018-07-27 05:30 | DB Locked | Final DBL Achieved |  | 2018-07-23 05:30 | 2017-12-18 05:30 | 2018-02-15 05:30 |  | Active | 2021-10-14 05:30 | 2021-10-18 05:30 | 2021-11-22 05:30 | 2021-11-15 05:30 | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Two-Year, Three-Arm, Randomized, Double-Masked, Multicenter, Phase III Study Assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Diabetic Macular Edema (KESTREL) | CRTH258B2301 Phase 3 (Kestrel) | P5 Ophthalmology | Navarro, Christelle | Dubey, Anjali | Naik, Akshay | Datta, Debtanu | Krishnan, Kripesh | James Teague | James Teague | Rao, S Shashikanth | Rao, S Shashikanth |  |  |  |  | DRM (DIAL) | Akula, Raghavender | Patnaik, Angella | Completed | 22-FEB-2021: PPC #15 implemented for edit checks amendment. No updates to RF, SMT or LSH. 12-OCT-2020: RF V12.0 finalized for PPC14 updates. SNOW#51 raised and LSP notified. 07-JUL-2020: RF up to date for all final DTS and PPCs implemented in the study. 18MAY2020: RF Finalized in CREDI. SNOW#51 raised for LSH updates. 15MAY2020: As confirmed by CTT, OPS001 form in operational and will not flow downstream. RF updated for MO4L table and sent for Peer Review. 06MAY2020: email sent to DBD for query on pending forms and DTS. Not yet confirmed. 29thNov19 (Shashi) No Pending Domains to be included in RF | None | None | 2018-08-20 05:30 |  | Nidamanuru, Kalyan Kumar | Varate, Rohit | Sai Krishna Mettugari | Completed | 2018-12-19 | Completed | 2019-05-30 05:30 |  | Retrospective DRM studies | 2018-08-22 05:30 | 2018-08-22 05:30 | Retrospective DRM studies | 2019-08-22 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | DV;#Y1;#Y5;#YR;#YD;#ZK03 | 2021-11-15 05:30 | 2021-11-18 05:30 | [9 empty] | NA | [5 empty] | 16 | 30 | 48 | 0 | 331 | 590 | 0 | 182 | 42 | 127 | 759 | 4 | 0 |  | Diabetic macular oedema | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-05-29 05:30 |  |  |  | DBL | Manoharan, Vivek | GDD annual target | Yes
CRTH258B | CRTH258B2302 | C1001506 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-06 05:30 | 2018-08-22 05:30 | DB Locked | Final DBL Achieved |  | 2018-07-27 05:30 | 2022-03-08 05:30 | 2018-02-12 05:30 |  | Completed | 2021-07-05 05:30 | 2021-06-08 05:30 | 2021-08-12 05:30 | 2021-07-16 05:30 | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A Two-Year, Two-Arm, Randomized, Double-Masked, Multicenter, Phase III Study Assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Diabetic Macular Edema (KITE) | CRTH258B2302 Phase 3 (Kite) | P5 Ophthalmology | Navarro, Christelle | Dubey, Anjali | Naik, Akshay | Datta, Debtanu | Krishnan, Kripesh | Abdelkader Si Bouazza | Abdelkader Si Bouazza | Rao, S Shashikanth | Rao, S Shashikanth |  |  |  |  | DRM (DIAL) | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 11-Feb-2021: Raised SNOW ticket to update LSH for PPC12. 13-Oct-2020: Rule File version 10 finalized for PPC11 updates 06-Jul-2020: No pending issues. 11-Jun-2020: MO4L is included in RF V9.0 and raised SNOW51 ticket for LSH update 18-May-2020: RF updated for MO4L and sent for peer review 29th Nov 19 - (Shashi) No pending domain to be included in RF. | None | None | 2018-11-28 05:30 | Legacy Process | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sai Krishna Mettugari | Completed | 2019-01-07 | Completed | 2019-05-29 05:30 | ​ |  | 2018-12-20 05:30 | 2018-12-20 05:30 | Retrospective DRM studies | 2019-07-24 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | DV;#YD | 2021-07-19 05:30 | 2021-07-21 05:30 | [9 empty] | NA | [5 empty] | 13 | 30 | 48 | 0 | 341 | 589 | 0 | 176 | 42 | 125 | 756 | 4 | 0 |  | Diabetic macular oedema | Yes | Global | Open | Yes | [10 empty] | 2019-05-29 05:30 |  |  |  | DBL |  | GDD annual target | Yes
CRTH258B | CRTH258B2304 | C3001622 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-04-30 05:30 | 2019-08-20 05:30 | 2019-09-05 05:30 | DB Conduct | Final DBL | 2023-03-23 05:30 | 2019-08-23 05:30 | 2018-11-16 05:30 | 2018-11-20 05:30 |  | Active | 2023-02-09 05:30 |  | 2023-03-23 05:30 |  | FALSE | Mission Possible | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A One-Year, Randomized, Double-Masked, Multicenter, Phase III, Two-Arm Study Assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Chinese Patients with Visual Impairment Due to Diabetic Macular Edema | CRTH258B2304 China Registration Study (KINGLET) | P5 Ophthalmology | Navarro, Christelle | Guo, Wenkai | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Yan Ling | Yan Ling | Lingampalli, Rohit | Rana, Aamir |  |  | 15-Dec-2021 : Sujit Palande will be backup for Aamir till 15-Mar-2022 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 30Apr2019 |  | DRM | Oguri, Praveen | Bairagi, Arpita | Completed | 23Jul2021: CRTH258B2304_Rule File_Version 4.0 is finalized in CREDI with all the three MO DTS included in it. SNOW-51 ticket is also raised with ticket number- RITM2802229. 21Jul2021: Updated the Rule file and included the 3 DTS. Released the Rule file_version3.1 for Peer Review. 20Jul2021: Requested the DBD to share two more MO DTS for my review which were already finalized in CREDI. Review completed and shared my comments to DBD. 13Jul2021 : MO DTS shared by DBD for review 26May2021 : Reassigned the study from Praveen Oguri to Arpita Bairagi. 05Nov2020: No Activity. 11Sep2020: No Activity. 29Jul2020 : Included below missing forms on 29th Jul and final. 27Jul2020 : ECG003_2, ECG003_3, OPS001, ZXN007, ZXN008 flagged in 20Jul missing report. New forms in PPC. 17Feb2020 : As per Missing DTS and Forms report we have 'IEG001' form and LBL, QS1L DTSs pending to be included in RF. Praveen to follow-up with DBD | None | None | 2019-10-31 05:30 | DB Set-Up Issues | Mettugari, Sai Krishna | Mettugari, Sai Krishna | Sai Krishna Mettugari | Completed | 2019-11-11 | Completed | 2019-11-21 05:30 |  |  | 2019-11-21 05:30 | 2019-11-22 05:30 | Pre-requisites not met | 2020-05-05 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | DV;#ZK03;#Y1;#Y5;#YD | [11 empty] | NA | [5 empty] | 9 | 20 | 48 | 0 | 217 | 568 | 0 | 165 | 32 | 118 | 718 | 3 | 0 |  | Diabetic macular oedema | No | Global | Open | Yes | [10 empty] | 2019-11-19 05:30 |  |  |  |  | R, Harini | None of the above | Yes
CRTH258B | CRTH258B2305 | C4003515 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-07-05 05:30 | 2019-07-31 05:30 | DB Locked | Final DBL Achieved |  | 2019-07-17 05:30 | 2019-04-01 05:30 | 2019-03-27 05:30 |  | Completed | 2021-04-06 05:30 | 2021-03-24 05:30 | 2021-07-06 05:30 | 2021-07-06 05:30 | FALSE | Mission Possible | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 12-Month, 2-Arm, Randomized, Double-Masked, Multicenter Phase III Study Assessing the Efficacy and Safety of Brolucizumab every 4 weeks versus Aflibercept every 4 weeks in Adult Patients with Visual Impairment due to Diabetic Macular Edema (KINGFISHER) | CRTH258B2305 q4w study (Kingfisher) | P5 Ophthalmology | Navarro, Christelle | Reddyvari, Hima Bindu | Naik, Akshay | Datta, Debtanu | Krishnan, Kripesh | Dana Sager | Dana Sager | Samuel, Giftson | Samuel, Giftson |  |  |  |  | DRM | Samuel, Giftson | Shrivastava, Nikhil | Completed | 12-Jan-2021: SNOW-51 was raised by Angella on 08th Dec2020 as per PPC#08. LSP and SMT developers were notified. No impact to Rule File. 26Nov2020: Backup: Angella Whats planned: Nothing planned as of now. 11-Jun-2020 (SHRIVNI5): RF V6.0 finalized for addition of 2 new ZX pages. Sent for LSH rebuild. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 03Mar2020 : Pending imaging DTS (MO1L to 4L) and ZX included in RF version 27Feb2020. No. pending forms and DTS | None | None | 2019-08-28 05:30 | Transition Study | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sai Krishna Mettugari | Completed | 2019-08-29 | Completed | 2019-09-03 05:30 |  | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-09-04 05:30 | 2019-09-04 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-12-10 05:30 |  |  | ZJ domain issues to be resolved and awaiting updates in next PPC. | 100 | RaveX - Inhouse | Yes | DV;#Y1;#Y5;#ZK03 | 2021-07-06 05:30 | 2021-07-08 05:30 | [9 empty] | NA | [5 empty] | 8 | 16 | 46 | 0 | 198 | 608 | 0 | 166 | 33 | 113 | 754 | 5 | 0 |  | Diabetic macular oedema | No | Global | Open | Yes | [10 empty] | 2019-09-03 05:30 | [5 empty] | None of the above
CRTH258C | CRTH258C2301 | C3002623 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-06-17 05:30 | 2020-02-03 05:30 | DB Locked | Final DBL Achieved |  | 2019-07-02 05:30 | 2019-01-21 05:30 | 2018-12-17 05:30 |  | Active | 2021-08-02 05:30 | 2021-07-26 05:30 | 2021-11-10 05:30 | 2021-11-11 05:30 | FALSE | Terminated study | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | An Eighteen-Month, Two-Arm, Randomized, Double Masked, Multicenter, Phase III Study Assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Macular Edema secondary to Branch Retinal Vein Occlusion (RAPTOR) | CRTH258C2301 BRVO | P5 Ophthalmology | Navarro, Christelle | Som, Dipasree | Naik, Akshay | Datta, Debtanu | Krishnan, Kripesh | Sue-zette Valera | Sue-zette Valera | Joshi, Alekhya | Palande, Sujit | Completed | 2021-07-20 05:30 |  |  | DRM | Joshi, Alekhya | Shrivastava, Nikhil | Completed | 26-Feb-2021: As per PPC#10, raised the SNOW-51 raised to rebuild DV and DV1 domains. LSP and SMT developers are notified. No impact to Rule File. 18Dec2020: SNOW-51 request raised for LSH setup WRT PPC#09. LSP notified regarding the same. No impact on Rule File. 26Nov2020: Backup: Angella Whats planned: Nothing planned as of now. 11-Jun-2020 (SHRIVNI5): RF V6.0 finalized for addition of 2 new ZX pages. Sent for LSH rebuild. 06-May-2020 (SHRIVNI5): RF V5.0 finalized for addition of 4 new ZJ pages. Sent for LSH rebuild. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 03Mar2020 : Study Eye (SC) pending form included in latest version 12Feb2020. No pending forms or DTS. | None | None | 2019-09-03 05:30 | Transition Study | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sai Krishna Mettugari | Completed | 2019-09-09 | Completed | 2019-09-17 05:30 | DRM Setup delayed as rule file updated for ALL_FORMS and setup need to be rebuilt in LSH | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-09-17 05:30 | 2019-09-17 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2020-03-19 05:30 |  |  | 04-Sep-2020: There are no Structural issues but only Data issues. If only Structural issues considered then DDPASS% is 100%. | 100 | RaveX - Inhouse | Yes | LB;#DV;#YR;#YD | 2021-11-12 05:30 | 2021-11-17 05:30 | LSH lock ticket was raised on 12-Nov-2021 after 7pm. Considering 13,14 Nov2021 weekends, hence ticket is considered from 15Nov2021 to 17Nov2021 meeting the KPI of 3WDs. | [8 empty] | NA | [5 empty] | 13 | 23 | 48 | 0 | 277 | 636 | 0 | 195 | 33 | 137 | 806 | 4 | 0 |  | Macular oedema; Retinal vein occlusion | Yes | Global | Wind Down | Yes | [10 empty] | 2019-09-05 05:30 | [5 empty] | GDD annual target
CRTH258C | CRTH258C2302 | C3002625 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-06-18 05:30 | 2019-07-09 05:30 | DB Locked | Final DBL Achieved |  | 2019-07-03 05:30 | 2018-12-14 05:30 | 2018-12-18 05:30 |  | Active | 2021-08-02 05:30 | 2021-07-26 05:30 | 2021-11-10 05:30 | 2021-11-10 05:30 | FALSE | Terminated trial | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | An Eighteen-Month, Two-Arm, Randomized, Double Masked, Multicenter, Phase III Study Assessing the Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Macular Edema secondary to Central Retinal Vein Occlusion (Raven) | CRTH258C2302 CRVO | P5 Ophthalmology | Navarro, Christelle | Patel, MilanKumar | Naik, Akshay | Datta, Debtanu | Krishnan, Kripesh | Sue-zette Valera | Sue-zette Valera | Samuel, Giftson | Rana, Aamir |  |  | Nov 2021 : Giftson transitioned to Aamir Rana |  | DRM | Samuel, Giftson | Shrivastava, Nikhil | Completed | 23-Feb-2021: SNOW-51 WRT PPC#08 is raised and notified LSP regarding the same. Rule File is not impacted. 26Nov2020: Backup: Angella Whats planned: Nothing planned as of now. 16-Jun-2020 (SHRIVNI5): RF V6.0 finalized for addition of 2 new ZX pages. Sent for LSH rebuild. 06-May-2020 (SHRIVNI5): RF V5.0 finalized for addition of 4 new ZJ pages. Sent for LSH rebuild. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 03Mar2020 : ZX and SC pending domains processed on 18Feb2020. No pending forms or DTS | None | None | 2019-08-28 05:30 |  | Pagolu, Sahithi Venkata | Pagolu, Sahithi Venkata | Sai Krishna Mettugari | Completed | 2019-08-29 | Completed | 2019-09-16 05:30 | Except ZJ DRM completed for all domains | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-09-16 05:30 | 2019-09-16 05:30 | KPI met - incorrect source date entry (example FPFV) 1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned. | 2019-09-16 05:30 |  |  | 04-Sep-2020: There are no Structural issues but only Data issues. If only Structural issues considered then DDPASS% is 100%. | 100 | RaveX - Inhouse | Yes | DV;#LB;#Y1;#Y5;#YR;#YD;#ZK03 | 2021-11-11 05:30 | 2021-11-16 05:30 | LSH lock ticket was raised on 11-Nov-2021 after 7pm. hence ticket is considered from 12Nov2021 to 16Nov2021 meeting the KPI of 3WDs. (13th,14th Nov2021 being weekend) | [8 empty] | NA | [5 empty] | 12 | 22 | 48 | 0 | 278 | 645 | 0 | 190 | 33 | 127 | 805 | 4 | 0 |  | Retinal vein occlusion | Yes | Global | Wind Down | Yes | [10 empty] | 2019-09-16 05:30 | [5 empty] | GDD annual target
CRTH258D | CRTH258D2301 | C3002634 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-04-15 05:30 | 2020-10-16 05:30 | 2020-11-30 05:30 | DB Conduct | DB Snapshot | 2023-06-30 05:30 | 2020-11-19 05:30 | 2019-12-02 05:30 | 2019-12-02 05:30 |  | Active | 2025-01-10 05:30 |  | 2025-02-21 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CRTH258D2301 PDR W/O DME Study 1 | P5 Ophthalmology | Navarro, Christelle | Bangera, Payal | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | Catherine Lavecchia | Catherine Lavecchia | Maricherla, Vijayroshan | Kala, Arpit |  |  | Oct-2021 : Giftson transitioned to Arpit Kala Jan-2021 : Roshan transitioned to Giftson Study was on hold since jul2020. on 04Sep2020 received email from TDM to kick start the activites again with golive as 07-Oct-2020 and FPFV as 02-Nov-2020 As per the RaveX master tracker 21Oct2019 the planned golive 15APr2020. |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 11-Oct-2021: Included MO5L DTS in RF_V4.0 and raised SNOW ticket for LSH set-up 07-Jul-2021: RF_V3.0 updated nd raised SNOW ticket for LSH set-up 06Jul2021 : MO1L, MO2L, MO3L and MO4L reflecting in missing form DTS report 18-Jun-2021: requested Lead DBP to share the DTSs(MO1L, MO2L, MO3L and MO4L) to review and add the table names in RF. 02-Mar-2021: RF_V2.0 is finalized in Subway 17-feb-2021: RF_V1.1 is released for peer review to include LBL, QS1L QS2L and QS3L DTSs. 21Jan2021: Kranthi: Incorrect template has been used and requested TDM to update template. Once the DTS is updated, table name will be included in RF and SNOW ticket will be raised. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 LBL DTS listed. Please check 10-Dec-2020: Requested DBP to share the LBL DTS if finalized. Rule File will be updated Once if DBP confirms. 16Oct2020 : RF final and Snow raised 30JUl2020: As per DBD and TDM study is on hold until further notice 07-Jul-2020(Kranthi): No pending issues 07Apr2020 : All forms included and released for Peer review. 27Mar2020 : DBD shared all the documents for RF development 19Mar2020 : Screen UAT expected to complete tomorrow , One form updates discussion ongoing. post which final docs will be shared by DBD. 09Mar2020: Following up with DBD 05Feb2020 : Few SS reviewed rest yet to receive from DBD. Followed up today. | None | None | 2020-10-16 05:30 |  | Praveen kumar, Chakka Giri | Varate, Rohit | Sai Krishna Mettugari | Completed | 2020-10-31 | Completed | 2020-11-27 05:30 | 19-Aug-2020: Study On-hold | Study Transition | 2020-11-27 05:30 | 2020-11-27 05:30 | Study Transition | 2020-12-08 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 5 | 19 | 44 | 0 | 235 | 436 | 0 | 149 | 33 | 108 | 577 | 5 | 0 |  | Proliferative diabetic retinopathy | No | Global | Open | Yes | [10 empty] | 2020-11-23 05:30 | [5 empty] | None of the above | Yes
CRTV199A_MA | CRTV199A2401 | C1001767 | Phase IV | RAVE_RAW | [7 empty] | 2014-01-24 05:30 |  | 2013-07-25 05:30 |  | Completed |  | 2016-10-11 05:30 |  | 2016-12-07 05:30 | FALSE |  |  |  | Alcon InHouse |  | INJECT: INvestigation of JETREAÂ® in Patients with Confirmed Vitreomacular Traction | JETREA Inject Regirstry GMA_RTV199A2401 | P5 Ophthalmology | [5 empty] | Christine Rosko | Christine Rosko | [66 empty] | Diabetes with ophthalmic manifestations |  | Global | Completed | Yes | [16 empty] | None of the above
CRTV199A_MA | CRTV199A2404 | C1001509 | Phase IV | RAVE_RAW | [7 empty] | 2015-07-24 05:30 |  | 2014-10-06 05:30 |  | Completed |  | 2015-11-14 05:30 |  | 2015-12-02 05:30 | FALSE |  |  |  | Alcon InHouse |  |  | JETREA NIS VMT French GMA Study_RTV199A2404 | P5 Ophthalmology | [5 empty] | Norbert Ahlers | [70 empty] | Terminated | [17 empty] | None of the above
CSAF312B1 | CSAF312B12201 | C4004375 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-01-25 05:30 | 2021-02-18 05:30 | 2021-03-16 05:30 | DB Conduct | Final DBL | 2023-06-05 05:30 | 2021-04-21 05:30 | 2020-07-30 05:30 | 2019-12-13 05:30 | 2021-01-15 05:30 | Active | 2023-04-24 05:30 |  | 2023-06-05 05:30 |  | FALSE | DCN Priority | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A 12-week parallel group, randomized, placebo-controlled, double-blinded, multi-center study to evaluate efficacy and safety of 2 concentrations of SAF312 eye drops (5 mg/ml and 15 mg/ml) used twice-daily in the treatment of post-operative corneal induced chronic pain (CICP) following Photorefractive Keratectomy (PRK) or Laser-assisted in Situ Keratomileusis (LASIK) surgeries | CSAF312B12201 PII Safety & Efficacy Study | P5 Ophthalmology | Navarro, Christelle | Beerla, Shirisha | Chougule, Poornima | Datta, Debtanu | Krishnan, Kripesh | Dana Sager | Dana Sager | Bonam, Rajesh Babu | Meda, Sreelakshmi |  |  | Oct-2021 : Pallabi transitioned to Sreelakshmi |  | DRM | Oguri, Praveen | R, Pratheeksha K | Completed | 26May2021 : Reassigned the study from Praveen Oguri to Pratheeksha. 19Feb2021: Study pushed to PROD on 18-Feb-2021. RF finalized on 19-Feb-2021(RITM2283995). Pratheeksha drafted the RF and Kranthi peer review support. 11Feb2021: Initial Go-live was planned on 25-Jan-2021 and then Go-live date changed to 12-Feb-2021. As per the latest update, G0-Live date is again pushed to 17-Feb-2021 tentatively. 10Feb2021 : Pratheeksha developed the Rule file and sent for Peer review (Kranthi) 02-Dec-2020: Sent email to Rajesh to provide study setup status and to share study specific forms for review. 05Nov2020: No Activity. 11Sep2020: No updates received from Lead DBD. 17Feb2020 : Followed up with DBD and yet to receive study specific forms for review. Awaiting SDTM annotations. No RF activity started | None | QS1L,QS2L,QS3L,QS4L,QS5L,QS6L | 2021-02-19 05:30 |  | Nidamanuru, Kalyan Kumar | Nidamanuru, Kalyan Kumar | Sai Krishna Mettugari | Completed | 2021-04-03 | Completed | 2021-04-09 05:30 |  |  | 2021-03-10 05:30 | 2021-03-10 05:30 |  | 2021-03-31 05:30 |  |  |  |  | RaveX - Inhouse | No | [12 empty] | NA | [5 empty] | 3 | 9 | 48 | 0 | 109 | 455 | 0 | 154 | 33 | 101 | 589 | 4 | 0 |  | Dry eye | No | Global | Open | Yes | [10 empty] | 2021-03-09 05:30 |  |  |  |  | Manoharan, Vivek | GDD annual target | Yes
CSAF312B1 | CSAF312X1101 | C3003206 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2021-10-12 05:30 | 2022-01-21 05:30 | 2022-02-01 05:30 | DB Conduct | Interim DBL | 2022-04-28 05:30 | 2022-02-01 05:30 | 2021-07-30 05:30 | 2021-08-02 05:30 | 2021-12-16 05:30 | Active | 2022-04-06 05:30 |  | 2022-05-23 05:30 |  | FALSE | Submission | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - OPHTHA | A randomized, participant- and investigator-masked, vehicle-controlled study to assess the safety, tolerability and pharmacokinetics of topical ocular SAF312 in Japanese healthy participants | CSAF312X1101 Japan Phase I | P5 Ophthalmology | Langlo, Francois | Tsukazaki, Mayuka | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | TETSURO TANAKA | TETSURO TANAKA | Moses, Leah | Moses, Leah |  |  |  | 1) Planned FPFV was changed after final protocol. (shifted to about 3 months later). We set the setup schedule based on updated FPFV. 2) A few SRFs were slow to prepare and approve. This is because it took time for discussions between Medical and Clinical. 3) Due to the complexity of the study design and timepoints, it took time to build the database and UAT. 4) The new form has been added along with Edit checks at the end time of Go-Live. | DRM | Bairagi, Arpita | Bairagi, Arpita | Completed | 21-Jan-2021: CSAF312X1101_Rule File_version 2.0 is finalized in Subway and SNOW-05 LSH (PROD)- New Study Setup ticket is raised with ticket number-RITM3410117 for LSH PROD Setup. 30-Dec-2021: CSAF312X1101_Rule File_version 1.0 is finalized in Subway and SNOW-05 New Study Setup (TEST) Ticket is also raised with Ticket number- RITM3338566 for LSH setup. LSP is also informed. SNOW-05 New Study Setup (PROD) will be raised on the Day of Go-Live: 14-Jan-2022. 29-Dec-2021: Peer Review is comepleted 6-Dec-2021: Released CSAF312X1101_Rule file_version 0.1 for peer review. 1-Dec-2021: Rule file development is started. 10-Nov-2021: DBD shared the ALS, SRFs and SDTM annotation for review. Comments were shared. 19Aug2021 : RF developer assigned with golive 12Oct2021. | None | None | 2022-01-21 05:30 |  | Saranji, Muthu | Varate, Rohit | Rohit Varate | Completed | 2022-02-08 |  | 2022-02-10 05:30 |  |  | 2022-02-10 05:30 | 2022-02-10 05:30 | [5 empty] | 0 | [22 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Eye pain | No | Global | Open | Yes |  |  | 2022-02-01 05:30 |  | 2022-02-04 05:30 | 2022-02-04 05:30 |  |  |  |  | 2022-01-31 05:30 | [5 empty] | None of the above
CSAF312A | CSAF312X2201 | C1200706 | Phase II | RAVE_SDTM | Rave EDC - Inhouse |  |  |  | DB Locked |  |  | 2016-12-01 05:30 |  | 2016-09-01 05:30 |  | Completed | 2018-02-21 05:30 | 2018-02-21 05:30 | 2018-03-19 05:30 | 2018-03-30 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Alcon InHouse | NIBR - OPHTHA | A randomized, vehicle-controlled, subject and investigator-masked, proof-of-concept study to evaluate the use of topical ocular SAF312 in the treatment of postoperative ocular pain in patients undergoing photorefractive keratectomy (PRK) surgery | CSAF312X2201 | N8 Ophthalmology - NIBR |  | Gomez, Emanuel | Ortega, Alexis | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Michael Ferriere | Carolina Cunha | [17 empty] | Rohit Varate | [28 empty] | GCE | [19 empty] | Ocular pain | No | Global | Completed | Yes | [16 empty] | None of the above
CSEG101A0_MA | CSEG101A0FR01 | C4008592 | Not Applicable |  | Other |  |  |  | Study Planned |  |  |  | 2021-02-26 05:30 | 2021-03-31 05:30 |  | Active | [5 empty] | NIS | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology |  | CSEG101A0FR01 RWE RC Nephropathy in SCD | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Bhataiya, Vishal | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Ashley O'Loughlin | Ashley O'Loughlin | [17 empty] | Sai Krishna Mettugari | [28 empty] | NA | [19 empty] | Sickle cell anaemia with crisis | No | Local | Open | Yes
CSEG101A_MA | CSEG101A2004 | C4006614 | Phase IV | Other | CRO - EDC |  |  |  | DB Conduct |  |  |  | 2019-10-30 05:30 | 2020-01-22 05:30 |  | Active |  |  |  |  | FALSE | None | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology |  | CSEG101A2004 Sickle Cell Pain Diary (SCPD-S) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Bhataiya, Vishal | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Linda Voice | Anne Ruault | [17 empty] | Sai Krishna Mettugari | [28 empty] | Other | [7 empty] | 30 | 0 | [10 empty] | Sickle cell anaemia with crisis | No | Global | Open | Yes | [16 empty] | None of the above
CSEG101A | CSEG101A2102 | C3000259 | Phase I | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-09-06 05:30 |  | 2017-07-06 05:30 |  | Completed | 2018-03-30 05:30 | 2018-02-05 05:30 | 2018-03-15 05:30 | 2018-04-06 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A phase I single dose, randomized, open-label, parallel group, single-center trial to assess the comparability of crizanlizumab pharmacokinetics and pharmacodynamics administered as SEG101 in comparison to SelG1 in healthy volunteers. | CSEG101A2102 NVS Healthy Volunteer N67 | PA Oncology (Hematology not for MA projects) | Navarro, Christelle | Das, Chiranjeeb | Gupte, Smita | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Raquel Merino Herranz | Neha Ruparelia | [15 empty] | Sundar, N Sushant |  | Sai Krishna Mettugari | [14 empty] | CRO | [6 empty] | ONC | Novartis | InHouse |  |  |  |  | Parexel | [20 empty] | Yes | Global | Completed | Yes | [16 empty] | None of the above
CSEG101A | CSEG101A2202 | C3001632 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2017-10-16 05:30 | 2017-12-29 05:30 | DB Conduct | Final DBL | 2023-08-11 05:30 | 2017-12-19 05:30 |  | 2017-07-31 05:30 |  | Active | 2023-06-30 05:30 |  | 2023-08-11 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A phase II, Multicenter, Open-Label Study to Assess PK/PD of SEG101 (crizanlizumab), with or without Hydroxyurea/Hydroxycarbamide in Sickle Cell Disease Patients with Vaso-Occlusive Crisis\n\n | CSEG101A2202 NVS Adult Study PK/PD N55 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shaik, Taniya Yunus | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Urs Albers | Urs Albers | Tadiparthy, Ramakanth | KADAM, NAVINA VIJAY | Completed | 2022-01-06 05:30 | Ramakanth has transitioned the study to Navina Kadam on 06-JAN-2022. |  | DRM (DIAL) | Maricherla, Vijayroshan | Shrivastava, Nikhil | Completed | 15-Dec-2021: RF V12.0 updated and finalized WRT PPC#13 and #14. SNOW-51 (RITM3296926) raised and LSP is notified. 29-Jan-2021: B12L DTS included in the Rule File V11.0 and finalized in CREDI. Raised SNOW-51 ticket and notified LSP regarding the same. 12-Jan-2021: SNOW-51 was raised on 05th Oct2020 to rebuild AE and refresh ZN domain as per PPC#12. LSP and SMT developers were notified. No impact to Rule File. 26Nov2020: Backup: Chandrakala Whats planned: Nothing planned as of now. 25-Aug-2020 (SHRIVNI5): RF V11.0 updated and finalized to update the domain of Rescreen form from 'SS' to 'DS'. SNOW ticket raised for LSH rebuild. 01Apr2020 : Reassigned RF from Roshan to Nikhil | LBG003_TR - There are database issues with new CRF form 'LBG003_TR' and thus it cannot be included in the current version of RF (V12.0). Once database is updated, then this form will be included in the next version of Rule File. Issues: 1. The result field “UCOLOR_LBVALUE” neither has dictionary value nor Analyte attached with it. 2. The form is not appearing in any folder for the data entry." | None | 2018-10-08 05:30 | Transition Study and Legacy process | Praveen kumar, Chakka Giri | Garje, Sagar | Sai Krishna Mettugari | Completed | 2018-10-23 | Completed | 2020-05-13 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-10-22 05:30 | 2018-10-22 05:30 | Study Transition | 2020-06-06 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 16 | 109 | 68 | 0 | 578 | 809 | 0 | 235 | 40 | 243 | 1092 | 3 | 0 |  | Sickle cell disease | Yes | Global | Open | Yes | [10 empty] | 2020-05-06 05:30 |  |  |  | Interim-Analysis | Sundar, N Sushant | None of the above | Yes
CSEG101A_MA | CSEG101A2203 | C4002430 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2019-09-19 05:30 |  | DB Conduct | DB Snapshot | 2022-06-09 05:30 | 2019-12-10 05:30 | 2019-06-28 05:30 | 2019-06-21 05:30 |  | Active | 2023-03-16 05:30 |  | 2023-04-27 05:30 |  | FALSE | Not Applicable | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | GMA - Oncology | A Phase II, multicenter, randomized, open label two arm study evaluating the effect of crizanlizumab + standard of care and standard of care alone on renal function in sickle cell disease patients &gt;/= 16 years with chronic kidney disease due to sickle cell nephropathy | CSEG101A2203 STEADFAST | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Kota, Ashok | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Katie Zhou | Katie Zhou | Choppadandi, Kranthikumar | Bakka, Sandeep |  |  |  |  | DRM | Choppadandi, Kranthikumar | Choppadandi, Kranthikumar | Completed | 26-SEG-2021: Working on RF updates for PPC and ZI1L DTS 21-Jan2021: Kranthi: QS1L and PPC03 changes were included in RF_V6.0 and raised SNOW ticket for LSh set-up on 18-jan-2021. LSh set-up will be completed by 22-Jan-2021 as per LSP's confirmation 30-Nov-2020: RF_V4.1 is released for peer review to include QS1L DTS 24-Nov-2020: DTS has been reviewed and provided comments. RF will be updated once the updated DTS is finalized. 23Oct2020 : PPC is implemneted and QS1L DTS to be final by next week as per DBD. 25-Sep-2020: QS1L DTS is kept on hold as per TDM. Team is working on Protocol Amendment 01 01-Sep-2020: QS1L DTS is kept on hold as per TDM. Team is working on Protocol Amendment 01 11-Aug-2020: Sent reminder for the updated QS1L DTS. QS1L DTS is kept on hold as per TDM. Team is working on Protocol Amendment 01. 28-Jul-2020: Still pending for QS1L DTS updates. 03-Jul-2020: DTS update is under progress. Requested DBP to share the status for QS1L which is flagged in missing report 11-Jun-2020: Sent a reminder to DBP for QS1L DTS updates 04-Jun-2020: Few concerns raised on QS1L DTS. 01-Jun-2020: LBL DTS added in RF V3.0. and requested DBP/TDM to share the final QS1L DTS 14-May-2020: Requested DBP to share all the required documents to include the DTS in RF. QS1L and LBL flagged in missing DTS report | None | None | 2019-10-11 05:30 |  | Nidamanuru, Kalyan Kumar | Agavekar, Amit | Sai Krishna Mettugari | Completed | 2019-10-18 | Completed | 2019-11-29 05:30 | completed |  | 2019-11-29 05:30 | 2019-11-29 05:30 |  | 2020-06-16 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA-;#AE;#DV;#EC;#ZJ;#ZK;#ZK02 | [11 empty] | NA | [5 empty] | 8 | 20 | 92 | 0 | 240 | 1133 | 0 | 270 | 36 | 235 | 1404 | 6 | 0 |  | Sickle cell disease | No | Global | Open | Yes | [10 empty] | 2019-11-28 05:30 | [5 empty] | None of the above | Yes
CSEG101A | CSEG101A2301 | C3000266 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2019-04-24 05:30 | 2019-05-22 05:30 | 2019-07-29 05:30 | DB Conduct | DB Snapshot | 2022-03-28 05:30 | 2019-07-26 05:30 | 2018-12-14 05:30 | 2019-01-31 05:30 |  | Active | 2027-07-29 05:30 |  | 2027-09-08 05:30 |  | TRUE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A phase III, Multicenter, Randomized, Placebo controlled, Double-blind Study to Assess Efficacy and Safety of Two Doses of Crizanlizumab versus placebo, with or without Hydroxyurea /Hydroxycarbamide Therapy, in Adolescent and Adult Sickle Cell Disease Patients with Vaso-Occlusive Crises | CSEG101A2301 NVS Adolescent and Adult Study N240 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | CHANDRA PATEL, SUBHASH | Dsouza, Carlton | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Raquel Merino Herranz | Raquel Merino Herranz | Ahuja, Mohit | Ahuja, Mohit |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 24Apr2019 |  | DRM | Ambati, Purnachander | Shrivastava, Nikhil | Completed | 11-Jan-2022: SNOW-51 (RITM3367938) ticket raised and notified LSH for SH/SMT updates WRT PPC#11. No impact to Rule File. 07-Jan-2022: B14L DTS included in the Rule File V21.0 and finalized. SNOW-51 raised and notified the LSP. 22-Jun-2021: RF V20.0 updated and finalized for an ahoc request by SDTM programmer to add FACAT in 2 FAMH forms. SNOW-51 raised and LSP has been notified. 26-May-2021: RF V19.0 updated for (CES001_TR, New Form - FAAES001 and lot of other updates requested by SDTM programmer) and finalized. SNOW-51 raised and LSP notified. 06-May-2021: RF V18.2 has been created WRT PPC#08 and other SDTM related requests. Released for peer review. Waiting for the comment/confirmation. 15-Apr-2021: PPC#08 related to protocol amendment is currently ongoing. RF and LSH are impacted. 10-Feb-2021: RF V18.0 finalized in CREDI WRT FA1L and FA2L DTS. SNOW-51 is raised and LSP is notified. 29-Dec-2020: RF V17.0 finalized in CREDI WRT PPC#07. SNOW-51 is raised and LSP is notified. 26Nov2020: Backup: Sujan Whats planned: PPC#07 is in draft state. PPC form is reviewed. Need to include in RF once database is updated. 22-Sep-2020 (SHRIVNI5): RF V15.0 with respect to PPC06 and "EC1" domain has been finalized and sent for LSH rebuild. 24-Jul-2020 (SHRIVNI5): RF V14.0 with respect to PPC05 has been finalized and sent for LSH rebuild. 05-Jun-2020 (SHRIVNI5): B11L DTS included in the RF V13.0 and SNOW-51 raised for LSH setup. 27May2020 : B11L flagged in missing DTS report. followup with DBD 03-May-2020 (SHRIVNI5): RF V12.0 finalized WRT PPC4. SNOW-51 ticket raised to process CM and DS domains. 01Apr2020 : Re-assigned RF from Bhaskar to Nikhil. 27Mar2020 : QS1L to QS7L final DTS included in RF and SNOW ticket raised on 17Mar2020. 03Mar2020 : QS1L to QS7L as per missing DTS report, DBD has not shared the finalized DTS until today. DTS tracker and no. of DTS shared are not matching Notified DBD. 22Jan2020 (SHRIVNI5): RF version 9.0 updated and SNOW-51 ticket raised for correcting the LB domain issue. 13Jan2020 (SHRIVNI5): All the forms and DTS are included in the rule file. 18Jul2019,BAICH3: RF v1.0 finalized. 09Jul2019,BAICH3: R4 Rulefile review comments shared. 04Jul2019,BAICH3: R1-RF review comments shared. | None | None | 2019-07-26 05:30 | Transition Study and Legacy process | Kommu, Ranjith Kumar | Agavekar, Amit | Sai Krishna Mettugari | Completed | 2019-07-18 | Completed | 2019-08-22 05:30 |  | Pre-requisites not met | 2019-08-29 05:30 | 2019-08-29 05:30 | Pre-requisites not met | 2020-01-08 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | EC;#Y1;#Y5;#YD;#ZJ;#ZK;#ZK02;#ZK03 | [11 empty] | NA | [5 empty] | 12 | 89 | 82 | 0 | 1092 | 1257 | 0 | 331 | 41 | 269 | 1567 | 6 | 0 |  | Sickle cell disease | Yes | Global | Open | Yes | [10 empty] | 2019-08-22 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Challa, Nandini | GDD annual target | Yes
CSEG101A | CSEG101A2401B | C4004866 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2021-01-07 05:30 | 2021-04-30 05:30 | 2021-06-15 05:30 | DB Conduct | Final DBL | 2029-02-26 05:30 | 2021-06-10 05:30 | 2020-12-08 05:30 | 2020-11-26 05:30 | 2021-01-25 05:30 | Active | 2029-01-15 05:30 |  | 2029-02-26 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases |  | CSEG101A2401B - Rollover protocol | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | GV, Srinivasan | Dsouza, Carlton | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Kaushal Pathak | Lambert Besemtabe Asuagbor | Rachakonda, Hima Sailaja | Ahuja, Mohit | Not Started |  | RF developer assigned on 23Dec2020 and moved golive date was 01Mar2021. The initial golive as 07Jan2021 when DBD assigned. Then it moved to 26-Feb-2021 followed by 01Mar2021. |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 03Aug2021:CSEG101A2401B_Rule file_version 2.0 is finalized in CREDI with IRV DTS included in it. SNOW-51 ticket is also raised with ticket number- RITM2834694 for LSH Setup 02Aug2021: Shared the comments with the TDM after completing the review. Updated the Rule file and released it for peer review. 29July2021: Received the IRV DTS for review and update in Rule file 30Apr2021: CSEG101A2401B Rule File Version 1.0 is finalized in CREDI and SNOW 05 ticket is also raised with ticket no.- RITM2524898 for LSH setup. 28Apr2021: DBD confirmed the Go-live date pushed to 29Apr2021. 22Apr2021: DBD confirmed the Go-live date pushed to 27Apr2021 14Apr2021: Rehana completed the review and confirmed to proceed with finalization. 12Apr2021: Arpita worked on the RF with mentoring from Kranthi . Sent the RF for review for 1 pending form. Rehana performing review. 15-Feb-2021: Rule File developed, peer review completed and ready to be finalized except one form . Review completed by chandrakala 20-Jan-2021: Reviewed ALS and SRFs, provided comments to Lead DBP.. Initiated the RF development | None | None | 2021-04-30 05:30 |  | Kadam, Sandeep | Kadam, Sandeep | Sai Krishna Mettugari | Completed | 2021-06-22 | Completed | 2021-06-28 05:30 |  | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-06-28 05:30 | 2021-06-28 05:30 | System or Application issues (RAVE/LSH/JReview/GPS) | 2021-06-28 05:30 | 2021-06-28 05:30 |  |  |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 1 | 64 | 35 | 0 | 286 | 421 | 0 | 140 | 35 | 88 | 544 | 1 | 0 |  | Sickle cell disease | No | Global | Open | Yes | [10 empty] | 2021-06-25 05:30 | [5 empty] | None of the above | Yes
CSEG101A_MA | CSEG101A2402R | C4007595 | Phase IV |  | Other |  |  | 2020-12-01 05:30 | DB Set-Up |  |  | 2019-12-10 05:30 | 2020-11-30 05:30 | 2021-09-30 05:30 |  | Active | 2024-01-20 05:30 |  |  |  |  | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology |  | CSEG101A2402R Research Collaboration | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Bhataiya, Vishal | Bhataiya, Vishal | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Ashley O'Loughlin | Ashley O'Loughlin | [17 empty] | Sai Krishna Mettugari | [28 empty] | Other | [19 empty] | Sickle cell disease | No | Global | Open | Yes
CSEG101A | CSEG101A2403 | C4009135 | Phase IV | NCDS_2 | Rave EDC - Inhouse | 2020-10-20 05:30 | 2021-05-04 05:30 | 2021-07-09 05:30 | DB Conduct | Final DBL | 2024-10-01 05:30 | 2021-07-14 05:30 | 2020-08-13 05:30 | 2020-07-30 05:30 |  | Active | 2024-08-20 05:30 |  | 2024-10-01 05:30 |  | FALSE | PASS study | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | Phase IV multi-center study to assess the safety of Crizanlizumab with or without hydroxyurea therapy in sickle cell disease patients with vaso-occlusive crises | CSEG101A2403 India PASS study | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | CHANDRA PATEL, SUBHASH | Dsouza, Carlton | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Urs Albers | Urs Albers | Sinha, Deepakshi | Sinha, Deepakshi | Not Started |  | 04May2021 : DB into production. 29Apr2021 : DB golive on track planned for 30Apr2021. Initial golive planned DB golive as 20Oct2020 when RF developer assigned 08Sep2020. |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 28July2021: DBD shared the updated DTS and requested to include the DTS in rule file. 21July2021: Shared the comments after DTS review with the DBD. Requested the DBD to inform once LB DTS is finalized. 20July2021: DBD shared LB DTS for review. 5thMay2021: CSEG101A2403_Rule file_Version 1.0 is finalized in CREDI and SNOW-05 ticket is also raised with ticket number- RITM2535784 for LSH Setup. 3rdMay2021: Peer Review process is completed. Peer Reviewer confirmed to proceed for finalization once study is pushed to production. 23Apr2021: Arpita working on RF with mentoring support from Kranthi. Released for peer review. Rehana supporting peer review. 17-Feb-2021: sent a reminder to lead DBP for the study Go-Live date and updated ALS 02-Dec-2020: Requested DBP to share the updated ALS and study status 06-Oct2020: Reviewed ALS and provided comments to Lead DBP. 25-Sep-2020: Kranthi: reviewed ALS, SRFs and provided comments to Lead DBP for Screen updates as required 08Sep2020 : RF developer (Kranthi) assigned with planned DB golive as 20Oct2020. | None | LB | 2021-05-05 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sai Krishna Mettugari | Completed | 2021-07-02 | Completed | 2021-07-02 05:30 |  |  | 2021-07-02 05:30 | 2021-10-02 05:30 | Pre-requisites not met | 2021-07-02 05:30 |  |  |  | 80 | RaveX - Inhouse | Yes | [12 empty] | NA | [7 empty] | 52 | 0 |  |  | 0 |  |  |  | 1000 | 2 | 0 |  | Vaso-occlusive crisis | No | Global | Open | Yes | [10 empty] | 2021-07-02 05:30 | [5 empty] | None of the above | Yes
CSEG101B | CSEG101B2201 | C3001140 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-07-19 05:30 | 2018-08-30 05:30 | DB Conduct | Final DBL | 2025-01-01 05:30 | 2018-10-01 05:30 | 2018-02-23 05:30 | 2018-02-28 05:30 |  | Active | 2024-11-20 05:30 |  | 2025-01-01 05:30 |  | FALSE | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A phase 2, Multicenter, Open-Label Study to Assess Appropriate Dosing and to Evaluate Safety of Crizanlizumab, with or without Hydroxyurea/Hydroxycarbamide, in Sequential, Descending Age Groups of Pediatric Sickle Cell Disease Patients with Vaso-Occlusive Crisis | CSEG101B2201_Pediatric Study N100 | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Sangoi, Manshi Dhiren | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Nadege Pfender | Nadege Aurore Pfender | Govula, Shashikanth | JAGTAP, ABHISHEK PRABHAKAR | Completed | 2022-02-07 05:30 | 1-Nov-2021 : Giftson transitioned study to Deepthi |  | DRM (DIAL) | Govula, Shashikanth | Patnaik, Angella | Completed | 20DEC2021: RF Version 18.0 has been finalized for RF error. SNOW #51 (RITM3273925) raised for SMT/LSH updates. 8DEC2021: RF Version 17.0 has been finalized for PPC #17 updates. SNOW #51 (RITM3273925) raised for SMT/LSH updates. 7DEC2021: SDTM annotations received for RF updates. 25NOV2021: SDTM annotations for PPC #17 RF updates were not provided. Have requested TDM and Lead DBD to provide the same. 19JAN2021: RF Version 16.0 finalized for PPC15 updates. SNOW#51 raised for LSH updates. 7JAN2021: SG: PPC15 implemented. Rule file update required. 11AUG2020: PPC#12 implemented on 8AUG, RF finalized and sent for LSH Setup on 11AUG2020. 16JUL2020 (Angella): RF Version 10.0 finalized and SNOW#51 raised for LSH updates for B11L DTS, PPC11 updates and ODM, SC and ZC domain issues as per SDTM confirmation. 22Jun2020 : B11L flagged in Missing DTS report. follow up with DBD. Requested Angella to look into it in Shashi's absence. Wrong DTS template used as per the comment in report 27May2020 : B11L flagged in Missing DTS report. follow up with DBD 06Mar2020 : Included raised the SNOW51 ticket(RITM1191206) for LSH set up for newly added/updated forms. Included CES001_TR pending form. Sent for LSH setup and SMT 02 Mar2020 : CES001_TR needs to be updated to split into CE and FACE needs to be checked with SDTM programmer and other stakeholders from DIAL and DRRA. B1 & CES002 included in RF last week of Feb. 10Feb2020 : CES002 pending to be included in RF. B1 DTS pending to be included in RF. Tentatively will e completed by 12Feb2020. (Kranthi Supporting in Shahsi's absence) | None | None | 2018-12-20 05:30 |  | Nidamanuru, Kalyan Kumar | Agavekar, Amit | Sai Krishna Mettugari | Completed | 2018-12-20 | Completed | 2019-07-15 05:30 |  | Retrospective DRM studies | 2018-12-24 05:30 | 2018-12-24 05:30 | Retrospective DRM studies | 2019-08-21 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 17 | 38 | 79 | 0 | 529 | 1142 | 0 | 346 | 34 | 289 | 1465 | 5 | 0 |  | Sickle cell disease | Yes | Global | Open | Yes | [10 empty] | 2019-07-15 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Sundar, N Sushant | None of the above | Yes
CSEG101B | CSEG101B2202 | C4007876 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2020-11-13 05:30 |  | 2022-04-05 05:30 | Study Planned | DB Go-live | 2023-02-14 05:30 |  | 2022-12-13 05:30 |  |  | Planned | 2027-01-12 05:30 |  | 2026-03-23 05:30 |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Rare Diseases | A phase 2, Multicenter, Randomized, Double-blinded Study to Evaluate Efficacy, PK, and Safety of Crizanlizumab at 8.5 mg/kg versus X mg/kg, with or without Hydroxyurea/Hydroxycarbamide, in Pediatric Sickle Cell Disease Patients | CSEG101B2202 Pediatric study 7.5mg/kg | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Abdelmalek, Fatna | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Raquel Merino Herranz | Raquel Merino Herranz | Gandla, Prashanth | Gandla, Prashanth | Not Started |  | 03May2021 : Mithun (DM GH) - update on t SEG101B2202- The trial might get started this year, nothing decided yet. GTPH has details about the meeting in May’21 where the decision will be made. As of now updated the status as DB set up planned. Study is on hold from 25MAR2020 Based on the FDA feedback to PPSR received earlier this week, it has been decided to hold the SEG101B2202 study until further notice as the concept sheet needs to be revised to meet the FDA requirements. Several options are currently under discussion and the GPT needs to figure out what is the best approach. |  |  | Saha, Saikat | Saha, Saikat | Not Started | [7 empty] | Sai Krishna Mettugari | [36 empty] | 74 | 0 |  |  | 0 |  |  |  | 1052 | 3 | 0 |  | Sickle cell anaemia with crisis | Yes | Global | Open | Yes | [16 empty] | None of the above
CSEG101B | CSEG101B2301 | C3000401 | Phase III | NCDS_2 |  |  |  | 2020-12-31 05:30 |  | Final DBL | 2028-03-08 05:30 |  | 2020-09-11 05:30 |  |  | On Hold | 2027-12-29 05:30 |  | 2028-03-08 05:30 |  | FALSE |  |  |  | InHouse |  | A phase 3, Multicenter, Randomized, Placebo-Controlled, Double-Blind Study to Assess Safety and Efficacy of Crizanlizumab with or without Hydroxyurea Therapy in Pediatric Sickle Cell Disease Patients with Sickle Cell-Related Pain Crises | CSEG101B2301_Pediatric_Study N250 | PA Oncology (Hematology not for MA projects) | [6 empty] | Raquel Merino Herranz | [54 empty] | 80 | 0 |  |  | 0 |  |  |  | 1100 | 10 | 0 |  | Pain; Sickle cell disease | No | Global | Wind Down | Yes | [16 empty] | None of the above
CSEG101C1 | CSEG101C12101 | C4003019 | Phase I | NCDS_2 |  |  |  | 2022-11-02 05:30 |  | Final DBL | 2023-07-07 05:30 |  | 2022-08-02 05:30 |  |  | Planned | 2023-06-02 05:30 |  | 2023-07-07 05:30 |  | FALSE |  |  |  | Outsourced |  |  | CSEG101C2101 HV | PA Oncology (Hematology not for MA projects) | [6 empty] | Farida Souami | [54 empty] | 105 | 0 |  |  | 0 |  |  |  | 1300 | 5 | 0 |  | Sickle cell disease | No | Global | Open | Yes | [16 empty] | None of the above
CSKO136A1 | CSKO136A12201J | C4012164 | Phase III | Other | Other |  |  | 2021-05-24 05:30 | DB Conduct | Final DBL | 2023-05-01 05:30 | 2021-05-06 05:30 | 2021-02-04 05:30 | 2022-01-19 05:30 |  | Active | 2023-03-20 05:30 |  | 2023-05-01 05:30 |  |  | Submission | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A randomized, double-blind, placebo-controlled, multicenter study of ensovibep (MP0420) in ambulatory adult patients with symptomatic COVID-19 | CSKO136A12201J Phase 2/3 OutPatient Trial | P6 Global Health | Vithala, Srinivas | Chandrakant, Khilari | Chandrakant, Khilari | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Kimberly Holmes; Michele Eckhardt | Kimberly Holmes | [17 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | [19 empty] | Corona virus infection | Yes | Global | Open | Yes
CSOK583A1 | CSOK583A12301 | C4003292 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2020-08-20 05:30 | 2021-03-24 05:30 | 2021-04-30 05:30 | DB Conduct | Interim DBL | 2023-01-26 05:30 | 2021-05-12 05:30 | 2020-06-02 05:30 | 2020-05-22 05:30 | 2021-03-24 05:30 | Active | 2023-05-05 05:30 |  | 2024-02-21 05:30 |  | FALSE | Submission | Kolla, Rajanikanth | Cluster C (fGSK,IHD,Sandoz) | InHouse | Biosimilars/ Sandoz | A 52-week multicenter, randomized, double-masked, 2-arm parallel study to compare efficacy, safety and immunogenicity of SOK583A1 to EyleaÂ®, administered intravitreally, in patients with neovascular age-related macular degeneration | CSOK583A12301 SOK583A1 Phase III Study Non-Onco | P2 SZ Biopharma | Marshall, Lee | Marthi, Padmini | Machado, Sundeep | Bhabhe, Nikhil | Ninan, Esther | Nadja Rudholzner; Shrihari Sundara Jathanakodi | Nadja Rudholzner | Gandla, Prashanth | Rao, S Shashikanth | Completed |  | Oct 2021 : Pallabi transitioned study to Shashi initial golive as 20Aug2020 when RF developer was assigned on 26Mar2020 |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 28Jun2021: DBD shared few DDPASS issues. Kranthi supported in reviewing the issues and promptly replied to the DBD 24Jun2021: CSOK583A12301 Rule file Version 3.0 is finalized in SUBWAY with LB1L DTS included in the Rule file. SNOW-51 ticket is also raised with ticket number RITM2705253. 24Jun2021: Released CSOK583A12301 V2.1 for Peer review with LB DTS included. 24Jun2021: DTS Review comments was shared with DBD and TDM. 23Jun2021: Clinical Programmer informed that LB data is not populating at downstream. Informed the DBD and CP that there is no LB pages in this study and therefore it is not populating. Also requested both to share LB DTS if any for my review. TDM shared the LB DTS which was finalized in May but it was not sent for review earlier nor it appeared in the Missing Forms/DTS report as well. 24Mar2021 : RF final and snow #05 raised by Arpita. 21-Jan-2021:Kranthi: Review of ALS is completed and provide the comments to Lead DBP. Initiated the RF development and waiting for the UAT SODs from Lead DBP. 26Mar2020: RF developer assigned. initial golive as 20Aug2020 when RF developer was assigned on 26Mar2020 | None | None | 2021-03-24 05:30 |  | Majumdar, Shreya | Majumdar, Shreya | Sandeep Kadam | Completed | 2021-04-14 | Completed | 2021-04-30 05:30 |  |  | 2021-04-30 05:30 | 2021-04-30 05:30 |  | 2021-07-30 05:30 |  |  |  | 100 | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 2 | 13 | 56 | 0 | 133 | 552 | 0 | 168 | 34 | 132 | 718 | 3 | 0 |  | Macular degeneration | No | Global | Open | Yes | [10 empty] | 2021-04-30 05:30 | [5 empty] | None of the above | Yes
CSOM230B | CSOM230B2219 | C1001517 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-05-23 05:30 |  | 2013-09-26 05:30 |  | Completed | 2018-04-13 05:30 | 2018-03-26 05:30 | 2018-06-26 05:30 | 2018-06-29 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A multi-center, randomized, open-label, Phase IV study to investigate the management of pasireotide-induced hyperglycemia with incretin based therapy or insulin in adult patients with Cushing's disease or acromegaly | SOM230B2219 Hyperglycemia mgmt in CD or Acro | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Deshpande Dubey, Aditi | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Lisa Burgmeyer | Judianne Wojna |  | Lingampalli, Rohit | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | Susan.Park@ppdi.com | Earlier DBD: Shelly Antle /Asha |  |  | 41 | 0 |  |  | 0 |  |  |  | 709 | 3 | 0 |  | Acromegaly; Cushing's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230B_MA | CSOM230B2406 | C1001772 | Phase III | NOVDD | [7 empty] | 2011-08-16 05:30 |  | 2011-03-16 05:30 |  | Completed |  | 2017-01-26 05:30 |  | 2017-03-23 05:30 | FALSE |  |  |  | Outsourced |  | Seascape: Safety and Expanded Access Study in Cushing's disease to Allocate Pasireotide Expertise | SOM230B2406 CD mono s.c. SEASCAPE | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Hassan El Gazri | Hassan El Gazri | [66 empty] | Cushing's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230B | CSOM230B2410 | C1001773 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-03-28 05:30 |  | 2012-07-10 05:30 |  | Active | 2024-05-01 05:30 | 2020-11-06 05:30 |  |  | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | Non-interventional study for the generation of long term safety and efficacy data of pasireotide s.c. in patients with CushingÂ¿s disease (Post-Authorization Safety Study) | CSOM230B2410 CD registry s.c. | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kalidindi, Neeharika | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Janet Lasher | Janet Lasher |  | Sinha, Deepakshi | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | Pauline.McBain@ppdi.com | Earlier DBD: Jugnu Kumari |  |  | 23 | 0 |  |  | 0 |  |  |  | 383 | 1 | 0 |  | Cushing's disease | No | Global | Wind Down | Yes | [16 empty] | None of the above
CSOM230B_MA | CSOM230B2411 | C1001774 | Phase II | NOVDD | CRO - EDC |  |  | 2013-08-23 05:30 | DB Locked |  |  | 2014-03-06 05:30 | 2013-05-10 05:30 | 2013-05-10 05:30 |  | Completed | 2019-06-30 05:30 | 2019-09-04 05:30 | 2019-08-08 05:30 | 2019-09-16 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | GMA - Oncology | A phase II trial to assess the efficacy and safety of pasireotde sc alone and in combination with cabergoline in patients with Cushing's disease | CSOM230B2411 CD combo sc plus Cabergoline CAPACITY | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Sadhu, Soumen Kumar | Bagayatkar, Rupali Sudesh | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Heather Patino | Heather Patino |  | Gandla, Prashanth | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | Gary.Lock@ppdi.com | Earlier DBD: Jugnu Kumari |  |  | 47 | 0 |  |  | 0 |  |  |  | 389 |  |  |  | Cushing's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230B | CSOM230B2412 | C1001775 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked | Final DBL | 2023-09-04 05:30 | 2013-06-10 05:30 |  | 2013-01-29 05:30 |  | Active | 2023-06-09 05:30 | 2020-10-29 05:30 | 2023-09-04 05:30 |  | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | An open label, multi-center pasireotide roll-over protocol for patients who have completed a previous Novartis-sponsored pasireotide study and are judged by the investigator to benefit from continued pasireotide treatment. | CSOM230B2412 STEP | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kalidindi, Neeharika | Deshpande Dubey, Aditi | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Anne Zuse | Anne Zuse |  | Lingampalli, Rohit | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | Kayleigh.Kirkpatrick@ppdi.com | Earlier DBD: Asha Rajanna |  |  | 13 | 0 |  |  | 0 |  |  |  | 106 |  |  |  | Acromegaly; Carcinoid tumour; Cushing's disease; Dumping syndrome; Melanoma; Neuroendocrine tumour | No | Global | Open | Yes | [16 empty] | None of the above
CSOM230C | CSOM230C1202 | C1001518 | Phase II | NOVDD | OC RDC - Inhouse |  |  |  | DB Locked |  |  | 2012-10-16 05:30 |  | 2012-07-12 05:30 |  | Completed |  | 2017-04-10 05:30 |  | 2017-04-17 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A multicenter, open-label, randomized, phase II study to evaluate efficacy, safety, pharmacokinetics and pharmacodynamics of pasireotide LAR in Japanese patients with active acromegaly or pituitary gigantism | Japan_SOM230C1202 P2 Acro | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | SAITO, MIWA | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | KAZUYUKI SUZUKI | KAZUYUKI SUZUKI | [17 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | [19 empty] | Acromegaly | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230C_MA | CSOM230C2402 | C1001779 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-07-19 05:30 |  | 2010-03-15 05:30 |  | Completed |  | 2017-02-28 05:30 |  | 2017-08-23 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A phase III, multicenter, randomized, parallel-group study to assess the efficacy and safety of double-blind pasireotide LAR 40 mg and pasireotide LAR 60 mg versus open-label octreotide LAR or lanreotide ATG in patients with inadequately controlled acromegaly | SOM230C2402 Acro LAR PAOLA | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Abdelmalek, Fatna | Abdelmalek, Fatna | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Hassan El Gazri | Hassan El Gazri | [17 empty] | Sai Krishna Mettugari | [28 empty] | PPD | [19 empty] | Acromegaly | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230C_MA | CSOM230C2413 | C1001780 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-03-31 05:30 |  | 2014-09-22 05:30 |  | Completed | 2018-11-12 05:30 | 2018-09-27 05:30 | 2018-11-09 05:30 | 2018-11-09 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | Pasireotide LAR in patients with uncontrolled acromegaly | CSOM230C2413 Acro LAR uncontrolled | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Vinola, Rose | Bagayatkar, Rupali Sudesh | Kachchhava, Avinash Balasaheb | Krishnan, Kripesh | Catherine Bouard | Catherine Bouard |  | Gandla, Prashanth | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Oncology | AP21 | PPD | mailto:Pavel.Kamyshev@ppdi.com | Earlier DBD: Asha Rajanna |  |  | 49 | 0 |  |  | 0 |  |  |  | 394 | 3 | 0 |  | Acromegaly |  | Global | Completed | Yes | [16 empty] | None of the above
CSOM230G | CSOM230G1401 | C3001043 | Phase IV | Other |  |  |  | 2018-10-15 05:30 |  |  |  | 2018-10-25 05:30 | 2019-06-28 05:30 | 2018-04-25 05:30 |  | Active | 2023-01-31 05:30 | 2020-10-23 05:30 |  |  | FALSE |  |  |  | Outsourced |  |  | CSOM230G1401 Japan PMS | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | HARUKA NISHIOKA | HARUKA NISHIOKA | [66 empty] | Cushing's disease | No | Global | Open | Yes | [16 empty] | None of the above
CSOM230G | CSOM230G2304 | C1001520 | Phase III | NOVDD | CRO - EDC |  |  | 2011-11-04 05:30 | DB Locked |  |  | 2011-11-04 05:30 |  | 2011-05-05 05:30 |  | Completed |  | 2016-12-21 05:30 |  | 2017-03-15 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | A randomized, double-blind, multicenter, phase III study to evaluate the efficacy and safety of pasireotide LAR in patients with Cushing¿s disease | SOM230G2304 Cushing's disease LAR Pivotal | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Abdelmalek, Fatna | Abdelmalek, Fatna | Regula, Ramakrishna | Krishnan, Kripesh | Judianne Wojna | Judianne Wojna | [17 empty] | Sai Krishna Mettugari | [28 empty] | PPD | [19 empty] | Cushing's disease | No | Global | Completed | Yes | [16 empty] | None of the above
CSOM230A0 | CSOM230X2103C | C1001515 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-06-16 05:30 |  | 2014-11-11 05:30 |  | Completed | 2019-02-25 05:30 | 2019-03-07 05:30 | 2019-05-24 05:30 | 2019-05-28 05:30 | FALSE |  | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Rare Diseases | An open label, phase I, dose-escalation study to evaluate the tolerability, safety, and effects on glucose metabolism of the co-administration of pasireotide and octreotide, s.c. and LAR formulations in healthy volunteers | SOM230X2103C P1 HV Combo (SMS995) | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Kohli, Deepti | Abdelmalek, Fatna | Chouhan, Mithun Mahesh | Krishnan, Kripesh | Sabine Turri | Sabine Turri |  | Sinha, Deepakshi | [15 empty] | Sai Krishna Mettugari | [28 empty] | Parexel | Oncology | BP21 | Parexel | ThinThin.Mencarini@parexel.com | Earlier DBD: Chandrima /Jugnu; Amendment happen for the study still waiting for CRO empty SAS shell to compare and release the study to production/ DTS updates going on |  |  | 33 | 0 |  |  | 0 |  |  |  | 564 | 4 | 0 |  | Glucose tolerance impaired | No | Global | Open | Yes | [16 empty] | None of the above
CSOM230Y | CSOM230Y2201 | C1200398 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2016-10-31 05:30 |  | 2015-10-30 05:30 |  | Completed | 2018-12-03 05:30 | 2018-09-25 05:30 | 2019-02-11 05:30 | 2019-02-11 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - NS | A Two Part Multicenter, Placebo-Controlled, Active-Comparator Controlled, Single Dose Study in Acute Episodic and Chronic Cluster Headache to Evaluate the Safety and Efficacy of SOM230 s.c. | CSOM230Y2201 | P4 Neuroscience | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Denise Serra | [15 empty] | Manoharan, Vivek |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | [12 empty] | CMED | [19 empty] | Cluster headache | No | Global | Completed | Yes | [16 empty] | None of the above
CSPP100A | CSPP100A1401 | C1001521 | Phase IV | Other |  |  |  | 2009-10-01 05:30 |  |  |  | 2009-11-04 05:30 | 2009-08-26 05:30 | 2009-09-27 05:30 |  | Completed | 2017-07-26 05:30 | 2017-07-06 05:30 | 2017-07-26 05:30 | 2017-07-06 05:30 | FALSE |  |  |  | Outsourced |  |  | JPN_Special Inv._SPP100A1401 | P6 Global Health | [6 empty] | YOHEI SHINFUKU | [66 empty] | Hypertension | No | Global | Terminated | Yes | [16 empty] | None of the above
CSPP100A | CSPP100A2365E2 | C1001522 | Phase III | NOVDD | [7 empty] | 2011-08-19 05:30 |  | 2011-06-17 05:30 |  | Completed |  | 2017-08-03 05:30 |  | 2017-09-19 05:30 | FALSE |  |  |  | Outsourced |  | A multicenter, 52 to 104 week extension study to evaluate the long term growth and development of pediatric hypertensive patients 3 - 17 years of age treated previously with Aliskiren | Ext. study ped. 6 - 17 yrs_SPP100A2365E2 | P6 Global Health | [5 empty] | Michele Valentin | Jeroze Farhad Engineer | [66 empty] | Hypertension | No | Global | Completed | Yes | [16 empty] | None of the above
CSPP100F | CSPP100F2301 | C3001258 | Phase III | NOVDD | [7 empty] | 2003-05-13 05:30 |  | 2008-12-05 05:30 |  | Completed |  |  |  | 2015-11-30 05:30 | FALSE |  |  |  | IDMA |  | A multicenter, randomized, double-blind, parallel group, active-controlled study to evaluate the efficacy and safety of both Aliskiren monotherapy and Aliskiren/Enalapril combination therapy compared to Enalapril monotherapy, on morbidity and mortality in patients with chronic heart failure (NYHA Class II - IV) | Efficacy_Safety_Aliskiren_Enalapril_CSPP100F2301 | P6 Global Health | [5 empty] | Ilse Devrieze | Chaitanya Nandam | [66 empty] | Congestive heart failure |  | Global | Completed | Yes | [16 empty] | None of the above
CSTI571A | CSTI571A2406 | C1001783 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2033-06-02 05:30 | 2013-03-26 05:30 |  | 2012-08-28 05:30 |  | Active | 2033-04-21 05:30 |  | 2033-06-02 05:30 |  | FALSE | 2 | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | An open label, multi-center imatinib roll-over protocol for patients who have completed a previous Novartis sponsored imatinib study and are judged by the investigator to benefit from continued imatinib treatment | CSTI571A2406 (STEP) Rollover PIV-CML/Phpos/M | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kumar HC, Vijay | Kumar HC, Vijay | Chitre, Vrushali | Nair, Sreesha | Vanessa McGuire | Vanessa McGuire |  | Lingampalli, Rohit | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | AP21 | PPD | Susan.Park@ppdi.com | Earlier DBD: Chandrima /Jugnu; Issue in loading data to CT4. many ticket has been raised. Issue is persisting prior to transition. |  |  | 17 | 0 |  |  | 0 |  |  |  | 117 |  |  |  | Chronic myeloid leukaemia | No | Global | Open: Reapproval | Yes | [16 empty] | None of the above
CSTI571I | CSTI571I2201 | C1001527 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Conduct | Final DBL | 2022-10-04 05:30 | 2014-07-14 05:30 |  | 2014-01-30 05:30 |  | Active | 2022-08-23 05:30 |  | 2022-10-04 05:30 |  | FALSE | 2 | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | A European observational registry collecting efficacy and safety data in newly diagnosed pediatric Philadelphiapositive (Ph+) Acute Lymphoblastic Leukemia (ALL) patients treated with chemotherapy + imatinib (+/-) hematopoietic stem cell treatment (+/-)HSCT) | CSTI571I2201 Registry (EU) CML/Phpos ALL Ped | P0 Oncology (Solid Tumors all MA Onc projects) | Iyer, Srinarayani | Kumar HC, Vijay | Kumar HC, Vijay | Chitre, Vrushali | Nair, Sreesha | Janet Ng-Sikorski | Janet Ng-Sikorski |  | Gandla, Prashanth | [15 empty] | Amit Agavekar | [28 empty] | PPD | Oncology | BP21 | PPD | Stephen.Beckwith@ppdi.com | Earlier DBD: Jugnu Kumari; novartis.com> | [14 empty] | Acute lymphoblastic leukaemia | No | Global | Open | Yes | [16 empty] | None of the above
CSTI571L | CSTI571L1401 | C1001529 | Phase IV | Other | Paper |  |  | 2012-06-21 05:30 | DB Locked |  |  | 2012-06-12 05:30 | 2019-12-16 05:30 | 2012-02-20 05:30 |  | Completed | 2021-03-29 05:30 | 2020-06-25 05:30 | 2021-05-31 05:30 | 2021-05-07 05:30 | FALSE | Japan PMS | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | Outsourced | Hematology | Special observational investigation of Glivec Hypereosinophilic syndrome or Chronic eosinophilic leukemia | CSTI571L1401 Japan PMS_HES CEL | P0 Oncology (Solid Tumors all MA Onc projects) | YAMADA, KAYO | MURAKAMI, TAKUMI | YAMADA, KAYO | YAMADA, KAYO | YAMADA, KAYO | NOBUTAKA NAKAGAWA | NOBUTAKA NAKAGAWA | [17 empty] | Amit Agavekar | [28 empty] | Other | [19 empty] | Chronic eosinophilic leukaemia; Hypereosinophilic syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CSTI571A0 | CSTI571X2101 | C1200228 | Phase I | NCDS |  |  |  | 2012-04-19 05:30 |  |  |  | 2012-04-19 05:30 | 2011-11-21 05:30 | 2011-11-21 05:30 |  | Completed | 2016-07-28 05:30 | 2016-07-28 05:30 | 2016-10-21 05:30 | 2016-10-21 05:30 | FALSE |  |  |  | InHouse |  | A multi-arm dose-finding phase Ib multicenter study of imatinib in combination with the oral phosphatidyl-inositol 3-kinase (PI3-K) inhibitor BKM120 in patients with Gastrointestinal Stromal Tumor (GIST) who failed prior therapy with imatinib and sunitinib | CSTI571X2101 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Sabine Hertle | Sabine Hertle | [15 empty] | Ghate, Dhananjay | [50 empty] | Gastroinestinal Stromal Tumours (GIST); Gastrointestinal stromal tumour | Yes | Global | [18 empty] | None of the above
CSTI571A0 | CSTI571X2103 | C1001784 | Phase I | NCDS | OC RDC - Inhouse |  | 2012-11-06 05:30 |  | DB Locked | Final DBL Achieved |  | 2013-02-27 05:30 |  | 2012-09-26 05:30 |  | Completed | 2018-11-26 05:30 | 2018-10-19 05:30 | 2018-12-12 05:30 | 2018-12-07 05:30 | FALSE |  | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | A dose-finding phase Ib multicenter study of imatinib in combination with the oral phosphatidyl-inositol 3-kinase (PI3K) inhibitor BYL719 in patients with gastrointestinal stromal tumor (GIST) who failed prior therapy with imatinib and sunitinib | CSTI571X2103 PI-GIST/L3-C (BYL719) | P0 Oncology (Solid Tumors all MA Onc projects) | Vithala, Srinivas | Kurup, Rashmi | Sardesai, Pallavi Sharad | Gracey Sugunan, Unni Krishnan | Nair, Sreesha | Sabine Hertle | Yan Zhou | Maricherla, Vijayroshan | [14 empty] | Mulla, Afreen |  | Amit Agavekar | [21 empty] | ONC | Novartis | InHouse |  | 2013-02-04 05:30 |  |  | NA | [7 empty] | 138 | 0 |  |  | 0 |  |  |  | 325 | 3 | 0 |  | Gastric cancer | Yes | Global | Completed | Yes | [16 empty] | None of the above
CTBM100C | CTBM100C2407 | C1001531 | Phase IV | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2015-07-15 05:30 |  | 2014-01-23 05:30 |  | Stopped (with patients) |  |  |  |  | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A prospective observational study in cystic fibrosis patients with chronic respiratory Pseudomonas aeruginosa infection treated with TOBIÂ® Podhaler (TM) (tobramycin inhalation powder) or other FDA approved inhaled antipseudomonal antibacterial drugs | Real World Usage of TIP in CF_CTBM100C2407 | P6 Global Health | Vithala, Srinivas | Vithanala, Kiran Kumar | Bhabhe, Nikhil | Fazili, Subeh Mohsin | Krishnan, Kripesh | Nipa Alon | Nipa Alon | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Sai Krishna Mettugari | [28 empty] | IQVIA | Pharma | AP21 | Quintiles | mailto:Ian.Stott@iqvia.com | [16 empty] | No | Global | Terminated | Yes | [16 empty] | None of the above
CTBM100C | CTBM100C2419 | C3000194 | Phase IV | NCDS_2 | Rave EDC - Inhouse |  | 2018-05-30 05:30 | 2018-06-27 05:30 | DB Locked | Final DBL Achieved |  | 2018-06-26 05:30 |  | 2017-05-31 05:30 |  | Stopped (with patients) |  | 2018-11-20 05:30 | 2019-07-31 05:30 | 2018-11-30 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A multicenter, human factors validation study in cystic fibrosis patients aged 6 years and older to evaluate the user interface of TOBIÂ® Podhaler (tobramycin inhalation powder) using placebo capsules | HF Validation Study in CF_CTBM100C2419 | P6 Global Health | Vithala, Srinivas | Vithanala, Kiran Kumar | Bhabhe, Nikhil | Fazili, Subeh Mohsin | Krishnan, Kripesh | Nipa Alon | Nipa Alon | Shrivastava, Nikhil | Sama, Ashok |  |  |  |  | Pre-DRM | Shrivastava, Nikhil | Shrivastava, Nikhil | Completed | 1 Study (CTBM100C2419) transferred to Mylan. No action required | Study Locked | Study Locked | 2018-07-09 05:30 | Legacy process | Agavekar, Amit |  | Sai Krishna Mettugari | Completed | 2018-07-19 | Not Applicable |  |  |  | 2018-07-13 05:30 | 2018-07-13 05:30 | Retrospective DRM studies | [5 empty] | RaveX - Inhouse | No | -NA- | [11 empty] | NA | [5 empty] | 2 | 2 | 27 | -1 | 29 | 256 | 0 | 104 | 29 | 96 | 381 | 1 | 1 |  | Cystic fibrosis | No | Global | Terminated | Yes | [16 empty] | None of the above
CTBM100D | CTBM100D1401 | C1200229 | Phase IV | Other |  |  |  | 2013-04-25 05:30 |  |  |  | 2013-04-25 05:30 | 2018-02-20 05:30 | 2012-11-28 05:30 |  | Completed | 2018-09-11 05:30 | 2018-06-07 05:30 | 2018-09-03 05:30 | 2018-09-11 05:30 | FALSE |  |  |  | Outsourced |  | Japan CPO studyÂ¿Drug use result survey of TOBI in Cystic Fibrosis | CTBM100D1401 JPN PMS | P6 Global Health | [6 empty] | MINE KIMURA | [66 empty] | Cystic fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CTBM100G | CTBM100G2202 | C1001533 | Phase II | NCDS | CRO - EDC |  |  |  | DB Locked |  |  | 2017-02-08 05:30 |  | 2015-12-02 05:30 |  | Completed | 2019-03-28 05:30 | 2019-03-20 05:30 | 2019-07-30 05:30 | 2019-05-21 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A randomized, blinded, parallel group, multi-center dose-finding study, to assess the efficacy, safety and tolerability of different doses of tobramycin inhalation powder in patients with Non-Cystic Fibrosis Bronchiectasis and pulmonary P. aeruginosa infection | CTBM100G2202 Dose Ranging Study in BE | P6 Global Health | Vithala, Srinivas | Vithanala, Kiran Kumar | Varshney, Kapil | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Duvvuri Krishna | [15 empty] | Praveen kumar, Chakka Giri |  | Sai Krishna Mettugari | [14 empty] | FSOM - Outsourced | [13 empty] | ICON | [7 empty] | 120 | 0 |  |  | 0 |  |  |  | 600 | 8 | 0 |  | Bronchiectasis | No | Global | Completed | Yes | [16 empty] | None of the above
CTIN816A0 | CTIN816A02101 | C4004209 | Phase I | Other | CRO - EDC |  |  | 2021-03-01 05:30 | DB Conduct | Final DBL | 2023-03-27 05:30 | 2021-03-01 05:30 | 2020-10-02 05:30 | 2020-09-25 05:30 |  | Active | 2023-02-20 05:30 |  | 2023-03-27 05:30 |  | FALSE | NIBR RACE | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI |  | CTIN816A02101 FIH study for TIN816. HVs | N0 ATI - NIBR | Langlo, Francois | Palnitkar, Prachi | Palnitkar, Prachi | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Nicolas Panchaud | Nicolas Panchaud | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Acute kidney injury | No | Global | Open | Yes | [16 empty] | None of the above
CTIN816A1 | CTIN816A12201 | C4004214 | Phase II |  | Other | 2022-03-10 05:30 |  | 2022-10-24 05:30 | Study Planned | DB Go-live | 2022-03-10 05:30 |  | 2022-05-26 05:30 |  |  | Planned | 2024-08-06 05:30 |  | 2024-09-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Undecided Sourcing | NIBR - ATI |  | CTIN816A12201 PoC AKI | N0 ATI - NIBR | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Andrea Biondani | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Acute kidney injury | No | Global | Open | Yes | [16 empty] | None of the above
CTIN816B1 | CTIN816B12201 | C4013569 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-23 05:30 | Study Planned | DB Go-live | 2022-08-01 05:30 |  | 2022-04-13 05:30 |  |  | Planned | 2024-12-17 05:30 |  | 2025-01-27 05:30 |  |  | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CTIN816B12201 POC/Ph2 | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Siddavaram, Dheeraj | Meda, Malathi | Tummalapenta, Venkateswarlu | Nair, Sreesha | Michele Sauer | Michele Sauer | Das, Devashish | Das, Devashish | [6 empty] | PRAKASH PATIL, PRATIKSHA | Not Started | 4 Jan 2022: RF programmer assigned. | [6 empty] | Amit Agavekar | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 800 | 6 | 0 |  | Acute kidney injury | No | Global | Open | Yes
CTKI258A0 | CTKI258A2X01B | C1200711 | Phase IV | NCDS | [7 empty] | 2014-05-28 05:30 |  | 2014-02-05 05:30 |  | Completed |  | 2016-11-28 05:30 |  | 2016-12-21 05:30 | FALSE |  |  |  | InHouse |  | An open label, multi-center, extension study to evaluate long-term safety and tolerability of dovitinib in patients with solid tumors, who continue to receive treatment with dovitinib (TKI258) in Novartis-sponsored, single agent dovitinib studies, which have fulfilled the requirements for the primary objective, and are benefitting from continued dovitinib treatment as assessed by the investigator | CTKI258A2X01B | P6 Global Health | [6 empty] | Beth McGrain | [15 empty] | Mettugari, Sai Krishna | [50 empty] | Solid tumour; Solid tumours | No | Global | [18 empty] | None of the above
CTMT212A | CTMT212A2109 | C1001536 | Phase I | NCDS | CRO - EDC |  | 2018-09-12 05:30 | 2018-09-11 05:30 | DB Locked |  |  | 2018-09-13 05:30 | 2018-04-06 05:30 | 2018-04-19 05:30 |  | Completed | 2019-01-28 05:30 | 2018-12-02 05:30 | 2019-03-04 05:30 | 2019-03-12 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | A randomized, single center, open-label, study to investigate the relative bioavailability of 24 months shelf-life DMSO testing in healthy subjects | CTMT212A2109 PhI 24 month DMSO | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Purra, Shashikanth | Ninan, Esther |  | Christina Kim | Goyal, Rishu | [14 empty] | Agavekar, Amit |  | Sandeep Kadam | [12 empty] | This is an FSOM trial with only PK and Y1 processed via LSH. | 100 | FSOM - Outsourced | Yes | -NA- |  |  |  |  | ONC | Quintiles | Outsourced |  |  | Kanchi, Pavan kumar | Mareedu, Vasu | IQVIA | [19 empty] | Malignant melanoma | No | Local | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CTMT212A | CTMT212A2301 | C1001791 | Phase III | GSK | [7 empty] | 2010-11-22 05:30 |  |  |  | Completed |  |  |  | 2017-04-25 05:30 | FALSE |  |  |  | Outsourced |  | MEK114267, a phase III randomized, open-label study\ncomparing (GSK1120212) trametinib to chemotherapy in\nsubjects with advanced or metastatic BRAF V600E/K mutation positive melanoma | PhII METRIC TMT212A2301 | P0 Oncology (Solid Tumors all MA Onc projects) | [5 empty] | Nathalie Force-Lambert | Nathalie Force-Lambert | [66 empty] | Melanoma | No | Global | Completed | Yes | [16 empty] | None of the above
CTMT212A_MA | CTMT212A2X01B | C1001790 | Phase IV | GSK | Other |  |  |  | DB Locked |  |  | 2010-11-02 05:30 |  | 2010-11-15 05:30 |  | Completed |  | 2018-01-15 05:30 |  | 2018-04-09 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK |  | PhIV Rollover solid tumor TMT212A2X01B | P0 Oncology (Solid Tumors all MA Onc projects) | Breton, Guillaume | Suryawanshi, Sandip | Prajapati, Vaishali | Purra, Shashikanth | Ninan, Esther | Ankur Modi | Ankur Modi | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Solid tumor | No | Global | Completed | Yes | [16 empty] | None of the above
CTMT212A | CTMT212X2101 | C1001793 | Phase I | GSK | CRO - EDC |  |  | 2015-01-07 05:30 | DB Locked |  |  | 2015-01-07 05:30 |  | 2020-01-28 05:30 |  | Completed | 2020-12-31 05:30 | 2020-12-29 05:30 | 2022-02-11 05:30 | 2021-02-10 05:30 | FALSE | None | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | An Open-Label, Dose-Escalation, Phase I/II Study to Investigate the Safety, Pharmacokinetics, Pharmacodynamics and Clinical Activity of the MEK Inhibitor Trametinib in Children and Adolescents Subjects with Cancer or Plexiform Neurofibromas and Trametinib in Combination with Dabrafenib in Children and Adolescents with Cancers Harboring V600 mutation | CTMT212X2101 Ph I/II Ped in TMT and TMT+DRB | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Shevate, Pravinkumar | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Derryn Friend | Derryn Friend | [17 empty] | Sandeep Kadam | [28 empty] | Parexel | [19 empty] | Glioma; Neuroblastoma; Neurofibromatosis; Solid tumor | Yes | Global | Open | Yes | [16 empty] | None of the above
CTMT212A | CTMT212X2102 | C1001796 | Phase I | NCDS | OC RDC - Inhouse |  |  |  | DB Locked | Final DBL Achieved |  | 2016-10-20 05:30 |  | 2017-06-16 05:30 |  | Completed | 2019-08-27 05:30 | 2019-08-29 05:30 | 2019-10-11 05:30 | 2019-10-10 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A Phase I, Open-Label Study to Determine the Effect of Repeat Dosing of Trametinib on the Pharmacokinetics of a Combined Oral Contraceptive (Norethindrone plus Ethinyl Estradiol) in Female Patients with Solid Tumors | CTMT212X2102 PhI DDI OC | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Nathalie Force-Lambert | Nathalie Force-Lambert | Ahuja, Mohit | Ahuja, Mohit | [13 empty] | Manoharan, Vivek |  | Sandeep Kadam | [12 empty] | DDPASS session will be conducting soon. | 0 | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | InHouse | 2016-05-26 05:30 | 2016-05-26 05:30 | Mareedu, Vasu | Kanchi, Pavan kumar | NA | [7 empty] | 80 | 0 |  |  | 0 |  |  |  | 692 | 1 | 0 |  | Solid tumour | No | Global | Completed | Yes | [14 empty] | DBL | Chakravarthy, Meghna | None of the above | Yes
CTMT212A0 | CTMT212X2106 | C1001797 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-03-21 05:30 |  | DB Locked | Final DBL Achieved |  | 2016-06-29 05:30 | 2018-07-18 05:30 | 2016-04-18 05:30 |  | Completed | 2019-10-04 05:30 | 2019-09-24 05:30 | 2019-12-12 05:30 | 2019-12-19 05:30 | FALSE |  | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | fGSK | A phase I/II study of safety and efficacy of ribociclib (LEE011) in combination with trametinib (TMT212) in patients with metastatic or advanced solid tumors | CTMT212X2106 PhI II Mek and LEE | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Mali, Astik | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther | Nathalie Force-Lambert | Nathalie Force-Lambert | Gehlawat, Priya | Bai, Chandrakala | [13 empty] | Challa, Nandini |  | Sandeep Kadam | [12 empty] | planned from 15th april 2019 |  | OCRDC - Inhouse | Yes | -NA- |  |  |  |  | ONC | Novartis | ICON | 2016-05-27 05:30 | 2016-05-27 05:30 | Gehlawat, Priya | Shewane, Roshni | NA | [7 empty] | 140 | 0 |  |  | 0 |  |  |  | 827 | 2 | 0 |  | Colorectal cancer; Pancreatic cancer; Solid tumour | No | Global | Completed | Yes | [14 empty] | DBL | Tidke, Shyam | None of the above | Yes
CTMT212A0_MA | CTMT212XUS35T | C1201435 | Phase IV | Other | Other |  |  | 2017-11-29 05:30 | DB Locked |  |  | 2015-08-12 05:30 | 2020-10-30 05:30 |  |  | Active | 2023-09-29 05:30 |  |  |  | FALSE | Submission | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | Outsourced | fGSK | Phase 2 study of Dabrafenib and Trametinib in patients with tumors with BRAF V600E or V600K mutations (excluding melanoma and thyroid cancer) | CTMT212XUS35T Ph2 Dabrafenib&Trametinibtumorsw/BRA | P0 Oncology (Solid Tumors all MA Onc projects) | Molander, Lei Ann | Parmar, Dhirendra | Bellamkonda, Vamsi Krishna | Sonmale, Pravin | Ninan, Esther |  | Pratibha Sharma | [17 empty] | Sandeep Kadam | [28 empty] | Other | [19 empty] | Solid tumour | No | Local | Open | Yes | [16 empty] | None of the above
CTNO155A0 | CTNO155A12101 | C4012722 | Phase I |  |  |  |  | 2022-08-15 05:30 |  | Final DBL | 2023-05-02 05:30 |  | 2022-04-03 05:30 |  |  | Planned | 2023-02-28 05:30 |  | 2023-05-02 05:30 | [5 empty] | FULL Outsourced |  |  | CTNO155A12101 PKS Bioavailability | N7 Oncology - NIBR | [6 empty] | Maria del Pilar Garcia Valencia | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155A0 | CTNO155A12102 | C4012723 | Phase I |  |  |  |  | 2022-09-12 05:30 |  | Final DBL | 2023-01-31 05:30 |  | 2022-07-27 05:30 |  |  | Planned | 2022-12-30 05:30 |  | 2023-01-31 05:30 | [5 empty] | FULL Outsourced |  |  | CTNO155A12102 PKS Food Effects Study | N7 Oncology - NIBR | [6 empty] | Daniel Ivan Perez Arango | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155A0 | CTNO155A12103 | C4012724 | Phase I | Other |  |  |  | 2022-12-01 05:30 |  | Final DBL | 2023-02-28 05:30 |  | 2022-10-13 05:30 |  |  | Planned | 2023-01-31 05:30 |  | 2023-02-28 05:30 | [5 empty] | FULL Outsourced |  |  | CTNO155A12103 PKS DDI Study | N7 Oncology - NIBR | [6 empty] | Daniel Ivan Perez Arango | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155A0 | CTNO155A12104 | C4012726 | Phase I | Other |  |  |  | 2022-08-12 05:30 |  |  |  | 2022-02-04 05:30 | 2022-04-03 05:30 | 2022-01-03 05:30 |  | Active | [8 empty] | FULL Outsourced |  |  | CTNO155A12104 PKS hADME | N7 Oncology - NIBR | [5 empty] | Melissa Hackling | Melissa Hackling | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155A0 | CTNO155A12105 | C4012725 | Phase I | Other |  |  |  | 2022-08-01 05:30 |  | Final DBL | 2022-11-29 05:30 |  | 2022-06-14 05:30 |  |  | Planned | 2022-11-01 05:30 |  | 2022-11-29 05:30 | [5 empty] | FULL Outsourced |  |  | CTNO155A12105 PKS Renal Impairment | N7 Oncology - NIBR | [6 empty] | Daniel Ivan Perez Arango | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155A0 | CTNO155A12106 | C4012727 | Phase I | Other |  |  |  | 2022-07-11 05:30 |  | Final DBL | 2022-11-04 05:30 |  | 2022-05-20 05:30 |  |  | Planned | 2022-10-07 05:30 |  | 2022-11-04 05:30 | [5 empty] | FULL Outsourced |  |  | CTNO155A12106 PKS Hepatic Impairment | N7 Oncology - NIBR | [6 empty] | Daniel Ivan Perez Arango | [66 empty] | Non-small cell lung cancer | No | Global | Open | Yes
CTNO155B1 | CTNO155B12101 | C4003620 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2019-07-08 05:30 | 2019-07-30 05:30 | DB Conduct | Final DBL | 2024-12-03 05:30 | 2019-07-30 05:30 | 2019-05-14 05:30 | 2019-03-12 05:30 |  | Active | 2024-09-24 05:30 |  | 2024-12-03 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | TCO | A Phase Ib, open-label, multi-center study to characterize the safety, tolerability, and preliminary efficacy of TNO155 in combination with spartalizumab or ribociclib in selected malignancies | CTNO155B12101 combo with PDR001 and ribociclib | N7 Oncology - NIBR | Langlo, Francois | Gosika, Ajay Kumar | Kansagara, Sachinkumar | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Ajaykumar Gosika; Birgitte Lucas; KAE ISHIHARA; Victor Antona Martin | Victor Antona Martin | Sama, Ashok | SIRIPURAM, RAJSHEKHAR TIRUPATI |  |  | Jan 2022 : Sindhuja Rapaka transitioned study to Rajshekhar. |  | DRM | Shafiudeen, Rehana Banu | Saha, Saikat | Completed | 28Jan2022: DBD shared the PPC#09 IA to analyze the changes are to be done in DB. Reviewed the IA and provided the comment that it won't require any RF updates. Asked to share the latest ALS and difference report to validate that. 1Oct2021 : RF peer review completed and RF is ready to be finalized. Notified the TDM that the RF is ready to be finalized once the DTS is finalized in the DMS. 1Oct2021 : RF completed and sent for peer review. 30Sep2021 : Received the updated DTS from the TDM and the latest ALS for RF development. 24Sep2021 : Received the study DTS to review. Provided the review comments to the TDM. 31-Aug-2021 : The study is transitioned to Saha, Saikat. 31-Aug-2021 : No Pending tasks. 26May2021 : Reassigned the study from Praveen Oguri to Rehana. 05Nov2020: No Activity. 11Sep2020: No Activity. 11Aug2020: B1S003_TR and B1S004_TR forms which were included in Rule file Version 5.0 27Jul2020 : B1S003_TR, B1S004_TR forms are listed in 20jul missing form report. 16Jul2020:Rule File v5.0 is finalized in CREDI. No pending items. 06Jul2020: RF will be transitioned from Ashok to Praveen 30-Mar-2020 : B12L DTS is included in the Rule File V4.0 and finalized in CREDI. All DTS are included and no pending DTS for this study. All Finalized DTS included in RF. 4 DTS in 'B1' are pending to be finalized. Mar2020: RF transitioned from Chandrakala to Ashok 13Dec2019: Transition completed RFv2.0. Inital RF developed by Lead DBD Ashok and transitioned to Chandrakala | None | None | 2019-08-26 05:30 | Transition study | Tidke, Shyam | Varate, Rohit | Rohit Varate | Completed | 2019-09-02 | Completed | 2019-09-02 05:30 |  | Pre-requisites not met | 2019-09-03 05:30 | 2019-09-03 05:30 | Pre-requisites not met | 2019-09-18 05:30 |  |  |  |  | RaveX - Inhouse |  | -NA- | [11 empty] | NA | [5 empty] | 9 | 62 | 135 | 0 | 951 | 1198 | 0 | 299 | 41 | 303 | 1542 | 3 | 0 |  | Colorectal cancer; Esophageal cancer; Gastrointestinal stromal tumour; Non-small cell lung cancer; Squamous cell carcinoma of head and neck | No | Global | Open | Yes | [10 empty] | 2019-09-01 05:30 | [5 empty] | None of the above
CTNO155A1 | CTNO155X2101 | C3000371 | Phase I | NCDS | OC RDC - Inhouse | 2017-04-18 05:30 | 2017-04-18 05:30 | 2018-06-08 05:30 | DB Conduct | Final DBL | 2024-04-09 05:30 | 2017-05-26 05:30 | 2018-01-19 05:30 | 2016-10-28 05:30 |  | Active | 2024-02-27 05:30 |  | 2024-04-09 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | An open-label, multi-center, phase I, dose finding study of oral TNO155 in adult patients with advanced solid tumors | CTNO155X2101 Phase I Advanced Solid Tumors Study | N7 Oncology - NIBR | Langlo, Francois | Govender, Daventha | Moreau, Sandrine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Thomas Hengelage | Thomas Hengelage | Tadiparthy, Ramakanth | Shewane, Roshni |  | 2020-05-14 05:30 | Study Transitioned to Roshni Shewane on 14-May-2020. | [10 empty] | Tidke, Shyam |  | Rohit Varate | [13 empty] | 0 | OCRDC - Inhouse | No | ZK03;#ZK |  |  |  |  | ONC | Novartis | ICON | 2017-04-18 05:30 | 2017-04-18 05:30 | Shewane, Roshni | Meda, Sreelakshmi | IQVIA | [7 empty] | 239 | 0 |  |  | 0 |  |  |  | 845 | 6 | 0 |  | Colorectal cancer recurrent; Esophageal carcinoma recurrent; Gastrointestinal stromal tumour; Malignant melanoma stage IV; Metastatic neoplasm; Non-small cell lung cancer metastatic; Non-small cell lung cancer recurrent; Squamous cell carcinoma of head and neck | No | Global | Open | Yes | [16 empty] | None of the above
CTQJ230A1 | CTQJ230A12001 | C4001987 | Not Applicable | NCDS_2 | Rave EDC - Inhouse | 2019-04-09 05:30 | 2019-03-29 05:30 | 2019-04-30 05:30 | DB Locked | Final DBL Achieved |  | 2018-11-27 05:30 | 2018-10-10 05:30 | 2018-10-17 05:30 |  | Completed | 2021-07-30 05:30 | 2021-07-30 05:30 | 2021-09-10 05:30 | 2021-08-25 05:30 | FALSE | Screening study | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Multi-center cross-sectional epidemiological study to characterize the prevalence and distribution of lipoprotein(a) levels among patients with established cardiovascular disease | CTQJ230A12001 Apo(a) Screening Study | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Bhandari, Aditi | Meda, Malathi | Tummalapenta, Venkateswarlu | Nair, Sreesha | Satya Konkesa | Satya Konkesa | Kurella, Rakesh Reddy | Rana, Aamir |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 09Apr2019 |  | DRM | Kurella, Rakesh Reddy | Patnaik, Angella | Completed | 07-JUL-2020: RF up to date for all final DTS and PPPCs implemented in the study. 6FEB2020: PPC2 had Codelist value updated for LBG001_TR_1. SMT update and LSH re-built is required for this. Currently except LB all data are extracted successfully. Notified SMT programmer and LSP. 4FEB2020: Confirmation on Data Availability pending from TDM. | None | None | 2019-04-15 05:30 |  | Thirugnanasambandam, Nivetha Lakshmi | Agavekar, Amit | Amit Agavekar | Completed | 2019-04-17 | Completed | 2019-05-28 05:30 |  | Pre-requisites not met | 2019-05-28 05:30 | 2019-05-28 05:30 | Pre-requisites not met | 2019-08-21 05:30 |  |  | DDPASS is completed and all the issues are closed. | 100 | RaveX - Inhouse | Yes | -NA- | 2021-08-26 05:30 | 2021-08-30 05:30 | [9 empty] | NA | [5 empty] | 6 | 1 | 12 | 0 | 13 | 121 | 0 | 39 | 2 | 37 | 160 | 1 | 0 |  | Atherosclerosis | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-04-18 05:30 |  |  |  | DBL | R, Harini | None of the above | Yes
CTQJ230A1 | CTQJ230A12102 | C4007082 | Phase I | NCDS_2 | Other |  |  | 2022-04-06 05:30 | DB Set-Up | DB Go-live | 2022-03-08 05:30 |  | 2019-12-09 05:30 | 2022-02-15 05:30 |  | Planned | 2022-07-31 05:30 |  | 2022-09-23 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM |  | CTQJ230A12102 China PK study | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti |  | Di Gan | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Arteriosclerotic cardiovascular disease | No | Global | Open | Yes | [16 empty] | None of the above
CTQJ230A1 | CTQJ230A12202 | C4003708 | Phase II | Other |  |  |  | 2021-11-11 05:30 |  | Final DBL | 2022-10-24 05:30 | 2021-11-23 05:30 | 2021-06-21 05:30 | 2021-07-07 05:30 |  | Active | 2022-09-05 05:30 |  | 2022-10-24 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CTQJ230A12202 Hepatic Impairment | P9 Cardiovascular Renal and Metabolism (CRM) | [5 empty] | Paola Paganoni | Paola Paganoni | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Arteriosclerotic cardiovascular disease | No | Global | Open | Yes | [16 empty] | None of the above
CTQJ230A1_MA | CTQJ230A12203 | C4012672 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-25 05:30 | DB Set-Up | DB Go-live | 2022-06-10 05:30 |  | 2022-04-29 05:30 |  |  | Planned | 2026-07-14 05:30 |  | 2026-08-25 05:30 |  |  | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | Efficacy of Lp(a) lowering therapy with pelacarsen to slow down progression of calcific aortic valve stenosis | CTQJ230A12203 Pelacarsen and CAVS progression | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Rani, Anushree | Meda, Malathi | Tummalapenta, Venkateswarlu | Nair, Sreesha | Salini James | Salini James | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | [7 empty] | 900 | 8 |  |  | Aortic stenosis | No | Global | Open | Yes
CTQJ230A1 | CTQJ230A12301 | C4000419 | Phase III | NCDS_2 | Rave EDC - Inhouse |  | 2019-12-02 05:30 | 2020-01-15 05:30 | DB Conduct | DB Snapshot | 2022-02-25 05:30 | 2019-12-12 05:30 | 2019-06-11 05:30 | 2019-05-13 05:30 |  | Active | 2025-05-30 05:30 |  | 2025-07-31 05:30 |  | FALSE | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized double-blind, placebo-controlled, multicenter trial assessing the impact of lipoprotein (a) lowering with pelacarsen (TQJ230) on major cardiovascular events in patients with established cardiovascular disease | CTQJ230A12301 Ph3 Outcomes Trial Apo(a)-LRx | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Kumar, Nitin | Meda, Malathi | Tummalapenta, Venkateswarlu | Nair, Sreesha | Carrie Guindon | Carrie Guindon | Yadav, Santosh | Thomas, Ankit |  |  |  |  | DRM | Patnaik, Angella | Bairagi, Arpita | Completed | 11Aug2021 : Reassigned the study from Angella to Arpita. 1-APR-2021: RF Version 5.0 is finalized for LB Domain update. Existing SNOW#51 (RITM2420454) updated for SMT and LSH updates. 31-MAR-2021: RF Version 5.0 is finalized for PPC5 updates and SNOW#51 (RITM2420454) raised for SMT and LSH updates. 03-MAR-2021: PPC5 IA reviewed and comments provided to DBD. 29-JAN-2021: RF Version 8.0 updated for FACM domain updates. SNOW #51 raised for SMT and LSH updates. 19-JAN-2021: RF Version 7.0 finalized for PPC4 updates. SNOW#51 raised for SMT and LSH updates. 14-DEC-2020: RF Version 6.0 finalized for FAAA1L, FAAA2L, FAAA3L, FAAA4L DTS tables. SNOW#51 raised for SMT and LSH updates. 10-DEC-2020: RF updated and released for Peer Review. 09-DEC-2020: Had reviewed the DTS draft. Not intimated on the DTS finalization. Have written to TDM/DBD for RF update initiation. 03-JUL-2020: RF Version 5.0 finalized for PPC2 updates and SNOW#51 raised for SMT and LSH updates. 17-JUN-2020: RF Version 4.0 finalized for HO, FACM Domain as per DDPASS comments from SDTM Programmer. SNOW #51 raised for SMT and LSH updates. 06-FEB-2020: RF Version 2.0 finalized for DTS tables QS1L and LBL. SNOW#51 raised for SMT and LSH updates. 03-FEB-2020: No outstanding form issue. Added LBL and QS1L table for DTS. Sent for Peer review. 31-JAN-2020: Field format issue identified during LSH set-up for SSG001 (SSTAT). To be fixed via PPC. 27-JAN-2020: RF Version 1.0 finalized. SNOW#05 raised for SMT creation and LSH set-up. 21JAN2020: Rule file created for all CRF domains and released for Peer Review. 7-JAN-2020: SDTM annotations for 10/32 forms received on 2nd Jan. Work in progress for these. 27-DEC-2019: 32 Global forms Rule file sent for Peer Review. 37 study specific forms SDTM annotations pending. 17-DEC-2019: Not completed yet. 10-DEC-2019: Working on the first draft of Rule File. | None | None | 2020-01-27 05:30 | SDTM annotations delayed | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Amit Agavekar | Completed | 2020-02-06 | Completed | 2020-02-06 05:30 | 29 domains - AE,APMH,CE,CM,DD,DM,DS,DV,EC,EG,FAAA,FAAE,FACE,FACM,FACM1(blinded),FAMH,HO,IE,LB,MH,ODM,PR,QS,SS,SU,SV,VS,ZE,ZJ | Pre-requisites not met | 2020-02-06 05:30 | 2020-02-06 05:30 | Pre-requisites not met | 2020-02-26 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 8 | 28 | 81 | 0 | 293 | 989 | 0 | 275 | 38 | 296 | 1323 | 6 | 0 |  | Atherosclerosis | No | Global | Open | Yes | [10 empty] | 2020-02-06 05:30 |  |  |  | DMC/Dry-Run/Snapshot | Nidamanuru, Kalyan Kumar | GDD annual target | Yes
CTQJ230A1 | CTQJ230A12302 | C4010387 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-05-27 05:30 |  | 2022-07-15 05:30 | DB Set-Up | DB Go-live | 2022-06-06 05:30 |  | 2022-02-19 05:30 |  |  | Planned | 2024-07-26 05:30 |  | 2024-09-05 05:30 |  |  | DCN Priority | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM | A randomized, double-blind, placebo-controlled, multicenter trial assessing the reduction of the rate of apheresis after treatment with TQJ230 compared to placebo in patients undergoing apheresis for isolated LP(a) in Germany | CTQJ230A12302 Apheresis trial | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Sridhar, Shashikala | Meda, Malathi | Tummalapenta, Venkateswarlu | Nair, Sreesha | Satya Konkesa | Satya Konkesa | Ennam, Sneha Laxminarayana | Ennam, Sneha Laxminarayana | [6 empty] | Saha, Saikat | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 50 | [7 empty] | 800 | 8 |  |  | Cardiovascular event prophylaxis | No | Global | Open | Yes
CTRI476B | CTRI476B1301E1 | C1001538 | Phase III | NOVDD | Paper |  |  |  | DB Locked |  |  | 2010-01-05 05:30 |  | 2009-06-18 05:30 |  | Completed | 2019-09-30 05:30 |  |  |  | FALSE |  | Rajanikanth Kolla | Cluster B (Haem,CRM,NS) | Outsourced | DF NS | A Extension Trial of multicenter, randomized, double-blind, placebo controlled, parallel-group study in children 4-14 years old with inadequately controlled partial seizures to investigate efficacy, safety and tolerability of TRI476 (oxcarbazepine) as adjunctive therapy. | JPN_Phase II/III EXT study_CTRI476B1301E1 | P6 Global Health |  | Tsukazaki, Mayuka | Okuzono, Seigou | Okuzono, Seigou | Nair, Sreesha | REIKO TAKAHASHI | REIKO TAKAHASHI | Tripathi, Shakuntala | R, Ankit | [15 empty] | Amit Agavekar | [28 empty] | Other |  | AP21 | [17 empty] | Epilepsy | No | Global | Terminated | Yes | [16 empty] | None of the above
CUFJ776A0 | CUFJ776A02101 | C4007085 | Phase I |  |  |  |  | 2024-07-01 05:30 |  | Final DBL | 2025-07-18 05:30 |  | 2024-01-31 05:30 |  |  | Planned | 2025-06-06 05:30 |  | 2025-07-18 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CUFJ776A02101 FIH | N0 ATI - NIBR | [6 empty] | Louise Mooney | [66 empty] | Acute kidney injury | No | Global | Open | Yes
CUNR844A | CUNR844A2101 | C4007086 | Phase I | Other | CRO - EDC |  |  | 2020-09-28 05:30 | DB Conduct | Final DBL | 2022-01-03 05:30 | 2020-09-28 05:30 | 2020-05-07 05:30 | 2020-05-14 05:30 |  | Active | 2021-06-09 05:30 | 2021-03-22 05:30 | 2022-01-03 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - OPHTHA | A randomized, investigator and participant-masked, placebo-controlled study to assess the safety, tolerability, and pharmacokinetics of single and multiple ascending doses of topical ocular UNR844 tosylate (eye drops) to healthy participants | CUNR844A2101 SADMAD Phase I US only | P5 Ophthalmology | Langlo, Francois | Soni, Kushal | Soni, Kushal | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [17 empty] | Rohit Varate | [28 empty] | Parexel | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Presbyopia | No | Global | Open | Yes | [16 empty] | None of the above
CUNR844A | CUNR844A2202 | C3001691 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2021-04-12 05:30 | 2021-04-14 05:30 | 2021-06-30 05:30 | DB Conduct | Interim DBL | 2022-08-10 05:30 | 2021-06-30 05:30 | 2020-10-30 05:30 | 2020-11-09 05:30 | 2021-03-23 05:30 | Active | 2023-03-20 05:30 |  | 2023-04-10 05:30 |  | FALSE | Submission | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | A randomized, placebo-controlled, double-masked, multi-center, dose-ranging study to evaluate the safety, and efficacy of UNR844 in subjects with presbyopia | CUNR844A2202_Phase 2b_Tosylate | P5 Ophthalmology | Navarro, Christelle | Reddyvari, Hima Bindu | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | James Carten | James Carten | Ganesan, Dhanalakshmi | Palande, Sujit | In Progress |  |  |  | DRM | R, Pratheeksha K | R, Pratheeksha K | Completed | 12Aug2021: QS8L DTS under review. 09Aug2021: QS8L DTS was not sent for review. Have asked the TDM to share the DTS for review. Once reviewed will be adding it in the RF. 09Aug2021 : QS8L DTS reflecting in report 05Aug2021. 13-Jul-2021: The ZX2L DTS has been added in the Rule File, SNOW Ticket has been raised and LSP has been notified 09-Jul-2021: The ZX2L DTS was not sent to me. Downloaded it from the CREDI. The DTS is under review. Once review is done will be adding it in the RF. 06Jul2021 : ZX2L reflecting in missing form DTS report 04Jun2021: ZX1L, QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, LB1L DTS's were added to RF and SNOW51 raised. 25May2021: DTS's downloaded from CREDI and started working on Rule File updates. ZX1L, QS1L, QS2L, QS3L, QS4L, QS5L, QS6L, QS7L, LB1L flagged in missing forms/DTS report 19may2021. DBD not shared the DTSs. 16Apr2021 : Rule File has been finalized and SNOW05 ticket has been raised on 16-Apr-2021 for LSH Set-up. 01Feb2021: RF developer Assigned. | None | QS8L | 2021-04-16 05:30 |  | Sultana, Salma | Sundar, N Sushant | Sai Krishna Mettugari | Completed | 2021-04-28 | Completed | 2021-05-16 05:30 |  |  | 2021-05-16 05:30 | 2021-05-16 05:30 |  | 2021-05-16 05:30 |  |  |  |  | RaveX - Inhouse | Yes | [12 empty] | NA | [5 empty] | 2 | 16 | 40 | 0 | 126 | 474 | 0 | 148 | 38 | 126 | 638 | 4 | 0 |  | Presbyopia | Yes | Global | Open | Yes | [10 empty] | 2021-05-13 05:30 | [5 empty] | None of the above
CUNR844A | CUNR844A2203 | C4001070 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-05-13 05:30 | 2019-04-05 05:30 | 2019-04-25 05:30 | DB Locked | Final DBL Achieved |  | 2019-04-26 05:30 | 2018-11-30 05:30 | 2018-12-12 05:30 |  | Completed | 2019-12-16 05:30 | 2019-12-16 05:30 | 2020-02-04 05:30 | 2020-01-17 05:30 | FALSE |  | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA | Phase II study UNR844 1.5% in subjects with presbyopia | CUNR844A2203 1.5% in subjects with presbyopia | P5 Ophthalmology | Ball, Michael | Dahiya, Sunil | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | James Carten | James Carten | Rao, S Shashikanth | Rao, S Shashikanth |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 13May2019 |  | DRM | Rao, S Shashikanth | Choppadandi, Kranthikumar | Completed | 06-Jul-2020: No pending issues. Study Locked 05Feb2020 : Study Locked 29th Nov 19 - (Shashi) No pending domains items to be included in RF. | Study Locked | Study Locked | 2019-04-15 05:30 | Legacy Process | Mettugari, Sai Krishna | Kadam, Sandeep | Sai Krishna Mettugari | Completed | 2019-05-22 | Completed | 2019-05-23 05:30 | Study Locked | Pre-requisites not met | 2019-05-23 05:30 | 2019-05-23 05:30 | Pre-requisites not met | 2019-08-30 05:30 |  |  |  |  | RaveX - Inhouse | Yes | DV;#Y1;#Y5;#YD | 2020-01-20 05:30 | 2020-01-21 05:30 | [9 empty] | NA | [5 empty] | 3 | 8 | 33 | 0 | 5 | 323 | 0 | 120 | 32 | 122 | 477 | 3 | 0 |  | Presbyopia | No | Global | Open | Yes | [10 empty] | 2019-05-21 05:30 |  |  |  |  | Sundar, N Sushant | GDD annual target | Yes
CUNR844A | CUNR844A2301 | C3001690 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-11-08 05:30 | Study Planned | DB Go-live | 2022-07-15 05:30 |  | 2022-06-28 05:30 |  |  | Planned | 2025-02-03 05:30 |  | 2024-01-22 05:30 |  | FALSE | NA | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CUNR844A2301 Phase 3 Presbyopia | P5 Ophthalmology | Navarro, Christelle | Dahiya, Sunil | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh | James Teague | James Teague | [17 empty] | Sai Krishna Mettugari | [36 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Presbyopia | No | Global | Open | Yes | [16 empty] | None of the above
CUNR844A | CUNR844A2302 | C3001693 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-02-28 05:30 | Study Planned | DB Go-live | 2022-11-18 05:30 |  | 2022-06-24 05:30 |  |  | Planned | 2025-03-03 05:30 |  | 2025-04-14 05:30 |  | FALSE | NA | Rajanikanth Kolla | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | DF OPHTHA |  | CUNR844A2302 Phase 3 Presbyopia | P5 Ophthalmology | Navarro, Christelle | Dahiya, Sunil | Dahiya, Sunil | Datta, Debtanu | Krishnan, Kripesh |  | Valda Murphy | [17 empty] | Sai Krishna Mettugari | [36 empty] | 60 | 0 |  |  | 0 |  |  |  | 900 | 8 | 0 |  | Presbyopia | No | Global | Open | Yes | [16 empty] | None of the above
CURJ984A | CURJ984A1401 | C3000244 | Phase IV | Other |  |  |  | 2019-06-24 05:30 |  |  |  | 2014-09-01 05:30 |  | 2014-05-23 05:30 |  | Completed | 2019-04-30 05:30 | 2018-02-28 05:30 | 2019-05-31 05:30 | 2019-05-30 05:30 | FALSE |  |  |  | Outsourced |  | Azarga Special use result study for long-term administration | CURJ984A1401 JPN PMS | P6 Global Health | [6 empty] | YUKIE YOSHIZAWA | [66 empty] | Glaucoma | No | Global | Completed | Yes | [16 empty] | None of the above
CVAL489K | CVAL489K2306 | C1001542 | Phase III | NOVDD | [7 empty] | 2012-11-08 05:30 |  | 2012-06-18 05:30 |  | Completed |  | 2017-01-24 05:30 |  | 2017-03-07 05:30 | FALSE |  |  |  | Outsourced |  | A 6 week, randomized, multicenter, double-blind, double-dummy study to evaluate the dose response of valsartan on blood pressure reduction in children 1-5 years old with hypertension, with or without chronic kidney disease, followed by a 20 week open-label titration phase | Pediatric (1-5 yrs)_VAL489K2306 | P6 Global Health | [5 empty] | Michele Valentin | Jeroze Farhad Engineer | [66 empty] | Hypertension | No | Global | Open | Yes | [16 empty] | None of the above
CVAL489O_MA | CVAL489O2401 | C1200292 | Phase IV | NCDS | CRO - EDC |  |  | 2018-04-16 05:30 | DB Locked |  |  | 2018-03-23 05:30 |  | 2018-01-09 05:30 |  | Completed | 2019-10-03 05:30 | 2019-10-10 05:30 | 2020-02-13 05:30 | 2019-12-06 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A multicenter, randomized, non-interventional, parallel design, 4-week duration study in adults to evaluate the number and frequency of out-of-office, blood pressure self-measurements to accurately diagnose the presence or absence of hypertension | CVAL489O2401 multice | P6 Global Health | Vithala, Srinivas | Sadhu, Soumen Kumar | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Kanan Jhala | [17 empty] | Sai Krishna Mettugari | [28 empty] | Parexel | [19 empty] | Hypertension | No | Global | Completed | Yes | [16 empty] | None of the above
CVAY736A | CVAY736A2101 | C3001744 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2018-10-30 05:30 | 2018-12-19 05:30 | DB Conduct | Interim DBL | 2022-07-15 05:30 | 2018-12-19 05:30 | 2018-05-22 05:30 | 2018-05-25 05:30 |  | Active | 2024-05-07 05:30 |  | 2024-07-09 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A randomized, open label, multiple dose, parallel group study to assess the safety and pharmacokinetic comparability of two VAY736 drug products in patients with rheumatoid arthritis | CVAY736A2101 PK study to compare 2 cell lines RA | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Tadakamalla, Pranitha | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Michaela Madlova; Sarka Mala | Sarka Mala | Bonam, Rajesh Babu | TEMBHARE, HITESH | Completed | 2019-12-12 05:30 |  |  | DRM (DIAL) | Sama, Ashok | Kuttoboina, Sujan Kumar | Completed | 06Jul2020: Rule file V5.0 is the latest. Not modified anything from 23Sep2019. Study will be transitioned from Ashok to Sujan. Feb2020 : Transitioned study from Chandrakala to Ashok. 23Sep2019:Rule file V5.0 finalized in CREDI 24Dec2019: Transition completed Initial versions created by Bonam, Rajesh Babu and then transitioned to Chandraka | None | None | 2018-12-17 05:30 | Transition Study and Legacy process | Varate, Rohit | Sahu, Ahallad | Rohit Varate | Completed | 2018-12-22 | Completed | 2019-05-23 05:30 | Rajesh(28Nov2019):Rule file is under final status with no domains are exluded. |  | 2018-12-21 05:30 | 2018-12-21 05:30 | Study Transition | 2019-08-14 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5 | [11 empty] | NA | [5 empty] | 12 | 26 | 45 | 0 | 141 | 620 | 0 | 180 | 33 | 144 | 797 | 3 | 0 |  | Rheumatoid arthritis | No | Global | Open | Yes | [10 empty] | 2019-05-23 05:30 |  |  |  | Interim-Analysis | Sundar, N Sushant | None of the above | No
CVAY736A | CVAY736A2103 | C4008180 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2022-03-04 05:30 |  | 2022-04-06 05:30 | DB Set-Up | DB Go-live | 2022-03-04 05:30 |  | 2021-09-10 05:30 | 2021-09-24 05:30 |  | Planned | 2025-10-05 05:30 |  | 2025-11-19 05:30 |  | FALSE | Biopsy Profiling | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | An open-label, non-randomized, biopsy-based mechanistic study on pharmacokinetics, pharmacodynamics, safety and tolerability of ianalumab in patients with SjÃ¶gren's syndrome | CVAY736A2103 PSS biopsy profiling study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Kulkarni, Aravind Rao | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Noemi Giglioli | Noemi Giglioli | Das, Devashish | Das, Devashish | Not Started |  | 06Oct2020 : RF developer assigned when go live as 23Nov2020. 21Aug2020 : DBD assigned with planned golive date as 23Nov2020. 21Aug2020 : As per the email from TDM Aravind Kulkarni for study DBD assignment the below timelines shared. FPFV- 01-DEC-2020, RIS- Since this study is from NIBR portfolio, we focus on FPFV, DB Live Date- 23-Nov-2020 |  | DRM | Oguri, Praveen | R, Pratheeksha K | Not Started | 29Nov2021: The ALS review is is over and comments have been shared with the DBD. 11Aug2021: As confirmed by the TDM, the study go-live will be on 07-Dec2021. 26-Apr-2021: Study protocol is not yet finalized and new proposed DB Go-Live is in Sep 2021. 26-Apr-2021: Sent email to Study DBD Susmitha to update on study build status and updated Go-Live date. 26Apr2021: Reassigned from Praveen to Pratheeksha. No RF activities done so far.. 02-Dec-2020: I will send study status request email after 15-Dec-2020 06Oct2020: RF developer (Praveen O) Assigned with planned Golive as 23Nov2020. | [6 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Sjogren's syndrome | No | Global | Open | Yes | [16 empty] | None of the above
CVAY736A | CVAY736A2201 | C1001544 | Phase II | NCDS | OC RDC - Inhouse |  | 2017-03-14 05:30 |  | DB Locked | Final DBL Achieved |  | 2017-06-27 05:30 |  | 2016-10-04 05:30 |  | Active | 2021-09-30 05:30 | 2021-09-23 05:30 | 2021-11-10 05:30 | 2021-10-27 05:30 | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo controlled multicenter phase 2 dose-ranging study to assess the safety and efficacy of multiple VAY736 doses administered subcutaneously in patients with moderate to severe primary SjogrenÂ¿s Syndrome. | Ph2 Dose Ranging Study_VAY736A2201 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Pawaskar, Madhura | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther | Yajuvinder Gulati | Yajuvinder Gulati | Narasetty, Indumathi | Meda, Sreelakshmi | [13 empty] | Tidke, Shyam |  | Sandeep Kadam | [13 empty] | 100 | OCRDC - Inhouse | Yes | LB;#Y1;#Y5;#YR;#ZK;#ZK03 |  |  |  |  | Pharma | Novartis | ICON | 2017-03-14 05:30 | 2017-03-14 05:30 | Meda, Sreelakshmi | Iliyas, Mohamed | NA | [7 empty] | 174 | 0 |  |  | 0 |  |  |  | 702 | 3 | 0 |  | Sjogren's syndrome | Yes | Global | Open | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CVAY736A | CVAY736A2301 | C4003152 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-05-31 05:30 |  | 2022-07-29 05:30 | DB Set-Up | DB Go-live | 2022-05-20 05:30 |  | 2021-12-01 05:30 | 2022-02-14 05:30 |  | Planned | 2027-08-19 05:30 |  | 2027-10-28 05:30 |  | FALSE | Pivotal and time critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo controlled, 2-arm multicenter phase 3 study to assess the efficacy and safety of ianalumab in patients with active SjÃ¶grenâs syndrome. | CVAY736A2301 Ph3 in Sjogrens | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Pawaskar, Madhura | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther | Deepak Narayanswamy; Janice Woznicki | Deepak Narayanswamy | Sinha, Deepakshi | Sinha, Deepakshi | Completed | 2021-05-18 05:30 | 18May2021: Study transitioned from Susmita to Madhu. 29Apr2021: Protocol is not yet finalized. Expected protocol finalization in June and go-live would be in September 2021. No work is started yet for this study. As confirmed by PDM, FPFV date finalization(may 2nd week) is ongoing and will be followed up and updated soon once finalized upon. Primary end point of the trial needs a revision and this has impacted overall timelines. FPFV not before 22Feb2022 as per Kapil and Unni. Initial golive 31May2021. Study transitioned to Deepakshi S on 13-Sept-2021. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Not Started | 26May2021: RF developer assigned. | [6 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Sjogren's syndrome | Yes | Global | Open | Yes | [16 empty] | None of the above
CVAY736A | CVAY736A2301E1 | C4003161 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2023-06-15 05:30 | Study Planned | DB Go-live | 2023-05-01 05:30 |  | 2022-12-16 05:30 |  |  | Planned | 2027-11-05 05:30 |  | 2028-01-14 05:30 |  |  | TBC | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID |  | CVAY736A2301E1 Ph3 Sjogrens Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Varshney, Kapil | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther |  | Fernando Jos�� Magalhaes de Carvalho Mota | [17 empty] | Sandeep Kadam | [36 empty] | 40 | [7 empty] | 450 | 8 |  |  | Sjogren's syndrome | No | Global | Open | Yes
CVAY736A | CVAY736A2302 | C4013878 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-07-29 05:30 | DB Set-Up | DB Go-live | 2022-06-24 05:30 |  | 2022-01-25 05:30 | 2022-02-15 05:30 |  | Planned | 2026-08-31 05:30 |  | 2026-10-12 05:30 |  |  | Pivotal and Time critical | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, placebo controlled, 3-arm multicenter phase 3 study to assess the efficacy and safety of ianalumab in patients with active SjÃ¶grenâs syndrome (NEPTUNUS-2) | CVAY736A2302 Phase 3 in Sjogrens | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Pawaskar, Madhura | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther | Deepak Narayanswamy; Janice Woznicki | Deepak Narayanswamy | [17 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | [7 empty] | 800 | 8 |  |  | Sjogren's syndrome | No | Global | Open | Yes
CVAY736B | CVAY736B2201 | C1001803 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2017-11-22 05:30 | 2020-05-29 05:30 | DB Conduct | DB Snapshot | 2022-03-15 05:30 | 2018-02-15 05:30 |  | 2017-06-29 05:30 |  | Active | 2025-12-25 05:30 |  | 2026-02-05 05:30 |  | FALSE | - IA results under analysis, to be re-checked and updated soon | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | Two part randomized, double-blind, placebo-controlled multicenter dose ranging and confirmatory study to assess the safety and efficacy of VAY736 in autoimmune hepatitis patients with incomplete response to or intolerance of standard therapy (AMBER) | Ph2 Dose Ranging AIH_CVAY736B2201 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Sampangi, Sridevi | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther | Tara D'Elia | Tara D'Elia | Munukutla, Valli | Rao, S Shashikanth | Completed | 2021-06-22 05:30 | Oct 2021 : Pallabi transitioned study to Shashi 22Jun2021 : Transition from Valli Munukutla to Goswami, Pallabi PPC-15 is ongoing. Moved all the changes to UAT on 7-Jun-2021 Transition from Nagendra Vedula to Valli Munukutla |  | DRM (DIAL) | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 13-JUL-21: PPC15 has been completed, SMT files have to update and no impact on RF. SNOW 51 request RITM2769117 has been created for to rebuild DV domain. 07-JUL-20: As of today, no pending forms and no pending DTS 05-JUN-20: No pending forms or pending DTS as on 05-JUN-20. RF has been finalized and SNOW 51 request created on 05-JUN-20 22-MAY-20: As part of PPC, new local lab form LBS002 and FMHI001_TR form: New field RESCDFA_8 has been added in Rule file and sent for peer review. 06-MAY-20: As part DRM DIAL, new EPOCH and Timepoints have been created and attached to the SNOW request. 04-May-20: Rule file has been finalized and SNOW request has been created 24-APR-20: Rule file updated as per clinical requirement and sent for peer review (Ashok). Change: Added new domain SS for "Subject Status" 13MAR2020: All pending issues has been corrected in Rule file and finalized. SR51 request has been created. 10Mar2020: LB1L issue identified by LSP. Need to check 02MAR2020: Rule file has been finalized and LSH setup update is ongoing. All forms and finalized DTSs in RF 13Feb2020 : SUjan to followup with DBD on pending LBG001_TR form as per the report. 20-JAN-20: LBG001_TR form is missing and will be added in the next version of the Rule file NVE:29 Nov 19: No Pending domains/updates expected. All domains(including 3rd party domains) are final. No DTS pending. LBL is added in Rule file and production is transferred | None | None | 2018-03-04 05:30 | Transition Study and Legacy process | Praveen kumar, Chakka Giri | Varate, Rohit | Sandeep Kadam | Completed | 2018-04-02 | Completed | 2020-05-13 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-04-01 05:30 | 2018-04-01 05:30 | Study Transition | 2019-11-07 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | DV;#LB;#Y1;#Y5;#ZK;#ZK03 | [11 empty] | NA | [5 empty] | 16 | 29 | 64 | 0 | 264 | 855 | 0 | 255 | 35 | 189 | 1079 | 7 | 0 |  | Autoimmune hepatitis | Yes | Global | Open | Yes | [10 empty] | 2020-05-05 05:30 | [5 empty] | None of the above | Yes
CVAY736I1 | CVAY736I12301 | C4015721 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  |  | DB Set-Up | Final DBL | 2027-11-18 05:30 |  | 2022-06-24 05:30 |  |  | Planned |  |  | 2027-11-18 05:30 |  |  | To be confirmed | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology |  | CVAY736I12301 Ph3 1L ITP | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shedge, Vijay | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Raquel Merino Herranz | Raquel Merino Herranz | [17 empty] | Amit Agavekar | [36 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Immune thrombocytopenic purpura | No | Global | Open | Yes
CVAY736J1 | CVAY736J12101 | C4007496 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-06-15 05:30 | 2021-08-11 05:30 | 2022-01-25 05:30 | DB Conduct | Final DBL | 2025-10-10 05:30 | 2022-01-24 05:30 | 2021-05-05 05:30 | 2021-01-26 05:30 |  | Active | 2025-09-01 05:30 |  | 2025-10-10 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase Ib, multi-center, open-label dose escalation and expansion platform study of VAY736 and select antineoplastic agents in patients with non-Hodgkin Lymphoma (NHL) | CVAY736J12101 TCO Phase Ib study | N7 Oncology - NIBR | Langlo, Francois | Muthappa, Helen | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Nicole Kundamal | Nicole Kundamal | Bonam, Rajesh Babu | Rao, S Shashikanth | Completed | 2021-09-30 05:30 | 30Apr2021 : Golive moved to 20Jun2021. Forms released for UAT, Global edit check programming ongoing. SSD final. Share documents with RF developer. Initial golive date 15Jun2020. Study Transitioned to Rao, S Shashikanth |  | DRM | Sama, Ashok | Bai, Chandrakala | Completed | 24Aug2021: Attached updated RF v2.0 to existing ticket which was in pending RITM2869126 as per LSP confirmation. 12Aug2021: RF v1.0 is finalized for Initial DB set-up. 09Aug2021: RF is ready for finalization, awaiting Go-Live notification scheduled for 10-Aug-2021. 02Jul2021: RF development initiated. 27May2021: Specification review in progress for RF development intiation. 26Mar2020 : RF Developer assigned as per initial golive as 15Jun2020. | None | None | 2021-08-12 05:30 |  | Ramayanam, Vinay | Ramayanam, Vinay | Rohit Varate | Completed | 2021-08-24 | Completed | 2021-08-27 05:30 |  |  | 2021-08-27 05:30 | 2021-08-27 05:30 |  | 2021-09-08 05:30 |  |  |  |  | RaveX - Inhouse | [13 empty] | IQVIA | [5 empty] | 2 | 98 | 123 | 0 | 803 | 1224 | 0 | 281 | 42 | 524 | 1790 | 1 | 0 |  | Diffuse large B-cell lymphoma; Non-Hodgkin's lymphoma | No | Global | Open | Yes | [10 empty] | 2021-08-26 05:30 | [5 empty] | None of the above
CVAY736K1 | CVAY736K12301 | C4009683 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2021-04-30 05:30 |  | 2022-08-01 05:30 | DB Set-Up | DB Go-live | 2022-05-19 05:30 |  | 2021-08-18 05:30 | 2021-12-21 05:30 |  | Planned | 2031-04-03 05:30 |  | 2029-10-03 05:30 |  | FALSE | DCN Priority | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double-blind, parallel group, placebo-controlled, multicenter phase 3 trial to evaluate the efficacy, safety and tolerability of ianalumab on top of standard-of-care therapy in patients with active lupus | CVAY736K12301 Lupus Nephritis Ph 3 | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Amrutkar, Pushpendra Sudhakar | Varshney, Kapil | Sarkhel, Biswadip | Ninan, Esther | Pranjali Gaunker | Janice Woznicki | Dadapogu, Jesica Priyadarshini | Dadapogu, Jesica Priyadarshini | Not Started |  | 28Apr2021 : Basis revised FPFV (03Mar2022), updated go live date (04Feb2022)in iBoW. Please note timelines are still being discussed at CTT level and we will keep you posted. Initial go live as 30Apr2021 when RF developer assigned on 01Feb2021. |  | DRM | Bairagi, Arpita | Bairagi, Arpita | Not Started | 01Feb2021: RF Developer assigned. | [6 empty] | Sandeep Kadam | [28 empty] | NA | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 800 | 8 | 0 |  | Lupus nephritis | Yes | Global | Open | Yes | [16 empty] | None of the above
CVAY736O1 | CVAY736O12301 | C4015723 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-22 05:30 | DB Set-Up | Final DBL | 2025-02-20 05:30 |  | 2022-05-05 05:30 |  |  | Planned | 2025-01-09 05:30 |  | 2025-02-20 05:30 |  |  | To be confirmed | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology |  | CVAY736O12301 Ph3 2L wAIHA | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shedge, Vijay | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Urs Albers | Urs Albers | [17 empty] | Amit Agavekar | [36 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Anaemia | No | Global | Open | Yes
CVAY736Q1 | CVAY736Q12301 | C4015993 | Phase III | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-09-22 05:30 | DB Set-Up | Final DBL | 2028-01-11 05:30 |  | 2022-05-05 05:30 |  |  | Planned | 2027-11-30 05:30 |  | 2028-01-11 05:30 |  |  | To be confirmed | Moharana, Dhaneswar | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Hematology |  | CVAY736Q12301 Ph3 2L ITP | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Shedge, Vijay | Shedge, Vijay | Fazili, Subeh Mohsin | Krishnan, Kripesh | Lambert Asuagbor | Lambert Besemtabe Asuagbor | [17 empty] | Amit Agavekar | [36 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Immune thrombocytopenic purpura | No | Global | Open | Yes
CVAY736C1 | CVAY736X2101 | C1200244 | Phase I | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-12-20 05:30 |  | 2010-09-22 05:30 |  | Completed | 2018-02-01 05:30 | 2018-01-22 05:30 | 2018-03-05 05:30 | 2018-04-10 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ATI | A dose escalation study to assess the safety, tolerability, pharmacokinetics and pharmacodynamics of VAY736 in rheumatoid arthritis patients | CVAY736X2101 | N0 ATI - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti |  | Louise Mooney | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Rheumatoid arthritis | No | Global | Completed | Yes | [16 empty] | None of the above
CVAY736A0 | CVAY736X2201 | C1200702 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2014-05-23 05:30 |  | 2013-08-07 05:30 |  | Completed | 2018-02-15 05:30 | 2018-02-07 05:30 | 2018-04-04 05:30 | 2018-04-04 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ID | A single dose, double-blind, placebo-controlled, parallel study to assess the pharmacodynamics, pharmacokinetics and safety and tolerability of VAY736 in patients with primary SjÃ¶gren's syndrome | CVAY736X2201 | N0 ATI - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Claudia Simonett | Claudia Simonett | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Sjogren's syndrome | No | Global | Completed | Yes | [16 empty] | None of the above
CVAY736A0 | CVAY736X2202 | C1200535 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-12-20 05:30 |  | 2013-08-09 05:30 |  | Completed | 2018-10-01 05:30 | 2018-09-13 05:30 | 2018-11-19 05:30 | 2018-11-19 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ID | A randomized, partially blind, placebo-controlled,proof-of-concept study to assess the effect of a single infusion of VAY736 on disease activity as measured by brain MRI scans in patients with relapsing-remitting multiple sclerosis | CVAY736X2202 POC in MS | N0 ATI - NIBR | Langlo, Francois | Soni, Kushal | Soni, Kushal | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Frederique Chaperon | Fr��d��rique Chaperon | [15 empty] | Girvasiya, Shaili |  | Rohit Varate | [14 empty] | FSOM - Outsourced | Yes | ZK;#ZK03 | [11 empty] | CMED | [19 empty] | Relapsing-remitting multiple sclerosis | No | Global | Completed | Yes | [16 empty] | None of the above
CVAY736D1 | CVAY736X2203 | C1200492 | Phase II | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2013-12-18 05:30 |  | 2013-07-25 05:30 |  | Completed | 2019-09-25 05:30 | 2019-09-25 05:30 | 2019-11-26 05:30 | 2019-12-02 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | A randomized, partial-blind, placebo-controlled trial evaluating the efficacy, safety, pharmacokinetics and pharmacodynamics of VAY736 in the treatment of patients with pemphigus vulgaris. | CVAY736X2203 PIE PoC in Pemphigus Vulgaris | N0 ATI - NIBR | Langlo, Francois | Chitre, Vrushali | Chitre, Vrushali | Tiwari, Ritesh | Gupta Bhaya, Soumya Kanti | Noemi Giglioli | Noemi Giglioli | [17 empty] | Rohit Varate | [28 empty] | CMED | [19 empty] | Pemphigus vulgaris | No | Global | Completed | Yes | [16 empty] | None of the above
CVAY736G1 | CVAY736X2207 | C1200365 | Phase II | NCDS | CRO - EDC |  |  | 2018-04-18 05:30 | DB Conduct | Final DBL | 2022-11-02 05:30 | 2017-12-20 05:30 |  | 2017-07-12 05:30 |  | Active | 2022-02-16 05:30 |  | 2022-11-02 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - RESP | A subject-, investigator-, and sponsor-blinded, randomized, placebo-controlled, multicenter study to investigate efficacy, safety, and tolerability of VAY736 in patients with idiopathic fibrosis | CVAY736X2207 Idiopathic Pulmonary Fibrosis PoC | N5 DAx - NIBR | Langlo, Francois | Gundu, Ananth Reddy | Soni, Kushal | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Diego Albrecht; Payal Shah | Diego Albrecht | [15 empty] | Varate, Rohit |  | Rohit Varate | [14 empty] | FSOM - Outsourced | [13 empty] | IQVIA | [19 empty] | Idiopathic pulmonary fibrosis | No | Global | Open | Yes | [16 empty] | None of the above
CVAY736F1 | CVAY736X2208 | C1200707 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-11-13 05:30 |  | DB Conduct | DB Snapshot | 2022-02-28 05:30 | 2018-12-19 05:30 |  | 2018-07-02 05:30 |  | Active | 2024-10-03 05:30 |  | 2024-12-30 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A multiple dose, double-blind, placebo-controlled, parallel cohort study to assess the pharmacodynamics, pharmacokinetics and safety and tolerability of VAY736 and of CFZ533 in patients with systemic lupus erythematosus (SLE) | CVAY736X2208 PIE PoC in SLE with VAY736 and CFZ533 | N0 ATI - NIBR | Langlo, Francois | Donta, Alekhya Balaiah | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Carole Sips; Giulio Loforese | Carole Sips | Ahuja, Mohit | Ahuja, Mohit |  |  |  |  | DRM (DIAL) | Sama, Ashok | Shrivastava, Nikhil | Completed | 25-Jun2021: RF V18.0 finalized WRT PPC#12 for the addition of 3 new Lab CRF forms. SNOW-51 raised and LSP has been notified. 22-Jun-2021: RF V17.1 updated and shared for peer review WRT PPC#12. Peer review ongoing. 29-Apr-2021: RF V17.0 updated and finalized WRT updating the test code for 'Joint Count’ form. SNOW-51 raised and LSP is notified. 15-Mar-2021: SNOW-51 raised to rebuild AE and MH domains as per PPC#10. LSP is notified. No impact to Rule File. 28-Jan-2021: QS6L DTS included in the Rule File V16.0 and finalized in CREDI. SNOW-51 is raised and LSP is notified. 12-Jan-2021: SNOW-51 was raised on 02nd Nov 2020 to rebuild DV domain as per PPC#09. LSP and SMT developers were notified. No impact to Rule File. 26Nov2020: Backup: Sujan Whats planned: Nothing planned as of now. 11-Aug-2020 (SHRIVNI5): RF V15.0 finalized on 07Aug2020 to update the ZW domain as per blinding requirement. 02Apr2020 : DSG005 and LBG003_TR (FA) included in RF Version 13.0 and finalized. Mar2020 : RF Transitioned from Chandrakala to Ashok 19Feb2020: DTS 'QS5L' included in RF version 12.0 and finalized. 14Feb2020 : FAAEN001, FAAEN003 forms are used for branching purpose and does not require to flow downstream. Missing form report can be ignored. QS5L DTS missing in RF as per Report need clarification from DBD and RF developer 10Dec2019: Transition completed(No dts, forms pending to be included in RF so far) with below actions pending from Mohit •RF v11.0 checklist is missing in CREDI. •RF v9.0 – 2 documents are uploaded in CREDI, need to get the duplicate removed. •‘QS5L’ dts expected to be final soon, RF to update post that. 29Nov2019: Latest Rule File Version 11.0 is shared with the LSP. It is confirmed by the LSP that DD domain is also published into PRE DRM successfully on 28thNov2019. So now all the domains present in the study are available in LSH. 22Nov2019: Transition initiated DD domain is not included in the Rule File currently. The Coding Dictionary was present in the Primary Reason question and Other Specify question. After study went live during the Rule File creating it was confirmed the Coding is not required. We did the PPC in Mar 2019 but at that time it was not noticed that Dictionary is also attached to other specify field also. Recently we have performed the PPC and Dictionary is removed from the forms. Views are refreshed however COding variables are still present. We requested Rave X Admin team to perform another refresh and if it doesn't work we will raise a ticket to Medidata. QS3L table also needs to included in the rule. The DTS for this was approved in Jul 19. That time it was thought to include this domain with DD domain because Vendor has confirmed they can't send production data by September. Once the issues with DD domain is resolved with included QS3L also. If it will take time more than a week then I will include it by end of this week. New LSH setup. Rule file sent for LSH Test setup. One issue working with LSH IT for a fix | None | None | 2019-01-03 05:30 | Transition Study and Legacy process | Gouni, Harita | Purohit, Hemanshu | Rohit Varate | Completed | 2019-01-04 | Completed | 2019-06-19 05:30 | Completed AE,CM,DD,DM,DS,DV,EC,EG, FAAE,IE,LB,MH,ODM,PR,SV, VS,ZJ,ZW domains are avilable for DIAL. |  | 2019-01-04 05:30 | 2019-01-04 05:30 | Pre-requisites not met | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse |  | LB;#Y1;#Y5;#ZJ;#ZK;#ZK02;#ZK03 | [11 empty] | NA | [5 empty] | 13 | 29 | 75 | 0 | 429 | 1058 | 0 | 271 | 36 | 191 | 1285 | 8 | 0 |  | Systemic lupus erythematosus | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-06-19 05:30 |  |  |  |  | R, Harini | None of the above | Yes
CVAY736H1 | CVAY736Y2102 | C1200307 | Phase I | NCDS_2 | Rave EDC - Inhouse |  | 2017-12-15 05:30 | 2018-04-16 05:30 | DB Conduct | Final DBL | 2024-11-29 05:30 | 2018-04-09 05:30 |  | 2017-09-21 05:30 |  | Active | 2024-10-15 05:30 |  | 2024-11-29 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | Phase Ib open-label study of VAY736 and ibrutinib in patients with chronic lymphocytic leukemia (CLL) on ibrutinib therapy | CVAY736Y2102 Chronic Lymphocytic Leukemia Study | N7 Oncology - NIBR | Langlo, Francois | Pelloni, Luca | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Alexandra Acosta | Alexandra Acosta | Choppadandi, Kranthikumar | Bakka, Sandeep |  |  |  |  | DRM (DIAL) | Rana, Aamir | Choppadandi, Kranthikumar | Completed | 07-Jul-2021: B14L DTS is still "On Hold" 06Jul2021 : B14L reflecting in missing form DTS report 19May2021 : B14L DTS not final yet. Flagged in report. As per DBD DTS on hold. 24-Mar-2021: B16L DTS included in RF_V11.0 04Feb2021 : B14L DTS not final yet. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021 B14L DTS listed. Please check 10-Dec-2020: B14L DTS Not yet finalized but listed in the report 14-Sep-2020: RF_V10.0 finalized due to PPC11 and PPC12 23Oct2020 : B14L DTS not final yet. Table is created in LSH so its flagging in report. As per TDM study team"We are actually not even sure if we would be getting anything from this vendor." 25Sep2020 : As per 02Sep2020 missing forms DTS report B14L DTS pending but DTS is not final yet 06-Jul-2020(Kranthi): No pending issues 13-MAY-20: (Sujan) New local lab form LBG003_TR has been added and sent for peer review | None | None | 2018-04-02 05:30 | Legacy Process | R, Harini | Varate, Rohit | Rohit Varate | Completed | 2018-04-11 | Completed | 2020-06-12 05:30 | The list of domains for DIAL are - AE, CM, DM, DS, MH, ODM and SV. |  | 2018-04-11 05:30 | 2018-04-11 05:30 | Pre-requisites not met | 2020-08-24 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 17 | 35 | 95 | 0 | 390 | 889 | 0 | 265 | 70 | 481 | 1440 | 6 | 0 |  | Chronic lymphocytic leukaemia | No | Global | Open | Yes | [10 empty] | 2020-05-05 05:30 | [5 empty] | None of the above
CVDT482A1 | CVDT482A11401 | C4014188 | Phase IV |  |  |  |  | 2023-04-01 05:30 |  | Final DBL | 2027-01-18 05:30 |  |  |  |  | Planned | 2027-01-15 05:30 |  | 2027-01-18 05:30 | [5 empty] | Outsourced |  |  | CVDT482A11401 PMS_Japan | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | KEIKO FUJINO | [66 empty] | Esophageal cancer | No | Global | Open | Yes
CVHB937A0 | CVHB937A02101 | C4004924 | Phase I | Other | Other |  |  | 2021-10-20 05:30 | Study Planned | Final DBL | 2026-02-19 05:30 | 2021-10-20 05:30 | 2021-04-23 05:30 | 2021-04-26 05:30 |  | Active | 2025-12-11 05:30 |  | 2026-02-19 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A first-in-human, randomized, participant-, investigator-, and sponsor-blinded, placebo-controlled, two-part, single ascending intravenous dose study, to assess the safety, tolerability, and pharmacokinetics of VHB937 in healthy non-Japanese and Japanese adults | CVHB937A02101 | N6 Neuroscience - NIBR | Langlo, Francois | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | Other | [7 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  | Alzheimer's disease | No | Regional | Open | Yes | [16 empty] | None of the above
CVOB560A1 | CVOB560A12101 | C4005189 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-09-05 05:30 | 2021-06-17 05:30 | 2021-06-29 05:30 | DB Conduct | Final DBL | 2025-03-13 05:30 | 2021-06-23 05:30 | 2020-10-15 05:30 | 2020-10-29 05:30 | 2021-04-26 05:30 | Active | 2025-01-02 05:30 |  | 2025-03-13 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO | A phase Ib, multicenter study of VOB560 in combination with MIK665 in patients with relapsed/refractory non-Hodgkin lymphoma, relapsed/refractory acute myeloid leukemia, or relapsed/refractory multiple myeloma | CVOB560A12101 Phase I VOB560 in combo w/ MIK665 | N7 Oncology - NIBR | Langlo, Francois | Bekker, Sandra | Vivier, Gregoire | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | KAE ISHIHARA; Laurent Susini | Laurent Susini | Ganesan, Dhanalakshmi | Kashyap, Sandeep | Not Started |  | 07May2021 : Iliyas, Mohamed (ICON), Madhu M, Supported Dhanalakshmi Study reassigned from Rohit to Dhanalakshmi in Dec2020. golive date moved to 02Feb2021. Initial golive as of 12Aug2020 RaveX master tracker prior to iBOW was 05Sep2020 |  | DRM | Choppadandi, Kranthikumar | Bairagi, Arpita | Completed | 11Aug2021 : Reassigned the study from Kranthi to Arpita. 18-Jun-2021: Finalized the RF_V1.0 and raised SNOW05 ticket(RITM2687394) for LSH set-up 10-Feb-2021: reviewed SRFs, ALS and SDTM annotations and provided the comments to Led DBP 21Jan2021: Provided ALS review comments to Lead DBP and requested for SDTM annotaions for study specific pages. 14Aug2020 : As per DBD "The protocol is still not finalized for ‘CVOB560A12101’. We are expecting start working on study after 03rd SEP." | None | None | 2021-06-18 05:30 | RF finalized within golive + 5 days | Gouni, Harita | Varate, Rohit | Rohit Varate | Completed | 2021-06-29 | Completed | 2021-08-04 05:30 |  | SMT creation is delay due to study complexity. | 2021-11-05 05:30 | 2021-11-05 05:30 |  | 2021-10-06 05:30 | 2021-10-06 05:30 |  |  | 0 | RaveX - Inhouse | No | Open label Study | [11 empty] | IQVIA | [5 empty] | 2 | 56 | 141 | 0 | 744 | 1213 | 0 | 308 | 40 | 463 | 1716 | 6 | 0 |  | Acute myeloid leukaemia; Multiple myeloma; Non-Hodgkin's lymphoma | No | Global | Open | Yes | [10 empty] | 2021-07-22 05:30 | [5 empty] | None of the above | Yes
CVPM087A | CVPM087A2101 | C3004146 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-03-26 05:30 | 2019-05-03 05:30 | 2019-05-10 05:30 | DB Conduct | Interim DBL | 2022-05-14 05:30 | 2019-05-22 05:30 | 2018-11-23 05:30 | 2018-11-23 05:30 |  | Active | 2025-01-28 05:30 |  | 2025-03-11 05:30 |  | FALSE | study does not fall in any of the above category of studies listed | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | Phase Ib study of gevokizumab in combination with standard of care anti-cancer therapies in patients with metastatic colorectal cancer, gastroesophageal cancer and renal cell carcinoma | CVPM087A2101 gevo+VEGF Ph1b | P0 Oncology (Solid Tumors all MA Onc projects) | Navarro, Christelle | Girme, Abhijit | Girme, Abhijit | Sahu, Vandana | Hiriyanna, Srinivas | Lillian Tseng | Lillian Tseng | Kurella, Rakesh Reddy | Rana, Aamir |  |  | 15-Dec-2021 : Sujit Palande will be backup for Aamir till 15-Mar-2022 Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 26mar2019 |  | DRM | Kurella, Rakesh Reddy | Patnaik, Angella | Completed | 30-JUN-2021: SNOW#51 raised for SMT/LSH updates pertaining to PPC #6. There are no RF updates for PPC #6. 08OCT2020: RF not impacted for PPC5 updates. SMT and LSH updates list has been provided to LSP. 28JUL2020: RF updated and SNOW#51 raised for SMT and LSH updates for SSG004 form. 27Jul2020 : SSG004 is listed in 20jul report 07-JUL-2020: RF up to date for all final DTS and Post Production updated till PPC3 implemented in the study. 26JUN2020: RF updates for PPC3 finalized and SNOW#51 raised for SMT and LSH updates. 11MAY2020: LB1L table already added in V3.0 of Rule file finalized on 27-JAN-2020. Not an issue (as in report it is validating for LBL table). Data is also flowing as confirmed by LSP. 06MAY2020: email sent to DBD for query on pending DTS. Not yet confirmed. 31MAR2020: RF V5.0 finalized in CREDI and SNOW#51 raised for LSH updates. 30MAR2020: PPC2 updates are released for Peer Review. 17MAR2020: Rule file finalized and SNOW#51 raised for LSH set-up. 16MAR2020: RF updated for DTS table B11L and sent for Peer review. 11FEB2020: UPVG001_1 is the unplanned assessment page which are related to unplanned blood collection page and is used in the study just for operational purpose. Hence this form should not be included in the rule file. 27JAN2020: Rule file V3.0 updated for Lab DTS. SNOW#51 raised. SMT updates requested. 11Jul19: SMT completed. no pending comments 06Jun19 : Peer review completed. Snow Ticket pending | None | None | 2019-06-13 05:30 |  | Sundar, N Sushant | Sundar, N Sushant | Sushant Sundar | Completed | 2019-06-14 | Completed | 2019-06-17 05:30 |  | Pre-requisites not met | 2019-06-17 05:30 | 2019-06-17 05:30 | Pre-requisites not met | 2019-09-13 05:30 |  |  |  |  | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 8 | 142 | 107 | 0 | 932 | 1970 | 0 | 442 | 41 | 348 | 2359 | 4 | 0 |  | Carcinoma in situ of digestive organs; Colorectal cancer; Renal cell carcinoma | No | Global | Open: Reapproval | Yes | [10 empty] | 2019-06-14 05:30 | [5 empty] | None of the above
CVPM087A | CVPM087A2301 | C3004150 | Phase III |  |  |  |  | 2023-12-15 05:30 |  | Final DBL | 2025-07-11 05:30 |  | 2023-04-06 05:30 |  |  | Planned | 2025-05-02 05:30 |  | 2025-07-11 05:30 | [5 empty] | InHouse |  |  | CVPM087A2301 1LCRC VPM087+Avastin+Folfox | P0 Oncology (Solid Tumors, all MA Onc projects) | [6 empty] | Susan Poggio | [66 empty] | Colorectal cancer metastatic | No | Global
CVPM087B | CVPM087B2301 | C4014426 | Phase III |  |  |  |  | 2023-10-02 05:30 |  | Final DBL | 2023-04-03 05:30 |  | 2023-06-15 05:30 |  |  | Planned | 2023-02-20 05:30 |  | 2023-04-03 05:30 | [5 empty] | InHouse |  |  | CVPM087B2301 2L mGEC chemo+Ram+Gevo | P0 Oncology (Solid Tumors all MA Onc projects) | [6 empty] | Susan Poggio | [66 empty] | Gastric cancer; Gastroesophageal cancer | No | Global | Draft | No
CWCD118B1 | CWCD118B12201 | C4016381 | Phase II |  | Rave EDC - Inhouse |  |  | 2022-10-31 05:30 | Study Planned | Final DBL | 2029-02-15 05:30 |  | 2022-06-29 05:30 |  |  | Planned | 2029-01-04 05:30 |  | 2029-02-15 05:30 |  |  | DCN Priority | Rao, Sreekanth | Cluster A (SolidT,IO,Resp) | InHouse | Solid Tumor | A randomized, double-blind, placebo-controlled, phase II study evaluating the efficacy and safety of ociperlimab (BGB-A1217) combined with tislelizumab (BGB-A317) plus chemotherapy versus placebo combined with pembrolizumab plus chemotherapy as first-line therapy for participants with locally advanced or metastatic triple negative breast cancer (TNBC) | CWCD118B12201 Phase II TNBC Ociperlimab + Tisle | P0 Oncology (Solid Tumors all MA Onc projects) | Boudraa, Yvane | Deshmukh, Priyanka Rajesh | Singh, Parul | Regula, Ramakrishna | Hiriyanna, Srinivas | Sandrine Bach-Berkowicz | Sandrine Bach-Berkowicz | [17 empty] | Sushant Sundar | [48 empty] | Triple negative breast cancer | No | Global | Open | Yes
CWVT078A1 | CWVT078A12101 | C4005316 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-10-18 05:30 | 2019-11-02 05:30 | 2019-12-11 05:30 | DB Conduct | Final DBL | 2024-02-16 05:30 | 2019-12-05 05:30 | 2019-06-13 05:30 | 2019-06-06 05:30 |  | Active | 2023-12-08 05:30 |  | 2024-02-16 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | TCO Mixed Model | TCO |  | CWVT078A12101 TCO Phase I Multiple Myeloma | N7 Oncology - NIBR | Langlo, Francois | Govender, Daventha | OMEYER, Delphine | Kansagara, Sachinkumar | Gupta Bhaya, Soumya Kanti | Adonai Fessehatsion; Alexandria Nudo | Adonai Fessehatsion | Bonam, Rajesh Babu | Prasanna Kumar, VTSSR | Completed | 2019-11-18 05:30 | Initial golive as of 04Oct2019 RaveX master tracker prior to iBOW was 18Oct2019 |  | DRM | Patnaik, Angella | Patnaik, Angella | Completed | 23-SEP-2021: RF Version 15.0 finalized in SubWay for RSS001 SDTM annotations update. SNOW #51 raised for SMT/LSH updates. 02-SEP-2021: RF Version 14.0 finalized in SubWay for B13L table addition for PRAHS DTS. SNOW #51 raised for SMT/LSH updates. 18-AUG-2021: RF Version 13.0 finalized in SubWay for B12L table addition for Navigate DTS. SNOW #51 raised for SMT/LSH updates. 15-APR-2021: RF Version 12.0 finalized in SubWay. SNOW#51 raised for SMT and LSH update. 15-APR-2021: RF Version 12.0 released for Peer Review for PPC6 updates. 30-MAR-2021: RF Version 10.0 finalized in SubWay. SNOW#51 raised for SMT and LSH update. 26-MAR-2021: LB1L DTS table added in RF Version 10.0 and released for Peer Review. 19-FEB-2021: RF Version 9.0 final and SNOW #51 raised for SMT and LSH updates. 18-FEB-2021: DB set-up issue highlighted to DBD. RF Version 9.0 released for Peer Review. 17-FEB-2021: RF updates ongoing for PPC5. Awaiting UAT SOD for Renderer testing. 20Nov2020 : RF is final and snow 51 raised for SMT and LSH updates for MOG001. 17NOV2020: DB updates for MOG001 have been initiated in PPC4. RF has been updated and sent for Peer Review. 3NOV2020: Sent a reminder to DBD on PPC confirmation. Will update the RF accordingly. 13OCT2020: MOG001 form added in PPC3 has set-up issues. RF update will be made once the issue is fixed. 16JUN2020: RF is finalized in SubWay and SNOW#51 raised for SMT and LSH updates. 4JUN2020: RF released for Peer Review. 21MAY2020: SRFs and SDTM annotations not yet received. Have sent a reminder today. 4MAY2020: Awaiting SRFs and SDTM annotations from DBD for updating the RF for the newly added forms in PPC1. 14FEB2020: Final BioAgilytix DTS&nbsp; (B11L) shared on 12FEB2020. Rule file updated and SNOW#51 raised. 11FEB2020 : Updated SMT attached to SNOW#51. PPC 1 is pending which will impact on SV domain in Rule file. 7FEB2020: EG domain updated for ECG DTS and SNOW#51 raised. SMT update requested. 21Jan2020: LSH Setup completed for all domains and no DTS is final yet 8-JAN-2020: Rule file finalized for all pending forms. Sent for SMT creation. 7-JAN-2020: Rule file sent for review for pending domains. Will be finalized by tomorrow. 29-DEC-2019: Rule file 3.0 for the pending domains sent for Peer Review post TA POD and SDTM confirmation. 13DEC2019: Rule file V2.0 updated for SV domain. Pending domains-TU,TR,PR,RS. 12-DEC-2019: SNOW will be raised once SMT files are received. 11-DEC-2019: Rule V1.0 sent for SMT creation. 3 forms not included in Rule file TUS001, TUS003, PRS003 which needs inputs from SDTM Programmer. Target date of completion for pending domains 17-DEC-2019. 10DEC2019: First round of Peer Review comments fixed and sent for Peer Review. TU, TR domain mapping pending from DBD and SDTM Team. 06Dec19 : Fixing peer review comments and ill be completed by 09Dec19. Rule file Peer Review ongoing. 1 Form input pending from Standards team. | None | None | 2019-12-11 05:30 | DB Set-up Issues | Nagalla, Lakshmi Naga Lavanya | Varate, Rohit | Rohit Varate | Completed | 2019-12-12 | Completed | 2019-12-13 05:30 |  |  | 2019-12-13 05:30 | 2019-12-13 05:30 | SNOW 05 was raised after FPFV,Pre-requisites not met | 2020-03-02 05:30 |  |  |  | 62 | RaveX - Inhouse | Yes | -NA- | [11 empty] | IQVIA | [5 empty] | 12 | 143 | 99 | 0 | 1722 | 1252 | 0 | 217 | 42 | 462 | 1756 | 2 | 0 |  | Multiple myeloma | No | Global | Open | Yes | [10 empty] | 2019-12-13 05:30 | [5 empty] | None of the above | Yes
CXEP527A0 | CXEP527A01101 | C4011226 | Phase I |  |  |  |  | 2023-05-15 05:30 |  | Final DBL | 2023-09-15 05:30 |  | 2023-01-15 05:30 |  |  | Planned | 2023-07-14 05:30 |  | 2023-09-15 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CXEP527A01101 Japan Ethnic Sensitivity study | N6 Neuroscience - NIBR | [6 empty] | TAKAHIRO MURAMOTO | [66 empty] | Schizophrenia | No | Global | Open | Yes
CXEP527A0 | CXEP527A02101 | C4007376 | Phase I | Other | Rave EDC - Inhouse |  |  | 2021-12-20 05:30 | Study Planned | Final DBL | 2022-12-20 05:30 | 2021-12-17 05:30 | 2021-10-04 05:30 | 2021-10-01 05:30 |  | Active | 2022-09-16 05:30 |  | 2022-12-20 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - NS | A first-in-human, randomized, participant- and investigator-blinded, placebo controlled, single and multiple ascending dose study to assess the safety, tolerability, and pharmacokinetics of XEP527 in healthy participants | CXEP527A02101 - First in Human HV | N6 Neuroscience - NIBR | Langlo, Francois | Mane, Kunal Yashavant | Mane, Kunal Yashavant | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Catherine Gray | [17 empty] | Rohit Varate | [28 empty] | NA | [7 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Schizophrenia | No | Global | Open | Yes | [16 empty] | None of the above
CXEP527A1 | CXEP527A12101 | C4011111 | Phase I |  |  |  |  | 2023-03-02 05:30 |  | Final DBL | 2024-05-28 05:30 |  | 2022-11-15 05:30 |  |  | Planned | 2024-04-02 05:30 |  | 2024-05-28 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CXEP527A12101 Proof of Mechanism in SZ and BPD | N6 Neuroscience - NIBR | [6 empty] | Denise Serra | [66 empty] | Bipolar disorder; Schizophrenia | No | Global | Open | Yes
CXXB750A0 | CXXB750A02101 | C4005535 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2020-07-09 05:30 | 2020-08-14 05:30 | 2020-08-03 05:30 | DB Conduct | Interim DBL | 2022-05-14 05:30 | 2020-07-29 05:30 | 2020-05-05 05:30 | 2020-05-01 05:30 |  | Active | 2022-07-22 05:30 |  | 2022-09-09 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - CVM |  | CXXB750A02101 Phase Ia FIH study | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Palav, Mahesh | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Jen Watts; Magdalena Markiewicz | Jen Watts | Gupta, Anshu | Palande, Sujit | Completed | 2021-07-20 05:30 | FPFV planned on 9-Jul-2020 and FPFT on 6-Aug-2020. TDM "For NIBR, we have a provision to release study before FPFT and this has been in agreement with Study Lead for CXXB750A02101 trial due to some la 13Apr2020 : TDM Mahesh Palav shared below timelines for DBD assignment. 1. Full protocol number : CXXB750A02101 2. Date of protocol finalization : 16-Apr-2020 3. Go-live Date (planned) : Under discussion (09-Jul-2020). 4. FPFV : 09-Jul-2020 |  | DRM | Shrivastava, Nikhil | Saha, Saikat | Completed | 13-Aug-2021 (Nikhil): Transition activities completed. Informed the study team. 11Aug2021 : Reassigned the study from Nikhil to Saikat. 29-Jun-2021: RF V4.0 finalized WRT PPC#01 (addition of new fields in SV and VE domains). SNOW-51 raised and LSP notified. 23-Jun-2021: Provided database comments to DBD and DBD is following up with team to get inputs and confirmation 31-Mar-2021: VS2L DTS included in the RF V3.0 and finalized. SNOW-51 ticket is raised. LSP and SMT developers have been notified. 25-Mar-2021: VS2L DTS was finalized but it was not informed to include in the Rule File. DTS was flagged in the Missing form and DTS report. Reviewed the DTS and added in the Rule File and released for peer review. 17-Feb-2021: Both DTS (LBL and VS1L) are already included in RF V2.0. LSP confirmed that LSH setup is ongoing. 20Jan2021 : LC: As per missing forms/DTS report dated 15jan2021LBL, VS1L DTS listed. Pending since last comment. Please check 9Dec2020: RF updated and released for review. 24Nov: For LBL Will share the Rule file for review by 26Nov. Requested DBD to share the VS1L DTS 18Aug2020: RF final and SNOW05 raised 12AUG2020: Rule file under development. Received latest SDTM annotations on 27July. 24JUN2020 [SK]: OSRM round 2 completed. By 30-JUN-20, SRF's will be approved and DBD will send study specific pages for RF developer review. 23Jun2020: Asked Sujan to support in Shashi's absence | None | None | 2020-08-18 05:30 | Transition study | Adi, Vishnupriya | Varate, Rohit | Rohit Varate | Completed | 2020-08-28 | Completed | 2020-08-31 05:30 |  | Pre-requisites not met | 2020-09-01 05:30 | 2020-09-01 05:30 | Pre-requisites not met | 2020-08-26 05:30 |  |  |  | 81 | RaveX - Inhouse | Yes | ZK;#Y1;#EC | [11 empty] | NA | [5 empty] | 3 | 18 | 53 | 0 | 177 | 547 | 0 | 164 | 33 | 152 | 732 | 3 | 0 |  | Heart failure with reduced ejection frac | No | Global | Open | Yes | [10 empty] | 2020-08-31 05:30 | [5 empty] | None of the above
CXXB750A1 | CXXB750A12101 | C4007533 | Phase I | NCDS_2 | CRO - EDC | 2021-10-04 05:30 |  | 2022-04-18 05:30 | Study Planned | DB Go-live | 2022-03-18 05:30 |  | 2022-01-07 05:30 | 2021-12-17 05:30 |  | Planned | 2022-10-21 05:30 |  | 2022-11-25 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | Outsourced | NIBR - CVM | A randomized, participant and investigator blinded, placebo-controlled, single dose study to investigate the safety and tolerability of XXB750 in heart failure participants with Reduced Ejection Fraction (HFrEF) | CXXB750A12101 Phase 1b study in HF patients | P9 Cardiovascular Renal and Metabolism (CRM) | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Swain, Swayam | Gupta Bhaya, Soumya Kanti | Valerie Brooks | Valerie Brooks | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Heart failure with reduced ejection frac | No | Global | Open | Yes | [16 empty] | None of the above
CXXB750B1 | CXXB750B12201 | C4010984 | Phase II | NCDS_2 | Rave EDC - Inhouse |  |  | 2022-10-17 05:30 | DB Set-Up | DB Go-live | 2022-09-24 05:30 |  | 2022-05-05 05:30 |  |  | Planned | 2024-05-13 05:30 |  | 2024-06-24 05:30 |  |  | None | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | DF CRM |  | CXXB750B12201 POC DRF | P9 Cardiovascular Renal and Metabolism (CRM) | Mahajan, Vinay | Joglekar, Prajakta | Subramanian, Mahaveeran | Tummalapenta, Venkateswarlu | Nair, Sreesha | Wojciech Smoron | Wojciech Smoron | [17 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 60 | [7 empty] | 800 | 6 |  |  | Uncontrolled hypertension | No | Global | Open | Yes
CXZE630A0 | CXZE630A02101 | C4008116 | Phase I | Other |  |  |  | 2023-05-17 05:30 |  | Final DBL | 2024-09-17 05:30 |  | 2022-12-28 05:30 |  |  | Planned | 2024-08-21 05:30 |  | 2024-09-17 05:30 |  | FALSE |  |  |  | FULL Outsourced |  |  | CXZE630A02101 SAD MAD in HV | N0 ATI - NIBR | [6 empty] | Louise Mooney | [54 empty] | 60 | 0 |  |  | 0 |  |  |  | 700 | 3 | 0 |  | Autoinflammatory disease | No | Global | Open | Yes | [16 empty] | None of the above
CYTB323A1 | CYTB323A12101 | C4003330 | Phase I | NCDS_2 | Rave EDC - Inhouse | 2019-04-15 05:30 | 2019-06-06 05:30 | 2019-06-28 05:30 | DB Conduct | DB Snapshot | 2022-05-16 05:30 | 2019-06-27 05:30 | 2018-12-19 05:30 | 2019-01-10 05:30 |  | Active | 2025-10-09 05:30 |  | 2025-12-18 05:30 |  | FALSE | NA | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology | Phase I, open label, multicenter, dose escalation study of YTB323 in adult patients with CLL/SLL and DLBCL | CYTB323A12101 YTB323 FIH rapid CAR-T | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | Hemnani, Nisha | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Massimiliano Quadrigli | Massimiliano Quadrigli | Shrivastava, Nikhil | Prasanna Kumar, VTSSR |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 15Apr2019 |  | DRM | Shrivastava, Nikhil | Choppadandi, Kranthikumar | Completed | 22Mar2021: LBG001_7_TR included in RF_V4.0 21Jan2021(Kranthi): Working with study TDM and DBP to complete the PPC asap for LBG001_7_TR page. Once the page is updated via PPC, RF will be updated. Target date to include LBG001_7_TR form in Rule File is 05-Feb-2021 26-Nov-2020: Lab parameters will be added to reference metadata by 30-Nov-2020. RF will be updated once the Lab parameters added. 06-Nov-2020: RF v3.0 is finalized in CREDI for PPC#3 updates. 'LBG001_7_TR' --Not included as the Analytes are not available in 'Reference metadata'. Informed to TDM and DBP accordingly. 06-Jul-2020: No pending issues. Verison 2.0 Added 5 B1 related DTS (B11L, B12L, B13L, B14L and B15L) under B1 domain. dded "LBG001_1_TR" (Hematology - Local Lab Results) form under union logic along with other quantitative lab pages. Earlier this forms was excluded due to duplicate analyte. Now it is corrected in PPC1. Added in Rule file on 30th Jan2020 13Jan2020 (SHRIVNI5): Rule file transition ongoing. 08Aug2019: Rule file finalized and archived in CREDI. SNOW ticket also raised for study setup in LSH. 08Aug2019: Working the received comments and will release for final round of review by Friday (09-Aug-2019). 30July2019: Received the 2nd round of comments. 26July2019: Shared the updated rule file for the 2nd round of review. 16Jul2019,BAICH3: Round 1 review comments shared. 10Jul19: Received for peer review. Will start review by12th and get back with comments in 3rd week. 10Jul19: Created the rule file and sent for peer review as 1st batch. 03Jul19: This is a big study complex with 172 unique forms and multiple study specific pages. The rule file is under creation. Planned to complete the Rule File by 10th Jul 2019. | None | None | 2019-08-08 05:30 | Legacy Process | Nagalla, Lakshmi Naga Lavanya | Garje, Sagar | Amit Agavekar | Completed | 2019-08-10 | Completed | 2019-08-29 05:30 |  | "1. LSH KPI met. LSH setup ticket was raised after FPFV. 2. Study Transitioned." | 2019-09-03 05:30 | 2019-09-03 05:30 | SNOW 05 raised after FPFV, pre-requisites not met | 2020-05-04 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | -NA- | [11 empty] | NA | [5 empty] | 6 | 25 | 221 | 0 | 724 | 1615 | 0 | 293 | 37 | 625 | 2277 | 13 | 0 |  | Acute lymphoblastic leukaemia; Chronic lymphocytic leukaemia recurrent; Diffuse large B-cell lymphoma refractory | No | Global | Open | Yes | [10 empty] | 2019-08-26 05:30 | [5 empty] | None of the above | Yes
CYTB323B1 | CYTB323B12301 | C4010481 | Phase III | NCDS_2 | Rave EDC - Inhouse | 2022-02-02 05:30 |  | 2022-04-21 05:30 | DB Set-Up | DB Go-live | 2022-04-27 05:30 |  | 2022-02-26 05:30 |  |  | Planned | 2028-11-23 05:30 |  | 2029-02-05 05:30 |  |  | Submission | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology |  | CYTB323B12301 YTB323 2L DLBCL Pivotal Study | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | A, Mohamed Noorul | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Helen Marquina | Helen Marquina | Prasanna Kumar, VTSSR | Prasanna Kumar, VTSSR | [5 empty] | Bairagi, Arpita | Bairagi, Arpita | Not Started | [7 empty] | Amit Agavekar | [28 empty] | NA | [7 empty] | 139 | 0 |  |  | 0 |  |  |  | 1100 | 10 | 0 |  | Diffuse large B-cell lymphoma refractory | No | Global | Open | Yes
CYTB323C1 | CYTB323C12301 | C4013396 | Phase III | NCDS_2 |  |  |  | 2022-09-19 05:30 |  | Final DBL | 2025-01-17 05:30 |  | 2022-07-13 05:30 |  |  | Planned | 2024-12-06 05:30 |  | 2025-01-17 05:30 | [5 empty] | InHouse |  |  | CYTB323C12301 YTB323 2L FL RCT | PA Oncology (Hematology not for MA projects) | [5 empty] | Janet Lasher | Janet Lasher | [54 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Lymphoma | No | Global | Open | Yes
CYTB323D1 | CYTB323D12301 | C4013419 | Phase III |  | Rave EDC - Inhouse |  |  | 2022-09-26 05:30 | Study Planned | DB Go-live | 2022-08-22 05:30 |  | 2022-06-24 05:30 |  |  | Planned | 2028-04-17 05:30 |  | 2028-05-29 05:30 |  |  | Pioneer | Moharana, Dhaneswar | Cluster B (Haem,CRM,NS) | InHouse | Hematology |  | CYTB323D12301 Transplant Ineligible DLBCL RCT | PA Oncology (Hematology not for MA projects) | Iyer, Srinarayani | KASTURINIVASA NARASIMHAIAH, SUSHMA RANI | Singh, Devendra | Bhartendu, Rishav | Nair, Sreesha | Laurence Bourdeau | Laurence Bourdeau | [17 empty] | Amit Agavekar | [28 empty] | NA | [19 empty] | Diffuse large B-cell lymphoma | No | Global | Open | No
CYTB323E1 | CYTB323E12201 | C4013420 | Phase II | NCDS_2 |  |  |  | 2022-01-03 05:30 |  | Final DBL | 2026-11-11 05:30 |  | 2022-05-20 05:30 |  |  | Planned | 2026-10-01 05:30 |  | 2026-11-11 05:30 | [5 empty] | InHouse |  |  | CYTB323E12201 1L HR DLBCL (Pilot trial) | PA Oncology (Hematology not for MA projects) | [6 empty] | Ian Miller | [54 empty] | 105 | [7 empty] | 1250 | 6 |  |  | Diffuse large B-cell lymphoma | No | Global | Draft | Yes
CYTB323E1 | CYTB323E12301 | C4013422 | Phase III | NCDS_2 |  |  |  | 2024-05-22 05:30 |  | Final DBL | 2024-12-17 05:30 |  | 2024-02-05 05:30 |  |  | Planned | 2024-11-05 05:30 |  | 2024-12-17 05:30 | [5 empty] | InHouse |  |  | CYTB323E12301 1L HR DLBCL (Ph3 trial) | PA Oncology (Hematology not for MA projects) | [6 empty] | Laurence Bourdeau | [54 empty] | 130 | [7 empty] | 1400 | 10 |  |  | Diffuse large B-cell lymphoma | No | Global | Draft | Yes
CZLO707A0 | CZLO707A02101 | C4005526 | Phase I | NCDS | CRO - EDC | 2021-06-01 05:30 |  | 2021-12-08 05:30 | DB Conduct | Final DBL | 2023-03-31 05:30 | 2021-12-07 05:30 | 2021-09-21 05:30 | 2021-09-03 05:30 |  | Active | 2023-02-03 05:30 |  | 2023-03-31 05:30 |  | FALSE | NA | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - CVM | A first-in-human, randomized, investigator- and participant blinded, sponsor open-label, placebo-controlled single and multiple ascending dose study to assess the safety, tolerability and pharmacokinetics of ZLO707 in healthy participants | CZLO707A02101 FIH SAD_MAD | N1 CVM - NIBR | Langlo, Francois | Sneha, Kumari | Sneha, Kumari | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Lee Anne Filosa | Lee Anne Filosa | [17 empty] | Rohit Varate | [28 empty] | CMED | [7 empty] | 50 | 0 |  |  | 0 |  |  |  | 700 | 2 | 0 |  | Hypercholesterolaemia | No | Global | Open | Yes | [16 empty] | None of the above
CZLO707A0 | CZLO707A02102 | C4010404 | Phase I | Other |  |  |  | 2023-01-25 05:30 |  | Final DBL | 2023-06-01 05:30 |  | 2022-09-28 05:30 |  |  | Planned | 2023-04-20 05:30 |  | 2023-06-01 05:30 | [5 empty] | FULL Outsourced |  |  | CZLO707A02102 Bridging & food effect study | N1 CVM - NIBR | [6 empty] | Emma Healy | [66 empty] | Hypercholesterolaemia | No | Global | Open | Yes
CZLO707A1 | CZLO707A12201 | C4010405 | Phase II |  |  |  |  | 2024-09-02 05:30 |  | Final DBL | 2025-08-11 05:30 |  | 2024-03-03 05:30 |  |  | Planned | 2025-06-25 05:30 |  | 2025-08-11 05:30 | [5 empty] | ED Undecided Sourcing |  |  | CZLO707A12201 POC study in Hypercholesterolemia | N1 CVM - NIBR | [6 empty] | Emma Healy | [66 empty] | Hypercholesterolaemia | No | Global | Open | Yes
CZOL446H | CZOL446H2337 | C1001547 | Phase III | NCDS | CRO - EDC |  |  |  | DB Locked | Final DBL Achieved |  | 2008-12-04 05:30 |  | 2008-04-27 05:30 |  | Completed | 2013-02-20 05:30 | 2018-03-05 05:30 | 2018-05-14 05:30 | 2018-04-13 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | InHouse | Global Health | A multicenter, randomized, double-blind, placebo controlled efficacy and safety trial of intravenous zoledronic acid twice yearly compared to placebo in osteoporotic children treated with glucocorticoids for chronic inflammatory conditions | CZOL446H2337 | P6 Global Health | Vithala, Srinivas | Sayyed, Imtiyaz | Bhabhe, Nikhil | Fazili, Subeh Mohsin | Krishnan, Kripesh |  |  | Bonam, Rajesh Babu | [16 empty] | Sai Krishna Mettugari | [21 empty] | Pharma | Novartis | InHouse |  |  |  |  | NA | [7 empty] | 100 | 0 |  |  | 0 |  |  |  | 650 | 10 | 0 |  | Osteoporosis | No | Global | Open | Yes | [16 empty] | None of the above
CZOL446H | CZOL446H2337E1 | C1001548 | Phase III | NOVDD | CRO - EDC |  |  |  | DB Locked |  |  | 2010-10-25 05:30 |  | 2010-07-02 05:30 |  | Completed | 2019-02-27 05:30 | 2019-02-27 05:30 | 2019-03-28 05:30 | 2019-04-02 05:30 | FALSE | NA | Indu Bala | Cluster E (Ophtha,GH,GMA,Rare,Haem) | Outsourced | Global Health | A 1-year, multicenter, open-label extension to CZOL446H2337 to evaluate safety and efficacy of zoledronic acid twice yearly in osteoporotic children treated with glucocorticoids | CZOL446H2337E1 1yr long-term saf sutdy ext - H2337 | P6 Global Health | Vithala, Srinivas | Vithanala, Kiran Kumar | Bhabhe, Nikhil | Fazili, Subeh Mohsin | Krishnan, Kripesh |  | Abhishek Sople | Kuttoboina, Sujan Kumar | Bora, Deepthi Reddy | [15 empty] | Sai Krishna Mettugari | [28 empty] | PPD | Pharma | AP21 | PPD | [16 empty] | Osteoporosis | No | Global | Completed | Yes | [16 empty] | None of the above
CZPL389A0 | CZPL389A2101 | C3001076 | Phase I | NCDS | OC RDC - Inhouse |  | 2017-11-20 05:30 | 2017-11-27 05:30 | DB Locked | Final DBL Achieved |  | 2017-11-27 05:30 |  | 2017-08-17 05:30 |  | Completed | 2019-03-20 05:30 | 2019-03-14 05:30 | 2019-04-15 05:30 | 2019-04-22 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | InHouse | NIBR - ATI | A multi-part study of ZPL389, a histamine H4 receptor antagonist, consisting of randomized, subject and investigator blinded, placebo-controlled, single and multiple ascending oral dose study parts to assess the safety, tolerability and pharmacokinetics in healthy Japanese and non-Japanese volunteers, and an open-label food effects study part in healthy volunteers (non-Japanese) | CZPL389A2101 SAD/MAD/ESS/Food | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Sandra Camenisch | Sandra Camenisch | Samuel, Giftson | [14 empty] | Kumar, Ranjeet |  | Rohit Varate | [12 empty] | Old OC study with IA1 and IA2 completed and DMC is going to be happened soon. | 100 | OCRDC - Inhouse | Yes | Y1;#ZK;#ZK02 |  |  |  |  | Pharma | Novartis | InHouse | 2017-11-20 05:30 | 2017-11-20 05:30 |  |  | NA | [7 empty] | 204 | 0 |  |  | 0 |  |  |  | 406 | 3 | 0 |  | Atopic dermatitis | No | Global | Completed | Yes | [14 empty] | DBL | Sundar, N Sushant | None of the above | Yes
CZPL389A0 | CZPL389A2103 | C3001079 | Phase I | NCDS | CRO - EDC |  |  | 2018-11-02 05:30 | DB Locked |  |  | 2018-10-16 05:30 | 2018-10-03 05:30 | 2018-10-10 05:30 |  | Completed | 2019-02-11 05:30 | 2019-02-14 05:30 | 2019-04-23 05:30 | 2019-03-25 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | ED Full Outsourced | NIBR - ATI | A single-center, open-label study to evaluate the absorption, distribution, metabolism and excretion (ADME) and pharmacokinetics of ZPL389 following a single oral dose of [14C]ZPL389in healthy male subjects | CZPL389A2103 Human ADME | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Melissa Hackling | Melissa Hackling | [15 empty] | Chakravarthy, Meghna |  | Rohit Varate | [14 empty] | FSOM - Outsourced | No | ZK | [11 empty] | PRA Health | [19 empty] | Atopic dermatitis | No | Global | Open | Yes | [14 empty] | DMC/Dry-Run/Snapshot | Polagoni, Bharghavi | None of the above | Yes
CZPL389A | CZPL389A2201 | C1200105 | Phase II | NCDS |  |  |  | 2015-05-01 05:30 |  |  |  |  | 2014-12-19 05:30 | 2014-12-19 05:30 |  | Completed | 2015-07-17 05:30 |  | 2015-08-06 05:30 | 2015-08-06 05:30 | FALSE |  |  |  | ED Outsourced |  | A randomized, double-blind, placebo controlled, parallel group study to determine the effects of 8 weeks treatment with oral ZPL-3893787 (30 mg od x 56 days) on pruritus in adult subjects with moderate to severe atopic dermatitis | CZPL389A2201_ZIARCO PoC_CREDI Only | P7 Immunology Hepatology and Dermatology | [6 empty] | Betty Van Veen | [66 empty] | Atopic dermatitis | Yes | Global | [18 empty] | None of the above
CZPL389A | CZPL389A2203 | C3000248 | Phase II | NCDS_2 | Rave EDC - Inhouse |  | 2018-05-09 05:30 | 2018-11-08 05:30 | DB Locked | Final DBL Achieved |  | 2018-11-14 05:30 |  | 2017-11-20 05:30 |  | Completed | 2020-09-01 05:30 | 2020-08-06 05:30 | 2020-10-27 05:30 | 2020-10-22 05:30 | TRUE | Study Terminated | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double blind, placebo controlled, parallel group dose ranging study to determine the efficacy and safety of oral ZPL389A (3 mg, 10 mg, 30 mg and 50 mg) capsules administered for 16 weeks in subjects with moderate to severe atopic dermatitis | CZPL389A2203 Ph2b Atopic Dermatitis | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kocharekar, Prasheela Chetan | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Aude Lacombe | Aude Eleonore Lacombe | Vedula, Nagendra | Munukutla, Valli |  |  |  |  | DRM (DIAL) | Vedula, Nagendra | Kuttoboina, Sujan Kumar | Completed | 16OCT20: RF has been finalized and SNOW 51 RITM1902167 has been created. Change: FAMH domain has been updated as per updated SDTM annotations and DS domain has been updated 09OCT20: RF has been finalized and SNOW 51 request RITM1879092 has been created. Change: As part of PPC, LB domain has been updated. Note: DBL has been planned on 14OCT20. 07-JUL-20: As of today, no pending forms and no pending DTS 31Mar2020 : Third party DTS's FAA11L, FAA12L and CM1L have been added as its been final and raise SNow ticket on 30thMar2020 12-FEB-20: Two DTS has been finalized ZW1L and ZW2L and same has been added in Rule file 03-FEB-20: Actigraphy DTS is finalized but data is not transferred yet, due to programing issues ongoing with third party vendor. TDM will update by 05-FEB-20. NVE:29 Nov 19: The mentioned 3rd party DTS are not final yet. Once they are final, the rule file needs to be updated. Actigraphy(End Point Data - ZW1L, Event Data - ZW2L), Adjudication(Conmed Event Adjudication - FACM, Liver Event Adjudication - CE and Cardiac Event Adjudication - FAA1) | None | None | 2018-11-30 05:30 | Transition Study and Legacy process | Kommu, Ranjith Kumar | Varate, Rohit | Sandeep Kadam | Completed | 2018-12-20 | Completed | 2019-06-04 05:30 |  |  | 2018-12-04 05:30 | 2018-12-04 05:30 |  | 2019-08-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK | [11 empty] | NA | [5 empty] | 15 | 24 | 57 | 0 | 182 | 810 | 0 | 244 | 36 | 216 | 1062 | 15 | 0 |  | Atopic dermatitis | Yes | Global | Terminated | Yes | [10 empty] | 2019-06-04 05:30 |  |  |  | DBL | Gouni, Harita | GDD annual target | Yes
CZPL389A | CZPL389A2203E1 | C3001045 | Phase II | NCDS_2 | Rave EDC - Inhouse | 2019-03-08 05:30 |  | 2019-05-30 05:30 | DB Locked | Final DBL Achieved |  | 2019-04-04 05:30 | 2018-09-20 05:30 | 2018-11-27 05:30 |  | Completed | 2020-09-01 05:30 | 2020-08-25 05:30 | 2020-10-22 05:30 | 2020-10-22 05:30 | FALSE | Study Terminated | Bala, Indu | Cluster C (fGSK,IHD,Sandoz) | InHouse | DF ID | A randomized, double blind, multicenter extension to CZPL389A2203 dose-ranging study to assess the short-term and long-term safety and efficacy of oral ZPL389 with concomitant or intermittent use of TCS and/or TCI in adult patients with atopic dermatitis (ZEST Extension) | CZPL389A2203E1 Ph2b ZEST Extension | P7 Immunology Hepatology and Dermatology | Paigaonkar, Gargi | Kocharekar, Prasheela Chetan | Srinivasan, Subramani | Vasi, Munir | Ninan, Esther | Khaleel Ahmad | Khaleel Ahmad | Vedula, Nagendra | Munukutla, Valli |  |  | Initial golive as of 03Mar20219 RaveX master tracker prior to iBOW was 08Mar2019 | [5 empty] | Study Terminated. No RF activities supported, as this study was built as part of CZPL389A2203 study. No separate study database was created for CZPL389A2203E1. |  |  |  |  | Kommu, Ranjith Kumar | Kommu, Ranjith Kumar | Sandeep Kadam | Completed | 2018-12-04 | Completed | 2018-12-19 05:30 |  |  | 2018-12-04 05:30 | 2018-12-04 05:30 |  | 2018-12-19 05:30 |  |  |  | 100 | RaveX - Inhouse | Yes | Y1;#Y5;#ZK | [11 empty] | NA | [7 empty] | 48 | 0 |  |  | 0 |  |  |  | 750 | 12 | 0 |  | Atopic dermatitis | Yes | Global | Terminated | Yes | [14 empty] | DBL |  | None of the above
CZPL389A | CZPL389A2206 | C3001078 | Phase I | NCDS | CRO - EDC |  |  | 2019-09-16 05:30 | DB Locked |  |  | 2019-08-16 05:30 | 2019-04-18 05:30 | 2019-04-16 05:30 |  | Completed | 2020-05-12 05:30 | 2020-05-04 05:30 | 2020-07-07 05:30 | 2020-06-08 05:30 | FALSE |  | Kolla, Rajanikanth | Cluster D (TM,TCO,Coding) | FULL Outsourced | NIBR - ATI | An open-label, single dose, three period, single sequence study in healthy volunteers with the CYP2D6 extensive and poor metabolizer genotype to evaluate the effect of the CYP1A2 inhibitor fluvoxamine on ZPL389 pharmacokinetics. | CZPL389A2206 Fluvoxamine DDI study | P7 Immunology Hepatology and Dermatology | Langlo, Francois | Temgire, Ganesh | Temgire, Ganesh | Kshetrapal, Abhishek | Gupta Bhaya, Soumya Kanti | Paola Paganoni | Paola Paganoni | [17 empty] | Rohit Varate | [28 empty] | Parexel | [19 empty] | Atopic dermatitis | No | Global | Completed | Yes | [16 empty] | None of the above